United Nations Development Programme Iraq

[Support Social Cohesion in Iraq – Stage I – No. 00092583]

Quarterly Progress Report

Q2 2016

| Project Title: | Support for Social Cohesion in Iraq – Stage I |
| --- | --- |
| UNDP Project #: | 00092583 |
| Project Duration: | 12 months |
| Project Resources: | KAICIID |
| UNDP Iraq Focal Point: | Dhafer Hasan – Programme Analyst |

| UNDAF Outcome(s) | Outcome A.1 |
| --- | --- |
| CP Outcome(s): | Outcome A.1.1 |
| Output(s): | Output 1: Community and opinion leaders in Iraq are able to actively promote social cohesion. Output 2: Iraqi governmental actors have strengthened capacity to understand and engage in social cohesion policy programming. Output 3: Social cohesion is mainstreamed across all UNDP programming in Iraq. Output 4: Restorative mechanisms among communities in partnership with local authorities in liberated areas |
| Implementing Partner: | United Nations Development Programme Iraq |
| Responsible Partner: | United Nations Development Programme Iraq |
| Project Location(s): | Nationwide |

Table of Contents

Executive Summary	3

Context	4

Implementation Progress	5

Output 1	5

5

Challenges	6

Issues	7

Lessons Learned	7

Future Plans	8

Financial Section	10

Table 1. Funding Overview	10

Table 2: Expenditure Status (by activity)	10

Table 3. Expenditure Status (by donor)	11

Annexes	12

Annex I:  Performance Tracking Matrix	12

Annex II: Risk Log	13

# Executive Summary

The development of a social cohesion policy framework in Iraq, if formulated and implemented in a consultative and participatory manner with full Iraqi ownership, has the potential to address some of the social implications of the last ten years of conflict and the legacy of the former regime, and to contribute to the rebuilding of trust between communities.  Given the correlation between social cohesiveness and development outcomes, this is an essential step towards achieving the realisation of Iraqis’ economic and social rights and towards promoting Iraq's resilience to future political, social and economic shocks.

This project is designed as stage I of an effort to promote social cohesion as part of a more inclusive, representative and resilient Iraq.  The future direction of the country is unclear with a number of potential outcomes as a result of the June 2014 crisis.  Within this context, enhancing Iraqi partners' understanding and capacity to promote social cohesion now may help shift momentum towards a more inclusive and resilient country.  Equally, building civil society and government partners' capacities regarding social cohesion will allow those actors to actively promote the concept more tangibly once some stability returns to the country.  These stage I efforts will focus on leveraging these two opportunities to shape the current environment to be more amenable to Iraqi-led efforts towards social cohesion; subsequent stages will look to providing more concrete technical assistance to Iraqi partners once they are willing and able to engage in more defined efforts.  Due to the lack of trust between groups and actors in Iraq, UNDP has been identified by Iraqi interlocutors as being able to play a worthwhile facilitating role regarding the concept of social cohesion.  However, to be meaningful, social cohesion efforts must be Iraqi-led and UNDP's efforts should only be to facilitate, encourage and to provide technical advice.

Stage I aims to shape the environment through two key mechanisms.  The first is to identify key community and opinion leaders in the country who can act as social cohesion champions.  While not selected for any formal decision-making responsibility, these champions will play an influential role in society.  UNDP will work with the social cohesion champions to build a common understanding of social cohesion issues within Iraq and to strengthen the champions' capacity to engage in social cohesion programming.  The champions will then be supported to use their networks to promote social cohesion messaging across Iraqi society, through media, civil society and informal networks.  If successful, it is envisaged that, at the end of the project, champions' influence over the public and up to decision makers will lead to a strong moral encouragement for the national government to engage constructively in the issue of social cohesion.

The second mechanism will aim to demonstrate how governments in the country can adopt a social cohesion approach to their work.  UNDP’s ability to work with the national government on such issues would be strengthened by success examples at the governorate level.  As such, UNDP intends to build the capacity of select governorate governments to adopt and implement a social cohesion approach at a whole-of-government level.  While having localised benefits, the efforts will also provide an example of how such an approach can work in Iraq.  Once the national situation stabilises, these examples can be used as demonstrators to encourage the national government to adopt a similar approach.

A final area of work for stage I activities will be to enhance the central government, and UNDP's, capacity to engage in social cohesion programming.  These activities will include developing practical programming principles for social cohesion, reviewing existing UNDP programming, providing training on how to incorporate social cohesion approaches for government and UNDP staff and developing a locally owned social cohesion index for the country.  By mainstreaming social cohesion within its own programming, UNDP will not only contribute to social cohesion directly, but would be setting an example for the government and for other UN and international agencies to do the same – it will also allow UNDP to fulfil its strategic priorities identified through its UNDAF, CPD and the UNDP Strategic Plan.

These efforts are seen to lay significant groundwork to allow Iraqi society and government to respond effectively to the issue of social cohesion.  It is expected that these activities will be the first stage of a long-term engagement by UNDP with the GoI regarding social cohesion.   Utilising the Iraqi-led concept of social cohesion developed through this project, and the priorities that process identifies, UNDP will engage with the executive and arms of the GoI throughout the course of this project to negotiate a technical assistance package that will allow the GoI to address the concept of social cohesion in Iraq.  Depending on the responsiveness of the GoI and the political context, such assistance may be negotiated before the conclusion of this project and could be incorporated into a substantive amendment to this project, or become a parallel, but complementary, project.

Note: Fund received will be sufficient to cover an effort to promote social cohesion as part of a more inclusive, representative and resilient Iraq. Therefore, this report is focusing on Output 1.

# Context

The Supporting Social Cohesion in Iraq – Stage I project will be divided into three outputs.

Output 1: Community and opinion leaders are able to actively promote social cohesion in Iraq

Activity 1.1: Identify social cohesion champions and strengthen their capacity to promote social cohesion

Utilising its existing networks, UNDP will identify up to sixty (60) Iraqis to act as social cohesion champions.  The role of these champions will be to promote ideas of social cohesion throughout Iraqi society and decision makers, and attempt to promote constructive public dialogue around the issue.

Social cohesion champions will be prominent Iraqis who are able to influence the public and decision makers.  Champions will be identified from various groups, such as, without limitation: academics and public intellectuals; prominent artists; religious leaders; tribal leaders; well-known civil society activists; community leaders; media personalities; sportspersons; and prominent professionals.

Other important factors involved in the selection of champions include:

- The group of social cohesion champions should be seen as representative of the various groups, communities and geographic regions within Iraq;

- Individual social cohesion champions should be seen as credible by most Iraqis;

- Champions may be politically involved but should not currently work in the bureaucracy or the executive;

- Champions should be capable and willing to use their networks to promote social cohesion within Iraq; and

- At least 40-60% of champions should be women.

Sixty champions may appear to be a large number for such a group of people.  The engagement of such a significant number, however, if selected appropriately, would represent a critical mass in terms of influence over public opinion in the country and would be able to draw on the support of a large number of peers.  Smaller groups, while perhaps more manageable logistically, would potentially lose focus or enthusiasm for action without such support.

After identification, UNDP will invite the champions to take part in an initial three- or four-day consultation session as a group, with UNDP holding a facilitation role.  Due to security considerations, this session is likely to take place, in order of preference, in Basra, Erbil, Amman or another location.  Due to the number of champions, there may be value in breaking them up into smaller, more workable, groups for consultation.

Without limitation, the initial meeting will involve:

- The use of a modified version of UNDP's Conflict-related Development Analysis framework to build a common understanding amongst champions of issues affecting social cohesion in the country through a participatory analysis process – in addition to promoting a consistent approach amongst the champions, the common analysis will also serve to inform UNDP's future programming and monitoring of the issue;

- A practical introduction, by UNDP, of potential ways to promote social cohesion through reference to international examples, focusing particularly on the complementary role of civil society and the adoption of a whole-of-government social cohesion approach; and

- Detailed discussion of ways in which champions can promote social cohesion in Iraq.

Media, and social media in particular, has a very prominent role in terms of public opinion in Iraq.  At present, social media appears to be used most effectively by those promoting intolerant ideas, with other actors dismissing it as a divisive influence.  In order to encourage effective usage of such platforms to promote social cohesion, UNDP will also promote a discussion of media and social media engagement during the consultation session, including provision of expert advice informed by work under activity 3.3 where appropriate.

Activity 1.2: Support activities by champions aimed at strengthening social cohesion

Utilising momentum gained from the consultations conducted under activity 1.1, UNDP will work with the champions to provide support for their ongoing efforts to promote social cohesion amongst society and decision makers.

Primarily, these efforts will involve using champions' influence to spread support for social cohesion through champions' informal and institutional networks.  Media interactions will be especially important and champions will be encouraged to use traditional and social media to promote social cohesion messages.  Other specific activities to promote social cohesion may also take place, identified by champions and relevant to the specific context.

In the first instance, UNDP's support for activities will take the form of an ongoing mechanism for advice, follow-up and discussion.  UNDP staff will be in regular contact with the champions to support, inform and discuss possible activities when needed, as well as to review ones already undertaken.

Additionally, two one- or two-day meetings will be held with the social cohesion champions, one mid-way through the project and the other at the end of project activities.  These meetings, facilitated by UNDP, will provide an opportunity for social cohesion champions to update their common analysis of social cohesion issues in the country, to share lessons learned and to identify common initiatives for promoting social cohesion.  The final meeting will also serve as an opportunity for evaluation and discussion of follow-on activities.

For the sake of Iraqi ownership it would be preferable for social cohesion champions to undertake specific activities aimed at promoting social cohesion with their, or their networks', resources.  Nevertheless, UNDP should be prepared to mobilise a small amount of resources to help with worthwhile initiatives by social cohesion champions which might otherwise not happen.  Such initiatives would be suggested by champions based on their context and accepted in accordance with UNDP's internal guidelines, together with a clear demonstration of need, value for money and impact.

At the end of output 1 activities, a final technical report will be produced by the UNDP team outlining the results, lessons learned and recommendations for further action.

# Implementation Progress

The Project had suffered from delay mainly because of the late arrival of the budget and the administration process to approve the Annual Work Plan and the budget. Meanwhile UNDP managed to update and build partnership with the National Reconciliation Committee (NRC) and SANAD (local organization specialized in peacebuilding) to support the implementation of the project.

Several meetings had been conducted with NRC to present the idea of the project and support them to be actively involved in the implementation process. NRC has prepared an initial list of participants to be invited for the workshop (Output one). They have also mentioned that they prefer to work with local NGO to implement this project.

The project document indicates that the project should end July 31, 2016 based on the agreement with the donor. Therefore, there is a need to extend the project without any additional cost. The process of no cost extension has been finalized with UNDP donor for this project (KAICIID). Based on the revised agreement with the donor, a new AWP will be developed and approved to cover the new extension (until the end of 2017).

Regular online meetings had been conducted with KAICIID to ensure they are properly updated and informed. The donor supported the idea of no cost extension and shifting the activities of the project to ensure the effectiveness of the project.

Due to the limited fund provided so far for the project, the focus of the implementation will be on Output 1. The assumption that this output will be more visible than others to attract more fund to complete the other outputs according to plan.

# Challenges

# The fund allocated for this project is limited to one output (output number 1).

# The security and political situation in Iraq increased the sense of frustration among community leaders and the community in general. This level of frustration makes it more difficult to advocate for a social cohesion agenda, although it is needed now more than ever.

# The National Reconciliation Committee (NRC) was identified as a partner, however, they are going under a lot of political pressure, which made them less responsive.

# UNDP is currently working on different initiatives addressing social cohesion and reconciliation, however, there is no clear mechanism in place to coordinate those efforts and harmonize the work. This may result in confusion of our partners, counterparts and community.

Issues

Lessons Learned

- Coordination among UNDP projects addressing social cohesion, especially among short term and long term interventions, is a must in order to ensure effectiveness.

- Working with local NGOs is essential to address social problems.

# Future Plans:

The revised agreement with the donor (No cost extension) is expected to be signed in the first week of August, 2016. Based on the extension of the project, the new AWP will be developed and approved to cover the implementation period of this project (until end of 2017). Main future activities for 2016 would include:

- Signing grant agreement with local organization specialized in social cohesion and peacebuilding.

- Identifying community leaders to participate in the first activity under output 1.

# Financial Section: 
Note: All financial data presented in this report are provisional. From UNDP Bureau of Management/Office of Finance and Administration, an annual certified financial statement as of 31 December will be submitted every year no later than 30 June of the following year.

## Table 1: Funding Overview

| Donor | Commitment (Currency of the Agreement) | Received (Currency of the Agreement) | Received (USD) | UNORE | Balance (Currency of the Agreement) |
| --- | --- | --- | --- | --- | --- |
| KAICIID | USD 308,000 | - | USD 308,000 | - | - |
| Total |  |  | USD 308,000 |  |  |

The table on funding overview will cover funding since inception of the project, and will include only those contributions for which legal basis i.e. agreement/ letters exchange, exist.   Column 1:  will include the name of the donor, with a new adjacent cell created for every different agreement signed with the same donor.  Column 2, commitment, will include the amount of the commitment as stated in the agreement in the same currency as in the agreement.  Column 3: shows the amount of the money received against every commitment. If the currency in the agreement is denominated in USD, this slot can be left blank.  Column 4: provides for the US equivalent of the received amount of the local currency, with Column 5: providing the United Nations Operational Rate of Exchange at the date of the receipt of funds. Column 6: provides for the balance of the contribution expected to be received from the donor.  This is arrived at through subtraction of total received amount from the commitments.

## Table 2: Expenditure Status (by activity)

| Activity | Budget (A) | Donor | Cumulative Expenditure Status at End of June, 2016 | Expenditure in Reporting from July to End of September , 2016 | 3rd Quarter Expenditure (F=D+E) | Total Expenditure (G=B+C+F) | Budget Balance (H=A-G) | Delivery Rate (%I =G/A) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Commitment (B) | -Expenses + full asset cost (C) | Commitment (D) | Expenses + full asset cost (E) |  |  |  |  |
|  | USD 308,000 | KAICIID | 0.00 | 30,810.00 | 0 | 0 | 0 | 30,810.00 | 277,190 | 10% |
| GMS | NA |  |  |  |  |  |  |  |  |  |
| Total | USD 308,000 | KAICIID | 0.00 | 30,810.00 | 0 | 0 | 0 | 30,810.00 | 277,190 | 10% |

## With regards, to GMS, projects should reflect only ATLAS records as GMS is expected to be posted on time this year.  Columns 1, 2 and 3 which respectively indicate activity, budget and donor of the project reflect the planned budget as in the AWP.  Column 4/5, which indicates Expenditure Status at date of closure of the last reporting phase, will show commitments and disbursement   up to that point. It is advised to use the IPSAS project resource management reports - fund resource overview; project resource overview; project budget balance; project transaction detail. This section has been re-aligned with these reports to make the reporting meaningful and easy.  Commitments are the written contractual obligations which the project has signed out, while disbursements indicate the amount of money which was actually paid for the obligations. In UNDP corporate terms: OPEN REPORTED COMMITMENTS as at the reporting period ARE UNRECEIPTED POs ONLY.    Columns 6/7 similarly indicate commitments and disbursements, however only for the reporting quarter.  Column 8, Quarterly expenditure, will sum up the commitments and disbursements in the reporting quarter.  Column 9, on total expenditures will add the quarter expenditure (column 8) to the expenditure status at the end of the last reporting quarter (columns 4/5).  Column 10, the Balance, is arrived at through subtracting, total expenditure (column 9), from the budget (column 2).  Finally the last column, Column 11, delivery, will be expressed in percentage terms, and is calculated by dividing total expenditure (column 9) by the budget (column2).

## Table 3: Expenditure Status (by donor)

| Donor | Budget | Activity | Expenditure Status at [Date] | Expenditure in Reporting Quarter | Quarter Expenditure | Total Expenditure | Balance | Delivery |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Commitment | Disbursement | Commitment | Disbursement |  |  |  |  |
| GMS |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |

The explanation under this section is similar to the above section, however here the difference is that on this table expenditure is categorized as per source of funding/donor.

# Annexes

## Annex I:  Performance Tracking Matrix

| Result/Goals | Performance Indicators | Baseline Info | Performance Benchmark and Targets | Implementation Progress in reporting quarter |
| --- | --- | --- | --- | --- |
| Community and opinion leaders are able to actively promote social cohesion in Iraq | 1.1.1 – Number of champions identified and engaged in consultation process (0; at least 40 (40-60% women) 1.1.2 – Common social cohesion analysis undertaken (none; developed) 1.2.1 – Number of media references to social cohesion (0; two per week) 1.2.2 – Number of champions attending mid-project meeting (0; at least 40) 1.2.3 – Number of champions attending end-of-project meeting (0; at least 40) 1.2.4 – Public opinion regarding social cohesion (not known; public opinion positive) 1.2.5 – Social cohesion index result at national level (no index; improvement) | Identify social cohesion champions and strengthen their capacity to promote social cohesion Support activities by champions aimed at strengthening social cohesion | - |

## Annex II: Risk Log:

| Project Title: Support for Social Cohesion in Iraq – Stage I | Award ID: | Dates:01 Aug 2014 – 31 Jul 2016 |
| --- | --- | --- |
| # | DESCRIPTION | DATE IDENTIFIED | TYPE | IMPACT & PROBABILITY | COUNTERMEASURES; MGMT RESPONSE | OWNER | SUBMITTED; UPDATED BY | LAST UPDATE | STATUS |
| 1 | Unstable security situation in Iraq | Prodoc |  | Potential delay in implementing the project activities P = 4 I = 3 | Countermeasure: Ongoing analysis of security situation and compliance with UNDP security guidelines Mgmt Response: Undertake activities in safer areas or outside of Iraq | UNDP Project Manager | UNDP Project Manager |  |  |
| 2 | Project becomes politically sensitive | Prodoc |  | Potential loss of cooperation of Iraqi counterparts and negative publicity P = 2, I = 4 | Countermeasure: Appropriate design and liaison with key Iraqi counterparts at the political level. Mgmt Response: Lobbying by UN officials, liaison with key Iraqi counterparts, effective communications response | UNDP Project Manager | UNDP Project Manager |  |  |
| 3 | Significant political instability in Iraq | Prodoc |  | Uncertainty over identification of counterparts and ability of counterparts to make decisions. P = 3, I = 2 | Countermeasure: Work across tiers of society to ensure that project activities can continue in political instability. Mgmt Response: Work with non-political actors and with counterparts from a wide range of political backgrounds in Iraq. | UNDP Project Manager | UNDP Project Manager |  |  |
| 4 | Cannot identify sufficient champions or Iraqi counterparts willing to engage in project activities | Prodoc |  | P = 1, I = 4 | Countermeasure: Ensure project activities are relevant to counterparts. Mgmt Response: Adjust project activites. | UNDP Project Manager | UNDP Project Manager |  |  |