|  | Atlas Award ID: | Annex-9: UNDP Quarterly Progress Report |  |
| --- | --- | --- | --- |
|  | Atlas Project ID: |  |  |
|  | Programme Title: | Iraq Crisis Response and Resilience Programme (ICRRP) |  |
|  | Project/Component Title: | Strengthening National and Regional Crisis Management Capacity in Iraq (Component-1) |  |
|  | CPD Outcome: |  |  |
|  | Report of | UNDP |  |
| Date of Submission (mm/dd/year) |  |
| Period covered by this report (mm/dd/year) | 01/01/2017 – 03/31/2017 |

Executive Summary

Key achievements

- 3 training events organized

- JCMC network meeting held and a visioning and planning workshop organized with an action plan as output

- JCMC ToR drafted and endorsed by the Prime Minister

- JCC 2017-2020 action plan developed and submitted to KRG Council of Ministers for endorsement

- The JCC Council, the HCF and CIMIC meeting took place once each during the period

- English language course provided to JCMC and JCC headquarters

- Coordination specialist imbedded into JCC Erbil office for in-house training and mentorship

- M&E Framework developed and baseline assessment started.

- Procurement process launched to identify training partner/s

- Dialogue launched with Bangladesh and Turkey for potential study visits to the disaster/crisis management authorities of these countries.

Key challenges (risks and issues) and mitigation measures

- Achievement of some milestones depends on a series of steps to be completed in sequence and some of those steps (such as KRG endorsement of the JCC strategy/roadmap for 2017-2020) are outside UNDP control.

- Nomination of staff to different trainings is not based on the Job descriptions or duties of the individuals.

- Security matters limited UNDPs space to visit many of the JCMC governorate teams

- JCMC is severely understaffed for its mandate and even for the range of activities it is currently undertaking

- Due to visa problems, the M&E expert could not start his work in January as planned. Moreover, as a Bangladeshi national, he was refused Iraqi visa and therefore could not conduct the baseline assessment for the JCMC.

Recommendations (on risks, issues and way forward if applicable, if any)

- Joint six-monthly planning with and individually for the JCMC and JCC vital

- Flexibility in implementation approach to take capacity-building measures on difficult/sensitive topics when there are opportunities

- Intensified advocacy with the JCMC to increase staff as this issue is a persistent bottleneck to nearly all milestones.

- Ensure that there is consistency in staff nominations to trainings so that target for each training topic are identified and the targeted staff in full attend the three-level training in the topic they are selected for.

- Find contracting arrangements that allow for access by UNDP to JCMC Governorate teams and focus on a smaller number of governorate offices in 2017 to improve the performance of pilot ‘models’.

- Maintain proactive risk monitoring and response.

Summary Expenditure Report

Progress Rating

| Milestone RAG Status | Rating |
| --- | --- |
| Completed |  |
| Started and on track or achievement expected per plan |  |
| Delayed or delays expected |  |

Section A: Progress achieved under overall goal (JCMC and JCC)

| Impact: Effective government leadership in crisis management results in enhanced population safety and welfare during crises in Iraq |
| --- |
| Indicator 1: Continuity and quality of coordination and collaboration between the JCMC and JCC as well as within their respective crisis management networks |
| Milestones | RAG | Progress from start to the end of Q1 |
| M1: JCMC and JCC senior management continue to meet bi-monthly and maintain regular contact to resolve issues at the technical level, October 2017 for Milestone 1. |  | No formal meetings took place during the reporting quarter but agreement reached to hold a meeting in Q2. Daily and weekly coordination took place around specific issues such as customs clearance and transportation of food and fuel supplies to volatile areas. RAG Status: on track |
| M2: JCMC and JCC have fully established efficient mechanisms for coordination and collaboration within their respective network of offices/focal points in governorates and line ministries, April 2017 for milestone 2 |  | On March 23, JCMC held its regular (two-monthly) network meeting with its governorate teams and ministerial focal points. All governorate focal points were present and the meeting was chaired by the head of JCMC. Daily communication and sharing of information is taking place through the WhatsApp group linking the JCMC offices/teams. The user rate of the WhatsApp group is very high and active, however weaknesses are found in the completeness and reliability of data and information shared. Weekly written reports from the governorate offices/teams are submitted to the JCMC. However, some of the offices are not consistent in submitting reports regularly and there are still gaps in completeness and reliability of the data and information shared. JCC held one meeting with its governorate offices during the reporting period. Information and reports are submitted by the governorate offices to JCC HQ daily and weekly but the format is not harmonized and consistent and the information is not complete requiring multiple follow-ups from JCC HQ. RAG Status: on track |
| Indicator 2: Government leadership in response planning and coordination as measured by quality and timeliness of plans and coordination efficiency |
| M1: As a standard practice, JCMC and JCC call their respective key government stakeholders and international partners to an emergency response planning meeting within 48 hours from the identification of an imminent threat/emergency and within 24 hours after a sudden emergency, by April 2017. |  | JCMC: When an urgent matter is brought to the attention of the JCMC HQ, the JCMC Head (who is also the head of the National Operations Centre (NOC)) decides what action to take and which entities to reach out to. He is directly linked to the office of the Prime Minister the JCMC is under direct administrative supervision of the General Secretary of the Council of Ministers (COMSEC) who is also the Chief of Staff of the Prime Minister. The head of JCMC/NOC holds weekly meetings with the UN Humanitarian Coordinator (HC). With offices in the governorates, focal points in the ministries and these close links to the senior decisions-makers, the structure of the JCMC allows for quick government action. However, the work is still done in a reactive manner and the JCMC’s role is primarily to act as the secretariat of the JCMC/NOC Head and the General Secretary. Moreover, the JCMC and the entire decision-making structure is vulnerable to political changes as the key decision-makers are political appointees. Today, the level of political support and leadership attention is high but the future is unpredictable. JCC: Daily communication between the JCC HQ and governorate teams permits quick transmission of information to the JCC HQ. JCC HQ is under direct supervision of the Minister of Interior of the KRG who is also chairing the JCC Council meetings, bringing together Director General level officials from key government offices. JCC is also chairing the Humanitarian Coordination Forum (HCF) with UNOCHA as co-chair and meetings are held monthly, although not consistently on schedule. The baseline assessment has rated the performance of the JCC Council as 3 out of 5 while the HCF receives 2.5 out of 5 from JCC partners. Issues raised include lack of consistency in meeting dates, HCF lacking decision-making strength. The Civil-Military Coordination (CIMIC) meeting is another JCC Coordination forum focused on coordination between civil and military actors. While the CIMIC forum met relatively consistently during 2016, no meetings were held in Q1 due primarily to resettlement of the JCC CIMIC officer to another country. During this period, JCC focused on task-based CIMIC coordination by liaising with various stakeholders around specific issues such as travel permits and security clearance of humanitarian supplies and personnel to East Mosul. One Council Meeting was organized but no HCF or CIMIC meetings were organized. RAG Status: completed (but continuity to be supported and documented in the subsequent quarters. The score allocated in the baseline assessment by the JCC itself (self-assessment) and its partners (partner perception) is 2.5/5 in average indicating that JCC has advanced well but remains below expectation in terms of performance. JCC and the partners demonstrated very similar perceptions of JCC’s weaknesses and strengths and offered similar ratings. No baseline assessment conducted on the JCMC) |
| M2: JCMC and JCC have established and manage efficient mechanisms for strategic government decision-making in response to imminent and sudden emergencies/crises, by April 2017 |  | JCMC: strategic decisions are made jointly by the head of JCMC/NOC, the General Secretary of the COMSEC and on particularly important matters the Prime Minister. A high-level committee composed of the PM’s Chief of staff, the KRG Minister of Interior, the JCC Director General and the UNHC was formed in 2016 and meets on strategic issues. JCC: Strategic decisions are made by the JCC Council and on matters above the Council’s authority, it is raised to either the Council of Ministers or the PM’s office. RAG Status: completed (these decision-making mechanisms are efficient and forceful) |

Section-B: Progress achieved under outcomes (JCMC)

| JCMC has a dedicated key function within the national disaster and crisis management system envisaged in the draft law and strategy. |
| --- |
| Indicator 1: Clearly defined JCMC mandate |
| Indicator 2: JCMC's coordination added value in the on-going crisis response operations as perceived by key recipients of JCMC services |
| Milestones | RAG | Progress from start to the end of Q1 |
| M1: Revised JCMC ToR officially endorsed by Q12017 |  | The ToR was revised and endorsed by the Prime Minister in February 2017. RAG Status: completed |
| M2: ToR for the JCMC Governorate Representation Offices officially endorsed by Q3, 2017 |  | A visioning and planning workshop was held for the JCMC head and governorate teams on March 29-30, 2017. In the workshop, it was suggested to develop ToR for the governorate offices and ministry focal points of the JCMC. This suggestion was unilaterally endorsed by all the participants. The ToR is expected to be drafted and endorsed by Q3. RAG Status: Achievement expected per plan |
| M1: JCMC's added value is recognized and appreciated by key 'clients' from Q2, 2017 |  | In the above-mentioned visioning and planning workshop, four areas of action were identified to improve the quality of JCMC products and services and ‘client’ awareness and perception of JCMC’s work. A workplan was developed to implement action priorities during 2017-2018. Progress will be monitored continuously. In addition to tracking activities, perception surveys will be conducted to measure progress. RAG Status: started and on track |
| M2: JCMC's visibility has increased by Q2, 2017 and progressively after |  | With the support of IOM, the JCMC developed a website in March 2017. The website will be launched in Q2, 2017. Jointly with IOM, UNDP will support JCMC in maximizing the use of the website as a platform for dissemination of information to external partners. Visibility activities are planned for 2017-2018 per the action plan agreed in the visioning and planning workshop. RAG Status: achievement expected per plan |

Section-C: Progress achieved under JCMC outputs (Summary of Quarterly Progress)

| Section: C.1 (JCMC) |
| --- |
| Output-1: JCMC has reached priority institutional development targets |
| Indicator 1: Clarity in duties and authorities of the JCMC as outlined in an officially endorsed mandate/ToR Indicator 2: Consistency between mandate and organizational structure of the JCMC, including the head office and the governorate offices |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestones and measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: Revised ToR for the JCMC head office and ToR for the governorate representation officers are officially endorsed and are informed by international standards and best practice in disaster and crisis management, Completed by Q1 for JCMC head office and Q2 for the governorate offices – 2017 |  | JCMC TOR were developed and endorsed in Q1 Agreement reached with JCMC headquarters and governorate offices/teams to develop ToR in Q3. RAG Status: on track | Capacity and situation assessments for selected JCMC Governorate offices to be conducted jointly by JCMC and UNDP in Q2 and Q3 |
| M2: JCMC head and governorate representation offices use an interactive web-portal for coordination, collaboration, exchange of information, learning and reporting. Completed by Q2 of 2017 by use and quality enhancement measured throughout the project period |  | No Action taken Q1 JCMC is making very active use of a WhatsApp group for daily communication within the network of offices. RAG Status: delays expected | Following discussions between JCMC, UNDP and IOM, it was agreed that, as a first step, JCMC should focus on launching and successfully administering a website. Once JCMC has succeeded with this, we will look into introducing an interactive intranet within that website and for internal use of the JCMC network of offices only. It is expected that this milestone will be delayed to Q4, 2017. |
| M3: JCMC Head Office operates through an efficient organizational set-up with an officially endorsed organogram, structured units and clearly defined roles and responsibilities for staff and management Organogram and JDs endorsed by Q1, 2017 and measurable change in efficiency achieved by Q2, 2017 |  | An organogram for JCMC HQ has been developed and endorsed by the JCMC Head JDs for the key functions were drafted in Q1 but JCMC has requested a revision of the JDs RAG Status: Started and on track | Revise the JDs for JCMC Head Office Jointly with JCMC, agree on a list of staff to be targeted for learning and training in each identified priority area for capacity building. |
| M4: JCMC Governorate offices operate though an efficiency organizational set-up with officially endorsed ToR and organogram Progress measured quarterly through the year |  | In the visioning and planning workshop held on March 29-30, gaps were identified and agreement was reached on priority action to achieve this milestone. RAG Status: on track | ToR developed in Q3. The ToR will include a basic organizational structure and JDs for key functions across all governorate offices for harmonization purposes. A capacity and needs assessment for governorate offices/teams will be carried out in Q2 and Q3 |
| Section C2 |
| Output 2: JCMC has enhanced the quality of products and services to priority recipients/clients |
| Indicator: 1 Consistency and continuity in the development and circulation of key information products such as weekly and monthly situation reports, daily briefs to the PM and other key government officials, topic specific reports, etc. Consistency and continuity of coordination and facilitation activities as measured through activity Indicator: 2 Quality and value added of information products and coordination/facilitation services as rated a) by key recipients and b) pre-defined (in the M&E plan) quality standards |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestones and measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: JCMC information and analysis products are tailored to the needs of individual key clients. By Q2,2017 with continued improvement to follow |  | During the visioning and planning workshop, a stakeholder mapping was carried out to identify JCMC’s key clients and their information and coordination needs and the current JCMC services and products to meet those needs. Action priorities were identified and agreed to improve the quality of these services and products. For communication and reporting in English, UNDP started in February 2017 to provide English language training to the JCMC HQ staff at two levels: basic and advanced. A procurement process was launched to identify training partners RAG Status: started and on track | An information analysis and reporting specialist will be commissioned in Q2 and imbedded into the JCMC in Q3 to provide in house training and mentorship. This will complement the support provided by IOM in information management English language training will continue A 3-level training program in information analysis and reporting will be launched |
| M2: JCMC has procedures and human capacities to conduct consolidated response gap analysis on a continuous basis. By Q2, 2017 with continued improvement to follow |  | Today JCMC has emergency-assistance focused response gap analysis done and presented through its weekly and monthly reports. It also consolidates priority action reports, situation briefs and updates for the PM and Chief of Staff and for the regular meetings between the head of JCMC/NOC and the UNHC. Discussions took place during Q1 on how to improve the quality of these information products and agreement reached that particular support must be provided to the JCMC governorate offices to improve the completeness and accuracy of information collected at the governorate level. Procurement process was launched to identify a training partner RAG Status: on track | An information and reporting specialist will be imbedded into the JCMC in Q2/Q3. A key task outlined in the ToR of the Specialist is supporting JCMC in improving the quality of its information products and train the staff in how to conduct gap analysis A 3-level training in need and gap analysis will be launched in Q2/Q3. |
| M3: JCMC has further refined and strengthened its procedures and work-flows to fulfill its facilitation role vis-à-vis key humanitarian partners. By Q2, 2017 with continued improvement to follow |  | During the visioning and planning workshop held on March 29-30, all the services and activities of the JCMC were mapped out and strengths and weaknesses identified and priority action to address gaps/weaknesses was agreed on Throughout the quarter, JCMC liaised between humanitarian actors, NOC and the MOI-Nationality Directorate for issuance of emergency visas, liaised with NOC, the Joint Operations Centre (JOC), humanitarian partners and governorate authorities to secure passage for humanitarian personnel and supplies and liaised with airport authorities for rapid customs clearances and liaised with the JCC in Erbil for movement and customs clearance involving KRI. While no baseline assessment was conducted, this part of JCMC’s work has repeated received praise and credit. Therefore, while the work procedures and flows are not formalized, the approach adopted is effective for the current purpose. However, for sustainability it will be necessary to transition from an organic and reactive approach a more systematized model. RAG Status: on track | Meetings and seminars with Q&A sessions are planned for Q2/Q3 to raise awareness about the work of JCMC among key stakeholders and strengthen the collaboration between these actors. The new JCMC website will have a section where organizations can access information about JCMC’s facilitation role and download forms for applications. |
| Section C.3 |
| Output 3: JCMC achieves priority staff development and learning targets |
| Indicators: 3.1 Number of staff benefitting from learning opportunities in priority thematic areas Indicators: 3.2 Progressive increase in learning outcomes for targeted staff and management as measured quarterly through knowledge tests |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestones and measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: Targeted staff have enhanced skills and knowledge in information analysis and reporting. By Q4, 2017 (quarterly progress measurement) |  | A 4-day training in information analysis and reporting was organized jointly for the JCMC and JCC in Q1. 12 staff from JCMC attended the training. Procurement process launched to identify training partner for continued training on this topic. RAG Status: on track | Information analysis and reporting specialist will be imbedded for in-house training and mentorship in Q2/Q3 3-level training program will be launched in Q2/Q3 |
| M2: Targeted staff have enhanced skills in managing teams and processes. By Q4, 2017 (quarterly progress measurement) |  | The JCMC head, the Executive Director and the Deputy Executive Director attended an intensive executive training in management and leadership in crisis Procurement process launched to identify training partner on this topic RAG Status: on track | 3-level training program will be launched in Q2/Q3 |
| M3: Targeted staff have enhanced skills and knowledge in coordination. By Q4, 2017 (quarterly progress measurement) |  | Procurement process launched to identify training partner RAG Status: on track | 3-level training program will be launched The Coordination Specialist will be imbedded within the JCMC |
| M4: Targeted staff have enhanced skills and knowledge in response gap analysis. By Q4, 2017 (quarterly progress measurement) |  | Same as above | Same as above |

| Section C.4 |
| --- |
| Output 4: Progress is made towards clarifying the role of JCMC in relation to the provision of the draft law and strategy |
| Indicator 1: Official government endorsement of revised JCMC ToR and JCMC technical input to the draft bill when submitted to the COMSEC for legal and technical review |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestones and measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: The scope of work of the JCMC is clearly defined and officially endorsed. By Q1, 2017 |  | ToR were developed and endorsed by the PM. RAG Status: completed | Through the MOFA, JCMC will send out the TOR to the international partners. |
| M2: Measures taken to consolidate the draft bill, national strategy and JCMC mandate. By Q4, 2017 |  | No action taken during the reporting period. RAG Status: achievement expected per plan | No action planned for Q2 |

Section D: Progress achieved under outcomes (JCC)

| Government leadership in crisis response is the norm with international stakeholders playing a supportive role when needed and requested |
| --- |
| Indicator 1: Clarity and consistency of legal, administrative and institutional arrangements for disaster and crisis management in the KRI Indicator-2: Existence of institutional and operational arrangements for building domestic expertise and good practice |
| Milestones | RAG | Progress from start to the end of Q1 |
| M1: KRG has a vision and Roadmap for creation of a consolidated regional disaster and crisis management system. By Q1,2017 |  | Following extensive consultations and with the support of UNDP, JCC developed a strategy (Road map) for 2017-2020 identifying key measures to be taken by the KRG to establish a system for disaster risk reduction, preparedness, response and early recovery. The strategy has been submitted to the KRG Council of Ministers for endorsement. RAG Status: started and on track |
| M2: Disaster and crisis management models tailored to the KRI context are presented to the Council of Ministers for consideration, selection and enforcement. By Q2, 2017 |  | Work towards this milestone is on hold until the strategy (Road map) is endorsed by the KRG Council of Ministers. It is likely that achievement of this milestone is delayed to Q3, 2017. RAG Status: Delayed or delays expected |
| M1: The mandate and scope of work of the Academy is officially expanded and a 3-year strategy developed and endorsed. By Q2, 2017 |  | Work towards this milestone is on hold until the strategy (Road map) is endorsed by the KRG Council of Ministers. It is likely that achievement of this milestone is delayed to Q3, 2017. RAG Status: Delayed or delays expected |
| M2: Partnerships are formed between the Academy and other similar learning centers and academic institutions nationally and internationally. By Q3, 2017 |  | Work towards this milestone is on hold until the strategy (Road map) is endorsed by the KRG Council of Ministers. RAG Status: on track or achievement expected per plan |

Section E: Progress achieved under JCC outputs (Summary of Quarterly Progress)

| Section: E1 |
| --- |
| Output 1: JCC achieves priority institutional development targets |
| Indicator 1: Degree of harmonization in organizational set-up, procedures and work-flows within the JCC network of offices Indicator 2: Extent of organized coordination and collaboration within the JCC network of offices |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestonesand measured against the previous quarter | Activities Planned for next quarter to achieve the milestones |
| M2: Harmonized standard operating tools, mechanisms and procedures are efficiently and consistently used. By Q3, 2017 |  | Baseline assessment started. No other action taken Q1 RAG status: on track or achievement expected per plan | Revise existing coordination and information sharing procedures and tools based on lessons learned in 2015. This is done with the support of the Disaster and Crisis Management specialist Complete baseline assessment |
| M2: The organizational structure and JD’s are revised for optimal performance against mandate. By Q3 |  | No action taken during the reporting period RAG Status: on track or achievement expected per plan |  |
| M3: Mechanisms, tools and procedures for efficient exchange of information, joint planning and coordination within the JCC network of offices are reinforced. By Q2, 2017 |  | Coordination Specialist was imbedded into JCC HQ in January and from February the same specialist was imbedded into JCC Erbil to support improved coordination With funding from another donor, JCC was provided with teleconference equipment to facilitate remote coordination Agreement was reached between UNDP and JCC HQ to allocate funds for regular field visits by JCC HQ to governorate offices and regular network meetings between the offices Baseline assessment started but not completed in Q1. RAG Status: started and on track | Coordination specialist continues to support JCC Erbil Disaster and Crisis management consultant will be imbedded into the JCC HQ to reinforce JCC HQ’s leadership role in internal and external coordination Baseline assessment completed. |

| Section E2 |
| --- |
| Output 2: Target JCC staff have gained increased skills and knowledge in priority topics |
| Indicator 1: # of people trained/mentored in each priority topic Indicator 2: Learning outcomes in each priority topic |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestones and measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: Targeted staff have enhanced skills and knowledge in the use of ICT and in information analysis and reporting. By Q4, 2017. Progress measured quarterly |  | The coordination specialist imbedded into JCC Erbil conducted a capacity assessment and approximately 80% of the 19 JCC Erbil staff demonstrated basic skills and knowledge and the remaining 20% more advanced skills and knowledge. This assessment formed the basis for the in-house training and mentorship provided. A post-training assessment will be carried out at the end of the specialist’s assignment to measure change/learning outcomes. RAG Status: on track or achievement expected per plan | Reach final agreement with MSB on division of responsibilities on this milestone and plan interventions for Q3 accordingly. Conduct end-of-training knowledge assessment |
| M2: Targeted staff have enhanced skills in managing teams and processes. By Q4, 2017 with progress measured quarterly |  | Baseline assessment started. No additional action taken in Q1 RAG Status: on track or achievement expected per plan | Complete baseline assessment Contract consultant to be imbedded into JCC Suleymanieh to help building capacity in coordination related process management |
| M3: Targeted staff have enhanced skills and knowledge in coordination. By Q4, 2017 with progress measured quarterly |  | Coordination specialist imbedded into JCC HQ in January and from February the same specialist imbedded into JCC Erbil for in house training and mentorship. M&E plan and tools developed English language training provided to JCC HQ staff Procurement process launched to identify training partner/s RAG Status: started and on track | Coordination specialist continues to support JCC Erbil Baseline assessment carried out A 3-level training program is launched A consultant contracted to be imbedded into JCC Suleymanieh for mentorship and in-house training |
| M4: Targeted staff have enhanced skills and knowledge in preparedness and response planning and M&E. By Q4, 2017 with progress measured quarterly |  | M&E plan and tools developed and baseline assessment started English language training provided to JCC HQ staff Procurement process launched to identify training partner/s Procurement process launched to identify a disaster and crisis management specialist for JCC HQ RAG Status: started and on track | Baseline assessment completed A 3-level training program is launched Disaster and crisis management specialist imbedded into JCC HQ |

| Section E.3 |
| --- |
| Output 3: JCC has improved the quality of coordination products and services in support of the on-going crisis response operations |
| Indicators: 3.1 Continuity and quality of key JCC services and products as rated by key recipients/participants |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestonesand measured against the previous quarter | Activities Planned for Next Quarter to achieve the milestones. |
| M1: Regular situation reports (such as daily and weekly briefs, thematic situation updates, Common Operating Pictures, and other information products) are produced and the quality is rated satisfactory or higher by key recipients. Gradual progress measured quarterly |  | Four-day training workshop organized on information analysis and reporting jointly for JCMC and JCC. 12 staff from JCC participated. M&E plan and tools developed to measure progress Procurement process launched for a 3-level training program Coordination specialist imbedded into JCC Erbil office to train and mentor the team on priority topics, including information processing and reporting RAG Status: started and on track | Coordination specialist continues to support JCC Erbil office. Baseline assessment carried out 3-level training program is launched |
| M2: Scenario plans, needs and gap analysis and resource mobilization plans are produced in a timely manner and rated satisfactory or higher by key recipients/users. Gradual progress measured quarterly |  | M&E plan and tools developed to measure progress Procurement process launched for a 3-level training program Procurement launched for a consultant in disaster and crisis management to be imbedded into JCC HQ RAG Status: started and on track | Baseline assessment carried out 3-level training program is launched Disaster and crisis managements specialist imbedded into JCC HQ |
| M3: Vital coordination mechanisms are activated and operate in an effective and harmonized way as measured by the rating of participating entities Gradual progress measured quarterly |  | Coordination specialist was imbedded into JCC HQ in January and from February the same specialist was imbedded into JCC Erbil. Agreement signed between UNDP and JCC for active support to the three JCC-led coordination mechanisms including the JCC Council, the JCC Humanitarian Coordination Forum and the CIMIC meeting English language training provided to JCC HQ staff to improve communication and coordination with international organizations M&E plan and tools developed RAG Status: started and on track | Coordination specialist will continue supporting JCC Erbil UNDP will actively support the JCC coordination forums M&E baseline assessment carried out English language training provided to all JCC offices Consultant contracted to provided in-house training and mentorship to JCC Suleymanieh |

| Section E4 |
| --- |
| Output 4: KRG introduces a legal, institutional and administrative framework for disaster and crisis management in the KRI |
| Indicator 1: Existence of strategies, concept notes, proposals and their endorsements by the KRG - MoI/COMSEC |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestonesand measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: Regional vision and strategy formulated. By Q2, 2017 |  | Following extensive consultations and with the support of UNDP, JCC developed a strategy (Road map) for 2017-2020 identifying key measures to be taken by the KRG to establish a system for disaster risk reduction, preparedness, response and early recovery. The strategy has been submitted to the KRG Council of Ministers for endorsement. RAG Status: started and on track | No action planned. JCC is leading in follow-up with the Council of Ministers through the Minister of Interior. |
| M2: Regional disaster and crisis management models/options presented for KRG consideration. By Q32017 |  | No action taken in Q1 RAG Status: on track or achievement expected per plan | Upon endorsement of the strategy/roadmap, UNDP and JCC will jointly launch the 360-degree study |
| M3: A strategy and action plan developed to operationalize the selected disaster and crisis management model and upon endorsement, implementation of strategy and action plan by Q3, 2017 |  | No Action taken in Q1. RAG Status: on track or achievement expected per plan | See above, action will depend on government endorsement of the strategy/road map. |
| M4: Champions of disaster management are identified and mobilized among senior KRG officials by Q1, 2017 |  | Discussions started but champions not yet identified/approached. RAG Status: delayed to Q2 | Identify champions and plan dialogue activities to encourage a well-informed and genuine interest from the identified champions. |

| Section E5 |
| --- |
| Output 5: The MoI has made institutional and operational arrangements for developing domestic expertise and good practice in disaster and crisis management |
| Indicators: 5.1 Change in the mandate of the Academy Indicator: 5.2 Partnership between JCC/the Academy and other institutions |
| Milestones | RAG | Description of Activities Achieved during reporting quarter under indicators and milestones and measured against the previous quarter | Activities Plans for Next Quarter to achieve the milestones. |
| M1: The mandate of the MoI Civil Defense Academy is officially expanded to incorporate all aspects of disaster and crisis management by Q2, 2017 |  | This task is included in the JCC Strategy for 2017-2020. However, no further action taken until the strategy is endorsed by the KRG Council of Ministers. As the endorsement, has been delayed beyond what was expected, it is likely that this milestone will be delayed to Q3. RAG Status: delayed to Q32017 | Depending on endorsement of the Strategy/roadmap, UNDP and JCC will jointly launch the study but most likely in Q3. |
| M2: A 3-year strategy developed for operationalization of the Disaster and Crisis Management Academy by Q3, 2017 |  | No Action taken in Q1. RAG Status: on track or achievement expected per plan | Action during Q2 will depend on government endorsement of the strategy/road map. |
| M3: Partnerships formed between JCC/The Academy and relevant academia and public/private learning centers by Q4, 2017 |  | No action taken in Q1 RAG Status: completion expected per plan | Upon endorsement of the strategy/road map, UNDP and JCC launch a study into how to build the academy and how to create strategic partnerships |
| M4: Partnerships formed between JCC/the Academy and ‘sister’ institutions with a similar mandate in other countries by Q3, 2017 |  | No action taken in Q1 RAG Status: completion expected per plan | Upon endorsement of the strategy/road map, UNDP and JCC launch a study into how to build the academy and how to create strategic partnerships |

Dfid Q1, 2017 Report

Annex-1: PROJECT RISK MONITORING

| SL # | Description | Type | Impact and Priority | Counter Measures / Management Response | Monitored by | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Weakened or lost political interest | Political | Description: For the JCMC, lost political interest could, in the worst-case, result in abolition of the office. A more likely impact would be that JCMC becomes less influential. For the JCC as a institution, given that it is a Directorate General, would survive lost political support but could, similar to the JCMC, lose its level of influence Probability (for the next quarter) = 1 Impact = 4 for JCMC and 3 for JCC | During the reporting period, there was no indication of this risk materializing. On the contrary, both the JCMC and JCC enjoyed high political support. Therefore, no measures were taken. JCC Dohuk is the exception as JCC is competing with BRHA for political support at the Governorate level. To this end, and through other funding sources, UNDP supported JCC Dohuk in strengthening its human resources team to gradually assume its mandated duties. | The Project Manager, JCMC Executive Director, JCC Director General | Reducing particularly with the JCMC ToR approved JCC Dohuk is the exception where the status remains unchanged |
| 2 | Resistance and obstruction from different spoilers from within the government | Political Operational | Description: During the first 1.5 years, the spoilers could prevent JCMC and JCC from carrying out their duties and even delay proposals, plans and activities. However, now that both the JCMC and JCC have solid mandates and political support, the negative impact of spoilers has been significantly reduced. P = 1 for both institutions for the next period I = 2 | No Action was needed during the reporting period other than ensuring that the JCMC ToR are approved. | The Project Manager, JCMC Executive Director, JCC Director General | Reducing except for JCC Dohuk where some challenges remain to be overcome |
| 3 | Removal of senior appointees and ‘champions’ of the institutions from office | Operational Organizational Political | Description: For both institutions, there would be a significant impact should key ‘guardians’ such as the Minister of Interior of the KRG, the JCC Director General or the head of NOC/JCMC leave or be removed from their positions. However, the impact would be particularly severe for the JCMC as it is more vulnerable due to its status as an office as opposed to a Directorate. P = 1 for the next period I = 3 for the JCC and 4 for the JCMC | No action was necessary during the reporting period as this risk remained low. | The Project Manager, JCMC Executive Director, JCC Director General | Unchanged |
|  | Failed government prioritization resulting from lack of understanding or appreciation for measures/steps necessary for advancing a national/regional agenda for strengthened disaster and crisis management | Political Operational | Description: For the JCMC the impact would be limited as no major policy/strategy decisions are planned for 2017 that could be derailed/prevented. For the JCC, the impact would be high as this could result in rejection of the JCC roadmap for 2017-2020 and thus prevent JCC from taking important steps forward P = 2 for the next reporting period I = JCMC 2, JCC 3 | JCC actively advocated with the Prime Minister’s office through the Minister of Interior to ensure approval of the Road Map No action was needed from UNDP in Q1. Advocacy and awareness raising needed for the second half of 2017. | The Project Manager, JCMC Executive Director, JCC Director General | Unchanged |
|  | Low staff motivation, disabling institutional environment for learning, and other factors obstructing real learning outcomes | Organizational Operational | Description: The impact for the JCMC would be medium to high: given the small number of staff, the motivation of each staff member is critical for organizational delivery. For the JCC, the impact would be medium and affect the continuity and quality of services and products P = 2 for the JCMC since salaries are paid and 3 for the JCC as salaries are not paid regularly and there is an accumulated fatigue. I = 4 for the JCMC and 3 for the JCC | UNDP agreed to technically and financially support key JCC Coordination forums to motivate staff support and contribution and help them feel as part of a performing and appreciated organization. For both the JCMC and JCC staff, the trainings and mentorships have been a strong motivating factor. | The Project The Project Manager, JCMC Executive Director, JCC Director General | Reduced compared to 2015 as portion of salary is paid and increase in number of staff for both JCMC and JCC has reduced the work load on individual staff. |
|  | JCMC and JCC are not able to lead on institutional and system strengthening under the pressure of delivering on their current responsibilities | Operational Organizational | Description: The small number of JCMC staff increases the impact to medium or high as any sudden emergency would require JCMC to paus organizational development measures. For the JCC, the impact is low to medium, particularly since the number of staff in both JCC Head Office and Governorate Offices have increased. P = 3 (Depending on development of Mosul operations) I = 4 for JCMC and 2 for the JCC | Some planned project activities were delayed to Q2 in agreement with the two institutions Agreed that the best modality for capacity building would be mentorship and on-the-job training to avoid operational disruptions through training workshops. | The Project Manager, JCMC Executive Director, JCC Director General | Increased |
|  | Failed government financing of the operations of JCMC and JCC | Operational | Description: If the two institutions had no budget at all, the impact would be high. However, while both institutions are lacking an activity budget, staff salaries (reduced salaries for JCC), rent and bills are covered by the government and therefore their operational costs are partially covered P = 3 I = 2 (the impact is reduced due to coverage of operational costs) | No space for advocacy within the reporting period given that the lack of budget is linked to a government blanket policy and no exception are made for specific institutions. The project financially supported certain JCMC and JCC activities such as travel and meetings to support continuity | The Project Manager, JCMC Executive Director, JCC Director General | Unchanged |
|  | Security conditions preventing UNDP staff and consultants from working in Erbil, Baghdad and the other relevant governorates | Operational | Description: The impact would be that the important mentorship, advisory and in-house training activities are delayed or cancelled. The impact is higher for the JCMC given the large number of governorate offices, some in particularly difficult security environments. This makes is difficult for support through international experts. Side-note: the Iraqi Government has placed a visa ban on Bangladeshi nationals and due to this the contacted UNDP M&E Expert – of Bangladeshi nationality – could not travel as planned. As a result, the M&E exercise was delayed and he could not travel to Baghdad to conduct the JCMC assessment. P = 3 for JCMC governorate offices and 1 for JCC and JCMC head offices I = medium to high | No action was taken but agreement reached with the JCMC that, in order to increase support to the governorate offices, a national consultant will be contracted by UNDP to jointly with the JCMC HO team increase support to the governorate offices. The project will increasingly look for national consultants for different capacity-building assignments for the JCMC and JCC head and governorate offices. | The Project Manager, JCMC Executive Director, JCC Director General | Unchanged |

# Comments

In Difd proposal , there are 3 milestones for output 1 , while in your report , there are 4 ..Clarification needed please ?

There are 4 in the log-frame

According to Difd proposal , under this output , there are 3 milestones , while you report only 2 , clarify please ?

fixed