## Master sheet
Jordan Acc Lab Results Framework
**Included on page 18 of the Revised Accelerator Lab Network Multi-country Project document**
Intended Outcome as stated in the UNDP Strategic Plan: Outcome 1: Accelerated delivery of top-quality programmatic results for the SDGs (SP Organizational Performance, Tier 3)
Outcome indicators as stated in the UNDP Strategic Plan: SP Organisational Performance 1.2.6 Percentage of country offices that pilot and/or scale innovative tools and methodologies
Applicable Output(s) from the UNDP Strategic Plan: Organisational Performance 1.2 Cross-cutting approaches fully integrated into UNDP programmes and projects
Project title and Atlas Project Number: Accelerator Lab Network (Project Number: 0011678)
EXPECTED OUTPUTS | OUTPUT INDICATORS[1] | DATA SOURCE | Year 4 (2022)
Output 1: UNDP Country Offices and partners will have increased capability for scanning, sensemaking and experimentation for sustainable development solutions in 60 developing countries. | 1.1 Number of new data sources used at Country Office level | Action plan, data partnership documentation. | 5 new data sources per lab
| 1.2 Diversity of different data sources used | Action plan, data partnership documentation. | 7 different data sources per lab
| 1.3 Number of sustainable development solutions identified and documented | Solutions mapping platform. | 25 new potential solutions per lab
| 1.4 Variety of innovation methods used to test and iterate over the different hypotheses | Innovation methods platform | 8 innovation methods per lab
Output 2: New sustainable development solutions will be scaled at country level as part of UNDP’s country programme and operations, national policy and/or local markets. | 2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | Blog tracker. | At least 10 blogs, or other (substantial) media posts published per year
| 2.2 Number of lab insights, processes or products which are taken up by governments or other partners | Survey of partners and governments. | At least 50% of our learning challenges have the public sector or other partner as counterpart
| 2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | Survey of partners and governments. | At least one government entity or partner has adopted an accelerator lab method.
| 2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | SenseMaker survey, UNDP Results Oriented Annual Report, Country Project Documents (CPDs, where applicable). | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects
Output 3: A core global level result will be that a global learning and scaling network is established and functioning. | 3.1 Size and density of the network effects among the Accelerator Labs | Teams, WhatsApp. | The lab interacts at least once a week with another lab in the network. 48 interaction per year
| 3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | Teams, WhatsApp. | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related.
| 3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | Google Analytics, Twitter, Medium and LinkedIn engagement metrics. | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account.
| 3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem. | Twitter, blog posts from identified actors of the Development ecosystem. | Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem.
Output 4: Acc Lab Jordan highlighted as a best practice model within the network | 4.1 AccLab Jordan advances equity and people's representation in UNDP work |  | 100% of our learning challenges consult with citizens and UNDP pillars
| 4.2 Enhance the effectiveness and efficiency of AccLab Jordan |  | At least 30% of our learning challenges complete an AccLab full learning cycle
The lab engages at least once a week with UNDP Jordan team members

## Acronyms
Acronym | Full name | Project Owner
MPR | Multipurpose Room - A project by the Governance and Peace pillar
SAIB | Society for Aid, Improvement, and Bridging | Hadil
RFT | Roof Top | Ru'a
PAR | Participatory Research - A collaboration with UNICEF | Hadil
IEF | Informal Economy Facility | Ru'a
CPD | Country Programme Document | Ayah
RCT | Random Control Trial
EB | Electricity Bill
WEE | Women Economic Empowerment | Ayah

## 2022 workplan (hidden)
Acc Lab Jordan 2022 Budget |  |  |  | Who |  |  |  |  | When (2022) | [11 empty] | When (2023)
OUTPUT INDICATORS | Year 4 (2022) | Activity |  | Acc Lab Accountable | Acc Lab responsible | UNDP support | Internal Partners | External Partners | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
1.1 Number of new data sources used at Country Office level | 5 new data sources per lab | 1.1.1 | Refer to 1.2 | Ayah | Ayah
1.2 Diversity of different data sources used | 7 different data sources per lab | 1.2.1 | PAR: Codesign PAR research questions and tools with UNICEF | Hadil | Hadil, Ru'a, Ayah | Bara'a | Youth, Innovation, + all pillars | UNICEF | bar: When (2022) Feb to When (2022) Mar
|  | 1.2.2 | CPD: Support in designing the stakeholders' consultations tools | Ayah | Hadil, Ru'a, Ayah | Dana, Rabia | Central Team | bar: When (2022) Jan to When (2022) Feb
|  | 1.2.3 | UNDP: refer to 2.2.7 | Ayah | Ayah | bar: When (2022) Jan to When (2022) Feb
|  | 1.2.4 | AccLab: Refer to 2.2.10 | Ayah | Ayah | bar: When (2022) Mar; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 1.2.5 | IEF: Conduct stakeholder mapping and power analysis | Ru'a | Ru'a (Ayah + Hadil?) | Salam, Michaela | Policy Advisory Team and IGSL | AZHJ, Ahmad Abboushi | bar: When (2022) Feb to When (2022) Apr
1.3 Number of sustainable development solutions identified and documented | 25 new potential solutions per lab | 1.3.1 | PAR: Document PAR results | Hadil | Hadil |  | Youth, Innovation | UNICEF | [13 empty] | Dependant on UNICEF progress | bar: When (2022) Jun to When (2022) Jul
|  | 1.3.2 | PAR: Document solutions mapped in PAR | Hadil | Ru'a |  | Youth, Innovation | [14 empty] | Dependant on UNICEF progress | bar: When (2022) Jul
|  | 1.3.3 | Gender: Map solutions for women transportation challenge | Ru'a | Ru'a |  | All pillars | bar: When (2022) May
|  | 1.3.4 | UNDP: refer to 2.2.7 | Ayah | Ru'a | bar: When (2022) Jan to When (2022) Feb
|  | 1.3.5 | AccLab: Refer to 2.2.10 | Ayah | Ru'a | bar: When (2022) Apr; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 1.3.6 | IEF: Co-design and co-run semistructured interviews | Ru'a | Ru'a, Ayah, Hadil | Salam, Michaela | Policy Advisory Team | AZHJ, Ahmad Abboushi | bar: When (2022) Mar to When (2022) Apr
1.4 Variety of innovation methods used to test and iterate over the different hypotheses | 8 experiments per lab | 1.4.1 | PAR: Run an experiment to test a hypotheses for one solution mapped from PAR | Hadil | Hadil, Ru'a, Ayah | TBD | Youth, Innovation (potentially one of the pillars -TBD) | Owners of the solution | bar: When (2022) Oct to When (2022) Dec
|  | 1.4.2 | MPR: Run an experiment to test MPR hypotheses | CANCELLED |  | Nancy, Wala | G&P | MoLA, Muncipalities, citizens | bar: When (2022) Jan to When (2022) Dec
|  | 1.4.3 | Gender: Run an experiment to test women transportation challenge hypotheses | Ru'a | Hadil |  | Potentially one of the pillars -TBD | bar: When (2022) Jun to When (2022) Sep
|  | 1.4.4 | SAIB: Supervise spatial design implementation done by SAIB | Hadil | Hadil |  |  | SAIB | bar: When (2022) Jan to When (2022) Jul
|  | 1.4.5 | SAIB: Supervise design research of the prototypes done by SAIB | Hadil | Hadil | Najd | Gender Specialist | SAIB | bar: When (2022) Nov
|  | 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Hadil | Hadil |  | Environment TBC | UNICEF | bar: When (2022) Feb to When (2022) Mar
|  | 1.4.7 | UNDP: Run two experiments to test hypotheses from UNDP Jordan work | Hadil | Hadil |  | TBD | TBD | bar: When (2022) May to When (2022) Jun; When (2022) Oct to When (2022) Nov
|  | 1.4.8 | AccLab: Run one experiment to test hypotheses for a learning challenge identified by AccLab | Hadil | Hadil |  | TBD | TBD | bar: When (2022) Oct to When (2022) Nov
2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | At least 10 blogs, or other (substantial) media posts published per year | 2.1.1 | SAIB: Publish a blog post in English and Arabic | Hadil | Hadil, copyeditor | Tala | Communications | SAIB TBC | bar: When (2022) Feb
|  | 2.1.2 | MPR: Publish a blog post English about the training workshops | CANCELLED | Hadil, copyeditor | Tala | Communications | bar: When (2022) Jan to When (2022) Dec
|  | 2.1.3 | IEF: Publish a series of 3 blog posts in English | Ru'a | Ru'a, copyeditor | Salam, Tala, Michaela | Communications + Policy Advisory Team | bar: When (2022) Jan; When (2022) May; When (2022) Aug
|  | 2.1.4 | UNDP: Publish a blog post on Exploring UNDP in Arabic | Ayah | Ayah, copyeditor | Tala | Communications | bar: When (2022) Apr
|  | 2.1.5 | PAR: Publish a media post about PAR | Hadil | Hadil, copyeditor | Tala | Communications, PR | UNICEF | bar: When (2022) May
|  | 2.1.6 | Manage a coverage in the newspaper about the AccLab | Ayah | Ayah | Tala | Communications, PR | bar: When (2022) Sep
|  | 2.1.7 | SAIB: Manage a radio interview | Hadil | Hadil | Tala | Communications, PR | SAIB | bar: When (2022) Dec
|  | 2.1.8 | Organize a media piece/event with the Arab states AccLabs | Ru'a / Ayah |  |  | Communications | RBAS AccLab Network | bar: When (2022) Jun to When (2022) Jul
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | At least 50% of our learning challenges have the public sector or other partner as counterpart | 2.2.1 | PAR: Refer to 1.4.1
|  | 2.2.2 | MPR: Design the co-creation tooklit | CANCELLED | Hadil, Ru'a, Ayah, consultant | Nancy, Wala | G&P | bar: When (2022) Jan to When (2022) Dec
|  | 2.2.3 | MPR: Train G&P team on the co-creation toolkit and the roadmap report | CANCELLED | Ru'a | Nancy, Wala | G&P | Municipalities MoLA | bar: When (2022) Jan to When (2022) Dec
|  | 2.2.4 | MPR: Develop the roadmap report | CANCELLED | Ru'a, consultant | Nancy, Wala | G&P | Municipalities | bar: When (2022) Jan to When (2022) Dec
|  | 2.2.5 | SAIB: Share knowledge of insights and processes of spatial design experiment with government/other partners | Hadil |  | Najd | Gender Specialist | SAIB Others TBD | bar: When (2022) Dec
|  | 2.2.6 | EB: Send a summary report on the elecricity bill project | Hadil | Hadil, Ayah | Rana | Env. pillar | bar: When (2022) Mar
|  | 2.2.7 | UNDP: Explore and map solutions under UNDP CO Jordan | Ayah | Ru'a, Ayah | Randa, Majida | All pillars | bar: When (2022) Jan to When (2022) Feb
|  | 2.2.8 | UNDP: Assess the solutions mapped under UNDP CO Jordan | Ayah | Hadil, Ru'a, Ayah | Randa, Majida | All pillars | bar: When (2022) Mar to When (2022) Apr
|  | 2.2.9 | UNDP: Propose learning challenges for potential collaboration with UNDP CO Jordan pillars | Ayah | Hadil, Ru'a, Ayah | Randa, Majida, | All pillars | bar: When (2022) Apr
|  | 2.2.10 | AccLab: Explore and map solutions under UNDP SDGs for Jordan | Ayah | Ru'a | TBD | TBD | bar: When (2022) Mar to When (2022) Apr; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 2.2.11 | AccLab: Assess the solutions mapped under SDGs for Jordan | Ayah | Hadil, Ru'a, Ayah | Randa, Majida | TBD | TBD | bar: When (2022) Jul
|  | 2.2.12 | UNDP: Propose learning challenges for potential collaboration with local partners | Ayah | Hadil, Ru'a, Ayah | Randa, Majida | TBD | TBD | bar: When (2022) Jul
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | At least one government entity or partner has adopted an accelerator lab method. | 2.3.1 | Refer to 2.2
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects | 2.4.1 | Refer to Output 1 and Output indicator 2.2
|  | 2.4.2 | WEE: Map the systems within the solid waste women business ideas and identify areas for collaboration with the team | Ayah | Ayah, Hadil | Ghadir | IGSL pillar | bar: When (2022) Jan to When (2022) Feb
3.1 Size and density of the network effects among the Accelerator Labs | The lab interacts at least once a week with another lab in the network. 48 interaction per year | 3.1.1 | PAR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.1.2 | MPR: Share some updates on Teams and WhatsApp | CANCELLED | Hadil, Ru'a, Ayah
|  | 3.1.3 | AccLab: Organise quarterly brown bag | AccLab Jo | Hadil, Ru'a, Ayah, comm. intern |  | Learning committee | bar: When (2022) Apr; When (2022) Jul; When (2022) Oct
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related. | 3.2.1 | PAR: Share the PAR report with the AccLab network and UNDP Jo | Hadil | Hadil, comms ntern | bar: When (2022) Nov
|  | 3.2.2 | MPR: Publish the RCT results | CANCELLED | consultant | Nancy, Wala | G&P pillar | bar: When (2022) Jan to When (2023) Jan
|  | 3.2.3 | AccLab: Post knowledge products on Teams AccLab channels | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.2.4 | AccLab: Share knowledge products via email to mailing lists related to Innovation, AccLabs, and the Arab states region | AccLab Jo | Hadil, Ru'a, Ayah
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account. | 3.3.1 | AccLab: Send a picture of the team doing an action: field visit, design session, experimentation | AccLab Jo | Comms. intern | Tala | Communications | bar: When (2022) Mar; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 3.3.2 | SAIB: Send a picture of SAIB construction work with a short description in Arabic and English | Hadil | Comms. intern | Tala | Communications | SAIB | bar: When (2022) Jul
|  | 3.3.3 | SAIB: Share knowledge of insights and processes of Spatial Design Experiment with government/other partners | Hadil | Hadil, Comms. intern |  | Communications, PR | SAIB | bar: When (2022) Dec
|  | 3.3.4 | MPR: Send a picture of various events under the experiement and training with a short description in Arabic and English | CANCELLED | Comms. intern | Tala, Nancy | G&P pillar | bar: When (2022) Jan to When (2022) Dec
|  | 3.3.5 | IEF: Send a picture of data collection for IEF | Ru'a | Comms. intern | Tala | Communications | bar: When (2022) Feb
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem. | 3.4.1 | AccLab: organise quarterly speaker series with partner organizations | AccLab Jo | Comms. intern |  | Communications | TBD | bar: When (2022) May; When (2022) Aug; When (2022) Nov
|  | 3.4.2 | MPR: Refer to 3.2.2 | CANCELLED
4.1 AccLab Jordan advances equity and people's representation in UNDP work | 100% of our learning challenges consult with cizitens and UNDP pillars | 4.1.1 | Refer to Output 1
|  | 4.1.3 | MPR: Run an RCT to evaluate the project hyotheses after implementation | CANCELLED | consultant | Nancy, Wala | G&P | bar: When (2022) Jan to When (2022) Dec
|  | 4.1.5 | AccLab: Design and launch Community Design Research Group | Ru'a | AccLab Jo | Randa | HR, TBD | CBOs TBC Youth/volunteer networks TBC | bar: When (2022) Apr to When (2022) Jun
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | At least 30% of our learning challenges go from sense to test | 4.2.1 | Refer to Output 1
| The lab engages at least once a week with UNDP Jordan team members | 4.2.2 | RT: Manage the rooftop renovation project | Ru'a | AccLab Jo | Mousa, Rana, Dana | Staff Assoc., Greening the blue team | bar: When (2022) Apr to When (2022) May
Refer to 3.4.1
Refer to 3.1.3

## 2022 budget summary (hidden)
Acc Lab Jordan 2022 Budget |  |  | Budget in JOD | [12 empty] | Codes
Category | Line item |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Donor code | Funder code
Exploration | 1.2.4 | AccLab: Explore under UNDP SDGs for Jordan | Budget in JOD Mar: 1200; Budget in JOD Jun: 1200; Budget in JOD Sep: 1200; Budget in JOD Dec: 1200; Budget in JOD Total: 4800 | 12298 | 30000
|  | AccLab: Design and launch Community Design Research Group | Budget in JOD Apr: 3500; Budget in JOD Total: 3500 | 12298 | 30000
Solutions mapping | 1.3.3 | Gender: Map solutions for women transportation challenge | Budget in JOD May: 1200; Budget in JOD Total: 1200 | 12298 | 30000
| 1.3.4 | UNDP: Map solutions under UNDP CO Jordan | Budget in JOD Total: 0 | 12298 | 30000
| 1.3.5 | AccLab: Map solutions under UNDP SDGs for Jordan | Budget in JOD Apr: 1200; Budget in JOD Jun: 1200; Budget in JOD Sep: 1200; Budget in JOD Dec: 1500; Budget in JOD Total: 5100 | 12298 | 30000
|  | IEF: Support IEF portfolio design activities | Budget in JOD Jun: 2000; Budget in JOD Total: 2000 | 12298 | 30000
Experimenting | 1.4.1 | PAR: Run an experiment to test a hypotheses for one solution mapped from PAR | Budget in JOD Jun: 2000; Budget in JOD Total: 2000 | 12298 | 30000
| 1.4.2 | MPR: Run an experiment to test MPR hypotheses | Budget in JOD Jun: 100; Budget in JOD Jul: 100; Budget in JOD Aug: 100; Budget in JOD Total: 300 | 12298 | 30000
| 1.4.3 | Gender: Run an experiment to test women transportation challenge hypotheses | Budget in JOD Jun: 5000; Budget in JOD Total: 5000 | 12298 | 30000
| 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Budget in JOD Mar: 1000; Budget in JOD Total: 1000 | 12298 | 30000
| 1.4.7 | UNDP: Run two experiments to test hypotheses from UNDP Jordan work | Budget in JOD May: 3500; Budget in JOD Oct: 3500; Budget in JOD Total: 7000 | 12298 | 30000
| 1.4.8 | AccLab: Run one experiment to test hypotheses for a learning challenge identified by AccLab | Budget in JOD Oct: 3500; Budget in JOD Total: 3500 | 12298 | 30000
Consultants |  | Hire an RCT consultant | Budget in JOD Sep: 8750; Budget in JOD Total: 8750 | 12298 | 30000
Communications |  | Buy social media sponsored ads | Budget in JOD Total: 0 | 12298 | 30000
|  | Produce a podcast | Budget in JOD Sep: 2000; Budget in JOD Total: 2000 | 12298 | 30000
|  | Hire a communications intern |  |  |  | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 2700 | 12298 | 30000 | Note: we are suggesting this compensation for the intern, happy to discuss another arrangement
|  | Hire a copyeditor (freelance) |  |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 630 | 12298 | 30000
|  | AccLab: Organise quarterly speaker series with partner organizations | Budget in JOD May: 350; Budget in JOD Aug: 350; Budget in JOD Nov: 350; Budget in JOD Total: 1050 | 12298 | 30000
Subscriptions |  | Buy an Adobe subcription | Budget in JOD Nov: 360; Budget in JOD Total: 360 | 12298 | 30000
Miscellaneous | 4.2.2 | RT: Manage the rooftop renovation project | Budget in JOD May: 2000; Budget in JOD Total: 2000 | 12298 | 30000
|  | Professional development fund: one for each AccLab team member (total 3) | Budget in JOD Total: 2100 | 12298 | 30000
[14 empty] | Total (JOD) | 54990
|  |  | Budget in JOD Dec: Total (USD); Budget in JOD Total: 77669.4915 |  |  | Note: we deducted the common services budget which are around $25k

## 2022 workplan Q1
Acc Lab Jordan 2022 Budget |  |  |  | Who |  |  |  |  | When (2022) | [11 empty] | When (2023)
OUTPUT INDICATORS | Year 4 (2022) | Activity |  | Acc Lab Accountable | Acc Lab responsible | UNDP support | Internal Partners | External Partners | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
1.1 Number of new data sources used at Country Office level | 5 new data sources per lab | 1.1.1 | AccLab: Collect data related to the AccLab core learning challenge and exploratory learning questions | Ayah | Ayah | bar: When (2022) May
1.2 Diversity of different data sources used | 7 different data sources per lab | 1.2.1 | PAR: Codesign PAR research questions and tools with UNICEF | Hadil | Hadil |  | Youth, Innovation, + all pillars | UNICEF | bar: When (2022) Mar to When (2022) Jul
|  | 1.2.2 | CPD: Support in designing the stakeholders' consultations tools | Ayah | Hadil, Ru'a, Ayah | Dana, Rabia | Central Team | bar: When (2022) Jan to When (2022) Feb
|  | 1.2.3 | UNDP: refer to 2.2.7 | Ayah | Ayah | bar: When (2022) Jan to When (2022) Feb
|  | 1.2.4 | AccLab: Refer to 2.2.10 | Ayah | Ayah | bar: When (2022) Mar to When (2022) Apr
|  | 1.2.5 | IEF: Conduct stakeholder mapping, and power analysis | Ru'a | Ru'a (Ayah + Hadil?) | Salam, Michaela | Policy Advisory Team and IGSL | AZHJ, Ahmad Abboushi | bar: When (2022) Mar to When (2022) May
|  | 1.2.6 | CPD: Participate in the CPD core team | Ayah | Ayah |  | Majida, Dana, Rabia, Baker | bar: When (2022) Feb to When (2022) Apr
|  | 1.2.7 | CPD: Participate in the CPD government consultations | Ayah | Ayah, Hadil |  | Majida, Dana, Rabia, Baker | bar: When (2022) Apr to When (2022) May
1.3 Number of sustainable development solutions identified and documented | 25 new potential solutions per lab | 1.3.1 | PAR: Document PAR results | Hadil | Hadil |  | Youth, Innovation | UNICEF | [13 empty] | Dependant on UNICEF progress | bar: When (2022) Aug to When (2022) Sep
|  | 1.3.2 | PAR: Document solutions mapped in PAR | Hadil | Ru'a |  | Youth, Innovation | [14 empty] | Dependant on UNICEF progress | bar: When (2022) Aug
|  | 1.3.4 | UNDP: refer to 2.2.7 | Ayah | Ru'a | bar: When (2022) Jan to When (2022) Feb
|  | 1.3.5 | AccLab: Refer to 2.2.10 | Ru'a | Ru'a | bar: When (2022) Apr; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 1.3.6 | IEF: Co-design and co-run semistructured interviews | Ru'a | Ru'a, Ayah, Hadil | Salam, Michaela | Policy Advisory Team | AZHJ, Ahmad Abboushi | bar: When (2022) Mar to When (2022) Apr
|  | 1.3.7 | AccLab: Map solutions and indigenous knowledge under the AccLab learning challenge and questions | Ru'a | Ru'a | bar: When (2022) May
1.4 Variety of innovation methods used to test and iterate over the different hypotheses | 8 experiments per lab | 1.4.1 | AccLab: Run 4 to 6 rapid prototypes to test ideas that emerged from weak signals and exploratory learning questions (including internal signals) | Hadil | Hadil |  | Potentially one of the pillars -TBD | TBD | bar: When (2022) May to When (2022) Sep
|  | 1.4.2 | SAIB: Supervise spatial design implementation done by SAIB | Hadil | Hadil |  |  | SAIB | bar: When (2022) Jan to When (2022) Jul
|  | 1.4.3 | SAIB: Supervise design research of the prototypes done by SAIB (post assessment) | Hadil | Hadil | Najd | Gender Specialist | SAIB | bar: When (2022) Nov
|  | 1.4.4 | UNICEF: Run an experiment to test Date Compost hyoptheses | Hadil | Hadil |  | Environment TBC | UNICEF
|  | 1.4.5 | AccLab: Design and run a portfolio of experiments for the Lab core learning challenge | Hadil | Hadil |  | TBD | TBD | bar: When (2022) Jun
2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | At least 10 blogs, or other (substantial) media posts published per year | 2.1.1 | SAIB: Publish a blog post in English and Arabic | Hadil | Hadil, copyeditor | Tala | Communications | SAIB TBC | bar: When (2022) Feb
|  | 2.1.2 | IEF: Publish a series of 3 blog posts in English | Ru'a | Ru'a, copyeditor | Salam, Tala, Michaela | Communications + Policy Advisory Team | bar: When (2022) Jan; When (2022) Jun; When (2022) Aug
|  | 2.1.3 | UNDP: Publish a blog post on Exploring UNDP in Arabic | Ayah | Ayah, copyeditor | Tala | Communications | bar: When (2022) Apr
|  | 2.1.4 | PAR: Publish a media post about PAR | Hadil | Hadil, copyeditor | Tala | Communications, PR | UNICEF | bar: When (2022) May
|  | 2.1.5 | Manage a coverage in the newspaper about the AccLab | Ayah | Ayah | Tala | Communications, PR | bar: When (2022) Sep
|  | 2.1.6 | SAIB: Manage a radio interview | Hadil | Hadil | Tala | Communications, PR | SAIB | bar: When (2022) Dec
|  | 2.1.7 | UNDP: write a blog post about CPD process | Ayah | Hadil, Ayah, Ru'a | Tala, Dana, Rabia, Majida | Communications, PR | bar: When (2022) May; When (2022) Dec
|  | 2.1.8 | AccLab: write a blog post about double diamond adapted for the AccLab Jordan | Hadil | Hadil, Ayah | Tala | Communications, PR | bar: When (2022) Jul; When (2022) Dec
|  | 2.1.9 | Organize a media piece/event with the Arab states AccLabs | Ru'a / Ayah |  |  | Communications | RBAS AccLab Network | bar: When (2022) Jun to When (2022) Jul
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | At least 50% of our learning challenges have the public sector or other partner as counterpart | 2.2.1 | SAIB: Share knowledge of insights and processes of spatial design experiment with government/other partners | Hadil |  | Najd | Gender Specialist | SAIB Others TBD | bar: When (2022) Dec
|  | 2.2.2 | EB: Send a summary report on the elecricity bill project | Hadil | Hadil, Ayah | Rana | Env. pillar | bar: When (2022) Jun
|  | 2.2.3 | UNDP: Explore and map solutions under UNDP CO Jordan | Ayah | Ru'a, Ayah | Randa, Majida | All pillars | bar: When (2022) Jan to When (2022) Mar
|  | 2.2.4 | AccLab: Choose the AccLab core learning challenge and exploratory challenges | Ayah | Hadil, Ru'a, Ayah | Randa, Majida, | All pillars | bar: When (2022) Apr
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | At least one government entity or partner has adopted an accelerator lab method. | 2.3.1 | AccLab: Handover a portfolio of solutions to one partner (core learning challenge or exploratory learning questions) | AccLab
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects | 2.4.1 | Refer to Output 1 and Output indicator 2.2
|  | 2.4.2 | WEE: Map the systems within the solid waste women business ideas and identify areas for collaboration with the team | Ayah | Ayah, Hadil | Ghadir | IGSL pillar | bar: When (2022) Jan to When (2022) Feb
|  | 2.4.3 | UNDP: Devise a plan for the technical support which AccLab will provide to the CO | Ayah | Ayah, Hadil, Ru'a | Randa, Majida | All pillars | bar: When (2022) May
3.1 Size and density of the network effects among the Accelerator Labs | The lab interacts at least once a week with another lab in the network. 48 interaction per year | 3.1.1 | PAR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah | bar: When (2022) Jan
|  | 3.1.2 | AccLab: Organise quarterly brown bag | AccLab Jo | Hadil, Ru'a, Ayah, comm. intern |  | Learning committee | bar: When (2022) Jun; When (2022) Sep; When (2022) Dec
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related. | 3.2.1 | PAR: Share the PAR report with the AccLab network and UNDP Jo | Hadil | Hadil, comms ntern | bar: When (2022) Nov
|  | 3.2.2 | AccLab: Post knowledge products on Teams AccLab channels | AccLab Jo | Hadil, Ru'a, Ayah | bar: When (2022) Jan
|  | 3.2.3 | AccLab: Share knowledge products via email to mailing lists related to Innovation, AccLabs, and the Arab states region | AccLab Jo | Hadil, Ru'a, Ayah | bar: When (2022) Jan
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account. | 3.3.1 | AccLab: Send a picture of the team doing an action: field visit, design session, experimentation | AccLab Jo | Comms. intern | Tala | Communications | bar: When (2022) Mar; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 3.3.2 | SAIB: Send a picture of SAIB construction work with a short description in Arabic and English | Hadil | Comms. intern | Tala | Communications | SAIB | bar: When (2022) Jul
|  | 3.3.3 | SAIB: Share knowledge of insights and processes of Spatial Design Experiment with government/other partners | Hadil | Hadil, Comms. intern |  | Communications, PR | SAIB | bar: When (2022) Dec
|  | 3.3.4 | IEF: Send a picture of data collection for IEF | Ru'a | Comms. intern | Tala | Communications | bar: When (2022) Feb
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem. | 3.4.1 | AccLab: organise quarterly speaker series with partner organizations | AccLab Jo | Comms. intern |  | Communications | TBD | bar: When (2022) May; When (2022) Aug; When (2022) Nov
4.1 AccLab Jordan advances equity and people's representation in UNDP work | 100% of our learning challenges consult with cizitens and UNDP pillars | 4.1.1 | Refer to Output 1
|  | 4.1.2 | AccLab: Design and launch Community Design Research Group | Ru'a | AccLab Jo | Randa | HR, TBD | CBOs TBC Youth/volunteer networks TBC | bar: When (2022) May to When (2022) Jul
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | At least 30% of our learning challenges go from sense to test | 4.2.1 | Refer to Output 1
| The lab engages at least once a week with UNDP Jordan team members | 4.2.2 | RT: Manage the rooftop renovation project | Ru'a | AccLab Jo | Mousa, Rana, Dana | Staff Assoc., Greening the blue team | bar: When (2022) Apr to When (2022) Jun
|  | 4.2.3 | Refer to 3.4.1
|  | 4.2.4 | Refer to 3.1.3
|  | 4.2.5 | AccLab: develop the AccLab menu of services | Ru'a | AccLab Jo | Randa, Majida | bar: When (2022) Jun to When (2022) Jul
|  | 4.2.6 | AccLab: develop the AccLab Jordan "brand" | Ayah | AccLab Jo | Randa | bar: When (2022) Jun to When (2022) Jul

## 2022 workplan original (hidden)
Acc Lab Jordan 2022 Budget |  |  |  | Who |  |  |  |  | When (2022) | [11 empty] | When (2023)
OUTPUT INDICATORS | Year 4 (2022) | Activity |  | Acc Lab Accountable | Acc Lab responsible | UNDP support | Internal Partners | External Partners | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
1.1 Number of new data sources used at Country Office level | 5 new data sources per lab | 1.1.1 | Refer to 1.2 | Ayah | Ayah
1.2 Diversity of different data sources used | 7 different data sources per lab | 1.2.1 | PAR: Codesign PAR research questions and tools with UNICEF | Hadil | Hadil, Ru'a, Ayah | Bara'a | Youth, Innovation, + all pillars | UNICEF | bar: When (2022) Feb to When (2022) Mar
|  | 1.2.2 | CPD: Support in designing the stakeholders' consultations tools | Ru'a | Hadil, Ru'a, Ayah | Dana, Rabia | Central Team | bar: When (2022) Jan to When (2022) Feb
|  | 1.2.3 | UNDP: refer to 2.2.7 | Ayah | Ayah | bar: When (2022) Jan to When (2022) Feb
|  | 1.2.4 | AccLab: Refer to 2.2.10 | Ayah | Ayah | bar: When (2022) Mar; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 1.2.5 | IEF: Conduct stakeholder mapping and power analysis | Ru'a | Ru'a (Ayah + Hadil?) | Salam, Michaela | Policy Advisory Team and IGSL | AZHJ, Ahmad Abboushi | bar: When (2022) Jan to When (2022) Mar
1.3 Number of sustainable development solutions identified and documented | 25 new potential solutions per lab | 1.3.1 | PAR: Document PAR results | Hadil | Hadil |  | Youth, Innovation | UNICEF | [13 empty] | Dependant on UNICEF progress | bar: When (2022) Jun to When (2022) Jul
|  | 1.3.2 | PAR: Document solutions mapped in PAR | Hadil | Ru'a |  | Youth, Innovation | [14 empty] | Dependant on UNICEF progress | bar: When (2022) Jul
|  | 1.3.3 | Gender: Map solutions for women transportation challenge | Ru'a | Ru'a |  | All pillars | bar: When (2022) May
|  | 1.3.4 | UNDP: refer to 2.2.7 | Ayah | Ru'a | bar: When (2022) Jan to When (2022) Feb
|  | 1.3.5 | AccLab: Refer to 2.2.10 | Ayah | Ru'a | bar: When (2022) Apr; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 1.3.6 | IEF: Co-design and co-run semistructured interviews | Ru'a | Ru'a, Ayah, Hadil | Salam, Michaela | Policy Advisory Team | AZHJ, Ahmad Abboushi | bar: When (2022) Feb to When (2022) Mar
1.4 Variety of innovation methods used to test and iterate over the different hypotheses | 8 experiments per lab | 1.4.1 | PAR: Run an experiment to test a hypotheses for one solution mapped from PAR | Hadil | Hadil, Ru'a, Ayah | TBD | Youth, Innovation (potentially one of the pillars -TBD) | Owners of the solution | bar: When (2022) Oct to When (2022) Dec
|  | 1.4.2 | MPR: Run an experiment to test MPR hypotheses | Hadil | Hadil, Ru'a, Ayah | Nancy, Wala | G&P | MoLA, Muncipalities, citizens | bar: When (2022) Jun to When (2022) Aug
|  | 1.4.3 | Gender: Run an experiment to test women transportation challenge hypotheses | Ru'a | Hadil |  | Potentially one of the pillars -TBD | bar: When (2022) Jun to When (2022) Sep
|  | 1.4.4 | SAIB: Supervise spatial design implementation done by SAIB | Hadil | Hadil |  |  | SAIB | bar: When (2022) Jan to When (2022) Jul
|  | 1.4.5 | SAIB: Supervise design research of the prototypes done by SAIB | Hadil | Hadil | Najd | Gender Specialist | SAIB | bar: When (2022) Nov
|  | 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Hadil | Hadil |  | Environment TBC | UNICEF | bar: When (2022) Feb to When (2022) Mar
|  | 1.4.7 | UNDP: Run two experiments to test hypotheses from UNDP Jordan work | Hadil | Hadil |  | TBD | TBD | bar: When (2022) May to When (2022) Jun; When (2022) Oct to When (2022) Nov
|  | 1.4.8 | AccLab: Run one experiment to test hypotheses for a learning challenge identified by AccLab | Hadil | Hadil |  | TBD | TBD | bar: When (2022) Oct to When (2022) Nov
2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | At least 10 blogs, or other (substantial) media posts published per year | 2.1.1 | SAIB: Publish a blog post in English and Arabic | Hadil | Hadil, copyeditor | Tala | Communications | SAIB TBC | bar: When (2022) Feb
|  | 2.1.2 | MPR: Publish a blog post English about the training workshops | Hadil | Hadil, copyeditor | Tala | Communications | bar: When (2022) Jun
|  | 2.1.3 | IEF: Publish a series of 3 blog posts in English | Ru'a | Ru'a, copyeditor | Salam, Tala, Michaela | Communications + Policy Advisory Team | bar: When (2022) Jan; When (2022) Mar; When (2022) Aug
|  | 2.1.4 | UNDP: Publish a blog post on Exploring UNDP in Arabic | Ayah | Ayah, copyeditor | Tala | Communications | bar: When (2022) Apr
|  | 2.1.5 | PAR: Publish a media post about PAR | Hadil | Hadil, copyeditor | Tala | Communications, PR | UNICEF | bar: When (2022) May
|  | 2.1.6 | Manage a coverage in the newspaper about the AccLab | Ayah | Ayah | Tala | Communications, PR | bar: When (2022) Sep
|  | 2.1.7 | SAIB: Manage a radio interview | Hadil | Hadil | Tala | Communications, PR | SAIB | bar: When (2022) Dec
|  | 2.1.8 | Organize a media piece/event with the Arab states AccLabs | Ru'a / Ayah |  |  | Communications | RBAS AccLab Network | bar: When (2022) Jun to When (2022) Jul
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | At least 50% of our learning challenges have the public sector or other partner as counterpart | 2.2.1 | PAR: Refer to 1.4.1
|  | 2.2.2 | MPR: Design the co-creation tooklit | Hadil | Hadil, Ru'a, Ayah, consultant | Nancy, Wala | G&P | bar: When (2022) Jan to When (2022) Mar
|  | 2.2.3 | MPR: Train G&P team on the co-creation toolkit and the roadmap report | Hadil | Ru'a | Nancy, Wala | G&P | Municipalities MoLA | bar: When (2022) Apr to When (2022) May
|  | 2.2.4 | MPR: Develop the roadmap report | Hadil | Ru'a, consultant | Nancy, Wala | G&P | Municipalities | bar: When (2022) Apr
|  | 2.2.5 | SAIB: Share knowledge of insights and processes of spatial design experiment with government/other partners | Hadil |  | Najd | Gender Specialist | SAIB Others TBD | bar: When (2022) Dec
|  | 2.2.6 | EB: Send a summary report on the elecricity bill project | Hadil | Hadil, Ayah | Rana | Env. pillar | bar: When (2022) Mar
|  | 2.2.7 | UNDP: Explore and map solutions under UNDP CO Jordan | Ayah | Ru'a, Ayah | Randa, Majida | All pillars | bar: When (2022) Jan to When (2022) Feb
|  | 2.2.8 | UNDP: Assess the solutions mapped under UNDP CO Jordan | Ayah | Hadil, Ru'a, Ayah | Randa, Majida | All pillars | bar: When (2022) Mar to When (2022) Apr
|  | 2.2.9 | UNDP: Propose learning challenges for potential collaboration with UNDP CO Jordan pillars | Ayah | Hadil, Ru'a, Ayah | Randa, Majida, | All pillars | bar: When (2022) Apr
|  | 2.2.10 | AccLab: Explore and map solutions under UNDP SDGs for Jordan | Ayah | Ru'a | TBD | TBD | bar: When (2022) Mar to When (2022) Apr; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 2.2.11 | AccLab: Assess the solutions mapped under SDGs for Jordan | Ayah | Hadil, Ru'a, Ayah | Randa, Majida | TBD | TBD | bar: When (2022) Jul
|  | 2.2.12 | UNDP: Propose learning challenges for potential collaboration with local partners | Ayah | Hadil, Ru'a, Ayah | Randa, Majida | TBD | TBD | bar: When (2022) Jul
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | At least one government entity or partner has adopted an accelerator lab method. | 2.3.1 | Refer to 2.2
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects | 2.3.2 | Refer to Output 1 and Output indicator 2.2
3.1 Size and density of the network effects among the Accelerator Labs | The lab interacts at least once a week with another lab in the network. 48 interaction per year | 3.1.1 | PAR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.1.2 | MPR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.1.3 | AccLab: Organise quarterly brown bag | AccLab Jo | Hadil, Ru'a, Ayah, comm. intern |  | Learning committee | bar: When (2022) Apr; When (2022) Jul; When (2022) Oct
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related. | 3.2.1 | PAR: Share the PAR report with the AccLab network and UNDP Jo | Hadil | Hadil, comms ntern | bar: When (2022) Nov
|  | 3.2.2 | MPR: Publish the RCT results | Hadil | consultant | Nancy, Wala | G&P pillar | bar: When (2022) Dec to When (2023) Jan
|  | 3.2.3 | AccLab: Post knowledge products on Teams AccLab channels | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.2.4 | AccLab: Share knowledge products via email to mailing lists related to Innovation, AccLabs, and the Arab states region | AccLab Jo | Hadil, Ru'a, Ayah
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account. | 3.3.1 | AccLab: Send a picture of the team doing an action: field visit, design session, experimentation | AccLab Jo | Comms. intern | Tala | Communications | bar: When (2022) Mar; When (2022) Jun; When (2022) Sep; When (2022) Dec
|  | 3.3.2 | SAIB: Send a picture of SAIB construction work with a short description in Arabic and English | Hadil | Comms. intern | Tala | Communications | SAIB | bar: When (2022) Jul
|  | 3.3.3 | SAIB: Share knowledge of insights and processes of Spatial Design Experiment with government/other partners | Hadil | Hadil, Comms. intern |  | Communications, PR | SAIB | bar: When (2022) Dec
|  | 3.3.4 | MPR: Send a picture of various events under the experiement and training with a short description in Arabic and English | Hadil | Comms. intern | Tala, Nancy | G&P pillar | bar: When (2022) May
|  | 3.3.5 | IEF: Send a picture of data collection for IEF | Ru'a | Comms. intern | Tala | Communications | bar: When (2022) Feb
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem. | 3.4.1 | AccLab: organise quarterly speaker series with partner organizations | AccLab Jo | Comms. intern |  | Communications | TBD | bar: When (2022) May; When (2022) Aug; When (2022) Nov
|  | 3.4.2 | MPR: Refer to 3.2.2 | Hadil
4.1 AccLab Jordan advances equity and people's representation in UNDP work | 100% of our learning challenges consult with cizitens and UNDP pillars | 4.1.1 | Refer to Output 1
|  | 4.1.3 | MPR: Run an RCT to evaluate the project hyotheses after implementation | Hadil | consultant | Nancy, Wala | G&P | bar: When (2022) Sep to When (2022) Nov
|  | 4.1.5 | AccLab: Design and launch People Support Group | Ru'a | AccLab Jo | Randa | HR, TBD | CBOs TBC Youth/volunteer networks TBC | bar: When (2022) Apr to When (2022) Jun
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | At least 30% of our learning challenges go from sense to test | 4.2.1 | Refer to Output 1
| The lab engages at least once a week with UNDP Jordan team members | 4.2.2 | RT: Manage the rooftop renovation project | Ru'a | AccLab Jo | Moussa, Rana, Dana | Staff Assoc., Greening the blue team | bar: When (2022) Apr to When (2022) May
Refer to 3.4.1
Refer to 3.1.3
Note on D43: I wouldn't consider mapping UNDP projects "solutions mapping". Mapping solutions in the AccLab context means grassroots solutions developed by someone trying to solve their own problems. -Ru'a Al-Abweh
Note on D53: these we can change change them every month as not to crowd the workplan and once completed we move them to another tab -Ayah Younis

## 2022 budget (hidden)
Acc Lab Jordan 2022 Budget |  |  | Budget in JOD
OUTPUT INDICATORS | Line item |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.1 Number of new data sources used at Country Office level | 1.1.1 | Refer to 1.2
Exploration | 1.2.1 | PAR: Codesign PAR methodology with UNICEF
| 1.2.2 | CPD: Support in designing the stakeholders' consultations tools | bar: Budget in JOD Jan to Budget in JOD Feb
| 1.2.3 | UNDP: Explore under UNDP CO Jordan | Budget in JOD Jan: 0; Budget in JOD Feb: 0
| 1.2.4 | AccLab: Explore under UNDP SDGs for Jordan | Budget in JOD Mar: 1500; Budget in JOD Jun: 1500; Budget in JOD Sep: 1500; Budget in JOD Dec: 1500
Solutions mapping | 1.3.1 | PAR: Document PAR results
| 1.3.2 | PAR: Document solutions mapped in PAR
| 1.3.3 | Gender: Map solutions for women transportation challenge | Budget in JOD May: 1500
| 1.3.4 | UNDP: Map solutions under UNDP CO Jordan
| 1.3.5 | AccLab: Map solutions under UNDP SDGs for Jordan | Budget in JOD Apr: 1500; Budget in JOD Jun: 1500; Budget in JOD Sep: 1500; Budget in JOD Dec: 1500
Experimenting | 1.4.1 | PAR: Run an experiment to test a hypotheses for one solution mapped from PAR | [12 empty] | 2000
| 1.4.2 | MPR: Run an experiment to test MPR hypotheses | Budget in JOD Jun: 120; Budget in JOD Jul: 120; Budget in JOD Aug: 120
| 1.4.3 | Gender: Run an experiment to test women transportation challenge hypotheses | Budget in JOD Jun: 6000
| 1.4.4 | SAIB: Supervise spatial design implementation done by SAIB | bar: Budget in JOD Jan to Budget in JOD Jul
| 1.4.5 | SAIB: Supervise design research of the prototypes done by SAIB | bar: Budget in JOD Nov
| 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Budget in JOD Mar: 1000
| 1.4.7 | UNDP: Run two experiments to test hypotheses from UNDP Jordan work | Budget in JOD May: 3500; Budget in JOD Oct: 3500
| 1.4.8 | AccLab: Run one experiment to test hypotheses for a learning challenge identified by AccLab | Budget in JOD Oct: 3500
Communications |  | Hire a communications intern |  |  |  | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | Note: we are suggesting this compensation
|  | Buy an Adobe subcription | Budget in JOD Nov: 360
|  | Buy social media sponsored ads | Budget in JOD Dec: 300
|  | Produce a podcast | Budget in JOD Sep: 2000
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | 2.2.1 | PAR: Refer to 1.4.1
| 2.2.2 | MPR: Design the co-creation tooklit | Budget in JOD Jan: 0; Budget in JOD Feb: 0; Budget in JOD Mar: 0
| 2.2.3 | MPR: Train G&P team on the co-creation toolkit and the roadmap report | Budget in JOD Apr: 0; Budget in JOD May: 0
| 2.2.4 | MPR: Develop the roadmap report | Budget in JOD Apr: 0
| 2.2.5 | SAIB: Share knowledge of insights and processes of spatial design experiment with government/other partners | bar: Budget in JOD Dec
| 2.2.6 | EB: Send a summary report on the elecricity bill project | bar: Budget in JOD Mar
| 2.2.7 | UNDP: Explore and map solutions under UNDP CO Jordan | bar: Budget in JOD Jan to Budget in JOD Feb
| 2.2.8 | UNDP: Assess the solutions mapped under UNDP CO Jordan | bar: Budget in JOD Mar to Budget in JOD Apr
| 2.2.9 | UNDP: Propose learning challenges for potential collaboration with UNDP CO Jordan pillars | bar: Budget in JOD Apr
| 2.2.10 | AccLab: Explore and map solutions under UNDP SDGs for Jordan | bar: Budget in JOD Mar to Budget in JOD Apr; Budget in JOD Jun; Budget in JOD Sep; Budget in JOD Dec
| 2.2.11 | AccLab: Assess the solutions mapped under SDGs for Jordan | bar: Budget in JOD Jul
| 2.2.12 | UNDP: Propose learning challenges for potential collaboration with local partners | bar: Budget in JOD Jul
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | 2.3.1 | Refer to 2.2
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | 2.3.2 | Refer to Output 1 and Output indicator 2.2
3.1 Size and density of the network effects among the Accelerator Labs | 3.1.1 | PAR: Share some updates on Teams and WhatsApp
| 3.1.2 | MPR: Share some updates on Teams and WhatsApp
| 3.1.3 | AccLab: organise quarterly brown bag | bar: Budget in JOD Apr; Budget in JOD Jul; Budget in JOD Oct
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 3.2.1 | PAR: Share the PAR report with the network
| 3.2.2 | MPR: Publish the RCT results | [12 empty] | x | bar: Budget in JOD Dec
| 3.2.3 | AccLab: Post knowledge products on Teams AccLab channels
| 3.2.4 | AccLab: Share knowledge products via email to mailing lists related to Innovation, AccLabs, and the Arab states region
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | 3.3.1 | AccLab: Send a picture of the team doing an action: field visit, design session, experimentation | bar: Budget in JOD Mar; Budget in JOD Jun; Budget in JOD Sep; Budget in JOD Dec
| 3.3.2 | SAIB: Send a picture of SAIB construction work with a short description in Arabic and English | bar: Budget in JOD Jul
| 3.3.3 | SAIB: Share knowledge of insights and processes of Spatial Design Experiment with government/other partners | bar: Budget in JOD Dec
| 3.3.4 | MPR: Send a picture of various events under the experiement and training with a short description in Arabic and English | bar: Budget in JOD May
| 3.3.5 | IEF: Send a picture of data collection for IEF | bar: Budget in JOD Feb
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | 3.4.1 | AccLab: organise quarterly speaker series with partner organizations | Budget in JOD May: 350; Budget in JOD Aug: 350; Budget in JOD Nov: 350
| 3.4.2 | MPR: Refer to 3.2.2
4.1 AccLab Jordan advances equity and citizens* representation in UNDP work | 4.1.1 | Refer to Output 1
| 4.1.3 | MPR: Run an RCT to evaluate the project hyotheses after implementation | bar: Budget in JOD Sep to Budget in JOD Nov
| 4.1.5 | AccLab: Design and launch Citizen Support Group | Budget in JOD Apr: 5000
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | 4.2.1 | Refer to Output 1
| 4.2.2 | RT: Manage the rooftop renovation project | Budget in JOD Apr: 0; Budget in JOD May: 2000
Refer to 3.4.1
Refer to 3.1.3
Consultants |  | Hire an RCT consultant | Budget in JOD Sep: 8750
Subcriptions |  | Buy an Adobe subcription | Budget in JOD Nov: 360
Buy clickup subcription
Communications |  | Buy social media sponsored ads
|  | Produce a podcast | Budget in JOD Sep: 2000
|  | Hire a communications intern |  |  |  | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | Note: we are suggesting this compensation
|  | Hire a copyeditor (freelance) |  |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70

## 2022 budget summary Q1
Acc Lab Jordan 2022 Budget |  |  | Budget in JOD | [12 empty] | Codes
Category | Line item |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Donor code | Funder code
Exploration | 1.2.4 | AccLab: Create exploration tools | Budget in JOD Mar: 1200; Budget in JOD Jun: 1200; Budget in JOD Sep: 1200; Budget in JOD Dec: 1200; Budget in JOD Total: 10000 | 12298 | 30000
Solutions Mapping |  | AccLab: Design and launch Community Design Research Group | Budget in JOD Apr: 3500; Budget in JOD Total: 3500 | 12298 | 30000
| 1.3.4 | UNDP: Map solutions under UNDP CO Jordan | Budget in JOD Total: 0 | 12298 | 30000
| 1.3.5 | AccLab: Map solutions under UNDP SDGs for Jordan | Budget in JOD Apr: 1200; Budget in JOD Jun: 1200; Budget in JOD Sep: 1200; Budget in JOD Dec: 1500; Budget in JOD Total: 4500 | 12298 | 30000
|  | IEF: Support IEF portfolio design activities | Budget in JOD Jun: 2000; Budget in JOD Total: 2000 | 12298 | 30000
Experimenting | 1.4.1 | AccLab: run 4 to 6 prototypes | Budget in JOD Jun: 2000; Budget in JOD Total: 7000 | 12298 | 30000
| 1.4.3 | AccLab: portfolio of experiments core learning challenge | Budget in JOD Jun: 5000; Budget in JOD Total: 12000 | 12298 | 30000
| 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Budget in JOD Mar: 1000; Budget in JOD Total: 1000 | 12298 | 30000
Consultants |  |  | Budget in JOD Sep: 8750 | 12298 | 30000
Communications |  | Buy social media sponsored ads | Budget in JOD Total: 360 | 12298 | 30000
|  | Regional media event | Budget in JOD Sep: 2000; Budget in JOD Total: 2000 | 12298 | 30000
|  | Hire a graphic designer | Budget in JOD Total: 1000
|  | Hire a communications intern |  |  |  | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 2700 | 12298 | 30000
|  | Hire a copyeditor (freelance) |  |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 630 | 12298 | 30000
|  | AccLab: Organise quarterly speaker series with partner organizations | Budget in JOD May: 350; Budget in JOD Aug: 350; Budget in JOD Nov: 350; Budget in JOD Total: 1050 | 12298 | 30000
Subscriptions |  | Buy an Adobe subscription | Budget in JOD Nov: 360; Budget in JOD Total: 360 | 12298 | 30000
Miscellaneous | 4.2.2 | RT: Manage the rooftop renovation project | Budget in JOD May: 2000; Budget in JOD Total: 2000 | 12298 | 30000
|  | Professional development fund: one for each AccLab team member (total 3) | Budget in JOD Total: 3000 | 12298 | 30000
[14 empty] | Total (JOD) | 53100
|  |  | Budget in JOD Dec: Total (USD); Budget in JOD Total: 75000 |  |  | Note: we deducted the common services budget which are around $25k
0
0

## Monthly 2022 workplan
Acc Lab Jordan 2022 Budget |  |  |  | Who |  |  | When (2022) |  | When?
OUTPUT INDICATORS | Year 4 (2022) | Activity |  | Acc Lab Accountable | Acc Lab responsible | Status Jan | Jan | Update | Feb | Updates | Mar | Updates | Challenges | Support needed
1.1 Number of new data sources used at Country Office level | 5 new data sources per lab | 1.1.1 | Refer to 1.2 | Ayah | Ayah
1.2 Diversity of different data sources used | 7 different data sources per lab | 1.2.1 | PAR: Codesign PAR research questions and tools with UNICEF | Hadil | Hadil, Ru'a, Ayah | In progress |  | We have reviewed the registration form. | x |  | x |  | delays from UNICEF in sharing the actual material we need to review (toolkit, guidelines..)
|  | 1.2.2 | CPD: Support in designing the stakeholders' consultations tools | Ayah | Hadil, Ru'a, Ayah | Completed | X | We organized a workshop to do stakeholders analysis and review the interview tools with the pillars | X | Tools are designed and people's consultations are completed |  |  | The timeframe within which we had to work
|  | 1.2.3 | UNDP: refer to 2.2.7 | Ayah | Ayah | Completed | x |  | x | Completed meetings and follow ups with pillars
|  | 1.2.4 | AccLab: Refer to 2.2.10 | Ayah | Ayah | [5 empty] | x
|  | 1.2.5 | IEF: Conduct stakeholder mapping and power analysis | Ru'a | Ru'a (Ayah + Hadil?) | In progress | x | Not started. Dependent on the outcomes of the questionnaire by AZHJ and there is a delay from their side. | x | refined SM diagram. Drafted PA tools | x |  | AZHJ surveys were planned to be finished by 3rd or 4th week of Feb but they were delayed until March 16. These surveys were suppsoed to provide insights to inform the SM and PA. We have also been told by the IEF team that based on the testing phase of the surveys, we may not get any useful insights for the SM & PA. Now replanning how we will do the SM & PA. | Ru'a needs Ayah and Hadil's brains to review the SM and draft PA tools and think together of a plan B.
1.3 Number of sustainable development solutions identified and documented | 25 new potential solutions per lab | 1.3.1 | PAR: Document PAR results | Hadil | Hadil
|  | 1.3.2 | PAR: Document solutions mapped in PAR | Hadil | Ru'a
|  | 1.3.3 | Gender: Map solutions for women transportation challenge | Ru'a | Ru'a
|  | 1.3.4 | UNDP: refer to 2.2.7 | Ayah | Ru'a | In progress | x |  | x
|  | 1.3.5 | AccLab: Refer to 2.2.10 | Ayah | Ru'a
|  | 1.3.6 | IEF: Co-design and co-run semistructured interviews | Ru'a | Ru'a, Ayah, Hadil | In progress |  |  |  |  | x |  | AZHJ is not cooperating. Need IEF lead to advise on the way forward
1.4 Variety of innovation methods used to test and iterate over the different hypotheses | 8 expriments per lab | 1.4.1 | PAR: Run an experiment to test a hypotheses for one solution mapped from PAR | Hadil | Hadil, Ru'a, Ayah
|  | 1.4.2 | MPR: Run an experiment to test MPR hypotheses | Hadil | Hadil, Ru'a, Ayah | Cancelled
|  | 1.4.3 | Gender: Run an experiment to test women transportation challenge hypotheses | Ru'a | Hadil
|  | 1.4.4 | SAIB: Supervise spatial design implementation done by SAIB | Hadil | Hadil | In progress | x | The exterior work on the first house has been done as well as some interior work. | x |  | x |  | The snow has caused a 5-day dealy.
|  | 1.4.5 | SAIB: Supervise design research of the prototypes done by SAIB | Hadil | Hadil
|  | 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Hadil | Hadil |  |  |  | x |  | x
|  | 1.4.7 | UNDP: Run two experiments to test hypotheses from UNDP Jordan work | Hadil | Hadil
|  | 1.4.8 | AccLab: Run one experiment to test hypotheses for a learning challenge identified by AccLab | Hadil | Hadil
2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | At least 10 blogs, or other (substantial) media posts published per year | 2.1.1 | SAIB: Publish a blog post in English and Arabic | Hadil | Hadil, copyeditor | In progress |  | The blog has been drafted | x
|  | 2.1.2 | MPR: Publish a blog post English about the training workshops | Hadil | Hadil, copyeditor | Cancelled
|  | 2.1.3 | IEF: Publish a series of 3 blog posts in English | Ru'a | Ru'a, copyeditor | In progress | x | Completed one blog |  | 1 blog submitted on Feb 9 and published on Feb 20.
|  | 2.1.4 | UNDP: Publish a blog post on Exploring UNDP in Arabic | Ayah | Ayah, copyeditor
|  | 2.1.5 | PAR: Publish a media post about PAR | Hadil | Hadil, copyeditor
|  | 2.1.6 | Manage a coverage in the newspaper about the AccLab | Ayah | Ayah
|  | 2.1.7 | SAIB: Manage a radio interview | Hadil | Hadil
|  | 2.1.8 | Organize a media piece/event with the Arab states AccLabs | Ru'a / Ayah
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | At least 50% of our learning challenges have the public sector or other partner as counterpart | 2.2.1 | PAR: Refer to 1.4.1
|  | 2.2.2 | MPR: Design the co-creation tooklit | Hadil | Hadil, Ru'a, Ayah, consultant | Cancelled | x |  | x |  | x
|  | 2.2.3 | MPR: Train G&P team on the co-creation toolkit and the roadmap report | Hadil | Ru'a | Cancelled
|  | 2.2.4 | MPR: Develop the roadmap report | Hadil | Ru'a, consultant | Cancelled
|  | 2.2.5 | SAIB: Share knowledge of insights and processes of spatial design experiment with government/other partners | Hadil
|  | 2.2.6 | EB: Send a summary report on the elecricity bill project | Hadil | Hadil, Ayah | [5 empty] | x
|  | 2.2.7 | UNDP: Explore and map solutions under UNDP CO Jordan | Ayah | Ru'a, Ayah | In progress | x | Meetings have been booked with pillars teams leaders. We are designing a plan for data collection tools | x | Tool designed to map UNDP CO projects. Sent to pillars to fill out by third week of March |  |  | CPD deadlines took priority and caused delay in mapping solutions.
|  | 2.2.8 | UNDP: Assess the solutions mapped under UNDP CO Jordan | Ayah | Hadil, Ru'a, Ayah | In progress |  |  |  |  | x
|  | 2.2.9 | UNDP: Propose learning challenges for potential collaboration with UNDP CO Jordan pillars | Ayah | Hadil, Ru'a, Ayah
|  | 2.2.10 | AccLab: Explore and map solutions under UNDP SDGs for Jordan | Ayah | Ru'a | [5 empty] | x
|  | 2.2.11 | AccLab: Assess the solutions mapped under SDGs for Jordan | Ayah | Hadil, Ru'a, Ayah
|  | 2.2.12 | UNDP: Propose learning challenges for potential collaboration with local partners | Ayah | Hadil, Ru'a, Ayah
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | At least one government entity or partner has adopted an accelerator lab method. | 2.3.1 | Refer to 2.2
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects | 2.4.1 | Refer to Output 1 and Output indicator 2.2
|  | 2.4.2 | WEE: Map the systems within the solid waste women business ideas and identify areas for collaboration with the team | Ayah | Ayah, Hadil | In progress | x | We created a tool for Ghadir and her team to map various elements for each of the 10 business ideas in order to identify areas for collaboration with the project where innovation can add value | x | We created a tool for WEE to map the needs for each of the businesses and identified design requirements.
3.1 Size and density of the network effects among the Accelerator Labs | The lab interacts at least once a week with another lab in the network. 48 interaction per year | 3.1.1 | PAR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah | In progress |  | Not started |  | Shared IEF blog on Teams Channels and Solution Mappers Whatsapp Group |  |  | I think we got busy with other work that we didn't prioritize doing this or we just forgot about it.
|  | 3.1.2 | MPR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah | Cancelled
|  | 3.1.3 | AccLab: Organise quarterly brown bag | AccLab Jo | Hadil, Ru'a, Ayah, comm. intern
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related. | 3.2.1 | PAR: Share the PAR report with the AccLab network and UNDP Jo | Hadil | Hadil, comms ntern
|  | 3.2.2 | MPR: Publish the RCT results | Hadil | consultant | Cancelled
|  | 3.2.3 | AccLab: Post knowledge products on Teams AccLab channels | AccLab Jo | Hadil, Ru'a, Ayah | In progress |  | Not started. No knowledge products yet |  | IEF blog shared on Teams Acclab Informality channel on Feb 20 and on Lab Updates channel on Feb 21. |  |  | Delay with the IEF blog being published, which we could have shared on Teams. Delay was partly due to Ru'a getting COVID and needing to take 3 days off at the end of Jan.
|  | 3.2.4 | AccLab: Share knowledge products via email to mailing lists related to Innovation, AccLabs, and the Arab states region | AccLab Jo | Hadil, Ru'a, Ayah | In progress |  | Not started. No knowledge products yet |  | IEF blog sent to several mailing lists: UNDP Jordan CO, Innovation Arab States, Global Innovation Practice, RBAP Innovation, Accelerator Labs, AccLab Global |  |  | Delay with the IEF blog being published, which we could have shared on Teams. Delay was partly due to Ru'a getting COVID and needing to take 3 days off at the end of Jan.
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account. | 3.3.1 | AccLab: Send a picture of the team doing an action: field visit, design session, experimentation | AccLab Jo | Comms. intern | Completed |  |  |  |  | x |  | Sent Tala photos of the IEF workshops with captions to be shared on social media and DeVibes newsletter. Not yet published (end of Mar)
|  | 3.3.2 | SAIB: Send a picture of SAIB construction work with a short description in Arabic and English | Hadil | Comms. intern
|  | 3.3.3 | SAIB: Share knowledge of insights and processes of Spatial Design Experiment with government/other partners | Hadil | Hadil, Comms. intern
|  | 3.3.4 | MPR: Send a picture of various events under the experiement and training with a short description in Arabic and English | Hadil | Comms. intern | Cancelled
|  | 3.3.5 | IEF: Send a picture of data collection for IEF | Ru'a | Comms. intern | Completed |  |  | x | Shared photos and caption of IEF sensemaking workshops to Tala for Devibes and social media |  |  | No comms intern yet
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem. | 3.4.1 | AccLab: organise quarterly speaker series with partner organizations | AccLab Jo | Comms. intern
|  | 3.4.2 | MPR: Refer to 3.2.2 | Hadil |  | Cancelled
4.1 AccLab Jordan advances equity and people's representation in UNDP work | 100% of our learning challenges consult with cizitens and UNDP pillars | 4.1.1 | Refer to Output 1
|  | 4.1.3 | MPR: Run an RCT to evaluate the project hyotheses after implementation | Hadil | consultant | Cancelled
|  | 4.1.5 | AccLab: Design and launch Community Design Research Group | Ru'a | AccLab Jo
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | At least 30% of our learning challenges go from sense to test | 4.2.1 | Refer to Output 1
| The lab engages at least once a week with UNDP Jordan team members | 4.2.2 | RT: Manage the rooftop renovation project | Ru'a | AccLab Jo
Refer to 3.4.1
Refer to 3.1.3

## Filter of 2022 workplan (hidden)
Acc Lab Jordan 2022 Budget
OUTPUT INDICATORS | Year 4 (2022) | Activity |  | Acc Lab Accountable | Acc Lab responsible | UNDP support | Partners | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.1 Number of new data sources used at Country Office level | 5 new data sources per lab | 1.1.1 | Refer to 1.2 | Ayah | Ayah
1.2 Diversity of different data sources used | 7 different data sources per lab | 1.2.1 | PAR: Codesign PAR methodology with UNICEF | Hadil | Hadil, Ru'a, Ayah | Bara'a | UNICEF
|  | 1.2.2 | CPD: Support in designing the stakeholders' consultations tools | Ru'a | Hadil, Ru'a, Ayah | Dana, Rabia |  | X | X
|  | 1.2.3 | UNDP: refer to 2.2.7 | Ayah | Ayah | Randa, Majida |  | x | x
|  | 1.2.4 | AccLab: Refer to 2.2.10 | Ayah | Ayah |  |  |  |  | x |  |  | x |  |  | x |  |  | x
1.3 Number of sustainable development solutions identified and documented | 25 new potential solutions per lab | 1.3.1 | PAR: Document PAR results | Hadil | Hadil |  | UNICEF
|  | 1.3.2 | PAR: Document solutions mapped in PAR | Hadil | Ru'a
|  | 1.3.3 | Gender: Map solutions for women transportation challenge | Ru'a | Ru'a | [6 empty] | x
|  | 1.3.4 | UNDP: refer to 2.2.7 | Ayah | Ru'a | Randa, Majida |  | x | x
|  | 1.3.5 | AccLab: Refer to 2.2.10 | Ayah | Ru'a |  |  |  |  | x |  |  | x |  |  | x |  |  | x
1.4 Variety of innovation methods used to test and iterate over the different hypotheses | 8 expriments per lab | 1.4.1 | PAR: Run an experiment to test a hypotheses for one solution mapped from PAR | Hadil | Hadil, Ru'a, Ayah | TBD | Owners of the solution
|  | 1.4.2 | MPR: Run an experiment to test MPR hypotheses | Hadil | Hadil, Ru'a, Ayah? | Nancy | MoLA, Muncipalities, citizens
|  | 1.4.3 | Gender: Run an experiment to test women transportation challenge hypotheses | Ru'a | Hadil | [7 empty] | x | x | x | x
|  | 1.4.4 | SAIB: Supervise spatial design implementation done by SAIB | Hadil | Hadil |  | SAIB | x | x | x | x | x | x | x
|  | 1.4.5 | SAIB: Supervise design research of the prototypes done by SAIB | Hadil | Hadil |  | SAIB | [10 empty] | x
|  | 1.4.6 | UNICEF: Run an experiment to test Date Compost hyoptheses | Hadil | Hadil |  |  |  | x | x
|  | 1.4.7 | UNDP: Run two experiments to test hypotheses from UNDP Jordan work | Hadil | Hadil | [6 empty] | x | x |  |  |  | x | x
|  | 1.4.8 | AccLab: Run one experiment to test hypotheses for a learning challenge identified by AccLab | Hadil | Hadil | [11 empty] | x | x
2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | At least 10 blogs, or other (substantial) media posts published per year | 2.1.1 | SAIB: Publish a blog post in English and Arabic | Hadil | Hadil, copyeditor | Tala |  |  | x
|  | 2.1.2 | MPR: Publish a blog post English about the training workshops | Hadil | Hadil, copyeditor | Tala
|  | 2.1.3 | IEF: Publish a series of 3 blog posts in English | Ru'a | Ru'a, copyeditor | Salam, Tala, Michaela |  | x |  | x |  |  |  |  | x
|  | 2.1.4 | PAR: Publish a media post about PAR | Hadil | Hadil, copyeditor | Tala | UNICEF
|  | 2.1.5 | UNDP: Publish a blog post on Exploring UNDP in Arabic | Ayah | Ayah, copyeditor | Tala
|  | 2.1.6 | Manage a coverage in the newspaper about the AccLab | Ayah |  | Tala
|  | 2.1.7 | SAIB: Manage a radio interview | Hadil |  | Tala | [12 empty] | x
|  | 2.1.8 | Organize a media piece/event with the Arab states AccLabs | Ru'a / Ayah | [8 empty] | x | x
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | At least 50% of our learning challenges have the public sector or other partner as counterpart | 2.2.1 | PAR: Refer to 1.4.1 |  |  |  | UNICEF
|  | 2.2.2 | MPR: Design the co-creation tooklit | Hadil | Hadil, Ru'a, Ayah, consultant | Nancy | Municipalities
|  | 2.2.3 | MPR: Develop the roadmap report | Hadil | Ru'a, consultant | Nancy | Municipalities
|  | 2.2.4 | MPR: Train G&P team on the co-creation toolkit and the roadmap report | Hadil | Ru'a | Nancy | Municipalities
|  | 2.2.5 | SAIB: Share knowledge of insights and processes of spatial design experiment with government/other partners | Hadil |  | Najd | [12 empty] | x
|  | 2.2.6 | EB: Send a summary report on the elecricity bill project | Hadil | Hadil, Ayah | Rana |  |  | x
|  | 2.2.7 | UNDP: Explore and map solutions under UNDP CO Jordan | Ayah | Ru'a, Ayah | Majida
|  | 2.2.8 | UNDP: Assess the solutions mapped under UNDP CO Jordan | Ayah | Hadil, Ru'a, Ayah | Randa, Majida
|  | 2.2.9 | UNDP: Propose learning challenges for potential collaboration with UNDP CO Jordan pillars | Ayah | Hadil, Ru'a, Ayah
|  | 2.2.10 | AccLab: Map solutions under UNDP SDGs for Jordan | Ayah | Ru'a
|  | 2.2.11 | AccLab: Assess the solutions mapped under SDGs for Jordan | Ayah | Hadil, Ru'a, Ayah | Randa, Majida
|  | 2.2.12 | UNDP: Propose learning challenges for potential collaboration with local partners | Ayah | Hadil, Ru'a, Ayah | Randa, Majida
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | At least one government entity or partner has adopted an accelerator lab method. | 2.3.1 | Refer to 2.2
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects | 2.3.2 | Refer to Output 1 and Output indicator 2.2
3.1 Size and density of the network effects among the Accelerator Labs | The lab interacts at least once a week with another lab in the network. 48 interaction per year | 3.1.1 | PAR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.1.2 | MPR: Share some updates on Teams and WhatsApp | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.1.3 | AccLab: organise quarterly brown bag | AccLab Jo | Hadil, Ru'a, Ayah
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related. | 3.2.1 | PAR: Share the PAR report with the network | Hadil | Hadil
|  | 3.2.2 | MPR: Publish the RCT results | Hadil | consultant
|  | 3.2.3 | AccLab: Post knowledge products on Teams AccLab channels | AccLab Jo | Hadil, Ru'a, Ayah
|  | 3.2.4 | AccLab: Share knowledge products via email to mailing lists related to Innovation, AccLabs, and the Arab states region | AccLab Jo | Hadil, Ru'a, Ayah
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account. | 3.3.1 | AccLab: Send a picture of the team doing an action: field visit, design session, experimentation | AccLab Jo | Comms. intern |  |  |  |  | x |  |  | x |  |  | x |  |  | x
|  | 3.3.2 | SAIB: Send a picture of SAIB construction work with a short description in Arabic and English | Hadil | Comms. intern | Tala | SAIB | [6 empty] | x
|  | 3.3.3 | SAIB: Share knowledge of insights and processes of Spatial Design Experiment with government/other partners | Hadil | Hadil, Comms. intern |  | SAIB | [11 empty] | x
|  | 3.3.4 | MPR: Send a picture of various events under the experiement and training with a short description in Arabic and English | Hadil | Comms. intern | Tala, Nancy | [5 empty] | x
|  | 3.3.5 | IEF: Send a picture of data collection for IEF | Ru'a | Comms. intern | Tala |  |  | x
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem. | 3.4.1 | AccLab: organise quarterly speaker series with partner organizations | AccLab Jo | Comms. intern | [6 empty] | x |  |  | x |  |  | x
|  | 3.4.2 | MPR: Publish the RCT results | Hadil
4.1 AccLab Jordan advances equity and citizens* representation in UNDP work | 100% of our learning challenges consult with cizitens and UNDP pillars | 4.1.1 | Refer to Output 1
|  | 4.1.3 | MPR: Run an RCT to evaluate the project hyotheses after implementation | Hadil | consultant
|  | 4.1.5 | AccLab: Design and launch Citizen Support Group | Ru'a | AccLab Jo | [5 empty] | x | x | x
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | At least 30% of our learning challenges go from sense to test | 4.2.1 | Refer to Output 1
| The lab engages at least once a week with UNDP Jordan team members | 4.2.2 | RT: Manage the rooftop renovation project | Ru'a | AccLab Jo | Moussa, Staff Assoc. |  | x | x | x
Refer to 3.4.1
Refer to 3.1.3

## 2022 budget draft (hidden)
Acc Lab Jordan 2022 Budget |  |  | Predicted expenditure (JOD)
OUTPUT INDICATORS | Year 4 (2022) | Activity | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
1.1 Number of new data sources used at Country Office level | 5 new data sources per lab | SAQADA | [9 empty] | 20000 |  |  | 20000
|  | Misc | [5 empty] | 8000 | [6 empty] | 8000
1.2 Diversity of different data sources used | 7 different data sources per lab | [13 empty] | 0
1.3 Number of sustainable development solutions identified and documented | 25 new potential solutions per lab | PAR | [10 empty] | 2865 |  | 2865
1.4 Variety of innovation methods used to test and iterate over the different hypotheses | 8 innovation methods per Action Plan | IEF experiment |  |  |  |  | 5000 | [7 empty] | 5000
|  | Date Compost |  |  |  |  | 1000 | [7 empty] | 1000
|  | Animal Feed |  |  |  |  | 3000 | [7 empty] | 3000
|  | Ghadha |  |  |  |  | 5000 | [7 empty] | 5000
|  | SAIB | 3010 | 1505 |  |  | 7525 | [7 empty] | 12040
2.1 Learning the Accelerator Lab Network shares with a public audience (outside of UNDP) | At least 10 blogs, or other (substantial) media posts published per year | budget for copyediting, a consultant, an intern | [12 empty] | 0
2.2 Number of lab insights, processes or products which are taken up by governments or other partners | At least 50% of our learning challenges have the public sector or other partner as counterpart | budget for promotional material, open houses, activities | [12 empty] | 0
2.3 Proportion of partners and governments that increase their take up of the innovation methods included in the Accelerator Lab Network suite | At least one government entity or partner has adopted an accelerator lab method. | [13 empty] | 0
2.4 Proportion of UNDP Country Office programming influenced by the Accelerator Lab Network’s work and methodologies | At least 50% of our learning challenges are providing actionable knowledge to ongoing CO projects | budget to do CO solutions mapping and exploration, like field trips, activities with CO teams, the community supporters model | [12 empty] | 0
3.1 Size and density of the network effects among the Accelerator Labs | The lab interacts at least once a week with another lab in the network. 48 interaction per year | [13 empty] | 0
3.2 Number of new models, approaches, and insights documented and disseminated throughout the network | 25% of information shared across the network should be methodology, or sustainable development issue and opportunity related. | budget for intern, reporter documenting our work, | [12 empty] | 0
3.3 Engagement of the broader Development ecosystem with published learnings from the Accelerator Lab Network | The Accelerator Labs Network’s work is featured at least 3 times per month in Country Office Social Media channels and tag UNDP Accelerator Labs accounts. The Lab team engages at least once a month across any social media conversation related to the work of the Accelerator Lab Network, from either personal or CO account. | Adobe subscription, budget to produce media, social media content, ads | [10 empty] | 360 |  | 360
3.4 Amount of influence the learnings and methods of the Accelerator Lab Network have on the discourse of the broader Development ecosystem | 2.5% of the conversation will be influenced by the Accelerator Lab Network Connect the Accelerator Lab’s publications to local development ecosystem through social media. Identify and engage with 10 new relevant local social media profiles of the broader Development Ecosystem. | [13 empty] | 0
4.1 AccLab Jordan advances equity and ciziten representation in UNDP work | 100% of our learning challenges consult with cizitens and UNDP pillars | Budget to create and sustain the community supporters model | [12 empty] | 0
4.2 Enhance the effectiveness and efficiency of AccLab Jordan | At least X% of our learning challenges complete an AccLab full learning cycle | Clickup subscription, do we need anything else for the office? | [5 empty] | 130 | [6 empty] | 130