## SWM
Title: | SWM |  |  |  | Year: 2018 | [11 empty] | Total Budget |  |  | 11,652,181.59 USD received (remaining 2,877,197.46) + approx. 3,848,601.25 USD not received yet of cost extension and amount could change based on currency fluctuation |  |  | Prepared by: | Murad Al Shishani & Botros Hijazeen
ID: | 00094965 | [15 empty] | Total Expenditure in 2018 (USD) |  |  | 4792095.3265 |  |  | Certified by: | Ghimar Deeb
| Activities | Sub Activity | Status | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Item Description | Quantity | Cost / Unit (USD) | Budget
[5 empty] | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec |  |  |  | Fund | Donor | Account Code | Budget Description | Amount USD $
| Activity 1 | Project Team | Ongoing | Process Payroll for Murad Al Shishani | [12 empty] | Payroll - Local | 12 | 4646.3 | 30000 | 12113 | 71400 | Service Contracts + annual bonus 1446.6 USD) | 57202.2
|  |  | Ongoing | Process Payroll for Ghimar Deeb | [12 empty] | Payroll - International P4 | 6 | 19044 | 30000 | 12113 | 61300 | FTA P4 | 114264
|  |  | Ongoing | Process Payroll for Botros Hijazeen | [12 empty] | Payroll - Local | 12 | 3672.6 | 30000 | 12113 | 71400 | Service Contracts + annual bonus 1135.9 USD) | 45207.1
|  |  | Ongoing | Process Payroll for Yousef Ayoub | [12 empty] | Payroll - Local | 12 | 1577 | 30000 | 12113 | 71400 | Service Contracts + annual bonus (467.3 USD) | 19391.3
|  |  | Not Started | Process Payroll for SC-4 (Technical Sorting Assistant) | [12 empty] | Payroll - Local | 9 | 1577 | 30000 | 12113 | 71400 | Service Contracts | 14193
|  |  | Ongoing | Process Payroll for Enas | [12 empty] | Payroll - Local | 12 | 2110.1 | 30000 | 12113 | 71400 | Service Contracts + annual bonus (637.4 USD) | 25958.6
|  |  | Ongoing | Process Payroll for Salam Twal (SC-11) | [12 empty] | Payroll - Local | 12 | 5790.4 | 30000 | 12113 | 71400 | Service Contracts + annual bonus (1817.8 USD) | 71302.6
|  |  | Ongoing | Process Payroll for Fatima Abu Snaineh | [12 empty] | Payroll - Local | 12 | 2855 | 30000 | 12113 | 71400 | Service Contracts + annual bonus (904.1 USD) | 35164.1
|  |  | Ongoing | Process Payroll for Yana Hamtini (Ref new cost extension) | [12 empty] | Payroll - Local | 12 | 2337.2 | 30000 | 12113 | 71400 | Service Contracts + annual bonus (709.8 USD) | 28756.2
|  |  | Ongoing | Process Payroll for Maha Alkhateeb (Ref new cost extension) | [12 empty] | Payroll - Local | 12 | 3672.6 | 30000 | 12113 | 71400 | Service Contracts + annual bonus 1135.9 USD) | 45207.1
|  |  | Ongoing | Process Payroll for Dania Batayneh (Ref new cost extension) | [12 empty] | Payroll - Local | 12 | 1323.7 | 30000 | 12113 | 71400 | Service Contracts | 15884.4
|  |  | Not Started | Process Payroll for Community engagment officer :SC-7 (Ref new cost extension) | [12 empty] | Payroll - Local | 10 | 2337.2 | 30000 | 12113 | 71400 | Service Contracts | 23372
|  |  | Not Started | Communications Advisor (SC-10) | [12 empty] | Payroll - Local | 4 | 5000 | 30000 | 12113 | 71400 | Service Contracts | 20000
|  |  | Ongoing | DSA for Al Ekaider and shouneh Engineering field Staff (3 persons *15 days) + (Livilihood 2 persons *6 days) | [12 empty] | DSA | 12 | 3901.08 | 30000 | 12113 | 71300 | Service Contracts | 46812.96
|  |  | Ongoing | Travel | [12 empty] | Travel | 2 | 2500 | 30000 | 12113 | 71300 | Service Contracts | 5000
|  |  | Ongoing | Procure the services of SWM Expert (Ammar Abu Drais) | [12 empty] | Procurement - Individuals | 1 | 56172.1893 | 30000 | 12113 | 71300 | National Consultant | 56172.1893
|  |  | Ongoing | Procure New Vehicle for the project (If another vehicle is procured) | [12 empty] | Procurement - Equipment | 1 | 25000 | 30000 | 12113 | 72200 | Procurement - Equipment | 25000
|  | PMU | Ongoing | Reimburse travel expenses for Hussain Mheidat | [12 empty] | Transportation Reimbursement | 12 | 706 | 30000 | 12113 | 71600 | Travel | 8472
|  |  | Ongoing | Reimburse travel expenses for Bassem Saaydeh | [12 empty] | Transportation Reimbursement | 12 | 350 | 30000 | 12113 | 71600 | Travel | 4200
|  | Admin Expenses | Ongoing | Provide margin for Miscellaneous Expenses | [12 empty] | Unanticipated expenses | 12 | 1000 | 30000 | 12113 | 74500 | Miscellaneous Expenses | 12000
|  |  | Ongoing | Training & Workshops | [12 empty] | Projectors, screens, etc | 6 | 833.333 | 30000 | 12113 | 73300 | Rental & Maint of Info Tech Eq | 4999.998
|  |  | Ongoing | Pay for Hospitality costs | [12 empty] | Meeting costs | 6 | 750 | 30000 | 12113 | 72700 | Hospitality/Catering | 4500
|  |  | Ongoing | Pay UNDP Jo for Professional Services | [12 empty] | Project professional services expenses to UNDP | 4 | 60000 | 30000 | 12113 | 74100 | Professional Services | 240000
|  |  | Ongoing | Provide staff and PMU with Stationary, office supplies, sanitation and PPE at site | [12 empty] | Supplies costs - Stationary, other office supplies and PPE at site | 12 | 500 | 30000 | 12113 | 72500 | Supplies | 6000
|  |  | Ongoing | Fuel & maintenance for the project cars | [12 empty] | Fuel & maintenance for the Car | 12 | 1500 | 30000 | 12113 | 72500 | Supplies | 18000
|  |  | Ongoing | Settle the IT Equipment Acquisition | [12 empty] | IT | 12 | 750 | 30000 | 12113 | 72800 | Information Technology Equipmt | 9000
|  |  | Ongoing | Cover staff Mobile phone charges | [12 empty] | Phone charges | 12 | 150 | 30000 | 12113 | 72400 | Communic & Audio Visual Equip | 1800
| Total for Activity 1 | [22 empty] | 957859.7473
| GMS for Activity 1 | [22 empty] | 76628.7798
| Grand Total for Activity 1 | [22 empty] | 1034488.527
| Activity 2 | Implementation of Roads, Solar Street Lighting, Signage & Green Belt | Not Started | Implementation of Roads, Solar Street Lighting, Signage & Green Belt | [12 empty] | Construction Works | 1 | 1000000 | 30000 | 12113 | 72100 | Contractual Services-Companies | 1000000
|  | Professional Engineering Design Review and Supervision for MSW Sanitary Landfill Cell, for Expansion of Physical Waste Disposal Capacity of Al-Ekaider Landfill in Irbid Governorate, Jordan (Phase IV and retention) | ongoing | Professional Engineering Design Review and Supervision for MSW Sanitary Landfill Cell, for Expansion of Physical Waste Disposal Capacity of Al-Ekaider Landfill in Irbid Governorate, Jordan (Phase IV and retention) | [12 empty] | Engineering Services | 1 | 88580 | 30000 | 12113 | 72100 | Contractual Services-Companies | 88580
|  | Implementation of Expansion of Physical Waste Disposal Capacity of Al Ekaider Landfill (Emergency Cell #1) in Irbid Governorate, Jordan | ongoing | Implementation of Expansion of Physical Waste Disposal Capacity of Al Ekaider Landfill (Emergency Cell #1) in Irbid Governorate, Jordan | [12 empty] | Construction Works | 1 | 0 | 30000 | 12113 | 72100 | Contractual Services-Companies | 0
| Total for Activity 2 | [22 empty] | 1088580
| GMS for Activity 2 | [22 empty] | 87086.4
| Grand Total for Activity 2 | [22 empty] | 1175666.4
| Activity 3 | Elaboration of Full Environmental a Impact Study for Solid Waste Transfer Station Facility in replacement for the one originally planned in Jerash Governorate , Jordan | Not Started | Elaboration of Full Environmental a Impact Study for Solid Waste Transfer Station Facility in replacement for the one originally planned in Jerash Governorate , Jordan | [12 empty] | EIA Study | 1 | 50000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 50000
|  | Elaboration of Full Environmental Impact Study for Solid Waste Transfer Station Facility and sorting facility in North Shouneh (#Ref. Canadan Cost Extension) | Not Started | [13 empty] | EIA Study | 1 | 50000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 50000
|  | Procure the services of SWM design Engineer for Shouneh TS design (Ref new cost extension) | Not Started | Procure the services of SWM design Engineer for Shouneh TS design (Ref new cost extension) | [12 empty] | Procurement - Individuals | 70 | 400 | 30000 | 12113 | 71300 | National Consultant | 28000
|  | Procure the services of SWM design Engineer for Jerash TS redesign and supervision support | Not Started | Procure the services of SWM design Engineer for Jerash TS redesign and supervision support | [12 empty] | Procurement - Individuals | 80 | 350 | 30000 | 12113 | 71300 | National Consultant | 28000
|  | Implementation of Transfer Station in replacement for the one originally planned in Jerash (Total of 1,050,000 .00USD) | Not Started | Issue ITB in July 2018 and begin implementation stage in October 2018 and finish in June 2019 | [12 empty] | Construction Works | 1 | 350000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 350000
|  | Implementation of Transfer Station and sorting facilities in North Shouneh (#Ref. Canadan Cost Extension) Total amount of 1,600,000 .00USD | Not Started | Issue ITB in May 2018 and begin implementation stage in July 2018 and complete in January 2019 | [12 empty] | Construction Works | 1 | 1000000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 1000000
|  | Elaboration of Full Socio-Economic study in North Shouneh (#Ref. Canadan Cost Extension) | Not Started | Elaboration of Full Socio-Economic study in North Shouneh (#Ref. Canadan Cost Extension) | [12 empty] | Socio-Economic Study | 1 | 90000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 90000
|  | Value Chain, SOP and intensive mechanism for the community recycling | Not Started | Value Chain, SOP and intensive mechanism for the community recycling | [12 empty] | Studies | 1 | 180000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 180000
| Total for Activity 3 | [22 empty] | 1776000
| GMS for Activity 3 | [22 empty] | 142080
| Grand Total for Activity 3 | [22 empty] | 1918080
| Activity 4 | Community outreach - Small grant (total 40,000.00) | Not Started | Community outreach - Small grant (total 40,000.00) | [12 empty] | Sorting and recycling of Solid Waste | 1 | 30000 | 30000 | 12113 | 72600 | Contractual Services - Companies | 30000
|  | Procure the services of trainers and capacity building (6 trainers - IC) | Not Started | Procure the services of trainers and capacity building (6 trainers - IC) | [12 empty] | Procurement - Individuals | 75 | 500 | 30000 | 30000 | 71300 | National Consultants | 37500
|  | RPA -Sorting Facilities Operation and Livelihood and Women Empowerment (Total 300,000.00 USD) | Not Started | RPA -Sorting Facilities Operation and Livelihood and Women Empowerment (Total 300,000.00 USD) | [12 empty] | RPA -Sorting Facilities Operation and Livelihood and Women Empowerment | 1 | 210000 | 30000 | 12113 | 72100 | Contractual Services - Companies | 210000
| Total for Activity 4 | [22 empty] | 277500
| GMS for Activity 4 | [22 empty] | 22200
| Grand Total for Activity 4 | [22 empty] | 299700
| Activity 7 | RPA - Composting Plant Operation and Livelihood and Women Empowerment | Ongoing | RPA - Composting Plant Operation and Livelihood and Women Empowerment | [12 empty] | RPA - Composting Plant Operation and Livelihood and Women Empowerment | 1 | 299390 | 30000 | 12113 | 72100 | NGO small grants and marketing | 299390
|  | Contractual Services Companies - Infrastructure | Ongoing | Irrigation system and other works | [12 empty] | Construction Works | 1 | 23147.25 | 30000 | 12113 | 72100 | Contractual Services - Companies | 23147.25
|  | Local Consultant | Ongoing | Local Consultants | [12 empty] | Procurement - Individuals - Remaining Payments for Ehab Al-Manaseer, | 1 | 14648.3051 | 30000 | 00110 | 71300 | National Consultant | 14648.3051
| Total for Activity 7 | [22 empty] | 337185.5551
| GMS for Activity 7 | [22 empty] | 26974.8444
| Grand Total for Activity 7 | [22 empty] | 364160.3995
| Total Programmable Budget 2018 | [22 empty] | 4437125.3024
| Total GMS for 2018 | [22 empty] | 354970.0242
| Grand Total for All Activities in 2018 | [22 empty] | 4792095.3265
Note on F47: Basma: Implmentation will start in Sept 2016 till March 2017
Note on U19: dell: Assumed 15 working days. To be advised by Ghimar
Note on U20: dell: Assumed 15 working days. To be advised by Ghimar
Note on F46: Basma: Implmentation will start in Sept 2016 till March 2017
Note on F59: Basma: Implmentation will start in Sept 2016 till March 2017
Note on F60: Basma: Implmentation will start in Sept 2016 till March 2017
Note on F55: Basma: Implmentation will start in Sept 2016 till March 2017

## SOCIAL COHESION
Title: | Social Cohesion |  |  |  |  | Total Budget 2018 | Prepared by:
ID: | 85571 | [5 empty] | Certified by:
| Activities | Fund | Donor | Account Code | Description | Amount USD $
Budget Description
Activity 1
[5 empty] | Others | 37037.04
[5 empty] | Staffing | 73824.53 | 73824.5307
| Total for Activity 1 |  |  |  |  | 110861.5707
| GMS for Activity 1 |  |  |  |  | 8868.9257 |  |  | 54549.79 | 94549.79
| Grand Total for Activity 1 |  |  |  |  | 119730.4964 | 140547.2164 | 119730.4964 |  | 87546.1019
| Activity 6 | 30000 | 141 | 72100 | Contractual Services | 159926.73 |  |  |  | 550380.1636
|  | 30000 | 141 | 71300 | Local Consultant | 25000 |  |  | 0 | 0
|  | 30000 | 141 | 75700 | Training Workshops & Confrences | 25000
|  | 30000 | 141 | 71600 | Travel | 20000
|  | 30000 | 141 | 74500 | Miscellaneous | 3000
|  | 30000 | 141 | 72600 | Grants | 276684.5326 |  | 276684.5326 | 276684.5326 | 295636.0152
|  | 30000 | 141 | 75100 | GMS | 40768.901
| Total for Activity 6 |  |  |  |  | 509611.2626 | 490336.5219 | 19274.7407
| GMS for Activity 6 |  |  |  |  | 40768.901
| Grand Total for Activity 6 |  |  |  |  | 550380.1636 | 529563.4436 |  |  |  | 20816.72
0
| (Activity 1 & 6)Total Programmable Budget 2018 |  |  |  |  | 620472.8333 |  |  | 0
| (Activity 1 & 6) Total GMS for 2018 |  |  |  |  | 49637.8267
| (Activity 1 & 6) Grand Total in 2018 |  |  |  |  | 670110.66
| Total Output 85571 |  |  |  |  | 670110.66

## PVE2
2018 Budget- PVEII |  |  |  |  | Old budget 2018 | New budget 2018 | Budget Revision
| Fund | Donor | Budget Code | Budget Description
Activity One: PMU | 32045 | 141 | 61300 | Salaries P4 | 76574.4 | 70000 | -6574.4
| 32045 | 141 | 64397 | DPC | 67500 | 107950 | 40450
| 32045 | 141 | 71400 | Service contract | 448630.2 | 421699.58 | -26930.62
| 32045 | 141 | 71500 | UNV | 13527 | 19320 | 5793
| 32045 | 141 | 72100 | Contractual ( Security , cleaning companies) | 34230.51 | 0 | -34230.51
| 32045 | 141 | 73100 | Rental | 54133.47 | 10625 | -43508.47
| 32045 | 141 | 72300 | Vehicle fuel | 25700 | 18285.31 | -7414.69
| 32045 | 141 | 72500 | Stationary | 0 | 4000 | 4000
| 32045 | 141 | 74200 | Printing & Communication | 0 | 2000 | 2000
| 32045 | 141 | 72400 | Internet & communication | 12750 | 32000 | 19250
| 32045 | 141 | 75700 | Training /Learning | 0 | 5000 | 5000
| 32045 | 141 | 71600 | Travel | 0 | 8394.8 | 8394.8
| 32045 | 141 | 74500 | Misc & Hospitality | 0 | 1500 | 1500
| 32045 | 141 | 72800 | IT equipment | 0 | 5000 | 5000
| 32045 | 141 | 74100 | Audit |  | 8636 | 8636
| 32045 | 141 | 74598/77300 | Reporting & Partnership | 0 | 0 | 0
| 32045 | 141 | 75100 | GMS | 58643.6464 | 57152.8552 | -1490.7912
Total Activity ( 1) |  |  |  |  | 791689.2264 | 771563.5452 | -20125.6812
Activity 2 PVE Strategy | 32045 | 141 | 72100 | Contractual Services | 30000 | 100000 | 70000
| 32045 | 141 | 71300 | Local Consultant | 50000 | 94117 | 44117
| 32045 | 141 | 75700 | Training Workshops & Confrences | 0 | 8562.96 | 8562.96
| 32045 | 141 | 71600 | Travel | 1500 | 5000 | 3500
| 32045 | 141 | 74500 | Miscellaneous | 1500 | 5000 | 3500
| 32045 | 141 | 71200 | International Consultants | 0 | 52330 | 52330
| 32045 | 141 | 75100 |  |  |  | 0
| 32045 | 141 | 75100 | GMS | 6640 | 21200.7968 | 14560.7968
Grand Total for Activity 2 |  |  |  |  | 89640 | 286210.7568 | 196570.7568
Activity Three: 3x6 Approach | 32045 | 141 | 72100 | Contractual Services | 180905.36 | 180905.36 | 0
| 32045 | 141 | 75700 | Training, Workshops and Conference (including Incetives for Beneficiaries) | 0 | 0 | 0
| 32045 | 141 | 72600 | Grants (Microbusinesses Seed Capital) | 177000 | 177000 | 0
| 32045 | 141 | 75100 | GMS | 28632.4288 | 28632.4288 | 0
Total Activity (3) |  |  |  |  | 386537.7888 | 386537.7888 | 0
Activity Four: Support to London Compact | 32045 | 141 | 71300 | Local Consultant | 0 | 0 | 0
| 32045 | 141 | 72100 | Contractual Services | 49013 | 118457.44 | 69444.44
| 32045 | 141 | 74200 | Communication & Visibility | 5000 | 5000 | 0
| 32045 | 141 | 71600 | Travel | 5000 | 5000 | 0
| 32045 | 141 | 75700 | Hospatility | 5000 | 500 | -4500
| 32045 | 141 | 75700 | Training, Workshops and Conference | 0 | 4000.28 | 4000.28
| 32045 | 141 | 74500 | Misc. | 5000 | 5000 | 0
| 32045 | 141 | 75100 | GMS | 5521.04 | 11036.6176 | 5515.5776
Total Activity (4) |  |  |  |  | 74534.04 | 148994.3376 | 74460.2976
Activity Five NGO Platform on PVE | 30000 | 182 | 72100 | Contractual Services | 63060 | 63060 | 0
| 30000 | 182 | 71300 | Local Consultant | 233094.76 | 233094.76 | 0
| 30000 | 182 | 64397 | DPC | 16905.2 | 16905.2 | 0
| 30000 | 182 | 75100 | GMS | 25044.7968 | 25044.7968 | 0
Overall Total/Activity (5) |  |  |  |  | 338104.7568 | 338104.7568 | 0
Total Budget |  |  |  |  | 1680505.812 | 1931411.1852 | 250905.3732
Note on G9: GTS!: 22598.87 needed for 2018 10000 will be taken form SDC
Note on G14: GTS!: 12605.2 will be taken form SDC
Note on F36: Mohammad Anakrih: This amount is from Turkey/Unilever. It is budgeted to cover the cost of Red Rose Project with PTI. Total amount (including GMS): 52,935USD Amount (excluding GMS): 49,013USD

## 85571
2018 Budget - Project 00085571 |  |  |  |  | Budget 2018
Activities | Fund | Donor | Account Code | Description
Activity 1 PMU | 30000 | 10282 | 71400 | Service contract | 46314.5
| 30000 | 10282 | 71500 | UNV | 39024.5
| 30000 | 10282 | 71600 | Travel | 12605.2
| 30000 | 10282 | 72300 | Materials and Goods | 10000
| 30000 | 10282 | 72500 | office supplies | 2917.4
| 30000 | 10282 | 75100 |  | 8868.928
Total Activity 1 |  |  |  |  | 119730.4964
Activity (2): Short-Term Employment | 30000 | 37 | 72100 | Contractual Services | 229508.73
| 30000 | 37 | 71300 | Local Consultant | 13935.96
| 30000 | 37 | 71600 | Travel | 0
| 30000 | 37 | 75100 | GMS | 19475.5752
| Total Donor 00037 |  |  |  | 262920.2652
| 30000 | 00145 | 72100 | Contractual Services | 113991.82
| 30000 | 145 | 75100 | GMS | 9119.3456
| Total Donor 00145 |  |  |  | 123111.1656
| 30000 | 10500 | 75700 | Training Workshops & Confrences | 3339.11
| 30000 | 10500 | 75100 | GMS | 267.1288
| Total UN Foundation 10500 |  |  |  | 3606.2388
Total activity 2 |  |  |  |  | 389637.6696
Activity ( 6) | 30000 | 10282 | 72100 | Contractual Services | 159926.73
| 30000 | 10282 | 71300 | Local Consultant | 25000
| 30000 | 10282 | 75700 | Training Workshops & Confrences | 25000
| 30000 | 10282 | 71600 | Travel | 20000
| 30000 | 10282 | 74500 | Miscellaneous | 3000
| 30000 | 10282 | 72600 | Grants | 276684.5326
| 30000 | 10282 | 75100 | GMS | 40768.901
Total Activity 6 |  |  |  |  | 550380.1636
Overall Total Budget / 00085571 |  |  |  |  | 1059748.3296
Note on F12: User: - Mohd Mughair = 6666 - Consulatant on CSOs
Note on F19: Mohammad Anakrih: The remaining of the Mara Mentor - online platform

## 94965
2018 Budget - Project 00094965 |  |  |  |  | Total Budget 2018
Activities | Fund | Donor | Account Code | Description
Activity 1 PMU | 30000 | 12113 | 61300 | Salaries P4 | 114262.53
| 30000 | 12113 | 64300 | DPC | 240000
| 30000 | 12113 | 71400 | Service contract | 385754.53
| 30000 | 12113 | 71500 | UNV | 15884.38
| 30000 | 12113 | 71600 | Travel | 64484.87
| 30000 | 12113 | 71300 | Local Consultant | 56172
| 30000 | 12113 | 72200 | office Equipment | 25000
| 30000 | 12113 | 72300 | Materials and Goods | 18000
| 30000 | 12113 | 72400 | Communication | 3800
| 30000 | 12113 | 72500 | Office supplies | 6000
| 30000 | 12113 | 72700 | Hospatiality | 500
| 30000 | 12113 | 72800 | IT equipment | 7000
| 30000 | 12113 | 74200 | Audio & Visual Equipment | 11000
| 30000 | 12113 | 74500 | Miscellaneous | 6002
| 30000 | 12113 | 75700 | Training Workshops & Confrences | 4000
| 30000 | 12113 | 75100 | GMS | 76628.8248
Total Activity 1 |  |  |  |  | 1034489.1348
ACTIVITY 2:Infrastructure of Al Ekea | 30000 | 12113 | 72100 | Contractual Services | 1088580
| 30000 | 12113 | 75100 | GMS | 87086.4
Total Activity 2 |  |  |  |  | 1175666.4
ACTIVITY 3:Transfer Stations&SW coll | 30000 | 12113 | 71300 | Local Consultant | 56000
| 30000 | 12113 | 72100 | Contractual Services | 1720000
| 30000 | 12113 | 75100 | GMS | 142080
Total Actvity 3 |  |  |  |  | 1918080
ACTIVITY 4:Local Communities Livelih | 30000 | 12113 | 71300 | Local Consultant | 37500
| 30000 | 12113 | 72100 | Contractual Services | 210000
| 30000 | 12113 | 72600 | Grants | 30000
| 30000 | 12113 | 75100 | GMS | 22200
Total Activity 4 |  |  |  |  | 299700
ACTIVITY 7:Composting | 30000 | 12113 | 71300 | Local Consultant | 14648
| 30000 | 12113 | 72100 | Contractual Services | 322537
| 30000 | 12113 | 72200 | office Equipment | 0
| 30000 | 12113 | 75100 | GMS | 26974.8
Total activity 7 |  |  |  |  | 364159.8
Total SWM budget |  |  |  |  | 4792095.3348
C