Post-2015 Focus Group

Dialogues on Partnerships with Civil Society

Process and action plan

Overview

In 2014 the UNCT in Jordan has been selected as one of seven countries to run the second round of post-2015 dialogues under the theme “Partnership with civil society and other actors”, along with Azerbaijan, Cambodia, Indonesia, Lesotho, Saint Lucia and Tunisia.

The consultations will enable civil society to contribute substantively to the shaping of key policies related to the implementation for the post-2015 development agenda by sponsoring open dialogues with the national government and key actors/stakeholders. This dialogue also aims at supporting strategic alliances among civil society networks to strengthen constituencies and amplify action on the implementation, monitoring and accountability of the future agenda.

The process

The second round of post-2015 dialogues in Jordan will encompass two streams:

- Exploring ways for the engagement of the civil society in the implementation of the future agenda. In particular, this stream will look into mechanisms through which the civil society can influence policymakers and play a role in the monitoring and accountability of the Post-2015 Development Agenda.

- Ensuring continuity with the first phase of consultations in Jordan, by discussing challenges and opportunities for the civil society around the main priorities emerged in the national consultations . It is recommended that UN agencies will take the lead in organizing thematic dialogues  related to their mandate.

The process will make use of a multidimensional approach, including offline and online activities,  namely:

- Dedicated events discussions with civil society to assess existing partnerships with the Government and to contribute with inputs at central and governorate level. The dialogues  will be organized around the four thematic areas by mandated UN agencies (Annex 1). Each event  will encompass two different sessions in order to embrace both abovementioned streams.

- Discussion sessions during other meetings and events already planned or organized by UN Agencies in Jordan. In this regard, the process will create linkages with the Beijing+20 consultations in Jordan.

- Selected interviews to capture in-depth views and complement findings with more articulated perspectives.

- E-discussions on the dedicated page of the “World We Want” website and on the social media accounts of the UN in Jordan.

Simultaneously, the Post-2015 Focus Group will also widely promote the “Mark A Difference” campaign and disseminate the MY World survey. Online and offline activities will include, amongst other, a media and social media strategy, the consolidation of the network of the  “Mark A Difference” volunteers and the organization of the “MY World Podium tour” in Jordan.

Stakeholders involved

- Civil society networks, women movements, youth groups and other civil society groups;

- Selectively, Private sector, focusing on mechanisms for civil society to play a major role in the implementation of the future framework;

- MOPIC and other national institutions (e.g. Parliament) to discuss potential partnerships with the civil society;

- Government of Jordan, to influence the official  positions in the post-2015 intergovernmental process;

- HM Queen Rania Al Abdullah and members of the Royal Family, for their awareness;

Visibility and communications

The UN Communications Group will support the Post-2015 Focus Group to establish a constant dialogue with the general public, while reinforcing the participatory communication style of civil society networks. The combination of different outreach efforts and methods (traditional media, social media and meet/tweet-ups) will not only increase the visibility of the process, but also encourage and enhance partners’ contributions at the national and local level. UNCG members will provide communication material during the events organized by their respective agencies.

Output

- Key summary of messages and recommendations to feed into the global dialogue

- A final report to be disseminated in Jordan and discussed with relevant stakeholders

Timeframe

| Deliverables | Deadline (2014) |
| --- | --- |
| Selection of consultant | By Mid-May |
| Preparation of templates and work plan, mapping of relevant existing mechanisms for civil society engagement and preparation of Ar-En documentation for the dialogue | By 22 May |
| Thematic events discussions and other dialogues during UN events | 25 May – 28 June (Ramadan starts) |
| Interviews | 1 July – 15 July |
| E-consultations and social media | Throughout, but mainly during Ramadan |
| Draft summary of key outcomes and recommendations from the consultations | By 7 August |
| Analytical report of the consultations | By 1 September |
| Organization of a workshop among relevant stakeholders to review and discuss the main findings of the consultations | 1-21 September 2014 |

Annex 1 – UN Agencies and Thematic Areas

|  | Areas of change | UN Agencies |
| --- | --- | --- |
| 1 | Strengthen the link between education and labor market, and support entrepreneurship to reduce unemployment and ensuring decent work | Leading Agency: UNESCO Partner Agencies: UNWOMEN, UNV, UNDP, UNOPS |
| 2 | Combat stereotypes to ensure gender equality and decrease geographical disparities; reduce poverty and ensure equal access to social services (health, education, etc…) | Leading Agency: UNWOMEN Partner Agencies: UNHABITAT, WHO, UNV, UNDP, IOM |
| 3 | Enhance accountability, respect Human Rights and contribute to regional stability | Leading Agency: UNDP Partner Agencies: UNV, UNESCO, UNWOMEN |
| 4 | Enhance awareness on environment, promote renewable energy and address water scarcity (sustainable development) | Leading Agency: WFP Partner Agencies: UNHABITAT, UNEP |

# Footnotes

The four “areas of change” are described in the National Consultations report for Jordan “Messages for the Future We Want” and will be outlined hereafter;

http://www.worldwewant2015.org/civilsociety2015