## AWP-2018
Title: | Property Tax Project Phase II | [7 empty] | Award: |  |  |  | 00075608 |  |  |  | Total Budget |  |  |  | 365568.5 |  |  |  |  | Prepared by: |  | Haitham AL-Sayed
ID: | 00075608 | [7 empty] | Year: |  |  |  | 2018 |  |  |  | Total Expenditures (1/1- 31 /12/ 2018) | [8 empty] | Certified by: |  | Diana Jraisat
Outcome: UNDAF Outcome 19: Strengthened institutions, systems and processes to promote, coordinate and implement pro-poor gender sensitive national development objectives based on good governance principles
Output | Activities | Sub Activity | Status / Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Budget |  |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of Contract | Duration | Type of Procurement | Nature of assignment / deliverable |  | Fund | Donor | Account Code | Budget Description | Amount USD
Output 1: Draft property-related tax laws are completed to establish the legal and institutional framework for the implementation of a modern property tax system | 1.1.1 Mobilize expertise in helping the Property Tax Law Review Committee to provide inputs to the draft law from a men and women’s perspective and any related regulations . | bar: Q2 Apr to Q2 Jun
| 1.1.2 Set up meetings with other partners including local authorities and women’s groups/experts for policy dialogue to further review the current draft property-related tax laws and regulations and share the lessons learned from the international best pr | [22 empty] | 30071 | JOR | 74100 | Professional Services | 2500 |  | MoF& UNDP | bar: Q2 Apr to Q3 Sep
| 1.1.3. Organize activities for sharing/disseminating information for public awareness on the draft property tax law able to equally reach men and women. | [22 empty] | 30071 | JOR | 72500 | Supplies | 0 |  | MoF | bar: Q3 Jul to Q3 Sep
75 | bar: Q3 Jul to Q3 Sep
Output 2: the current nationwide de centralized property tax information system upgraded and implemented in all municipalities | 2.1. Upgrade the 65 municipalities that have installed the old system to the enhanced property tax information system. Train users on the upgraded installed system. |  | Upgrade 15 municipalities to the enhanced system. | [20 empty] | 04000 | UNDP | 72800 | Information tech. equip. (Computer Hardware) | 0 |  | MoF&MoMA | bar: Q1 Jan to Q3 Sep
| 2.1.1. Complete the installation of the new computer systems and network infrastructure in the municipalities or other local authorities using the old system. |  | 15 municipalities were completed. | Purchase of 2 servers | [19 empty] | 30071 | JOR | 72800 | Information tech. equip. (Computer Hardware) | 100000 |  | MoF&MoMA | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 3000
| 2.2. The upgraded property tax information system and related IT infrastructure is installed in the remaining municipalities and other local authorities not yet covered in Phase I. The users of the new system are trained. |  | 10 municipalities were completed. | [20 empty] | 04000 | UNDP | 72400 | Communications (Leased Lines) | 0 |  | MoF&MoMA | bar: Q1 Jan to Q3 Sep
| 2.2.1. Complete the installation of the upgraded computer systems and network infrastructure in the remaining municipalities or other local authorities not yet covered in Phase I. |  | 20 municipalities were completed. | [20 empty] | 30071 | JOR | 72100 | Contractual Serv. Company (Information Tech.) | 5000 |  | MoF&UNDP | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 150
| 2.2.2. Install the upgraded property tax information system (software) in the remaining municipalities or other local authorities not yet covered in Phase I. |  | 10 municipalities were completed. | Oracle software license | [19 empty] | 30071 | JOR | 72800 | Information technology (Oracle Software) | 0 |  | MoF&MoMA | bar: Q1 Jan to Q3 Sep
| 2.2.3. Conduct training and workshops on property tax administration and property tax information system for various users/stakeholders including gender training sessions explaining the gender differences in the property tax system and how this effects |  | 25 employees trained | conducted a training, workshops and conferences. | [19 empty] | 30071 | JOR | 72500 | (Supplies) Training, workshops and conferences. | 10000 |  | MoF&MoMA | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 300
| 2.2.4. Provide administrative and technical support to all municipalities. |  | weekly visits | field travel | [19 empty] | 30071 | JOR | 71600 | Travel | 15000 |  | MoF | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 450 | bar: Q1 Jan to Q3 Sep
| 2.3. Develop the upgraded Property Tax Information System to support the new features such as information on mass property valuation, geographic and image information, PDA, barcode readers, and e-payment. |  |  | in cooperation with RGC | [19 empty] | 04000 | UNDP | 72100 | Contractual Serv. Company (Information Tech.) | 0 |  | MoF&UNDP | bar: Q3 Jul to Q3 Sep
| 2.3.2. Expand the current property tax information system to include rezoning revenue for all municipalities and other local authorities. |  | 15 municipalities were completed. | Prepared an Action plan | [19 empty] | 30071 | JOR | 72400 | Communications (Leased Lines) | 0 |  | MoF&MoMA | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 0
| 2.3.3. Supervise the development of the enhanced Property Tax Information System including the development of systems documentation and user’s manuals. |  | 3 user manuals were prepared | Printing & Publications | [19 empty] | 30071 | JOR | 74200 | Printing & Publications | 0 |  | MoF&MoMA | bar: Q2 Apr to Q3 Sep
[27 empty] | GMS | 0
| 2.3.4. Perform systems installation and pilot testing. |  | tested in 5 pilot sites | running test | [19 empty] | 30071 | JOR | 71300 | Local Consultants | 0 |  | MoF | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 0 | bar: Q1 Jan to Q3 Sep
| 2.3.5. Deliver user training and perform systems maintenance. |  | Running Maintenance. | Maintenance Contract | [19 empty] | 30071 | JOR | 73300 | Maintenance of Equipment | 10000 |  | MoF&UNDP | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 300
Output 3: Equitable, cost-effective, and comprehensible assessment systems designed | 3.1. Provide technical assistance for capacity development throughout in the development of mass assessment models for property tax purposes |  | Meeting with GAM & Municipalities | [20 empty] | 30071 | JOR | 71600 | Travel | 0 |  | MoF | bar: Q3 Jul to Q3 Sep
[27 empty] | GMS | 0 | bar: Q3 Jul to Q3 Sep
| 3.1.1. Obtain through the Land and Survey Department sex-disaggregated property sales data and representative samples of property tax objects for selected municipalities |  | sign agreement with Land and Survey Department to provide the project technical data | DLS is providing the project with upgraded data | bar: Q1 Jan to Q3 Sep
| 3.1.2. Analyze sex-disaggregated property sales data and representative samples of property tax objects and develop models for mass property valuation |  | DLS is providing the project with upgraded data | bar: Q1 Jan to Q1 Mar
| 3.1.5. Provide technical assistance and deliver training and workshops to introduce computer-assisted mass appraisal (CAMA) techniques/models using actual sex-disaggregated data from Jordan (using international best practices as examples) | [28 empty] | MoF, MoMA, GAM, DAI
| 3.2. Develop property valuation and assessment manuals (to describe step-by-step procedures for property valuation model development and application) | [28 empty] | MoF, MoMA, GAM, DAI | bar: Q3 Jul to Q3 Sep
| 3.3. Design and produce technical specifications for the development of a computer-assisted mass assessment (CAMA) system able to collect and analyze sex-disaggregated data to be integrated into the Property Tax Information System. | [28 empty] | MoF, MoMA, GAM, DAI
| 3.3.5. Prepare a field report and conduct a half-day seminar to disseminate the lessons learned. | [28 empty] | MoF, MoMA, GAM, DAI
| 3.4.1. In cooperation with the Land & Survey Department, develop a geographic information system (GIS) using appropriate tools and technology. |  | In cooperation with RGC | will prepare an agreement | [25 empty] | MoF, MoMA, GAM, DAI | bar: Q3 Jul to Q3 Sep
Output 4: Property tax compliance mechanisms drafted and implemented. | 4.1. Implement cost-effective taxpayer education and awareness campaign programs targeting equally women and men,, building on the lessons learned from past initiatives |  | awareness campaign | [20 empty] | 30071 | JOR | 71300 | Local consultants | 0 |  | MoF, MoMA, GAM, DAI
[27 empty] | GMS | 0
| 4.1.1. Evaluate the effectiveness of the previous taxpayer education and awareness campaign programs, and identify the most cost-effective approach. |  | dissemination of publications | Printing & Publications | [19 empty] | 30071 | JOR | 74200 | Printing & Publications | 0 |  | MoF, MoMA, GAM, DAI | bar: Q3 Jul to Q3 Sep
[27 empty] | GMS | 0 | bar: Q3 Jul to Q3 Sep
Output 5: Smooth transition between the previous phase and the new project is ensured through the interim support of the Project Management Unit | 5.1. Continue the project management support to the implementation and facilitate change management | [22 empty] | 04000 | UNDP | 71400 | Contractual services - individuals | 0 |  | MoF&UNDP | bar: Q1 Jan to Q3 Sep
[24 empty] | 30071 | JOR | 71400 | Contractual services - individuals | 204965 |  | MoF&UNDP | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 6148.95
| 5.2. provide assistance to the government in finalizing a sustainable structure to ensure the institutionalization of this project within the Ministry of Finance. |  |  | conduct a meeting with stakeholders and concerned parties | [19 empty] | 30071 | JOR | 74500 | Sundry | 7455.87 |  | MoF&UNDP | bar: Q1 Jan to Q3 Sep
[27 empty] | GMS | 223.68
[24 empty] | 30071 | JOR | 72200 | Equipment and furniture (Office Machinery) | 0 |  | MoF&UNDP
| 5.2.3. Review the various proposed structure of the department | [22 empty] | 30071 | JOR | 72500 | Supplies (Stationery & Publications) | 0 |  | MoF&UNDP
Output 6: A Property Tax Directorate established in line with the new proposed law that is capable of regulating and monitoring assessment value able to equally consider men and women’s perspectives in implementing the decentralized property tax system | 6.1. Assign a high level committee within MoF, MOMA, and MOPSD to review and recommend the best structure for institutionalizing the processes within a government structure | [26 empty] | 0 |  | MoF | bar: Q3 Jul to Q3 Sep
| 6.1.1. - Provide technical assistance to assist MOF to design the vision, functions, institutional structure, human resources requirements and budget for the new directorate or Division | [22 empty] | 30071 | 00140 | 71200 | international consultant | 0 |  | DAI and UNDP
0
6.1.2. - Support the recruitment of the required staff to operate and undertake the management of the property tax system in the country
6.1.3. • Carry of a capacity assessment of recruited staff to identify gaps in knowledge to undertake functions Develop a tailor made learning programme to overcome these gaps in knowledge
6.1.4. Institutionalize the property tax-related training programs through the involvement of the training center at the Ministry of Finance
6.2. Support the implementation of a fully functionally division
6.2.1. - Assist the staff in the new division to develop its yearly action plan, including
6.2.2. - an action plan on advocacy
6.2.3. - Provide strategic Management advice to implement the activities of the action plan, which should include its regulatory, planning , monitoring ,management functions and technical advisory support to governorate and municipalities levels
Total Budget | [27 empty] | 365568.5