Agreed by UNDP Resident REPRESENTATIVE:

| (Enter Name, Position) | Signature | Date: (Month, day, year) |
| --- | --- | --- |

Knut Ostby		………………………………………..	………………………………

INITIATION   PLAN

for a GEF Project Preparation Grant (PPG) or
Programme Coordination Budget (PCB)

Brief Description of Initiation Plan

The Economic and Conservation Division under Kiribati’s Ministry of Environment, Land, and Agricultural Development (MELAD) requested GEF’s assistance through UNDP to carry out a medium-sized project (MSP): Integrating Global Environmental Priorities into National Policies and Programmes. The project will design and create an Environmental Management Information System (EMIS) that serves to create new and improved environmental data and information.

In addition the project will also structure a compliance monitoring system (CMS). The CMS would be used as part of the learning and re-tooling (i.e., adaptive collaborative management) of programmes and plans to ensure that their implementation proceed to deliver the agreed-upon objectives and expected outcomes.

The Project Preparation Grant (PPG) is requested to design the MSP through appropriate situation analysis and extensive stakeholder consultation. A key objective of the PPG will be to assess existing data for both the components. From these, establish the baseline context, to clarify GEF increment and to plan activities to all stakeholders. Also the PPG will help develop a strategic results framework that has optimal resource allocation from GEF and other stakeholders to meet the project objectives. Key sub-activities supported by the PPG include:  (1) baseline studies and strategy development for both components – EMIS and CMS; (2) Secure government support on implementation arrangement and commitment to project strategy and (3) Put together a defined sustainability and M&E Plans for the project. The output of the PPG will be the Project Document ready to Request for GEF CEO Endorsement.

GEF PPG/PCB approved grant document and TBWP

Project PREPARATION GRANT (ppg)

Project Type:

type of Trust Fund:

Submission date:  09/06/2012

Re-submission date: 12/19/2012, 02/25/2013

GEF Project ID: 5130

GEF Agency  Project ID: 4936

Country(ies): Kiribati

Project Title: Integrating Global Environmental Priorities Into National Policies And Programmes

GEF Agency(ies): , ,

GEF Focal Area(s):

a.   Project preparation Timeframe

| Start date of PPG | 06/01/2013 |
| --- | --- |
| Completion date of PPG | 12/01/2013 |

B.  proposed project preparation activities ($)

| Describe the PPG activities and justifications: The PPG will cover the following preparatory activities: 1. Baseline studies and strategy development: A) Environmental management information system - Assess existing data and information management systems; - Assess best practices for data and information management systems for environment in the region and all SIDS and identify best model for Kiribati; - Undertake stakeholder analysis; - Uundertake training needs assessment, as appropriate; - Prepare project strategy to develop integrated, real-time, coherent, comprehensive environmental management information system, including proposed outputs, activities, inputs and timetables. This should build on existing information management systems; B) Compliance monitoring system - Assess present system to monitor compliance with Rio conventions and report to conventions; - Undertake stakeholder analysis; - Assess best practices for compliance monitoring systems for environmental performance in the region and in all SIDS and identify best model for Kiribati. - Prepare project strategy to develop integrated, comprehensive compliance monitoring system that is integrated into national reporting on other socio-development issues (poverty, MDGs, etc). This should include proposed outputs, activities, inputs and timetables. This should build on existing compliance monitoring and reporting systems; 2. Secure government commitment to project strategy: Make contact with key agencies. Negotiate with key government representatives to ensure full agreement on the project objectives, outcomes, outputs, and activities, including partnerships for support and government co-financing. 3. Secure government commitment to project implementation arrangements: Undertake consultations with key government representatives to secure agreement on project implemenetation arrangements, including roles, responsibilities, and accountabilities of lead and partner agencies. 4. Explore and secure bilateral and multilateral financing opportunities: Explore potential for partnerships with bilateral and multilateral donor agencies and organizations, including networking among other potential regional and international development organizations. Negotiate partnerships with on-going projects to re-align their activities to meet project objectives will be considered. If appropriate, finalize co-financing agreements. This activity will target, at a minimum, the following potential financial partners: - World Bank; - Government of Taiwan; - Government of the United States; - Government of Australia; - The European Union 5. Define Monitoring and Evaluation (M&E) Plan: A detailed M&E work plan and delivery strategy will be defined, including clear identification of responsibilities and accountabilities, as well as an appropriate budget allocation (based on best practices and UNDP guidelines). The Plan will reflect the requirements of the GEF M&E Policy and Capacity Building M&E framework. The Plan will also include provisions for an independent evaluation and provision to ensure the learning of lessons from implementation at both the mid-point and termination of the project. The Plan will also use the Capacity Development Indicators (as developed by UNDP) to establish the baseline and monitor progress. This will be done together with the use of the Capacity Development Scorecard (GEF Tracking Tool). 6. Define Sustainability Plan: The Sustainability Plan will outline an exit strategy, leading to the continuation of concerned activities without the need of long-term international financing. 7. Validation workshop Representatives from all relevant stakeholders will gather to discuss and validate the final draft proposal. The final product of the proposed PPG phase will be a UNDP/GEF compliant medium-sized project document for submission to UNDP and GEF, including the following: • A detailed work plan with detailed roles and responsibilities for project implementation; • A targeted, in-depth analysis of the baseline situation and needs; • An updated report on the partnership and co-financing opportunities for the proposed project; • Explicit specification of all capacity building activities to be financed under the project and the rationale of their additionality to meeting Rio Convention objectives; • A detailed deconstruction of the project strategy using the Logical Framework Approach (log frame); • A detailed monitoring and evaluation plan for the project that builds upon the log frame; • A stakeholder participation plan; • Endorsement letters from the government and letters confirming co-financing commitments; • Medium-Size Project document per GEF and UNDP formatting and submission requirements; • Terms of Reference for key project staff, project management committee and key consultants. |
| --- |
| List of Proposed Project Preparation Activities | Output of the PPG Activities | Trust Fund | Grant Amount (a) | Co-financing (b) | Total c = a + b |
| Baseline study/strategy development 1A | Analysis papers and strategy for creating EMIS |  | 5,000 | 5,000 | 10,000 |
| Baseline study/strategy development 1B | Analysis papers and strategy for creating CMS |  | 4,000 | 5,000 | 9,000 |
| Secure government committment | Letters of endorsement and full commitment |  | 0 | 1,000 | 1,000 |
| Secure co-financing | Letters of co-financing and/or MoUs. |  | 1,000 | 1,000 | 2,000 |
| Define M&E Plan | Clear plan for monitoring and evaluating the project |  | 0 | 3,000 | 3,000 |
| Define Sustainability Plan | Clear plan for ensuring sustainability of project outcomes |  | 0 | 3,000 | 3,000 |
| Validation workshop | Commitment to the project from concerned stakeholders |  | 5,000 | 1,000 | 6,000 |
| Prepare project documentation | Complete documentation for UNDP and GEF approval of a medium-sized proejct. |  | 9,000 | 1,000 | 10,000 |
|  |  |  |  |  | 0 |
|  |  |  |  |  | 0 |
|  |  |  |  |  | 0 |
|  |  |  |  |  | 0 |
| Total Project Preparation Financing |  | 24,000 | 20,000 | 44,000 |

C.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| Grant Amount | 24,000 | 2,280 |
| Co-financing | 20,000 |  |
| Total | 44,000 | 2,280 |

D.  PPG  Amount requested by agency(ies), focal area(s) and country(ies) 1

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Kiribati | 24,000 | 2,280 | 26,280 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total PPG Amount | 24,000 | 2,280 | 26,280 |

1 No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.   PPG Budget

| Cost Items | Total Estimated Person Weeks for Grant (PW) | Grant Amount ($) | Co-financing ($) | Total($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 20.00 | 10,000 | 2,500 | 12,500 |
| International consultants* | 3.00 | 7,500 | 2,500 | 10,000 |
| Travel |  | 1,500 |  | 1,500 |
| workshops |  | 5,000 | 5,000 | 10,000 |
| advocacy and support |  |  | 10,000 | 10,000 |
|  |  |  |  | 0 |
| Total PPG Budget |  | 24,000 | 20,000 | 44,000 |

* Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

F.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF LDCF/SCCF/NPIF Trust Fund criteria for project identification and preparation.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Officer in Charge UNDP-GEF |  | December, 19, 2012 | Tom Twining-Ward, UNDP Green-LECDRS | +421 2 59337 386 | tom.twining-ward@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Type of Consultant | Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be Performed |
| --- | --- | --- | --- | --- |
|  | Data And Information Management Expert | 500 | 10.00 | Undertake baseline studies and strategy development related to ‘data and information management’: - Assess existing data and information management systems; - Undertake stakeholder analysis; - Undertake training needs assessment; - Prepare project strategy to develop integrated, real-time, coherent, comprehensive environmental management information system, including proposed outputs, activities, inputs and timetables. This should build on existing information management systems; - Contribute to drafting of project design and GEF submission document. |
|  | Convention Compliance/Reporting Expert | 500 | 10.00 | Undertake baseline studies and strategy development related to ‘compliance monitoring system’: - Assess present system to monitor compliance with Rio conventions and report to conventions; - Undertake stakeholder analysis; - Undertake training needs assessment; - Prepare project strategy to develop integrated, comprehensive compliance monitoring system that is integrated into national reporting on other socio-development issues (poverty, MDGs, etc). This should include proposed outputs, activities, inputs and timetables. This should build on existing compliance monitoring and reporting systems; - Contribute to drafting of project design and GEF submission document. |
|  | Capacity Development And Project Design Expert | 2500 | 3.00 | - Work together with the local consultants (LC), UNDP and national counterparts on setting PPG implementation strategy; - Finalize PPG work plan, TOR for LCs, and design consultation and validation workshops. - Oversee completion of background studies, ensuring they are appropriate in scope and provide required analys; - Facilitate and guide consultations to determine project strategy, priorities, key partners, and key barriers to success; - Provide technical and professional support to the LC and national stakeholders. - Develop the project strategy; detailed budget, work plan and logical framework, develop a replication strategy. - Draft final project documents. |

1 Provide dollar amount per person week.

2   Provide person weeks  needed to carry out the task

Total Budget and Work Plan

| Award ID: | 00073694 |
| --- | --- |
| Award Title: | KI Integrating Global Env. Priorities in Natn'l Policy |
| Business Unit: | FJI10 |
| Project Title: | Integrating Global Environmental Priorities Into National Policies And Programmes |
| Project ID: | 00086402 |
| PIMS No. | 4936 |
| Implementing Partner (Executing Agency) | Environment and Conservation Division (ECD), Ministry of Environment, Land, and Agricultural Development (MELAD) |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 2013 (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Development of medium-size project document | UNDP/MELAD | 62000 | GEF | 71200 | International Consultant | 7,500 |
|  |  |  |  | 71300 | Local Consultant | 10,000 |
|  |  |  |  | 71600 | Travel | 1,500 |
|  |  |  |  | 75700 | Training, Workshops & Conferences | 5,000 |
|  |  |  |  |  | Total Outcome 1 | 24,000 |
|  |  |  |  | TOTAL | 24,000 |

| Summary of Funds: |  |  |
| --- | --- | --- |
|  |  |  | 2013 |  |
|  |  | GEF | 24,000 | $ |
|  |  | Government | 20,000 | $ |
|  |  | TOTAL | 44,000 | $ |

# Footnotes

Summary table should include all financing of all kinds: GEF financing, co-financing, cash, in-kind, etc.  etc

# Text boxes

Total budget:		 $44,000

Allocated resources:	 $44,000

- Government/

- In kind contributions

- Other:

  - GEF	    $24,000

  - Co-finance  $20,000

Programme Period:                                2013-2017

PPG Title:          Integrating Global Environmental Priorities into National Policies and Programmes ATLAS Award ID:                                  00073694

ATLAS Project ID:                                 00086402

PIMS Project ID:                                    4936

Duration:	                                   6 months

Management Arrangement:                    DIM

Country ___Kiribati__

UNDAF Outcome(s) and Indicator(s):

UNDAF Outcome Area 1(2013-2017): Environmental management climate change and disaster risk management

CP/CPAP Outcome(s) and Indicator (s):

Outcome 1.1: Resilience strengthen at national and community level through integrated sustainable environment management, climate change adaptation/mitigation and disaster risk.

UNDP Strategic Plan 2008-2011 Key Result Area:

Key result area 4.1. : Mainstreaming environment and energy

Project Output(s) and Indicator(s): Endorsed Project document for submission to GEF Secretariat for approval