Introduction

Project Description:

The Government of Kiribati is undertaking a cross-cutting capacity development project aimed at targeting the critical need for new and improved environmental data and environmental analysis to strengthen the foundations of Kiribati’s policy and planning frameworks in order to meet commitments to the Rio Conventions. The Kiribati Capacity Building (CB2)/Cross-Cutting Capacity Development (CCCD) project is in-line with the GEF-5 CCCD Programme Frameworks two (2) and five (5), which calls for countries (2) to generate, access and use information and knowledge and (5) to enhance capacities to monitor and evaluate environmental impacts and trends. It is a direct response to national priorities identified through the NCSA conducted in 2007-2011 and reiterated in the recently approved Kiribati Integrated Environment Policy (KIEP) and the approved Kiribati Joint Implementation Plan for Climate Change and Disaster Risk Management (KJIP). Through a learning-by-doing process, this project will harmonize existing environmental information systems, and integrate internationally accepted measurement standards and methodologies, as well as develop a more consistent reporting on the global environment. Under the first component, the project will target the development of capacities at the individual and organizational level, strengthening technical skills to collect data and transform information into knowledge. Under the second component, the project will target a more holistic construct of monitoring and evaluation systems through strengthening the institutionalization of these systems as a means to feed lessons learned and best practices from interventions to decision-makers/policy-makers. Through the provision of better environmental information, the project will increase the capacity of national and local levels’ stakeholders and counterparts to diagnose and understand complex dynamic nature of national and global environmental problems and develop local solutions; including the greater capacity to monitor and evaluate environmental programs and projects and also to better report on the state of the environment, including the national reports to the MEAs. Finally, the development of capacity of decision-makers will strengthen the environmental governance system in place in Kiribati.

Challenges:

Collection, storage, maintenance, archiving, generation and utilization of environmental data are major issues within ECD because of its limited institutional capacity. Some data/information is readily available within the various Units of ECD. Yet proper information collection, storage, maintenance, archiving, generation, utilization and collation is not undertaken because of individual and institutional limitations. There is also a lack of technical capacity within ECD to develop, maintain and operate this environment information management system for national, regional and international reporting on the state of the environment in Kiribati. This project will address this critical need to provide better environmental information in Kiribati. This is a timely response to address this national priority, particularly when considering the emerging issues due to global climate change. The possibility to monitor and record environmental data will be useful to respond to threats including negative impacts of global climate change on the local environment, which is the basis of livelihoods, human health and economy in Kiribati. (Please refer to section 2.0 below for the list of planned activities within the 1st quarter 2016)

2.0 Implementation Status

| Activities (as per AWP) | Status | Issues | Solutions |
| --- | --- | --- | --- |
| Day-to-day PMU coordination (Room renovation) | The renovation is undergoing. Doors, painting and decorating are yet to be the least for completion. | There is insufficient amount of fund to employ contractors | Some experienced and skillful staff members within ECD have put up effort to accomplish most of the renovation. |
| IT equipment procurement | The procurement has been pending since. | Lack of Technical assistance from within ECD to accomplish the task | PMU needs the technical assistant |
| Progress Reporting | This is the second offline progress reporting to be submitted ever since the project started up in July 2015. | ATLAS access has been unreliable and inconsistent | More training on the application of ATLAS is required for PMU staff. Additionally a better internet connection will ensure reliable means of communication with UNDP and external stakeholders. |

- Major Achievements

- The renovation is almost completed (refer to annex 1 for photo)

- The advertisement of local consultants was started.

Though the project has accomplished few activities, the review, the assessment of the current technology within ECD and the PMU overseeing of the renovation of office space to house the IT equipment, most activities have not been undertaken due to the unavailability of expertise from the local pool. As indicated previously in the first narrative report, the activities are as follows:

Review existing databases and management information, Identify environmental information needs Design and develop an environmental data repository, including the collection, QC and validation of produced data. Establish protocol for provision of data and information, Establish and set benchmarks, Assess existing technologies in use IT equipment procurement Progress Reporting

ECD has since requested UNDP to procure expertise on behalf of Government. It is expected that consultants will be hired by end of second quarter 2016. In the meantime, the PMU continues to oversee the renovation of office space to house the IT equipment.

Additionally the main focus for next quarter is to closely work with the consultant accomplishing all activities that have been planned in the AWP.

| Objectives and Outcomes | Indicator | Baseline | Targets End of Project | 2015 Progress | 2016 Progress | 2017 Progress (please add additional columns for later years) |
| --- | --- | --- | --- | --- | --- | --- |
| Objective: To improve information management and compliance monitoring in order to achieve global environmental benefits. | ECD stated as the primary source for environmental information in Kiribati by a significant number of national, regional and international development partners | Capacity of the main stakeholders for translating environmental information from EMIS into decision-making is low and dispersed over many organizations | 50% of stakeholders have benefitted from capacity development activities for better use of this information in decision-making and policy-making | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Reported availability of better environmental monitoring information | Collection and use of up-to-date environmental management information is ad-hoc and feebly coordinated | Up-to-date environmental information is being used by policy-makers and also by the public | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Quality of monitoring reports and communications to measure implementation progress of the Rio Conventions | Current reports are produced with limited data, weak analysis and weak trend analysis There are not fully responding to the national and international requirements. | Reports present adequate disaggregated data at local level, are informative and present environmental trends over time | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Capacity development scorecard rating | Capacity for: Engagement: 3 of 9 Generate, access and use information and knowledge: 6 of 15 Policy and legislation development: 3 of 9 Management and implementation: 3 of 6 Monitor and evaluate: 1 of 6 (total score: 16/45) | Capacity for: Engagement: 6 of 9 Generate, access and use information and knowledge: 10 of 15 Policy and legislation development: 7 of 9 Management and implementation: 5 of 6 Monitor and evaluate: 4 of 6 (total targeted score: 32/45) | Not applicable for the reporting period | Not applicable for the reporting period |  |
| COMPONENT 1.0: ENVIRONMENTAL MANAGEMENT INFORMATION SYSTEM (EMIS) |  |
| Outcome 1: An operational environmental management information system (EMIS) providing accurate and timely information. Output 1.1: An environmental data repository with standards, norms and protocols to collect, analyze, store and make available accurate, and reliable environmental information related to all three Rio Conventions, and of direct use by decision-makers. Output 1.2: An information technology architecture in place to store, manage and provide public access to environmental information. Output 1.3: Environmental information available and disseminated to stakeholders. | An environmental data repository architecture in place | No data architecture is in place to structure environmental information at ECD | Environmental data is stored in a structured way and easily accessible | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Information technologies in place to store the data repository | Limited technology is in place to support data management for an EMIS | Hardware, communication and networking equipment is in place to store environmental data and provide easy access to this information | 3rd QTR: Not applicable for the reporting period 4th QTR: IT equipment and consultant Procurement have been pending | Not applicable for the reporting period |  |
|  | Agreements for data sharing in place | Information is shared on an ad-hoc basis among institutions following formal requests made at Secretary level | 3-4 agreements are in place between ECD and 3-4 agencies/institutions to share data on a regular basis | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Use of this environmental information in decision-making and policy-making | Limited environmental information is used to develop policies and programmes | 3-4 policies, programmes or plans are developed using environmental information from the EMIS | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Environmental information is shared regionally and internationally | Limited interaction exists at the regional level to share environmental information | 2 regional sharing procedures in place by the end of the project | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Quality, quantity and timeliness of reports submitted to conventions | Reports are not submitted on time and do not contain much primary collected data | National communications/ reports are submitted on time and contain primary data collected by the EMIS | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Public states higher awareness of environmental information products | Public and decision-makers are not aware about existing environmental information | 50% of Members of Parliament are aware about existence of easily accessible environmental information at ECD | Not applicable for the reporting period | Not applicable for the reporting period |  |
| COMPONENT 2.0: ENVIRONMENTAL INDICATORS AND COMPLIANCE MONITORING SYSTEM (CMS) |  |
| Outcome 2: A Compliance Monitoring System (CMS) developed and tracking key environmental indicators. Output 2.1: An institutionalized set of environmental indicators. Output 2.2: An operational compliance monitoring system. | Adequate environmental indicators monitored | The existing set of environmental indicators is not comprehensive and does not respond to the information requirements | Set of environmental indicators in place and responds to national and international information requirements | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Adequate national standards, norms, procedures for monitoring these environmental indicators are officially in place | There is no unified set of standards, norms and procedures to collect data, conduct observations and make sampling | Adequate official standards, norms and procedures are in place and use by the relevant institutions | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | An in-service training programme for public servants include course(s) covering environmental information management and monitoring system | There is no training programme for public administrators on environmental information management and monitoring system | The catalogue of in-service training programme include course(s) on environmental information management and monitoring system | Not applicable for the reporting period | Not applicable for the reporting period |  |
|  | Number of public servants trained by taking the course(s) on EMIS and CMS | 0 | 100 Public Servants are trained using the new training programme | Not applicable for the reporting period | Not applicable for the reporting period |  |

Annex 1.

Bokai, painting the walls of the partition that can approximately cater for five members of the staff.

# Text boxes

Country – Kiribati

Project Title – Integrating global environmental priorities into national policies and programs

Implementing Partner – Environment & Conservation Division (ECD), Ministry of Environment, Lands and Agricultural Development (MELAD)

GEF Implementing Agency – United Nations Development Programme (UNDP)

Period Covered – Jan-Mar 2016

QUARTERLY PROGRESS REPORT

1st Quarter 2016