ENABLING ACTIVITIES FOR THE PREPARATION OF ST. KITTS AND NEVIS’ SECOND NATIONAL COMMUNICATION TO THE UNFCCC

OPERATIONAL WORKPLAN 2009

# Project Summary

PIMS 3452

Award ID: 00040164

Project ID: 00045305

Project development objective

To strengthen technical and institutional capacity to assist St. Kitts and Nevis to mainstream climate change concerns into sectoral and national development priorities

Project immediate objective

To prepare and submit St. Kitts and Nevis’ second national communication (SNC) to the UNFCCC and meet its Convention obligations

# Project Strategy

Note that the work plan details activities for the duration for the entire project. However it is specifically concerned with activities occurring in year 1. Hence, the activities which take place beyond this timeframe show an indication of which quarter they commence in, or in cases where none of the activities under that outcome begin in year 1 the duration of the activity is given. They do not have any budget specifications and this column is shaded. Those activities are also excluded from the Gantt chart.

## Output 1: National circumstances

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| The most recent climate, socioeconomic, environmental and other relevant data are compiled. Data from the initial national communication (INC) are updated, expanded, and gaps filled. | Data on climate, environment, the economy, socioeconomics, and all other relevant information are collected and compiled by the end of Y2. Chapter completed by the end of Y2. | Data is comparable to that used in the INC. More recent data has been collected since the INC. The different datasets are based on similar timeframes. |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 1.1 Validate the gaps of information identified under stocktaking | Department of Physical Planning and Environment (DPPE) |  |  |  |  |  | 0 |  |
| 1.2 Identify the respective sources of information | DPPE | List of sources. |  |  |  |  | 0 |  |
| 1.3 Collection of data and information from all relevant sources | Consultant | Datasets. |  |  |  | Q5 |  |  |
| 1.4 Update information, fill in data gaps and add new information | Consultant | Updated data. |  |  |  | Q5 |  |  |
| 1.5 Draft the National Circumstances section of the SNC | DPPE | Drafted section. |  |  |  | Q7 |  |  |
| 1.6 Circulate the section for comment | Technical Advisory Committee (TAC) | Received comments. |  |  |  | Q7 |  |  |
| 1.7 Finalise the section | DPPE | Completed section. |  |  |  | Q8 |  |  |

## Output 2: Greenhouse gas inventory

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| Greenhouse gas inventories (GHGIs) for 2000 and selected years are completed. Institutional capacity for conducting greenhouse gas inventories (GHGIs) is enhanced. | GHGI Report completed by the first quarter of Y3. | Stakeholders are willing to collaborate and share information. Adequate skilled agency staff and/or private professionals are available. Where data is unavailable default values and other variables will be used and are comparable with collected data. |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 2.1 Review existing information on the previous GHGI and be familiarised with IPCC guidelines | DPPE |  |  |  |  |  | 0 |  |
| 2.2 Identify and mobilise national and international experts in targeted sectors and related areas of relevance for GHGI team | DPPE | Membership list of GHGI Team. |  |  |  |  | 3,000 |  |
| 2.3 Analyse the acceptability of the available methodologies estimates and decide on the methods and tools to be used for the inventory | GHGI Team, DPPE | Selected methods. |  |  |  |  | 1,500 |  |
| 2.4 Determine the source categories for which surveys for filling data gaps will be conducted | GHGI Team, DPPE | Categories. Designed surveys. |  |  |  |  | 500 |  |
| 2.5 Training workshops for national personnel in GHGI methods. | GHGI Team | Training reports. Practical assessments. |  |  |  |  | 3,500 |  |
| 2.6 Review available activity data already archived and identify new activity data needed for estimates of GHG emissions for 1994-2000 | GHGI Team | Archived records. |  |  |  |  | 1,500 |  |
| 2.7 Identify possible sources of data | GHGI Team | List of emission sources and sinks. |  |  |  |  | 500 |  |
| 2.8 Collect the necessary activity data from the available sources, and identify gaps | GHGI Team | Datasets. Details of data gaps. |  |  |  |  | 5,000 |  |
| 2.9 Re-estimate the GHG emissions inventory for 1994 | GHGI Team | Inventory results. |  |  |  |  | 1,500 |  |
| 2.10 Estimate the GHG emissions inventory for 2000 and select years | GHGI Team | Inventory results. |  |  |  |  | 2,000 |  |
| 2.11 Prepare a draft inventory for 2000 and select years, including key source analysis and uncertainty analysis | GHGI Team | Draft GHGI report. |  |  |  | Q5 |  |  |
| 2.12 Conduct a technical peer review | TAC | Received comments. |  |  |  | Q6 |  |  |
| 2.13 Organise a national workshop to present the findings of the GHGI | DPPE | Workshop report. |  |  |  | Q8 |  |  |
| 2.14 Incorporate comments from the review process and finalise the GHGI report | DPPE | Completed GHGI report. |  |  |  | Q9 |  |  |
| 2.15 Archive activity data, emission factors and estimates | DPPE | Archived records. |  |  |  | Q6 |  |  |

## Outcome 3: Programmes containing measures to facilitate adaptation to climate change

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| Capacity is built to conduct vulnerability and adaptation (V&A) assessments. V&A assessments are carried out across key sectors to provide information on the extent of vulnerability to climate change. Appropriate adaptation options are identified and prioritised. National capacity is strengthened to respond with adaptation measures. | Public awareness programmes initiated by the end of Y1. Adaptation action plan drafted by the first quarter of Y2. V&A chapter finalised by mid-Y3. | Adequate skilled agency staff and/or private professionals are available. Stakeholders are willing to collaborate and share information. |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 3.1 Identify and mobilise national and international experts in targeted sectors and related areas of relevance for V&A team | DPPE | Membership list of V&A Team. |  |  |  |  | 3,000 |  |
| 3.2 Undertake training activities for national personnel in conducting V&A assessments (ongoing) | V&A Team | Training reports. Practical assessments. |  |  |  |  | 5,000 |  |
| 3.3 Determine the scope, approaches, tools and methods to be used in the V&A assessment | DPPE, V&A Team | Identified tools, methods, etc. |  |  |  |  | 1,000 |  |
| 3.4 Identify and collect the data and information needed | V&A Team | Datasets. |  |  |  |  | 5,000 |  |
| 3.5 Develop environmental and socioeconomic baselines | V&A Team | Baseline data. |  |  |  |  | 2,500 |  |
| 3.6 Refine and utilise scenario modelling to determine the magnitude of vulnerability | DPPE, V&A Team | V&A scenarios. |  |  |  |  | 6,000 |  |
| 3.7 Identify and assess vulnerability and risk of priority areas/sectors to the impacts of climate change | V&A Team | Priorities in summary document. |  |  |  |  | 4,500 |  |
| 3.8 Identify previous and ongoing adaptation responses | DPPE, V&A Team | Summary document. |  |  |  |  | 1,500 |  |
| 3.9 Identify, analyse and prioritise potential adaptation response measures (policy, technology, tools, etc), and create a corresponding action plan | DPPE, V&A Team | Summary document. Action plan. |  |  |  | Q5 |  |  |
| 3.10 Develop the draft V&A chapter | DPPE | Draft V&A report. |  |  |  | Q7 |  |  |
| 3.11 Circulate the draft for internal and stakeholder technical review | TAC | Received comments. |  |  |  | Q8 |  |  |
| 3.12 Organise a national workshop to present the findings of the V&A | DPPE | Workshop report. |  |  |  | Q9 |  |  |
| 3.13 Finalisation of V&A chapter | DPPE | Completed V&A section. |  |  |  | Q10 |  |  |
| 3.14 Develop and execute a training programme to implement adaptation measures, based on the reviewed and approved action plan | DPPE, V&A Team | Training modules. Workshop reports. |  |  |  | Q9 |  |  |
| 3.15 Design and initiate a series of related public awareness programme to publicise vulnerability and adaptation measures | DPPE | Educational material. Media reports. |  |  |  |  | 2,000 |  |
| 3.16 Archive and document all V&A related studies and estimates | DPPE | Archived records. |  |  |  | Q7 |  |  |

## Outcome 4: Programmes containing measures to mitigate climate change

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| National capacity is developed in mitigation analysis. An emissions abatement analysis is conducted to identify prospective mitigation options with benefits relating to sustainable development and energy security. Mitigation initiatives already underway are documented. | Training in mitigation analysis completed by mid-Y2. Mitigation and abatement analysis reports completed by mid-Y3. | Adequate skilled agency staff and/or private professionals are available. Stakeholders are willing to collaborate and share information. |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 4.1 Identify and mobilise national and international experts in targeted sectors and related areas of relevance for Mitigation team | DPPE | Membership list of Mitigation Team. |  |  |  |  | 2,000 |  |
| 4.2 Undertake training activities for national personnel in conducting mitigation assessments (ongoing) | Mitigation Team | Training reports. Practical assessments. |  |  |  |  | 5,000 |  |
| 4.3 Identify methodological tools and approaches to develop mitigation scenarios | Mitigation Team | Identified tools, methods, etc. |  |  |  |  | 1,000 |  |
| 4.4 Collect all relevant macroeconomic and other data and define assumptions | Mitigation Team | Datasets |  |  |  |  | 2,500 |  |
| 4.5 Develop baseline scenarios for priority sectors considering GHGI estimates for baseline year 2000 | Mitigation Team | Baseline scenarios. |  |  |  | Q5 |  |  |
| 4.6 Develop/update GHG abatement scenario for the energy and transport sectors for the period 2000-2025 | Mitigation Team | New abatement scenario. |  |  |  | Q6 |  |  |
| 4.7 Estimate GHG reduction potential and other economic costs for scenarios for the energy and transport sectors against the baseline scenario | Mitigation Team | Scenario results. |  |  |  | Q6 |  |  |
| 4.8 Identify GHG abatement measures previously done and currently underway | DPPE | Summary document. |  |  |  |  | 1,500 |  |
| 4.9 Review the status of the relevant policy and legal frameworks for climate change to identify potential mitigation options | DPPE | Summary document with mitigation options. |  |  |  |  | 1,500 |  |
| 4.10 Identify potential GHG abatement measures and/or technology options | Mitigation Team | Mitigation options. |  |  |  | Q7 |  |  |
| 4.11 Undertake environmental, socioeconomic, technological and financial analysis of mitigation measures and/or technology options and prioritise | Mitigation Team | Analysis report. |  |  |  | Q8 |  |  |
| 4.12 Identify barriers and policy needs for implementation of mitigation measures | DPPE | Summary document. |  |  |  | Q8 |  |  |
| 4.13 Formulate screening criteria; screen options and finalise list of mitigation measures and technologies | DPPE | Screening criteria. Top 3/4 priority mitigation measures. |  |  |  | Q8 |  |  |
| 4.14 Develop the draft GHG abatement analysis chapter | DPPE | Draft abatement analysis. |  |  |  | Q9 |  |  |
| 4.15 Circulate the draft for stakeholder review | TAC | Received comments. |  |  |  | Q9 |  |  |
| 4.16 Organise a national workshop to present the findings of the GHG abatement analysis | DPPE | Workshop report. |  |  |  | Q9 |  |  |
| 4.17 Finalise the mitigation and abatement analysis chapter | DPPE | Completed section. |  |  |  | Q10 |  |  |
| 4.18 Develop and execute a training programme for implementing approved mitigation measures | DPPE, Mitigation Team | Training modules. Workshop reports. |  |  |  | Q8 |  |  |
| 4.19 Design and initiate a public awareness programme to publicise GHG mitigation options | DPPE | Educational material. Media reports. |  |  |  | Q5 |  |  |
| 4.20 Archive and document all GHG mitigation analysis related studies and estimates | DPPE | Archived records. |  |  |  | Q7 |  |  |

## Outcome 5: Other information considered relevant to the achievement of the objective of the Convention

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| Information is provided relevant to other activities outside the SNC which help St. Kitts and Nevis to meet its UNFCCC commitments. | Chapter is completed by the first quarter of Y3. |  |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 5.1 Collect, synthesise and provide information relevant to education, capacity building and public awareness activities | DPPE | Summary document. |  |  |  |  | 0 |  |
| 5.2 Collect, synthesise and provide information on steps taken to integrate climate change into socioeconomic policies and national development plans | DPPE | Summary document. |  |  |  |  | 0 |  |
| 5.3 Collect, synthesise and provide information transfer of and access to environmentally sound technologies | DPPE | Summary document. |  |  |  | Q6 |  |  |
| 5.4 Collect, synthesise and provide information on climate change research and systematic observations | DPPE | Summary document. |  |  |  | Q6 |  |  |
| 5.5 Collect, synthesise and provide information on other relevant ongoing initiatives | DPPE | Summary document. |  |  |  | Q6 |  |  |
| 5.6 Summarise all information collected in a draft chapter, and distribute for review | TAC | Draft chapter. Received comments. |  |  |  | Q7 |  |  |
| 5.7 Finalise the chapter | DPPE | Completed chapter |  |  |  | Q8 |  |  |
| 5.8 Design and initiate a public awareness programme to publicise | DPPE | Educational material. Media reports. |  |  |  | Q5 |  |  |

## Outcome 6: Constraints and gaps, and related financial, technical and capacity needs

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| Information is provided on the barriers, issues and gaps relating to the financial, technical and capacity needs of Barbados as pertain to the SNC, and implementation of the UNFCCC. | Chapter is completed by the third quarter of Y3. |  |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 6.1 Review the status of constraints and gaps (technological, institutional, financial, capacity, methodological) from previous studies | DPPE | Summary document. |  |  |  |  | 0 |  |
| 6.2 Identify new constraints and gaps for each thematic area (inventory, V&A, abatement) and indicate required needs | DPPE | Summary document. |  |  |  | Q5 |  |  |
| 6.3 Summarise constraints, gaps and needs identified and draft a synthesis report | DPPE | Draft chapter. |  |  |  | Q8 |  |  |
| 6.4 Distribute draft chapter for comments | TAC | Received comments. |  |  |  | Q8 |  |  |
| 6.5 Review comments and finalise the chapter | DPPE | Completed chapter. |  |  |  | Q9 |  |  |

## Outcome 7: Preparation and submission of SNC

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| All chapters of the SNC are finalised and compiled, and approved by Government. | SNC finalised and submitted by the end of Y3. | All chapters are finished on schedule. |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | TIME | BUDGET US$ | LINKAGES |
| 7.1 Compile draft SNC report | DPPE | Draft report. | Q9 |  |  |
| 7.2 Circulate draft for comments and review | DPPE | Received comments. | Q9 |  |  |
| 7.3 Obtain political approval | DPPE | Cabinet decision. | Q10 |  |  |
| 7.4 Finalisation, publication and submission of the SNC | DPPE | Finalised SNC. UNFCCC receipt correspondence. | Q11 |  |  |

## Outcome 8: Implementation procedures and project management arrangements

| Key performance indicators | Target | Risks/Assumptions |
| --- | --- | --- |
| Project Management Unit (PMU) is established and effective. Project implementation guided by monitoring and evaluation (M&E) programme. | PMU operational within 1 month of project start up. M&E benchmarks and targets realised. |  |
| ACTIVITIES | RESPONSIBLE PARTY | SOURCE OF VERIFICATION | Q1 | Q2 | Q3 | Q4 | BUDGET US$ | LINKAGES |
| 8.1 Recruitment of PMU staff and establishment of the PMU office | DPPE | Staff recruited. PMU operational guidelines. |  |  |  |  | 41,000 |  |
| 8.2 Establish technical teams | DPPE | Membership lists of technical teams. ToRs for teams. |  |  |  |  | 0 |  |
| 8.3 Update the composition of the Technical Advisory Committee (TAC) | DPPE | Membership list of TAC. |  |  |  |  | 0 |  |
| 8.4 Inception meeting | Project Steering Committee (PSC), DPPE | Inception report with annual work plan (AWP). |  |  |  |  | 0 |  |
| 8.5 Biannual meetings of the PSC | PSC | Meeting reports. |  |  |  |  | 750 |  |
| 8.6 Development of impact assessment framework (IAF) | PMU | IAF. |  |  |  |  | 2,000 |  |
| 8.7 Upgrade and maintain the electronic network and other communications among experts and institutions | TAC | Successful tests. |  |  |  |  | 2,000 |  |
| 8.8 Quarterly and mid-term reviews | PMU, UNDP | Quarterly reports. Mid-term evaluation. |  |  |  |  | 1,000 |  |
| 8.9 Annual review meetings | PMU | Annual progress report (APR). Annual M&E evaluations and audit. Revised AWP based on M&E findings. |  |  |  |  | 3,250 |  |
| 8.10 Final project evaluation and audit | Consultants | Evaluation reports. |  |  |  | Q12 |  |  |

# Gantt Chart and Budget

| Activity | Q1 (Jan – Mar) | Q2 (Apr – Jun) | Q3 (Jul – Sep) | Q4 (Oct – Dec) | Budget US$ |
| --- | --- | --- | --- | --- | --- |
| 1.1 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 1.2 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 2.1 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 2.2 |  |  |  |  |  |  |  |  |  |  |  |  | 3,000 |
| 2.3 |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |
| 2.4 |  |  |  |  |  |  |  |  |  |  |  |  | 500 |
| 2.5 |  |  |  |  |  |  |  |  |  |  |  |  | 3,500 |
| 2.6 |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |
| 2.7 |  |  |  |  |  |  |  |  |  |  |  |  | 500 |
| 2.8 |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 |
| 2.9 |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |
| 2.10 |  |  |  |  |  |  |  |  |  |  |  |  | 2,000 |
| 3.1 |  |  |  |  |  |  |  |  |  |  |  |  | 3,000 |
| 3.2 |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 |
| 3.3 |  |  |  |  |  |  |  |  |  |  |  |  | 1,000 |
| 3.4 |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 |
| 3.5 |  |  |  |  |  |  |  |  |  |  |  |  | 2,500 |
| 3.6 |  |  |  |  |  |  |  |  |  |  |  |  | 6,000 |
| 3.7 |  |  |  |  |  |  |  |  |  |  |  |  | 4,500 |
| 3.8 |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |
| 3.15 |  |  |  |  |  |  |  |  |  |  |  |  | 2,000 |
| 4.1 |  |  |  |  |  |  |  |  |  |  |  |  | 2,000 |
| 4.2 |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 |
| 4.3 |  |  |  |  |  |  |  |  |  |  |  |  | 1,000 |
| 4.4 |  |  |  |  |  |  |  |  |  |  |  |  | 2,500 |
| 4.8 |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |
| 4.9 |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |
| 5.1 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 5.2 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 6.1 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 8.1 |  |  |  |  |  |  |  |  |  |  |  |  | 41,000 |
| 8.2 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 8.3 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 8.4 |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
| 8.5 |  |  |  |  |  |  |  |  |  |  |  |  | 750 |
| 8.6 |  |  |  |  |  |  |  |  |  |  |  |  | 2,000 |
| 8.7 |  |  |  |  |  |  |  |  |  |  |  |  | 2,000 |
| 8.8 |  |  |  |  |  |  |  |  |  |  |  |  | 1,000 |
| 8.9 |  |  |  |  |  |  |  |  |  |  |  |  | 3,250 |
|  | TOTAL FOR YEAR 1 | 113,000 |

Unallocated funds:

Output 2 = $5,000

Output 3 = $3,500

Over budgeted:

Output 4 = $11,500