**Work Plan for the 2nd National Communications for St. Kitts and Nevis for 2009**

|  |  |
| --- | --- |
| **Programme Area** | **Schedule of activities** |
|  | J | F | M | A | M | J | J | A | S | O | N | D |
| **Greenhouse Gas Inventory** |   |   |   |   |  |  |  |  |  |  |  |  |
| Training Workshop on IPCC Software Methodologies and Establishment of Local GHG inventory team |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of existing data and identification of data needs |  |  |  |  |  |  |  |  |  |  |  |  |
| Collection of data |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of Data, and undertake uncertainty assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation of Draft Inventory and Technical Review |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Workshop to present greenhouse gas inventory  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Vulnerability and Adaptation** |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Workshop, Training of assistants |  |  |  |  |  |  |  |  |  |  |  |  |
| Collection of Baseline Data |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis of Baseline Data and Quality Control |  |  |  |  |  |  |  |  |  |  |  |  |
| Assessment of Specific Vulnerabilities of Pilot Areas |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of Adaptation Options |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation of Draft Report |  |  |  |  |  |  |  |  |  |  |  |  |
| Dissemination of Report /Validation Workshop |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalization of Report |  |  |  |  |  |  |  |  |  |  |  |  |
| **Mitigation and Abatement Analysis** |  |  |  |  |  |  |  |  |  |  |  |  |
| GHG Mitigation and Abatement workshop. Training of personnel, identification of national experts, scope and methodology  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collection of data for GHG baseline scenarios for various sectors, 2000-2025 |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of GHG mitigation technologies, barriers analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalization of GHG Mitigation and Abatement Chapter |  |  |  |  |  |  |  |  |  |  |  |  |
| **Technology Transfer, Systematic Observations and Research Requirements** |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and update of technology needs assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of systematic observations needs |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalize chapter on Technology Transfer, Systematic Observation and Research requirements |  |  |  |  |  |  |  |  |  |  |  |  |
| **Public Education and Awareness, Constraints, Gaps, Financial, Technical and Capacity Needs** |  |  |  |  |  |  |  |  |  |  |  |  |
| Review constraints and gaps from previous studies |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of needs to improve public education and awareness |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of new constraints and gaps (technical, institutional, methodological, financial and capacity) |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification of capacity needs and financial and technical requirements |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalize chapter on Public Education and Awareness, Constraints, Gaps, Financial, Technical and Capacity Needs |  |  |  |  |  |  |  |  |  |  |  |  |
| **National Circumstances and Finalization of National Communications** |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft National Circumstances section |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalize National Circumstances |  |  |  |  |  |  |  |  |  |  |  |  |
| Compilation of Draft National Communications |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Project Workshop |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalization of National Communications |  |  |  |  |  |  |  |  |  |  |  |  |