Project Title: 	Support to Transitional Justice in Kosovo

UN Organizations

Name of Representative Ms. Therese Arnesen Signature Name of Organization OHCHR Date& Seal

Name of Representative Mr. Andrew Russell Signature Name of Organization UNDP Date & Seal Name of Representative Ms. Flora Macula Signature Name of Organization UN Women Date & Seal Name of Representative Tajma KURT Signature Name of Organization IOM Date & Seal

Support to Transitional Justice in Kosovo

Joint Project Document

Joint Project Outcome:	The measurable enhancement of the capacities of critical institutional and civil society actors to engage in and steer an inclusive, participatory, victim-centred and gender-sensitive transitional justice process in Kosovo. This, in turn, will contribute to the creation of a more conducive environment for a successful transitional justice process in Kosovo. In this manner, the Joint Project will contribute to vindicating the dignity of victims, improving community relations, strengthening civic trust, and, in the long term, to reconciliation and the prevention of future violence.

| CDP Outcomes: | CDP Outcome 2.1: “Institutions responsible for delivering public services and social justice are accountable and responsive to rights holders”. CDP Outcome 2.2: “Key civil society actors increasingly influence the accountability of governance for public services and social justice”. |
| --- | --- |

| Expected UNDP KPAP Outcome: Expected Accomplishment of OHCHR | KPAP Outcome 2: “By 2015, rule of law institutions are more efficient, transparent, gender responsive and accountable”. Expected Accomplishment 3.2 of the OHCHR “Steps taken to establish transitional justice mechanism relating to serious human rights violations during the conflicts in the former Yugoslavia” |
| --- | --- |

| Project Outputs: | Capacity of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation to fulfil its mandate is strengthened; Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened; and Public and stakeholder awareness of and participation in transitional justice are increased. |
| --- | --- |

Implementing Agencies:	United Nations Development Programme (UNDP), Office of the High Commissioner for Human Rights (OHCHR), International Organization for Migration (IOM), UN Women

Partners: 	Members of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation, Secretariat of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation, Office of the Prime Minister, Civil Society

Table of Contents

I.	Situation Analysis	4

Beneficiaries and Partners	6

Current Initiatives	6

II.	Strategy	6

Key Principles	8

Ownership by Kosovo stakeholders	8

Joint project outcomes and relation to key strategic documents	8

Project Set-Up and Implementation Arrangements	9

Further Considerations	11

Outline of outputs and indicative activities	11

Output 1 – Capacity of the IMWG on dealing with the past and reconciliation to fulfil its mandate is strengthened.	11

Output 2 – Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened.	12

Output 3 – Public and stakeholder awareness of and participation in transitional justice is increased.	13

III.	Results and Resources Framework	15

IV.	Annual Work Plan	22

V.	Fund Management Arrangements	31

VI.	Management Arrangements	31

VII.	Monitoring Framework And Evaluation	33

VIII.	Legal Context	38

IX.	Annexes	39

# Situation Analysis

Kosovo is currently at an important juncture regarding transitional justice. In June 2012 an Inter-Ministerial Working Group (IMWG) on Dealing with the Past and Reconciliation was created in Kosovo, with the main purpose of drafting a “transitional justice strategy”. Although transitional justice formed part of the Ahtisaari Plan, this is the first time since the 1999 conflict that an attempt to initiate a comprehensive process in Kosovo on this issue has occurred. With the closing of the International Civilian Office (ICO), formerly responsible for supporting implementation of the Ahtisaari Plan, UNDP/OHCHR/IOM/UN Women propose to support this process through the Joint Project ‘Support to Transitional Justice in Kosovo’.

Kosovo’s complex and disputed past is reflected in its present, a place deeply divided on questions of legitimacy and identity, notably reflected in the current dialogue between Pristina and Belgrade. As Kosovo hopes to build a better future, one of its biggest challenges remains dealing with its past. Similarly to the rest of the region, Kosovo is marked by a largely unaddressed legacy of violations of human rights and international humanitarian law. While much of the physical destruction from the conflict has been repaired and rebuilt, outstanding grievances on the part of a population, still affected by the conflict, have not yet been dealt with.

The conflict in Kosovo in the late 1990s led to tens of thousands of casualties and hundreds of thousands of civilians being displaced from their homes. The immediate post-conflict period was marked by lawlessness, continued killings, destruction and unlawful occupation of property, and displacement of civilians. To this day, victims’ rights have not been addressed in a satisfactory manner, excluding, among others, any comprehensive reparations programme. Many issues remain unaddressed – for example, according to the ICRC, 1,775 persons out of the 6,024 persons reported missing to the ICRC from the period of 1998 to 2000 remain unaccounted for. Furthermore, property related issues resulting from the conflict remain a major obstacle to dealing with the past.

In addition, while it is known that sexual and gender-based violence (SGBV) occurred during the conflict, the number of female and male victims is unknown and a culture of shame and silence surrounds the issue. Limited progress has been achieved in this regard. On 29 January 2014, the Institutions approved the Action Plan for Implementation of UNSCR 1325, which includes as one of its three outcomes the provision of redress to survivors of conflict related SGBV. On 7 March 2014, President Jahjaga, with a special Presidential Decree, established the “National Council on the Survivors of Sexual Violence during the conflict in Kosovo” (the Council). The Council brings together representatives of key ministries that can support survivors, civil society and international stakeholders towards an improved, better coordinated response. Some of the Council members are also members of the IMWG. Furthermore, the Assembly approved the Law No. 04/L-172 on Amending and Supplementing the Law No.04/L-054 on the Status and the Rights of the Martyrs, Invalids, Veterans, Members of Kosovo Liberation Army, Sexual Violence Victims of the Conflict, Civilian Victims and Their Families, which legally recognizes victims of sexual violence during the armed conflict in Kosovo as civilian victims . Kosovo authorities are currently in the process of drafting the sub-legal acts necessary for the implementation of the amendment.

The lack of consensus about the past continues to hamper any prospect of reconciliation. For example, a recent study confirmed previous findings that indicate that many Kosovans from all ethnic backgrounds believe their rights to have been violated in the recent past, but that many of them categorically deny the possibility that members of their own community may have committed conflict crimes. On the question whether all perpetrators of conflict crimes are considered criminals, regardless of their ethnic belonging or that of the victims, a negative trend has taken place over the past five years, whereby in 2012 Kosovans were less likely than in 2007 to consider perpetrators of conflict crimes as criminals if they belonged to their own community, with a steady 10% drop within the K-Albanian and K-Serbian community and a 22% drop within other non-majority communities since 2007. Simplistic, group-based and mutually exclusive readings of the past are also reflected in the history lessons taught to the younger generation who have no memory of the conflict. As is the case with text books of neighbouring countries, Kosovo’s high school pupils are being taught a one-sided story, where presentation of crimes is limited to those ‘committed by the other side, presenting oneself as the victim and the other as the aggressor’.

Regarding the delivery of justice, the record for Kosovo is bleak. There is a general perception that the international community, largely in charge of conflict crimes cases since the end of the conflict systematically failed to adjudicate conflict crimes cases in Kosovo, and that this has always been ‘a priority in name only’. Only five cases pertaining to conflict crimes committed in Kosovo were handled at the International Criminal Tribunal for the Former Yugoslavia (ICTY), mostly to divisive and controversial effect within Kosovo and regionally. There is no evidence that this has contributed to reconciliation or that it has opened public space for critical debate about the past. Meanwhile, domestic courts in Kosovo, for which UNMIK and EULEX have been largely responsible, have only concluded 14 cases of conflict crimes with final verdicts, 13 years after the end of the conflict. Evidently, a culture of impunity prevails in Kosovo, adversely affecting the rule of law, civic trust, and any prospect of reconciliation.

In sum, Kosovo society remains profoundly affected by its past, as well as deeply divided along and across community lines with mutually exclusive understandings and interpretations of the past. It is thus in need of a comprehensive, inclusive, gender-sensitive, victim-centred, and consultative process of transitional justice.

For the United Nations, transitional justice includes the ‘full range of processes and mechanisms associated with a society’s attempt to come to terms with a legacy of large-scale past abuses, in order to ensure accountability, serve justice and achieve reconciliation. These may include both judicial and non-judicial mechanisms, with differing level of international involvement (or not at all) and individual prosecutions, reparations, truth seeking, institutional reform, vetting and dismissals, or a combination thereof’. Transitional Justice processes and mechanisms are a critical component of the United Nations framework for strengthening the Rule of Law, and guiding principles for these processes and mechanisms include their need to employ, amongst others, an inclusive, consultative, comprehensive, victim-centred and gender-sensitive approach.

In line with the Decision of 4 June 2012, the process of dealing with the past in Kosovo should be conducted according to the United Nations principles on transitional justice and combating impunity as well as in respect of human rights norms and standards. In accordance with this approach, transitional justice should combine the elements of truth-seeking, justice initiatives, reparations and guarantees of non-recurrence in a complementary and mutually reinforcing manner.

In the longer term, the final goal of any transitional justice process is the restoration of civic trust and reconciliation among and within communities. It is based on the understanding that public awareness and knowledge about past crimes, free debate about the past, a human-rights based approach to reparations for all victims, and an end to the culture of impunity, constitute a precondition to any meaningful reconciliation process and the consolidation of the rule of law. The United Nations has stressed the connection between transitional justice and the rule of law, which in turn is widely recognised to positively impact peace, security, and social and economic development. From a human development perspective, such a comprehensive, inclusive, gender-sensitive, and victim-centred transitional justice process has the potential to improve the lives of Kosovan victims, society at large, and future generations.

## Beneficiaries and Partners

All people and communities, including women, children, and minority communities, of Kosovo will benefit from a comprehensive and inclusive Transitional Justice process that helps Kosovo to move forward by addressing the past and building the ground for reconciliation and lasting peace.

Immediate beneficiaries and partners of the project are the members of the IMWG on Dealing with the Past and Reconciliation and a range of Civil Society Organisations (CSOs) – including those dealing with women’s issues – who will benefit from expert and technical support in the process of drafting and engaging with a Transitional Justice Strategy. In regards to Transitional Justice efforts in relation to conflict related SGBV, the IMWG will closely work with the National Council on the Survivors of Sexual Violence during the conflict in Kosovo and women’s organizations who work with survivors. The project will strive to ensure the IMWG and Council cooperate and coordinate closely to avoid duplication of efforts.

Specifically, the entire Joint Project will be led with two partners in mind – the IMWG and Civil Society. The design, implementation, and sequencing of activities will be informed by their needs, capacities, and priorities, in line with the principle of local ownership. The aim is to create a conducive environment for Kosovo’s Transitional Justice process. As such, UNDP, OHCHR, IOM and UN Women have no pre-set vision of an ideal result of this process. Rather, the Joint Project will adhere only to the stated principles, established by the United Nations, by which any Transitional Justice process should be conducted. The aim is to support and facilitate the work of the Project partners in realising the transitional justice mechanisms they see most suitable for Kosovo.

## Current Initiatives

UNDP’s Transitional Justice Perception survey completed in 2012 provides a baseline setting out the perception of a representative selection of Kosovans from all communities on transitional justice issues.

UN Women, as well as OHCHR, have supported the drafting of the Action Plan on Implementation of UNSCR 1325 throughout 2012 and 2013. Moreover, the Security and Gender Group, has advocated for and supported work done to provide redress to survivors of conflict-related SGBV. The Group, and especially its sub-group on Conflict-Related Sexual and Gender-Based Violence, have also served as a forum to ensure consultations with a wider group of relevant stakeholders on conflict related SGBV.

In relation to the work of the IMWG, UNDP’s Advancing Gender Justice Project in early 2013 hired one staff member engaged as Administrative Assistant to the IMWG (who will be funded by UNDP’s Advancing Gender Justice in that position until 31 May 2014), situated in the Office of the Prime Minister of Kosovo (OPM).The rationale was to provide interim administrative support to the OPM covering the period of setting up the IMWG and the initial phase of IMWG’s work, with the aim of bridging the time until the Joint Project on Support to Transitional Justice will provide more systematic and sustained support to the entire process of transitional justice, both logistically and substantively.

In relation to the work of the Council, UN Women and OHCHR are supporting Council members who are involved in drafting sub-legal acts for the implementation of the Law No. 04/L-172 through expertise and an opportunity to exchange experiences with stakeholders in Bosnia and Herzegovina. Furthermore, in 2012-2013, UN Women, in cooperation with the Kosovo Judicial Council, has provided capacity building trainings to local and international judges, prosecutors and investigators working on conflict crimes cases with SGBV elements.

# Strategy

UNDP and OHCHR drafted this project document in 2013 consultation with relevant stakeholders based on their extensive involvement, experience and expertise on transitional justice in more than 20 countries. In addition, this joint project document was enriched by consultations with relevant stakeholders in and outside of Kosovo. In order to support the broader efforts within Kosovo in regard to transitional justice it has to be acknowledged that the UN eschews one-size-fits-all formulas and the importation of foreign models and bases its work upon a thorough analysis of local needs and capacities. Notwithstanding Kosovo’s unique context, this Joint Project acknowledges the number of activities in the field of transitional justice, such as the continuous work of the ICTY, the ICRC facilitated working group on missing persons, and the RECOM initiative.

On 4 June 2012, a decision establishing an Inter-Ministerial Working Group (IMWG) in Kosovo on Dealing with the Past and Reconciliation with the main purpose of establishing a comprehensive, inclusive and gender-sensitive approach for dealing with the past in Kosovo, amounting to a  Transitional Justice Strategy. The IMWG consists of 16 members from the central level and eight civil society representatives, as well as members of the international community as observers (UN Women, OHCHR). The IMWG Secretariat is situated within the Office of the Prime Minister (OPM), providing administrative and logistical support to the IMWG convenes and communicates regularly, and has already met several times since its establishment. In November 2013, the IMWG held a three-day substantive and planning work shop sponsored by UNDP. During this workshop, the IMWG prepared its work plan. The work plan, rules and procedures as well as the IMWG budget was approved by Kosovar authorities in October 2014 and immediately following, the IMWG split into four sub working groups based on the four UN pillars of transitional justice. UNDP has assisted these sub groups through the Joint Project Team and various trainings provided by the implementing UN agencies based on the IMWG requests.

The June 2012 decision mandates the IMWG to ‘deal with gross human rights violations and serious violations of international humanitarian law in the past in Kosovo including the last conflict and the transition period, taking into consideration the views of all communities in Kosovo in order to promote reconciliation and lasting peace’. As such, the IMWG may design and implement a broad range of transitional justice initiatives, strategies, policies and measures. It is also expected to disseminate information about its work and to conduct broad consultations with representatives of the affected population.

The decision establishing the IMWG also foresees international support to the process of developing a transitional justice strategy and the implementation of this strategy, whereby international organizations and embassies may contribute the necessary resources, providing professional expertise, and providing administrative assistance within the IMWG Secretariat in support of the IMWG’s mandate’.

A broad-based, Kosovo-wide consultation process is vital to the IMWG’s work, and a central part of the support offered to the IMWG by the Joint Project. As stated, a comprehensive process of consultations with affected communities is key to ensuring transitional justice efforts are human-rights based and focus on the rights and needs of victims and their families in particular. In the Kosovo context, it will be particularly important to ensure the consultation process makes a pro-active effort to include all categories of victims, and consults with victims broadly, beyond the organisations and associations that claim to represent them. Such consultations may use qualitative or quantitative methods. Quantifiable information may be collected, analysed and interpreted, e.g. through a public opinion survey to inform the work of the IWMG. This method can grasp large-scale representative data, however, its drawback is that it ‘tends to propose a limited range of options and may preclude respondents from suggesting novel or otherwise unanticipated transitional just arrangements’. The IMWG will thus also benefit from support in conducting large-scale qualitative consultations throughout Kosovo. The aim of this method is to view the issues through the eyes of the respondents and participants, taking the form of workshops, seminars, community meetings and focus groups, while ensuring the participation of all relevant interest groups.

Importantly, broad-based Kosovo-wide consultations should be viewed not as outreach activities or public relations exercises, but rather as a two-way information stream. ‘Consultations are a form of vigorous and respectful dialogue whereby the consulted parties are given the space to express themselves freely, in a secure environment, with a view to shaping or enhancing the design of Transitional Justice programmes’. They are thus the basis upon which the IMWG will develop the most suitable transitional justice strategy for Kosovo.

The overall objective of the UNDP/OHCHR/IOM/UN Women Joint Project is to support the process of drafting a transitional justice strategy for Kosovo, employing both top-down and bottom-up approaches. In accordance with the decision outlining the IMWG’s mandate, the Joint Project will provide logistical and substantive support to the IMWG Secretariat, including to the process of consultations, which will form an essential part of the IMWG’s work and will define its legitimacy and local ownership.. Secondly, in parallel to this institutional element, the Joint Project will also focus at the grassroots level by strengthening the capacity of CSOs to contribute in their important role of engaging with the authorities in drafting and implementing transitional justice mechanisms and processes. In addition to work within the IMWG Secretariat and Civil Society, the Joint Project aims to create a conducive environment for the IMWG’s work by raising public and stakeholder awareness of and participation in the process of dealing with the past. The Joint Project thus foresees several types of support:

- Technical, logistical, and substantive support to the IMWG in fulfilling its mandate;

- Capacity-building of civil society to engage in the process of transitional justice; and

- Awareness-raising on transitional justice principles and mechanisms among the population and key stakeholders in Kosovo.

## Key Principles

While implementing the Joint Project, due consideration will be paid to the guiding principles included in the 2010 Guidance Note of the Secretary-General on transitional justice. In addition, implementation will be directed by further principles, including:

- The value of local ownership in all stages of the Joint Project; and

- The importance of inclusiveness, comprehensiveness, broad consultations, transparency and gender-sensitivity throughout the Joint Project.

The Joint Project will be implemented based on the needs and priorities of the aforementioned beneficiaries and partners. Therefore, it is paramount to adopt an inclusive and consultative process throughout the duration of the project to ensure that it generates meaningful results. Consequently, UNDP/OHCHR/IOM/UN Women will incorporate the knowledge and expertise of various stakeholders in Kosovo and will do their utmost to ensure coordination and avoid overlap or competition with any of the other actors in the field of transitional justice in Kosovo. The implementation and management arrangements described in detail below include a range of tools and provisions to ensure compliance with these principles.

## Ownership by Kosovo stakeholders

Undertaking a comprehensive transitional justice process is a challenging endeavour. It is a delicate endeavour in which all actors, be they officials, members of civil society, international supporters, or facilitators of the process need to be sensitive to the concerns of all members of society, especially vulnerable, women, or marginalised victims. For such a difficult process to successfully gain broad legitimacy among the population, it is paramount that it is thoroughly locally owned, and perceived as such. There is also growing evidence that transitional justice measures that evolve over time and involve strong local ownership result in greater political stability in post-conflict settings.

An appreciation of this central necessity governs how the Joint Project is and will be designed and implemented; special consideration will be given to the principle of local ownership in outreach activities conducted as part of the Joint Project.

## Joint project outcomes and relation to key strategic documents

The Joint Project is expected to contribute to the measurable enhancement of the capacities of critical institutional and civil society actors to engage in and steer an inclusive, participatory, victim-centred and gender-sensitive transitional justice process in Kosovo. This, in turn, will contribute to the creation of a more conducive environment for a successful transitional justice process in Kosovo. In this manner, the Joint Project will contribute to vindicating the dignity of victims, improving community relations, strengthening civic trust, and, in the long term, to reconciliation and the prevention of future violence.

The Joint Project is linked to key strategic documents through contributions towards:

- The UN Kosovo Team’s Common Development Plan (CDP) Strategic Theme 2 ‘Accountability for delivering social inclusion’, more specifically UN Outcome 2.1. ‘Institutions responsible for delivering public services and social justice are accountable and responsive to rights holders’ and UN Outcome 2.2. ‘Key civil society actors increasingly influence the accountability of governance for public services and social justice’;

- Outcome 2 of the UNDP Kosovo Programme Action Plan (KPAP): “By 2015, central and local Institutionss more effectively plan, implement and administrate policies which are participatory, gender-responsive and human rights centred”; and

- Expected Accomplishment 3.2 of the OHCHR Stand-alone Office in Kosovo: “Steps taken to establish transitional justice mechanism relating to serious human rights violations during the conflicts in the former Yugoslavia”

Specifically, the Joint Project is expected to achieve the following specific results, which contribute to the above listed outcomes and accomplishments:

- Sufficient substantive knowledge and technical capacities among key institutional and civil society stakeholders to engage in a transitional justice process;

- Improved awareness and understanding among the general population of transitional justice mechanisms and processes; and

- A conducive environment for the realisation of a transparent and inclusive transitional justice process spanning several years, including broad consultations leading to a victim-centred and gender-sensitive transitional justice strategy for Kosovo.

## Project Set-Up and Implementation Arrangements

Joint Project organogram:

The Joint Project will support the process of transitional justice in Kosovo, and in particular the development of a transitional justice strategy by the IMWG.

The Senior Adviser on Transitional Justice (SATJ), with high-level expertise in the area of transitional justice, along with the Project Manager, who is in charge of overseeing and coordinating the implementation of all project activities, will work closely with the IMWG.  The SATJ will be an international owing to need for outside expertise. An international expert from UN Women will also support the work of the TJRC on specific gender related topics for a certain period of time. The Joint Project will also include the possibility to contract short-term consultants, most likely international, in order to provide in-depth expertise in certain critical areas. The remainder of the project staff will be local. All staff are required to have human rights knowledge and know how to effectively implement gender mainstreaming in the areas covered by the Joint Project. The project team reports to the Project Board, which includes representatives of the implementing UN Agencies, the UN Kosovo Team, the donors, as well as stakeholders and beneficiaries of the Joint Project. The Project Board is to meet twice a year so that the Joint Project can be adjusted if necessary and to monitor and offer guidance on the Joint Project’s implementation.

As outlined in the decision establishing the IMWG, the Office of the Prime Minister established a Secretariat to provide administrative and logistical support to the IMWG. The Joint Project will support the Secretariat with one staff member. With the help of this staff member, the Secretariat will serve the IMWG and facilitate its work wherever needed, e.g. related to outreach, consultations, and drafting.

The IMWG, mandated by and reporting to the Kosovo authorities, is supported by the Secretariat and the expertise available within the project team, including an expert provided by UN Women, plus short term consultants if required. In addition, the IMWG will benefit from activities that strengthen the capacity of its members and raise awareness of the transitional justice process more widely, beyond its own membership. This will contribute in a significant way to the work of the IMWG and to creating a conducive environment for the drafting of a transitional justice strategy for Kosovo. Outreach activities, support to Kosovo-wide consultations, and targeted capacity-building, among other activities, will all contribute to this goal. However, the Secretariat and the IMWG remain independent of the Joint Project. They report directly to the OPM and define their priorities in line with decisions taken within the IMWG, informed by the outcome of broad-based consultations.

As seen in the organigram above, the Joint Project is committed to a stakeholder-owned process, offering direct support to it through the Secretariat and the project team.  This stakeholder owned process creates a conducive environment for the work of the IMWG and may inform its work. Planning and implementation of project activities will therefore be timed with the progress, needs, and priorities of the IMWG in mind, to act as a catalyst and enabler where possible. Key staff that will enable this flow of information and sensitive timing of activities are the Project Manager and the SATJ, who will ensure close contact and consultation with partners from the central level and civil society.

## Further Considerations

Key considerations to keep in mind while implementing the project include:

- The political sensitivity of any project on transitional justice; and

- The vulnerability of the project outputs to political developments beyond the Joint Project’s control.

It must be noted that due to its politically sensitive context, any project in this field is a long-term endeavour and its immediate impact and results may be hard to measure in the initial phase. In this sense, the process of awareness-raising, holding inclusive and participatory consultations and public debates about the past is significant in itself. The politically sensitive nature of transitional justice also requires greater flexibility in the planning and timing of project implementation. Thus, the timeline of activities of the Joint Project will be less predictable than in conventional projects. The activities outlined in sections below are purposefully kept at the level of indicative activities, with a view to designing them based on the ongoing developments and needs of the Joint Project’s partners and beneficiaries. The Joint Project team will need to remain flexible while adapting to political and social developments, while ensuring full transparency to the Project Board that allows for oversight of any substantial changes to the joint project document.

Finally, the Joint Project is highly sensitive to changes in the political environment, which are beyond the control of OHCHR/UNDP/IOM/UN Women. Risks arising from this fact are recorded in the Joint Project’s risk log and the Joint Project will make all efforts to operate in a conflict sensitive manner and to manage identified risks during the implementation of the project. See Annexes below for a detailed risk log.

## Outline of outputs and indicative activities

The following outputs will be realized by the activities supported and/or implemented by the IMWG Secretariat and the Joint Project team. As discussed above, identification, planning and implementation of indicative activities described in the joint project document are subject to continuous re-assessment of the needs and priorities of the Joint Project partners. Outputs 1 and 2 are the main priorities for the initial establishment of the Joint Project.  The list below should not be understood as final.

### Output 1 – Capacity of the IMWG on Dealing with the Past and Reconciliation to fulfil its mandate is strengthened.

This Output is divided into two activity results (Activity IDs in Atlas):

- Enhanced logistical capacity of IMWG to fulfil its mandate; and

- Enhanced substantive capacity of IMWG to fulfil its mandate.

Regarding the IMWG’s logistical capacity to fulfil its mandate, the Joint Project will provide the IMWG’s Secretariat, located within the OPM, with one staff member. He/She will be tasked to support all of the Secretariat’s work, including organising meetings, ensuring the flow of information within the IMWG, supporting logistically as well as administratively the consultation and drafting processes. This activity is in line with the needs of the Joint Project partners - given the limited human resources within the OPM and its already significant workload, a comprehensive transitional justice process requires further staffing. Throughout the Joint Project’s duration, logistical support will be provided to the Secretariat to ensure maximum impact of the IMWG’s work.

Substantive support will be provided to the IMWG most notably through the SATJ, situated within the Joint Project team. The SATJ will be available to guide the IMWG’s work throughout the process by providing high-level expertise and relevant training. Targeted capacity building, knowledge exchange and trainings will be conducted to increase IMWG members’ understanding of all four pillars of transitional justice. Additionally, upon request of the IMWG, the Joint Project will be able to engage external experts to develop policy papers on pertinent transitional justice issues in order to provide comprehensive and persuasive policy recommendations. This may be necessary in cases where the IMWG identifies areas in need of up-to-date knowledge, analysis, and/or awareness-raising. Potential themes may include reparations, needs assessment of victims, economic losses, public apologies, memorialisation, conflict related SGBV, to name but a few. The IMWG will benefit from this type of substantive input which, where appropriate, may be followed by respective awareness-raising activities. Additionally under this Output the Joint Project may organise, as warranted, study visits for various members of the IMWG Secretariat and members of sub-groups of the IMWG to other geographical areas that are dealing, have dealt with, or are struggling to deal with similar transitional justice processes. This type of exchange can be critical in providing input and lessons from other cases on both the substantive and procedural aspects of transitional justice. In other instances, these kinds of exchanges have been described as transformative for individuals involved in transitional justice processes to grasp the complexity and importance of their task.

The activities under this Output will ensure that the IMWG and its Secretariat have sufficient logistical and substantive capacity to successfully implement their mandate, that includes but is not limited to: draft and adopt their rules of procedure as well as their action plan for drafting a transitional justice strategy for Kosovo (TJSK); and ensuring the drafting of an all-inclusive and gender sensitive transitional justice strategy for Kosovo.  The IMWG rules of procedure, and IMWG work plan for 2015-2017 were approved by the Kosovo authorities in October 2014. Recently, the IMWG split into four sub-groups based on the UN pillars of transitional justice. The issue of conflict related SGBV will be treated as a cross-cutting issue for all four sub-groups.

### Output 2 – Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened.

This Output is divided into two Activity Results (Activity IDs in Atlas):

- Increased capacity of Civil Society Organisations for contributing to transitional justice;

- Targeted transitional justice advocacy support to specific victims groups and weaker segments of society;

The inclusiveness and legitimacy of any dealing with the past process rests upon the participation of civil society. As outlined above, the implementation of activities under this Output will be targeted at civil society, working directly on transitional justice issues, primarily the eight CSOs who are full members of the IMWG. The Joint project will also support online information sharing in this regard. The aim of this Output is to ensure that all sections of society have increased understanding and capacity to be able to meaningfully contribute to the process of transitional justice. The activities foreseen under this Output aim to reach civil society broadly, and would be primarily represented under the eight civil society members of the IMWG. Ensuring a broad selection of Kosovan civil society will significantly facilitate the broad-based consultation process towards an inclusive and comprehensive Transitional Justice Strategy for Kosovo.

Foreseen activities under Output 2, to be implemented through the Civil Society partners and with the staff and resources available in the Joint Project team, include trainings by local and international experts on issues pertaining to transitional justice. Beneficiaries will include: academia; religious institutions; media; professional associations; human rights activists; youth organisations; women’s organisations; missing persons organisations; veterans’ or victims’ associations; and other relevant groups.

Output 2 also foresees meetings of CSOs from across the Balkan-region, including youth and women CSOs that could contribute to the transitional justice process and facilitate exchange of experiences. This activity will enhance the capacity of civil society to form regional, multi-ethnic, and Kosovo-wide alliances on transitional justice issues, and strengthen the links that already exist. The activity’s aim is to engage more of Serb/Albanian civil society within as well as outside Kosovo, which have not yet been included in Kosovo’s transitional justice process and includes the establishment and maintenance of an online information sharing platform. The regional dimension of transitional justice is an important one in the case of Kosovo. The conflict forced many people from Kosovo, so by including minority communities and persons abroad who could be relevant to transitional justice, the consultation process could be strengthened. Working with civil society on regional and multi-ethnic alliance building offers a welcome entry point for the regional dimension of the Joint Project.

Additionally, the Joint Project envisages targeted transitional justice advocacy support to specific victims groups and weaker segments of society to increase their transitional justice awareness. This includes support to specific groups of victims of human rights violations and weaker segments of society   (including RAE, women, youth, etc) for their voice to be heard on their specific transitional justice needs.

### Output 3 – Public and stakeholder awareness of and participation in transitional justice is increased.

This Output is divided into three Activity Results (Activity IDs in Atlas):

- Broad consultation process supported;

- Increased public awareness of transitional justice; and

- Increased awareness of transitional justice among key stakeholders.

As stated by the UN Secretary General, ‘robust national consultations are now understood to be essential prerequisites to ensure that transitional justice mechanisms reflect the needs of conflict-affected communities, including victims’. The IMWG and its Secretariat will require extensive support in making the consultation process adhere to international standards and the requirements of inclusiveness, gender-sensitivity, and comprehensiveness outlined in the decision establishing the IMWG. Some adjustments to the frequency of consultations may be necessary according to project needs. The Joint Project will provide assistance in designing and conducting the consultations, making use of the SATJ’s substantive expertise, the support staff placed within the Secretariat, and the use of local and international experts where needed, while respecting that the process is led by the IMWG which holds decision-making power. UNDP, UN Women, IOM and OHCHR will provide expert legal and technical support, while promoting the participation of victims, women and vulnerable groups, and supporting capacity building of partners.

No transitional justice initiative can be sufficiently legitimate and successfully implemented without a measure of victims’ direct involvement. Therefore, special emphasis will be placed by the Joint Project on including victims and witnesses of past abuses, taking into account the situation of the most marginalised groups in Kosovo, such as the Roma, Ashkali and Egyptian (RAE) population. Activities under this Output, related to the consultation process, are logically linked to capacity development of victim associations and other CSOs, implemented under Output 2. The Joint Project, in its support role, is committed to ensuring a consultation process that is culturally sensitive and confidential where appropriate, and to employing a “do-no-harm” approach particularly towards most vulnerable groups. Sensitisation of the public and key stakeholders prior to the consultation process will also be necessary in order to manage expectations – which will be implemented in line with the priorities set out by the IMWG. Special emphasis will be placed on ensuring access of marginalised stakeholders and those victims, especially women, whose access to consultations may be restricted for geographical, cultural, financial or other reasons.  Additionally, the Joint Project will offer expert substantive support to the IMWG and its Secretariat in design and implementation of the consultation process.

In the area of awareness-raising on transitional justice, the Joint Project will implement public awareness activities throughout its duration. Beyond introducing a wider public to the concept of transitional justice, the aim is also to sensitise the population and manage expectations that may arise from the IMWG’s work. Awareness-raising activities will be timed in accordance with the progress made by the IMWG and will cover the print, digital and TV media throughout Kosovo with the aim of raising awareness both of issues to do with transitional justice and of relevant Kosovo authorities’ processes underway, such as eventually a Transitional Justice Strategy for Kosovo. Through Public Service Announcements on television, a wide audience will be reached and provided with short information on transitional justice. The aim is to sensitise the population to the concept with the ultimate aim of opening up public space for debate.

Additionally, the project will identify several types of human rights violations related to the conflict (such as but not limited to: sexual and gender based violence (SGBV); property; and missing persons.) and aims to promote public debate, such as by hiring a film maker through a special project fund based on an open application process to produce at least one short documentary based on a victim’s testimony (most likely anonymous), which will be screened on prime time television followed by a discussion or call-in show.

Related to stakeholder awareness, the Joint Project will further conduct activities to raise awareness of transitional justice among key stakeholders from academia, media, civil service, the judiciary, civil society, and interest groups such as veterans’ or victims’ associations. The Joint Project will aim to create and use synergies with other actors involved in the transitional justice process, so to enhance and enlarge the awareness of transitional justice. These will include roundtables focusing on various aspects of transitional justice in various places in Kosovo. The Joint Project will seek to arrange visits by prominent experts on transitional justice to meet with relevant stakeholders and to discuss identified issues. In addition, visits of relevant Special Rapporteurs to Kosovo will be facilitated under this Output. Experts could jointly be used for consultations for the IMWG and for public lectures to increase public awareness.

The Joint Project could also support the establishment of a permanent multidisciplinary academic resource centre on transitional justice at the Universities of Pristina and Mitrovica.

The range of activities implemented under this Output, which will enhance awareness of and participation in transitional justice by the general public and key stakeholders, will contribute to a conducive environment for the IMWG’s work and the development, and eventually the creation of a Transitional Justice Strategy for Kosovo.

# Results and Resources Framework

Project Outcome: The measurable enhancement of the capacities of critical institutional and civil society actors to engage in and steer an inclusive, participatory, victim-centred and gender-sensitive transitional justice process in Kosovo. This, in turn, will contribute to the creation of a more conducive environment for a successful transitional justice process in Kosovo. In this manner, the Joint Project will contribute to vindicating the dignity of victims, improving community relations, strengthening civic trust, and, in the long term, to reconciliation and the prevention of future violence

CDP Outcome 2.1: “Institutions responsible for delivering public services and social justice are accountable and responsive to rights holders”. CDP Outcome 2.2: “Key civil society actors increasingly influence the accountability of governance for public services and social justice”.

Partnership Strategy: The project will partner with the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation, the Office of the Prime Minister, and a range of diverse Civil Society Organisations

Joint Project title and ID (ATLAS Award ID): Support to Transitional Justice in Kosovo (Award ID: 00076799)

| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | INPUTS |
| --- | --- | --- | --- |
| Output 1: Capacity of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation to fulfil its mandate is strengthened. Indicator: % of progress made in drafting a Transitional Justice Strategy. Baseline: No transitional justice strategy in place | Target (year 1) - Rules of Procedures and Action Plan to draft National Transitional Justice Strategy prepared Target (year 2) - Strategy drafting underway (50%) Target (year 3) - Strategy completed (100%) | 1.1. Enhanced logistical capacity of IMWG to fulfil its mandate. 1.1.1. Secretariat Officer at IMWG Secretariat 1.1.2. Provide logistical support to the drafting process 1.2. Enhanced substantive capacity of IMWG to fulfil its mandate 1.2.1. Senior Adviser on Transitional Justice providing expertise and training (serves all three Outputs) 1.2.2. Development of policy papers through engaging external experts in order to provide comprehensive and persuasive policy recommendations upon request of the IMWG 1.2.2. Finalize the draft strategy in light of results of consultations 1.2.3. Capacity building and thematic workshops | Salaries Equipment and operational expenses International and Local Consultants Transportation and Hospitality during study visits |
| Output 2: Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened. Indicator 1: Number of NGO staff completing trainings trained. Baseline 1: Zero Indicator 2: Number of comments and interventions made by CSOs on drafts produced by Inter-Ministerial Working Group that are ultimately accepted into documents. Baseline 2: Zero | Target for indicator 1 (by year 3) - 50 participants Target for indicator 2 (by year 3) - 20 | 2.1. Increased capacity of CSOs for transitional justice 2.1.1. maintain an online information sharing platform (website for public access, but also with private login capabilities) 2.1.2. Support exchange of expertise and experience between CSOs in Kosovo and those in the region and beyond who have worked on TJ, in order to increase advocacy and monitoring on TJ 2.2. Targeted transitional justice advocacy support to specific victims groups and weaker segments of society 2.2.1. Increase transitional justice awareness of specific groups of victims of human rights violations Such as Roma, Ashkali and Egyptians. 2.2.2 Empower specific groups of victims of human rights violations and weaker segments of society for their voice to be heard. | Salaries UNDP project staff Equipment and operational expenses Transportation and Hospitality for meetings |
| Output 3: Public and stakeholder awareness of and participation in transitional justice are increased. Indicator 1: % increase in stakeholder and public awareness of Transitional Justice. Baseline 1: - 2012/2013 Transitional Justice Survey conducted by UNDP’s Advancing Gender Justice project Indicator 2: % of NGOs –that support the consultations process Baseline 2: Zero | Target for indicator 1 (by year 3) - 20% increase from 2012/2013 survey Target for indicator 2 (by year 3) 50% of all NGOs working on TJ in Kosovo offer their support on consultations | 3.1. Broad consultation process supported 3.1.1. Methodological and logistical support to the consultation process - workshops with stakeholders to design the Consultations plan. 3.1.2. Expert substantive support to the IMWG and its Secretariat in design and implementation of the consultation process. 3.1.3 Facilitating public consultations 3.2. Increased public awareness of transitional justice 3.2.1. Awareness-raising initiatives on transitional justice 3.3. Increased awareness of transitional justice among key stakeholders 3.3.1. Invite prominent experts on transitional justice to meet with relevant stakeholders and academic institutions in Kosovo for knowledge exchange on identified transitional justice issues 3.3.3 Kick-off Transitional Justice Conference | International and Local Consultants Per-Diems, transport Relevant material and documentation Communications material |

# Annual Work Plan

Years: 2016

| EXPECTED OUTPUTS | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount in USD |
| Output 1: Capacity of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation to fulfil its mandate is strengthened. Indicator: First Draft of Transitional Justice Strategy Baseline: No strategy in place Target: Draft TJ Strategy prepared by the end of November 2016 Gender Marker Rating Rationale: related to 8PA and GES | Enhanced logistical capacity of IMWG to fulfil its mandate 1.1.1. Facilitate the work of the IMWG Secretariat, with recruitment of one Secretariat Officer | X | X | X | X | UNDP | Switzerland | Project management , financial/logistic support Contractual Services | 14,026 18,000 |
|  | 1.1.2. Support the development of the Strategy on TJ, through engagement of local consultants to facilitate the work of IMWG on strategy drafting | X | X | X | X | UNDP | Switzerland | Contractual services/IC | 8,000 |
|  | 1.2. Enhanced substantive capacity of IMWG to fulfil its mandate 1.2.1. Senior Adviser on Transitional Justice providing expertise and training | X | X | X | X | UNDP | Switzerland | In kind contribution | In kind contribution |
|  | 1.2.2. Finalisation of the draft strategy in light of results of consultations |  |  |  | X | UNDP | Switzerland | Contractual Services/IC | 20,345.06 |
|  | 1.2.3.Organise capacity building and thematic workshops for IMWG members and Secretariat in cooperation with academia; CSO’s and International Experts | X | X |  |  | UNDP | EU | Contractual services Venue Translation costs | 26,319.48 |
| Output 2: Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened. Indicator 1: # of NGO staff trained Baseline 1: 0 Target: Minimum 10 NGOs participated in training Gender Marker: Rating Rationale: related to 8PA and GES | 2.1. Increased capacity of CSOs for transitional justice 2.1.1. Maintain an online information sharing platform | X | X | X | X | UNDP | UNDP | In-kind contribution | In-kind contribution |
|  | 2.1.2. Support exchange of expertise and experience between CSOs in Kosovo and those in the region and beyond related to TJ in order to increase advocacy and monitoring on TJ | X | X | X | X | UNDP | Switzerland | Venue Translation | 4,000 |
|  | 2.2. Targeted transitional justice advocacy support to specific victims groups and weaker segments of society 2.2.1. Increase TJ awareness of specific groups of victims of human rights violations, such as Roma Ashkali and Egyptians |  | X | X |  | UNDP | Switzerland Switzerland | Project management , financial/logistic support Venue Translation | 5,000 5,000 |
|  | 2.2.2. Empower specific groups of victims of human rights violations and weaker segments of society for their voice to be heard. |  | X | X |  | UNDP | Switzerland France | Contractual services Venue Training material Translation | 2,000 5,037 |
| Output 3: Public and stakeholder awareness of and participation in transitional justice are increased. Indicator : % increase in stakeholder and public awareness of Transitional Justice. Baseline: 2012 Transitional Justice Survey conducted by UNDP Target: 20% increase in stakeholder and public awareness Gender Marker: Rating Rationale: related to 8PA and GES | 3.1 Broad consultation process supported 3.1.1. Methodological and logistical support to the consultation process –Workshops with stakeholders to design the Consultations plan. 3.1.2 Expert substantive support to the IMWG and its Secretariat in design and implementation of consultation process. 3.1.3 Facilitating public consultations (transport, per-diem, meeting rooms, etc) 3.2. Increased public awareness of transitional justice | X X | X X X | X | X | UNDP | Switzerland EU EU EU | Project management , financial/logistic support Contractual services Contractual services Contractual services Grants Translation | 15,000 4,861 5,634.44 42,023 |
|  | 3.2.1. Awareness-raising initiatives on transitional justice (including usage of the tools produced by the project during 2014/2015) | X | X | X |  | UNDP | France | Contractual services, public campaigns and outreach | 4,697 |
|  | 3.3. Increased awareness of transitional justice among key stakeholders 3.3.1. Sharing of experience between experts on transitional justice and Kosovo stakeholders on transitional justice issues. | X | X | X |  | UNDP | EU | Contractual services Travel Venue cost | 4,559.89 |
|  | 3.3.3. Kick-off Transitional Justice Conference, to launch the public consultations |  | X |  |  |  | EU | Contractual services Venue Material Translation Travel | 11,213 |
| Output 1 | 86,690.54 |
| Output 2 | 21,037 |
| Output 3 | 87,988.33 |
| OUTPUTS SUB TOTAL | 195,715.87 |
| Communication 1% | 1,957.16 |
| SUB TOTAL | 197,673.03 |
| General Management Services 8% | 15,813.84 |
| GRAND TOTAL | 213,486.87 |

# Fund Management Arrangements

The Joint Project will be implemented jointly by UNDP Kosovo, OHCHR Kosovo, IOM Kosovo and UN Women Kosovo. All project funds will be received and managed by the UNDP Kosovo Office.

Various activities will be implemented through contractors under the overall supervision of OHCHR and UNDP and project partners where relevant. OHCHR and UNDP will be responsible for assuring qualitative management and results of the Joint Project. Contractors will be selected according to the applicable OHCHR and UNDP procedures and will be responsible to deliver the envisaged activities under the overall supervision of OHCHR and UNDP. OHCHR and UNDP will appoint focal points from their offices, and a local project team will be hired to implement the Joint Project. The focal points will be responsible for assuring qualitative management and results of the project as well as for coordinating inputs from the members of the Project Board.

# Management Arrangements

This Joint Project will be implemented though the direct execution (DEX) modality. This implies that UNDP, UN Women, IOM and OHCHR are directly responsible for managing, reporting and achieving the expected outputs of the Joint Project.

The donor(s) will be Senior Supplier(s) of the Joint Project, operating according to the terms specified in cost sharing agreements (CSA) between UNDP, OHCHR, UN Women, IOM and the donor(s). See Annex below for the CSA.

The project will establish a Project Board, which will be comprised of representatives of the Senior Supplier(s), senior beneficiaries, the executive (UNDP, OHCHR, IOM and UN Women in Kosovo), and the Project Manager. Other relevant stakeholders not pertaining to the Project Board can be invited to contribute as observers on an ad hoc basis.

The Project Board will be responsible for providing general oversight to ensure achievement of results on the primary project outcomes and making consensus strategic management decisions when guidance is required by the Project Manager; this including approval of project plans and revisions, as well as meeting the requirements of the UN Common Development Plan and well as agency-specific plans and strategies.

The UN Development Coordinator in Kosovo will be the chairperson of the Project Board. Project Board meetings will be organized by the Project Board as needed, but not less than once every six months.

Project Quality Assurance will be provided by the UNDP Kosovo Governance Team and the OHCHR Stand-alone office in Kosovo, who will ensure that objective and independent project oversight is carried out for the purpose of meeting project management targets.

The Project Manager will be responsible for managing day-to-day project operations (administrative elements) and decision-making. These will be executed on behalf of and according to the decisions of the Project Board. The Project Manager will supervise the staff of the Joint Project as well as closely coordinate project-activities with all relevant stakeholders, particularly the IMWG and its Secretariat.

# Monitoring Framework And Evaluation

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the table below: Quality Management for Project Activity Results.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted (see annex 1), a Risk Log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format.

- A project Lesson-learned Log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project.

- A Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events.

Annually

- Annual Report. An Annual Report shall be prepared by the Project Manager and shared with the Project Board. As minimum requirement, the Annual Report shall consist of the Atlas standard format for the QPR covering the whole year with updated information for each above element of the QPR as well as a summary of results achieved against pre-defined annual targets at the output level.

- Annual Project Review. Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Final Evaluation

The Joint Project will also conduct an independent final project evaluation which will lead to a final report and lessons learned report. Evaluation will be carried out in collaboration with Kosovo and international organizations. The evaluation will consider achievement of development goals according to parameters of the relevance and responsiveness of the actions, their effectiveness and efficiency, and the impact and sustainability of results, focusing especially upon their contribution to capacity development.  The evaluation will also provide recommendations for follow-up activities.

Quality Management for Project Activity Results

| Output 1 – Capacity of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation to fulfil its mandate is strengthened. |
| --- |
| Activity Result 1.1 (Atlas Activity ID) | Enhanced logistical capacity of IMWG to fulfil its mandate | Start Date: End Date: |
| Purpose | IMWG has the logistical, administrative, and technical capacity to fulfil its mandate |
| Description | Secretariat Officer at IMWG Provide logistical support to the drafting process |
| Quality Criteria | Quality Method | Date of Assessment |
| Efficiency of the proceedings of the working group | Consultations with project partners |  |
| Efficiency of the drafting process for a Transitional Justice Strategy for Kosovo | Consultations with project partners |  |

| Output 1 – Capacity of the Inter-Ministerial Working Group on Dealing with the Past and Reconciliation to fulfil its mandate is strengthened. |
| --- |
| Activity Result 1.2 (Atlas Activity ID) | Enhanced substantive capacity of IMWG to fulfil its mandate | Start Date: End Date: |
| Purpose | Members of the IMWG have access to information and training that will improve their work on transitional justice. |
| Description | Senior Adviser on Transitional Justice (SATJ) providing expertise and training (serves all three Outputs) Development of policy papers through engaging external experts in order to provide comprehensive and persuasive policy recommendations upon request of the IMWG Organize, as warranted, study visits for IMWG members to countries that are dealing with, have dealt with, or are struggling to deal with similar transitional justice processes. |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of knowledge products available to the IMWG thanks to the Project | Knowledge products produced |  |
| Understanding of transitional justice on the part of IMWG members | Assessment of SATJ, project staff and external stakeholders |  |

| Output 2 – Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened. |
| --- |
| Activity Result 2.1 (Atlas Activity ID) | Increased capacity of Civil Society Organisations for transitional justice | Start Date: End Date: |
| Purpose | CSOs can play a critical and constructive role in the transitional justice process. |
| Description | Conduct trainings on transitional justice with CSOs Support for coordination and networking between CSOs working on transitional justice (including online information sharing) Provide small grants for projects related to transitional justice Hold meetings of CSOs from the region, including youth CSOs, who contribute to the transitional justice process and facilitate exchange of experiences (in order to include ethnic minorities and other people in the region who are relevant to bridge relations and maximize the value of the consultation process) Support exchange of expertise between CSOs in Kosovo and those in the region and beyond who have worked on TJ. |
| Quality Criteria | Quality Method | Date of Assessment |
| Feedback from CSOs on trainings | Feedback questionnaires |  |
| Sustainability of contacts between CSOs after regional meetings are held | Ongoing monitoring of CSO activity in the field of TJ by the project |  |
| Number of initiative during TJ process on which CSOs cooperate | Ongoing monitoring of TJ process by the project |  |
| Number of inputs from CSOs on drafts produced by IMWG | Minutes of IMWG meetings |  |

| Output 2 – Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened. |
| --- |
| Activity Result 2.2 (Atlas Activity ID) | Targeted transitional justice advocacy support to specific victims groups and weaker segments of society | Start Date: End Date: |
| Purpose | Specific victims groups and weaker segments of society are better equipped to take a vital part in the transitional justice process. |
| Description | Increase transitional justice awareness of specific groups of victims of human rights violations and weaker segments of society, including victims of SGBV. Support specific groups of victims of human rights violations and weaker segments of society for their voice to be heard on their specific transitional justice needs |
| Quality Criteria | Quality Method | Date of Assessment |
| Feedback from advocates on coaching | Feedback questionnaires |  |
| Increased presence and tj activity specific groups of victims of human rights violations and weaker segments of society | Project records |  |

| Output 2 – Capacity of civil society to contribute to a transitional justice process in a constructive and critical manner is strengthened. |
| --- |
| Activity Result 2.3 (Atlas Activity ID) | Enhanced capacity of the media to report on transitional justice issues | Start Date: End Date: |
| Purpose | Media can play a positive role in sensitising the population and managing expectations during the transitional justice process. The risk of provocative and destructive reporting on transitional justice is reduced. |
| Description | Hold roundtables with editors of major newspapers to discuss transitional justice and issues arising when reporting on it Provide trainings on transitional justice for journalists to increase their knowledge on technical issues and host discussions |
| Quality Criteria | Quality Method | Date of Assessment |
| Feedback from trainings | Feedback questionnaires |  |
| Number of negative, unhelpful, or destructive stories on transitional justice process in Kosovo’s media | Ongoing monitoring by project team |  |

| Output 3 – Public and stakeholder awareness of and participation in transitional justice is increased. |
| --- |
| Activity Result 3.1 (Atlas Activity ID) | Broad consultation process supported | Start Date: End Date: |
| Purpose | IMWG can gather views from a very broad spectrum of society to inform the Transitional Justice Strategy for Kosovo. |
| Description | Methodological and logistical support to the consultation process Expert substantive support to the IMWG and its Secretariat in design and implementation of consultation process Facilitating public consultations |
| Quality Criteria | Quality Method | Date of Assessment |
| Civil society attendance at consultation meetings | Attendance sheets |  |
| Geographical and thematic coverage of the consultation process | Assessment of SATJ, project staff and external stakeholders |  |

| Output 3 – Public and stakeholder awareness of and participation in transitional justice is increased. |
| --- |
| Activity Result 3.2 (Atlas Activity ID) | Increased public awareness of transitional justice | Start Date: End Date: |
| Purpose | Public understands better the process of transitional justice and some key mechanisms and principles, and can take part in it when consulted. |
| Description | Awareness-raising initiatives on transitional justice Produce at least one short film on human rights violations related to the conflict (such as SGBV, property, missing persons) followed by a discussion on TV and/or call-in show Follow-up survey based on the 2013 UNDP baseline survey to measure awareness of and attitudes about transitional justice (end of project) |
| Quality Criteria | Quality Method | Date of Assessment |
| Attitudes, awareness and understanding of transitional justice | Survey at end of project |  |
| Number of viewers during TV discussions | Viewer data |  |
| Reach of individual awareness-raising activities (number of billboards, public service announcements, etc.) | Project records |  |

| Output 3 – Public and stakeholder awareness of and participation in transitional justice is increased. |
| --- |
| Activity Result 3.3 | Increased awareness of transitional justice among key stakeholders | Start Date: End Date: |
| Purpose | Key stakeholders understand transitional justice process, mechanisms and principles. |
| Description | Invite prominent experts on transitional justice to meet with relevant stakeholders and academic institutions in Kosovo for knowledge exchange on identified issues Facilitate the visits of relevant Special Rapporteurs to Kosovo Kick-off Transitional Justice Conference Supporting the establishment of a permanent multidisciplinary academic resource center on transitional justice in the law faculties at the Universities of Pristina and Mitrovica Feasibility assessment on the willingness and need for an ICTY Information Centre in Pristina |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of participants at roundtables and events | Attendance records |  |
| Press coverage of roundtables and events | Press monitoring by project |  |

# Legal Context

The project document shall be the instrument envisaged and defined in the Supplemental Provisions to the Project Document, attached hereto and forming an integral part hereof, as the “Project Document”.

UNDP, OHCHR, UN Women and IOM as the Implementing Partners shall comply with the policies, procedures and practices of the United Nations safety and security management system.

UNDP, OHCHR, UN Women and IOM agree to undertake all reasonable efforts to ensure that none of the project funds are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# Annexes

Annex 1: Offline Risk Log

| Project Title: Joint Project ‘Support to Transitional Justice in Kosovo’ *Probability (P) and Impact (I) is measured on a scale of 1-5, (1 being the lowest risk) | Award ID: 00076799 | Date: 16 January 2014 |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Change in central Kosovo institutions leads to new membership and leadership of IMWG. | 15.09.2015 | Political | Capacity building would have to be restarted. Political commitment to transitional justice might decrease. P=4; I=3 | Active lobbying efforts with new central Kosovo institutions to avoid changes in IMWG membership and for continued support of TJ process by the Project and wider stakeholders (donors; international organisations). | Project Manager | UNDP Programme Analyst |  |  |
| 2 | Relations between Pristina and Belgrade and/or between K-Albanians and K-Serbs worsen leading to violence or instability | 15.09.2015 | Political | Partners become unwilling to discuss TJ and Reconciliation, IMWG process stalls, project activities can’t be implemented as planned. P=1; I=4 | Project staff will remain alert to changes in the political environment and will use the project’s flexible nature to adapt activities to partners’ needs and sensitivities. Where the IMWG’s work stalls, independent project activities can be implemented. | Project Manager | UNDP Programme Analyst |  |  |
| 3 | Kosovo central institutions’ Commitment to transitional justice process decreases | 15.09.2015 | Political | The process of the IMWG fulfilling its task slows down or stalls. P=2; I=4 | Project staff will monitor any changes in Kosovo central institutions’ commitment and will lobby for the TJ process. The joint project team makes every effort to support active members of the IMWG to de-block situations where the IMWG’s work stalls. | Project Manager | UNDP Programme Analyst |  |  |
| 4 | Disagreements between OPM/Secretariat and Joint Project Team | 15.09.2015 | Organisational | Implementation arrangements as foreseen in Joint Project Document become difficult to implement. P=2; I=3 | The Joint Project team will use mediation skills to overcome disagreements, if disagreements persist Project Board will provide guidance. | Project Manager | UNDP Programme Analyst |  |  |
| 5 | Ineffective coordination between CSOs | 15.09.2015 | Organisational | CSOs compete with one another and duplicate efforts. P=3; I=3 | The Joint Project Team will use mediation skills and aim to create incentives for better coordination among CSOs. | Project Manager | UNDP Programme Analyst |  |  |
| 6 | CSOs refuse to take part in Joint Project due to their perception of an ‘internationally imposed process’ or due to their rejection of a Kosovo institutions’-led process. | 15.09.2015 | Strategic | Output 2 becomes impossible to implement. P=1; I=4 | Outreach to CSOs will be done in sensitive way to avoid misunderstandings about the nature of the project. | Project Manager | UNDP Programme Analyst |  |  |
| 7 | Social and cultural norms limit the project’s scope of raising transitional justice issues, including e.g. SGBV, in the media and during consultations. | 15.09.2015 | Environmental | Transitional justice process cannot take place in its entirety, certain topics remain taboo. P=2; I=4 | A culturally sensitive approach will be taken throughout project implementation to avert this risk. | Project Manager | UNDP Programme Analyst |  |  |

|  | UNITED NATIONS DEVELOPMENT PROGRAMME Terms of Reference |
| --- | --- |
| Title: Project Manager Project: ‘Support to Transitional Justice in Kosovo’ Department: OHCHR/UNDP Reports to: UNDP Governance Adviser Level: SB4 (q3, q4, q5) |

II. Organizational Context

Under the direct supervision of UNDP Governance Adviser, the Project Manager has the overall responsibility for achieving the project results (outputs) as defined in the approved project document and in the annual work plans through timely and quality implementation and monitoring. The Project Manager is supervising and leading the project staff. Provide leadership to the project team and outsources partners and contractors and build smooth relationship with partners.

III. Functions / Key Results Expected

Summary of functions: Management of the project, implementing activities by mobilizing goods and services, in accordance with UNDP POPP and UNDP Kosovo Standard Operating Procedures; Monitoring of progress and risks, ensuring that changes are controlled and problems addressed; Reporting on progress including measures to address challenges and opportunities; Support partnerships and advocacy activities at project level; and Ensure implementation of knowledge management activities. Management of the project, implementing activities by mobilizing goods and services, in accordance with UNDP POPP and the UNDP Kosovo Standard Operating Procedures: Prepare annual project work-plans and related sub-plans (procurement plan, quarterly plans if required, and others as necessary); Build, motivate and lead a high-performing project team; coordinate and supervise the work of the project personnel; Ensure timely and good-quality implementation of work-plan activities; Continuously monitor progress against the approved work-plan; identify changes in the external environment and promptly agree necessary solutions/actions ( ex. related to the planning and implementation of activities, need for new activities) with UNDP office and Project Board; Mobilize personnel, goods and services, training and micro-capital grants to initiative activities, including drafting terms of reference and work specifications and overseeing all contractors’ work; Manage requests for the provision of financial resources by UNDP, through advance of funds, direct payments, or reimbursement using the FACE (Fund Authorization and Certificate of Expenditures); Monitor financial resources and accounting to ensure accuracy and reliability of financial reports; ensue preparation of budget revisions as necessary; follow up with UNDP programme associate and finance staff on issues; and Coordinate an exit strategy at least 6 months ahead of the project closure date; ensure closure of the project is done according to the established procedures. Monitoring of progress and risks, ensuring that changes are controlled and problems addressed; Reporting on progress including measures to address challenges and opportunities: Monitor events as determined in the project monitoring schedule plan, and update the plan (in Atlas and off-Atlas) as required; Periodically update the project information Atlas Project Management module; Manage and monitor the project risks initially identified and submit new risks to the project board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log; Organize regular Board meetings and perform regular progress reporting to the project board as agreed to with the board; Prepare progress reports with the frequency and using the template recommended by the UNDP office. Submit the report to supervisor in the UNDP programme team for review and clearance, according to the agreed timetable. Share report with the project board; Ensure reporting to donor is prepared timely and the reports are meeting the standards; Support the preparation of reviews and evaluations as defined in the project document; and Prepare final project reports and papers. Support partnerships and advocacy activities at project level: Be familiar with the activities of other development projects in the sector/area, establish contact and keep up-to date with their work; Create and maintain partnerships with local institutions, private sector, and project target areas; and Support the partnerships and advocacy activities agreed by the UNDP/OHCHR office in the area/sector covered by the project. Ensure implementation of knowledge management activities: Regular exchange of information/experience with other projects, cross-learning and sharing results and good practices; Ensure the project has the required communication package and preparation, upon request of the UNDP office, of information materials for dissemination within UNDP globally and regionally, and to external stakeholders; Capture lessons learnt during project implementation – a lessons learnt log can be used in this regard; Participation in regular internal meetings; and Participation in training events, communities of practice, codifying and sharing knowledge, facilitation and organization of training for project staff to enable them to perform at the required level.

IV. Impact of Results

The results of the work of Project Management have a direct impact on the implementation of the project and the achievement of results. Specifically, the results have an impact on the planning, implementation, monitoring and coordination of project activities and resources (human, financial, material assets etc) in order to meet expected results, and contribute to the overall success and impact of the UNDP/OHCHR office work in Kosovo.

V. Competencies

Corporate Competencies: Demonstrates integrity by modeling the UN’s values and ethical standards; Promotes the vision, mission and strategic goals of UNDP/OHCHR; Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability; and Treats all people fairly without favouritism. Functional competencies: Ability to conduct strategic planning, results-based management and reporting; Ability to lead monitoring of management projects; Ability to lead business process; Ability to affect staff behavioural/attitudinal change; Ability to perform a variety of specialized tasks related to Results-Based Management, including support to design, planning and implementation of the programme, managing data, reporting; Analytical and strategic thinking/results orientation; Excellent interpersonal skills and ability to communicate effectively, both orally and in writing; Ability to establish effective working relations in a multicultural team environment; and Excellent supervisory, management and team-building skills.

| VI. Recruitment Qualifications |
| --- |
| Education: | Master Degree or equivalent in post-conflict peace-building, transitional justice, international relations, social sciences, or other relevant fields |
| Experience: | Min three (3) years of post-Master relevant working experience in project/programme management or managing staff and operational systems, and/or establishing relationships among international organization and local institutions/communities Previous experience in development assistance or related work for an international agency or donor organization or NGO Proven ability to coordinate complex programs with diverse range of partners |
| Language Requirements: | Fluency in both oral and written English, Albanian and/or Serbian |

# Footnotes

For the purpose of this Project Document, the terms ‘Transitional Justice’ and ‘Dealing with the Past’ are used interchangeably, while preference is given to the use of the term ‘Transitional Justice’.

Decision No. 03/77, 04.06.2012. The IMWG consists of 12 Kosovo institutions and eight civil society representatives, as well as members of the international community as observers and its Secretariat is situated within the Office of the Prime Minister (the Decision will be amended to add three more members; Ministry of Internal Affairs; Agency for Gender Equality, and Office for Good Governance).

Article 2.5 of the Comprehensive Proposal for the Kosovo Status Settlement (S/2007/168/Add.1).

Estimated numbers of casualties and displaced persons vary by source and are highly disputed.

See for example Report of the High Commissioner for Human Rights on the situation of human rights in Kosovo, Federal Republic of Yugoslavia, E/CN.42000/32, 17 March 2000.

ICRC, ‘Kosovo: ICRC hands over software for management of missing persons data’, 8 June 2012 http://www.icrc.org/eng/resources/documents/news-release/2012/kosovo-news-2012-06-07.htm.

OHCHR, Healing the spirit : Reparations for survivors of sexual violence related to the armed conflict in Kosovo, June 2013, http://www.ohchr.org/Documents/Issues/Women/WRGS/PeaceAndSecurity/StudyHealingTheSpirit.pdf; HRW, Kosovo: Rape as a weapon of "Ethnic cleansing", Chap IV. The Consequences of Rape. http://www.hrw.org/reports/2000/fry/Kosov003-03.htm#P400_82668.

Decision No. 09/168, 29 January 2014.

Law No. 04/L-172, of 20,March  2014.

Report on the Perceptions on Transitional Justice in Kosovo, 2012, prepared by UBO Consulting, January 2013, UNDP Kosovo (); and ‘Public Perceptions on Transitional Justice’, Report on Transitional Justice Opinion Polling Survey, UNDP Kosovo, May 2007.

Report on the Perceptions on Transitional Justice in Kosovo, 2012, prepared by UBO Consulting, January 2013, UNDP Kosovo (currently in draft form, to be finalised by end of January 2013).

‘Kosova 1912 – 2000 in the history textbooks of Kosova, Albania and Serbia’, Shkëlzen Gashi, published by the Kosovo Association for Human and Child Rights (KAHCR) and the Kosova Education Centre (KEC), 2012, p.53.

‘Justice failed in Kosovo’, Amnesty International, 30 January 2008, http://www.amnesty.org/en/news-and-updates/report/justice-failed-kosovo-20080130 and ‘Kosovo, Time for EULEX to Prioritize War Crimes’, Amnesty International, April 2012, quoted in ‘Challenges in Dealing with the Past in Kosovo: From Territorial Administration to Supervised Independence and Beyond’, Nora Refaeil, in Politorbis No. 54 (2/2012), December 2012, p.90.

‘Kosovo’s War Crimes Trials: An Assessment 10 Years on, 1999-2009’, OSCE, May 2010, p.6.

‘A Turbulent Year for Transitional Justice in the Balkans’, Marija Ristic, Balkan Transitional Justice, 2012, accessed at http://www.transconflict.com/2013/01/turbulent-year-for-transitional-justice-in-the-balkans-911/; ‘Hague Verdicts Don’t ‘Justify’ Croatia’s, Kosovo’s, Wars’, Florian Bieber, Balkan Transitional Justice, 29 November 2012, http://www.balkaninsight.com/en/article/hague-verdicts-don-t-justify-croatia-s-kosovo-s-wars; ‘Serbian Fury at Haradinaj Verdict’, Amra Zejneli, Branka Mihajlovic, Milos Teodorovic, Institute for War & Peace Reporting, TRI Issue 767, 3 December 2012.

‘Regional Approach to Healing the Wounds of the Past’, Bekim Blakaj, in Politorbis No. 54 (2/2012), December 2012, p.83.

‘The Rule of Law and Transnational Justice in Conflict and Post-Conflict Societies’, Report of the Secretary-General S/2004/616, 23 August 2004.

Guidance Note of the Secretary-General, United Nations Approach to Transitional Justice, March 2010.

Guidance Note of the Secretary-General, United Nations Approach to Transitional Justice, March 2010.

Report of the independent expert to update the set of principles to combat impunity, Diane Orentlicher, E/CN.4/2005/102/Add.1, 8 February 2005.

A/HRC/21/46.

Report of the Special Rapporteur on the promotion of truth, justice, reparation and guarantees of non-recurrence to the Human Rights Council, http://www.ohchr.org/Documents/HRBodies/HRCouncil/RegularSession/Session21/A-HRC-21-46_en.pdf.

Report of the Secretary General on the rule of law and transitional justice in conflict and post-conflict societies, 12 October 2011, S/2011/634.

The Security and Gender Group (SGG), was established in 2007 and is chaired by UN Women. Its members are civil society organizations (Kvinna til Kvinna, Kosova Women’s Network, Kosovo Gender Studies Centre, Association of Women in the Kosovo Police), Kosovo Institutions (Agency for Gender Equality, Women’s Caucus, Kosovo Police, Kosovo Security Forces) and International Organizations (UNMIK, UNDP, UNICEF, UN-HABITAT, OHCHR, UNFPA, WHO, UNOPS, UNHCR, UN Women, EU Office, EULEX, OSCE and KFOR).

Members of the Conflict Related Sexual and Gender-Based Violence sub-group include also members outside of the SGG, and they are: Kvinna till Kvinna, Kosova Women’s Network Agency for Gender Equality, Women Caucus, OHCHR, UN Women, UNFPA, UNMIK, EULEX, OSCE, EU Office, Kosovo Rehabilitation Centre for Torture Victims, Medica Kosova; and two observers: British Embassy Pristina and Office of the President.

See for example http://www.undp.ba/index.aspx?PID=21&RID=95 and the Report of the UNHCHR on human rights and transitional justice, A/HRC/18/23, 4 July 2011.

Decision No. 03/77, 04.06.2012.

Decision No. 03/77, 04.06.2012.

Decision No. 03/77, 04.06.2012.

‘Rule-of-Law Tools for Post-Conflict States: national consultations on transitional justice’, HR/PUB/09/2, Office of the United Nations High Commissioner for Human Rights, 2009.

Rule-of-Law Tools for Post-Conflict States: national consultations on transitional justice’, HR/PUB/09/2, Office of the United Nations High Commissioner for Human Rights, 2009, p.8.

Rule-of-Law Tools for Post-Conflict States: national consultations on transitional justice’, HR/PUB/09/2, Office of the United Nations High Commissioner for Human Rights, 2009, p.3.

Guidance Note of the Secretary-General, United Nations Approach to Transitional Justice, March 2010.

Report of the Secretary General on the rule of law and transitional justice in conflict and post-conflict societies, 12 October 2011, S/2011/634.

As mentioned above, the Secretariat was previously  supported through one administrative assistant paid through UNDP’s Advancing Gender Justice project.

Report of the Secretary General on the rule of law and transitional justice in conflict and post-conflict societies, 12 October 2011, S/2011/634.

Rule-of-Law Tools for Post-Conflict States: national consultations on transitional justice’, HR/PUB/09/2, Office of the United Nations High Commissioner for Human Rights, 2009, p.18.

# Text boxes

Programme Duration: Two years

Anticipated start/end dates: September 2015 – November 2016 (This document is an update to the original project document)

Total estimated budget 2015*: USD 152,995.12

Total estimated budget 2016*: USD 213,486.87

* Total estimated budget includes both programme costs and indirect support costs as well as the transferred unspent balance (Swiss and France)

Brief Description

The Joint Project ‘Support to Transitional Justice in Kosovo’ will support and facilitate the process of transitional justice in Kosovo by working with partners that include the authorities and civil society in Kosovo. Through activities implemented in three project outputs, a conducive environment for transitional justice process will be created. Outputs include increased capacity of partners and beneficiaries to engage in a comprehensive, gender-sensitive transitional justice process, and enhanced public and stakeholder awareness of and participation in transitional justice in Kosovo.