## 2017 AWP
Project Title: | Support to the effective management of the UNDP Kuwait Junior Professional Officer Programme | [7 empty] | Award Number: |  |  |  | 101063 |  |  |  | Total Budget |  |  |  |  | 208060 |  |  | Prepared by: | Abdullah Kamal
Project Number: | 101063 | [7 empty] | Year: |  |  |  | 2017 |  |  |  | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | CPD 4.2
Indicative Output(s): | 4.1
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | Scope of Work ( High Level) | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
Output 1 Third and subsequent batch(s) of Kuwaiti JPOs effectively recruited, with necessary institutional arrangements in place Indicators: 1.1 - Number of pre-shortlisting seminars conducted on the JPO experience 1.2 - Shortlists for each of the selected posts prepared in accordance with UNDP policies and procedures. 1.3 - Conduct a pre-departure workshop for each batch of the selected JPOs. 1.4 - Establish institutional arrangements required to support JPOs during and beyond the term of their assignment. Baseline: 1.1 : 0 1.2 : 0 1.3 : 0 1.4 : 0 Targets: 1.1 : 3 1.2 : 3 1.3 : 3 1.4 : 1 | 1.1 In respect of each batch, organise a seminar for long-listed applicants on the JPO experience, UNDP mandate and function etc. | Set up a seminar for the Shortlisted listed applicants to inform them about the programme and the UNDP's mandate | [14 empty] | 2 | 8000 |  |  | 2 | catering and logistics |  |  |  | 16000 | 2 seminars for long listed candidates completed | UNDP | bar: Q4 Dec
| Sub Total | [24 empty] | 16000
| 1.2 Coordinate with GSSCPD to prepare draft shortlists for each of the JPO posts in accordance with UNDP policies and procedures. | • Finalise selection of positions and advertise them on the UNDP job site; | [14 empty] | 2 | [8 empty] | 0 | Selection finalised | GSSCPD & UNDP | bar: Q1 Mar to Q2 Apr
|  | • Establish a hotline, social media page, website and/or other appropriate mechanism to respond to queries regarding the recruitment process; | [14 empty] | 2 | [8 empty] | 0 | a hotline, social media page, website and other appropriate mechanism to respond to queries regarding the recruitment process conducted | A.Kamal
|  | • Conduct initial screening of applications for eligibility; | [14 empty] | 2 | [8 empty] | 0 | screening conducted | GSSCPD & UNDP | bar: Q2 Apr; Q4 Nov to Q4 Dec
|  | • In conjunction with GSSCPD, convene shortlisting panel(s) and conduct shortlisting for each post; | [14 empty] | 2 | [8 empty] | 0 | shortlisting panels convened | GSSCPD & UNDP | bar: Q2 Apr to Q2 May; Q4 Dec
|  | • Contact applicants to ensure all necessary documentation has been provided; | [14 empty] | 1 | [8 empty] | 0 | candidates contacted for missing docs | GSSCPD & UNDP | bar: Q4 Nov
|  | • In conjunction with GSSCPD, convene longlisting panel(s) and conduct longlisting for each post; | [14 empty] | 1 | [8 empty] | 0 | longlisting convened | GSSCPD & UNDP | bar: Q2 May to Q2 Jun
|  | • Submit draft shortlists to JPOSC for screening of qualifications and relevant experience to ensure eligibility for consideration. | [14 empty] | 2 |  |  |  |  | National |  | 75700 |  | 0 | draft shortlist submitted to JPOSC & DESA | A.Kamal | bar: Q3 Jul; Q4 Dec
| Sub total | [24 empty] | 0
| 1.3 Conduct a pre-departure workshop for each batch of the selected JPOs. | Prepare draft agenda for the workshop and set up venue | [14 empty] | 2 | [8 empty] | 0 | bar: Q4 Dec
|  | Set up workshop logistics and related services | [14 empty] | 2 | 8000 | [7 empty] | 16000 | bar: Q4 Dec
| Sub total | [24 empty] | 16000
| 1.4 Establish institutional arrangements required to support JPOs during and beyond the term of their assignment. | Establish a career tracking database for all current and former JPOs; | [14 empty] | 1 | [8 empty] | 0 | bar: Q3 Aug to Q4 Dec
|  | Finalise a comprehensive and effective performance appraisal system for Kuwaiti JPOs; | [14 empty] | 1 | [8 empty] | 0 | bar: Q3 Sep to Q4 Dec
|  | Establish a mentoring network for the third and subsequent batch(s) of JPOs to include former JPOs and key development champions across Government, civil society, private sector and academia sectors in Kuwait; | [14 empty] | 1 | [8 empty] | 0 | bar: Q4 Oct to Q4 Dec
|  | Establish an alumni network to include all former JPOs | [14 empty] | 1 | [8 empty] | 0 | bar: Q4 Dec
| Sub total | [24 empty] | 0
| 1.5 Conduct a study-tour by key GSSCPD personnel to the JPOSC and at least one donor country located in Europe to examine best practices of longstanding donors to the JPO programme. | Prepare necessary agreements and approvals from JPOSC regarding the study tour | [14 empty] | 1 | [8 empty] | 0 | JPOSC and DESA contacted to inquire whether it is feasible to cionduct the study tour after deployment of batch 3 | A.Kamal | bar: Q3 Sep
|  | Set up the logistics and travel expenses | [14 empty] | 1 | 30000 | [7 empty] | 30000 | bar: Q3 Sep
| Sub Total | [24 empty] | 30000
Total Output1 | [25 empty] | 62000
Output 2: Effective communications and advocacy strategy drafted and implemented Indicators: 2.1 Number of articles, TV / radio spots and social media messages promoting the UNDP Kuwait JPO programme during the application phase. 2.2 Number of articles, TV / radio spots and social media messages promoting the UNDP Kuwait JPO programme after recruitment of the third and subsequent batch(s) of JPOs. 2.3 1 regional symposium on the Kuwait model of engagement in the JPO programme conducted. Baseline: 2.1 : 0 2.2: 0 2.3: 0 Targets: 2.1 : 80 2.2: 40 2.3: 1 | 2.1 | Draft a communications strategy, including analysis of target audiences and relevant media | [23 empty] | 0 | Draft starategy/media plan developed | A.kamal | bar: Q4 Oct to Q4 Nov
|  | Post advertisements in print, radio and social media for the JPO application phase | [14 empty] | 2 | 5000 | [7 empty] | 10000 | advertisements posted on traditional and social media | A.kamal | bar: Q2 Apr to Q2 May
|  | Arrange media interviews with current and former JPOs and relevant Government and UNDP personnel to publicise the JPO application phase; | [23 empty] | 0 | Media interviews were conducted with former interviews, inquiring about their experiences | A.kamal | bar: Q2 Apr to Q2 May
|  | Conduct a social media messaging campaign on the JPO programme to publicise the JPO application phase. | [14 empty] | 2 | 5000 | [7 empty] | 10000 | social media campaign conducted successfully | A.kamal | bar: Q2 Apr to Q2 May
| Sub total | [24 empty] | 20000
| 2.2 Implement the communications strategy for the UNDP Kuwait JPO programme across a range of media to highlight to publicise its success stories to the Kuwaiti stakeholders. | Draft op-eds, arrange media interviews, post social media messages, publish success stories online. | [14 empty] | 8 | [8 empty] | 0 | Media interviews , success stories and social media were all approached to increase exposure of the JPO programme. Number of applicants ~2000 | A.Kamal | bar: Q2 Apr; Q4 Oct to Q4 Nov
|  | Publish and disseminate facts sheets to stakeholders | [14 empty] | 2 | 5000 | [7 empty] | 10000 | Fact sheet disseminated through GSSCPD colleagues about the programme to all related stakeholders | GSSCPD & UNDP | bar: Q2 Apr; Q4 Nov
|  | Publish and disseminate an illustrated report on the achievements of the UNDP Kuwait JPO programme since deployment of the first batch of Kuwaiti JPOs in 2013 | [14 empty] | 1 | 20000 | [7 empty] | 20000 | bar: Q3 Sep to Q4 Oct
|  | Conduct annual activities to celebrate International Youth Day, 12 August | [15 empty] | 30000 | [7 empty] | 0 | bar: Q3 Aug
|  | Contribute to national reporting on the relevant SDGs and targets | [14 empty] | 1 | 10000 | [7 empty] | 10000 | bar: Q3 Sep
| Sub total | [24 empty] | 40000
| Conduct a regional symposium for the GCC to showcase the Kuwait model of engagement in the JPO programme and share best practices and lessons learned with prospective donor countries. | Prepare background paper on the Kuwait model | [14 empty] | 1 | 15000 | [7 empty] | 15000 | bar: Q4 Oct to Q4 Dec
|  | Convene regional symposium | [14 empty] | 1 | 35000 | [7 empty] | 35000 | bar: Q4 Dec
| Sub total | [24 empty] | 50000
Total Output 2 | [25 empty] | 110000
Output 3: Comprehensive reinsertion strategy prepared Indicators: 3.1 Reinsertion strategy for former JPOs drafted. Baseline: 3.1 : 0 Targets: 3.1 : 1 | 3.1 Prepare a draft strategy for the appropriate recruitment of former JPOs upon completion of their assignment, in line with national policy goals. | Engage a strategic human resources specialist on a short-term consultancy to draft a reinsertion / talent management strategy including an analysis of the Kuwaiti recruitment mechanisms and relevant policies and legislation, entry-points for recruitment and recommendations on mechanisms to support recruitment of former JPOs in appropriate positions in government, civil society, private sector and academia. | [14 empty] | 1 | 30000 | [7 empty] | 30000 | bar: Q4 Oct to Q4 Dec
| sub total | [24 empty] | 30000
Total Output 3 | [25 empty] | 30000
Output 4: Project implementation and monitoring Indicators: 4.1 Project coordinator hired Baseline: 4.1 : 0 Targets: 4.1 : 1 |  |  |  | Project Manager | [14 empty] | SC | 6 | [5 empty] | 0
|  |  |  | Translation Services | [21 empty] | 0
|  |  |  | GMS | [13 empty] | 0.03 | [7 empty] | 6060
| Sub Total | [24 empty] | 6060
Total Output 4 excluding GMS | [25 empty] | 0
Total Budget | [25 empty] | 202000
Total Budget including 3% GMS | [25 empty] | 208060
|  |  |  | current consultant | Q2 Jun: Contract to be renewd |  |  |  | Advertised
|  |  |  | Under hiring process | Q2 Jun: Activity
Agreed by (signatures):
|  | Secretary General of the Supreme Council for Planning and Development |  |  | Q4 Dec: UNDP Deputy Resident Representative
|  | Dr. Khalid Mahdi |  |  | Q4 Dec: Dima AL-Khatib
Note on B20: Abdullah Kamal: Prepare a TOR for the activity