## 2016 AWP
Project Title: | Joint Programme to Support the Public Authority of Manpower | [7 empty] | Award Number: |  |  |  | 87622 |  |  |  | Total Budget |  |  |  |  | USD 2,412,627 (UNDP 642 K) |  |  | Prepared by:
Project Number: | 00094565 | [7 empty] | Year: |  |  |  | 2016 |  |  |  | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
UNDP
Outcome 3: Kuwait CPD 2015-2018 outcome 3: Governance and institutional management is efficient, transparent, accessible, competitive and accountable
Output 1: Programme management unit established and functional | Activities (as per Atlas AWP) | Sub Activity |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Budget
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
210000
Total Output 1 Budget | [25 empty] | 210000
IOM
Outcome 3: Kuwait CPD 2015-2018 outcome 3: Governance and institutional management is efficient, transparent, accessible, competitive and accountable
Output 2.1: Research programmes and workshops contribute to evidence-based policy, planning, implementation and monitoring within PAM. Baselines: - No research available to support evidence-based policy development; - Limited knowledge of non-market drivers of labour mobility; - Labour Mobility Management Structures not fully aligned with GoK’s labour market and economic development goals. Targets: - Three comprehensive research reports and three dissemination workshops contribute to evidence-based decisions in PAM - PAM authorities officially recognize value of research and support ongoing research to inform policy development; - PAM has greater understanding of how non-market factors impact labour mobility in GoK and recommendations on how to address this; - PAM evaluates and implements at least five of the recommendations to better align labour mobility management structures with economic development objectives. Indicators: - Number of comprehensive research reports produced, endorsed and dissemination workshops that contribute to evidence-based decisions in PAM; - % of workshop participants acknowledging greater understanding of non-market drivers and able to implement knowledge in their day-to-day work; - # of adjustments to PAM procedures carried out to better align with labour market objectives, as per recommendations of report. | Activities (as per Atlas AWP) | Sub activity | Status/Progress | Action | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4 | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Budget |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
| Activity 2.1.1: Undertake the necessary measures for the programme Mobilization - Selection of programme manager, programme technical consultants and assistants; - Nomination of PAM staff focal point to engage Programme implementation; - Establishment of Steering Committee to guide research initiatives. | [24 empty] | 137000 | bar: Q1 Jan to Q1 Feb
| Activity 2.1.2: Comparison and analysis of two labour recruitment corridors to determine demand driven and non-market-driven factors leading to labour mobility's. - Call for Proposals (CfP) and ToRs to identify appropriate research consultant(s) - Select research consultant(s) and approve proposed research methodology - Review draft report - Finalize report - Dissemination workshop | [24 empty] | 68000 | bar: Q1 Jan to Q3 Sep
| Activity 2.1.3: Analysis of GoK Labor Mobility Management Structures and Recommendations for alignment with objectives of 2035 National Vision - CfP and ToRs to identify appropriate research consultant(s) - Select research consultant(s) and approve proposed research methodology - Benchmarking of PAMs permit issuance procedures against regional and international equivalents - Review draft report - Finalize report and recommendations - Dissemination workshop | [24 empty] | 111000 | bar: Q1 Mar to Q3 Sep
| Activity 2.1.4: Scenarios programme of impact of reduction in foreign workers on the Kuwaiti economy and labour force - CfP and ToRs to identify appropriate research consultant(s) - Select research consultant(s) and approve proposed research methodology | [24 empty] | 45000 | bar: Q3 Sep to Q4 Dec
Total Output 2.1 | [25 empty] | 361000
Output 2.2: Workshops, study tour, roundtable, and pilot programme contribute to PAM’s engagement in best practices relating to the fight against human trafficking and the exploitation of foreign workers Baseline: - No available assessment of shelter - No workshops held on shelter management - No exploitation scale for Vots available - Shelter medical SoPs outdated - No national referral mechanism available - No database available in shelter - Shelter staff received no training on psychosocial support -Shelter staff received no training on international best practices in operating a hotline for VoTs - Shelter staff have not received English training courses. - No shelter setup and operations manual available Target: - 1Shelter assessment report issued - 5 PAM staff trained on shelter management - Exploitation scale for VoTs developed - Shelter medical SoPs updated - National referralmechanism developed - database developed for shelter - Shelter are trained on international best prectices in providing psychosocial support to VoTs -Shelter staff receive English training courses -50 Vots trained and reemployed in Kuwait Shelter setup and operations manual developed Indicators: - % of shelter assessment completed. - # of PAM staff trained on shelter management - workshop held (Yes /No) -Exploitation scale developed (Yes/ No) -Exploitation Scale endorsed by PAM (Yes/ No) -Work shop held on Shelter Medical SoPs (Yes/No) -Recommendations on Shelelter Medical SoPs Developed (Yes/ No) - Recommendations on Shelter Medical SoPs endorsed by PAM (Yes / No) - Workshop held on national referral mechanism developed (yes/ no) - National referral mechanism developed (Yes/ No) - National referral mechanism endoresed by PAM and other relevant government entities - Database developed (Yes/No) -Shelter staff trained on operating database (Yes/No) -Worshop Held on Phychosocial support (Yes/No) - Phychosocia support is integrated into shelter operation SoPs (Yes / No) - Worshop held on international best practices in operationg a hotline forVoTs (Yes/ No) -Intenational Best practices in operating otline for VoTs is integrated in shelter SOPs (Yes / No) - Shelter staff complete two levels fo English training (Yes/ No) - # of Vots trained - # of VoTs employed - # of trainings conducted - Shelter setup and operations manual developed for PAM (Yes / No ) - Shelter setup and operations manual endoresed by PAM | Activity 2.2.1: PAM and other relevant GoK officials engage in activities to ensure shelter conditions meet international standards - Assessment of the shelter for runaway workers carried out; - One national workshop conducted to disseminate results of assessment and raise awareness on international standards for shelters; - Study tour to a neighboring country conducted to share experiences, promote technical assistance, and enforce international best practices on shelter management; - Technical roundtable conducted on shelter management to promote dialogue and exchange | [24 empty] | 62000 | bar: Q1 Feb to Q2 May; Q3 Jul to Q3 Aug
| Activity 2.2.2:Prepare logistics and hold workshop to develop and exploitation scale for VoTs. Activity 2.2.3: prepare logistics and hold workshop to develop medical screening procedures and setup Activity 2.2.4: Prepare logistics and hold workshop to develop national referral mechanism for VoTs Activity 2.2.5: Develop and electronic database for shelter and train shelter staff on operating database Activity 2.2.6: Prepare logistics and hold workshop on international best practice in providing phychosocial support to VoTs Activity 2.2.7: Prepare logistics and hold workshop on international best practices in operationg a hotline for VoTs Activity 2.2.8: Enroll staff in English language training Activity 2.2.9: Hold tailored training to support the re-employment of VoTs in Kuwait Activity 2.2.9: drafting, Editing, Printing and Translation of Shelter Setup and Operations Manual | [24 empty] | 100000 | bar: Q3 Jul to Q4 Dec
Total Output 2.2 | [25 empty] | 162000
Total IOM Budget | [25 empty] | 523000
ILO
Outcome 3: Kuwait CPD 2015-2018 outcome 3: Governance and institutional management is efficient, transparent, accessible, competitive and accountable
Output 3: Improving the tripartite participation in the International Labor Standards system and promoting the application of conventions Output 3.1: Kuwait Government and social partners, trained on reporting on ratified and un-ratified ILO Conventions as well as implementing ILO Conventions Baseline: Lack of training to Kuwait Government and social partners, on reporting Target:At least 8 Government, 8 Employers and 8 Workers representatives participated in a Standards training courses in the ILO Training Centre in Turin and Kuwait. Indicator: No of Government, Employers and Workers representatives participated in a Standards training course in the ILO Training Centre in Turin nd Kuwait. | Activities (as per Atlas AWP) | sup activities | Status/Progress | Action | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4 | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
Activity 3.1.1. Hands-on assistance to reps of the relevant institutions on reporting, and practical training and assistance to Employers and workers. | bar: Q1 Jan to Q2 Jun
Output 3.2 Government and Social Partners trained on issues concerning International Labour Standards Baseline: Insufficient capacity related to international labour standards Target: 2 workshops held on the ratification and application of conventions 100, 111, 122, 129,187, and 189 Indicator: No. of Workshops held on the ratification and application of conventions 100, 111, 122, 129,187, and 189. | Activity 3.2.1: Training on ILS on equality and non-discrimination in particular on the Equal Remuneration Convention, 1951 (No. 100) and the Discrimination (Employment and Occupation) Convention, 1958 (No. 111). Activity 3.2.2: Training and labour law review on ILS on employment policy, OSH, LI and domestic workers, in particular Conventions No. 81, 122, 129, 155, 187, 189. Activity 3.2.3: Technical assistance and labor law review . | bar: Q3 Jul to Q4 Dec
Output 3.3 Judges, lawyers and legal educators trained on International Labour Standards and their use in domestic courts decisions. Baseline: Lack of training on international Labour Standards. Target: Three trainers of the Kuwait Institute for Judicial Studies, and 5 judges from Kuwait, 2 from each of other GCC countries trained in an international activity for judges and lawyers in the ILO Training Centre in Turin. Indicator: - No of cases in court proceedings of trained judges. -No of trainers and judges from Kuwait trained in the ILO Training Centre in Turin -No of Information materials produced in Arabic Language | Activity 3.3. 1: Training of trainers through the participation at the inter-regional level activity for judges and lawyers in Turin; Activity 3.3.2: Adaptation and translation of training material | bar: Q2 Apr to Q4 Dec
Output 3.4: Parliamentarians and their advisors trained on ILS to be used as a reference for their legislative reviews and actions. Baseline: No capacity building workshops to parliamentarians held Target: One capacity building workshop held on ILS implementation for parliamentarians Indicator: capacity building workshop held on ILS implementation for parliamentarians(Y/N) | Activity 3.4.1: Training on ILS and legislative action for the Parliamentarians. | bar: Q3 Jul to Q4 Dec
Total Budget Output 3 | [25 empty] | 198533.5
Output 4: Labour Inspection System modernized and effective in line with the ILS and OSH services improved and strengthened. Baseline: Applicable LI system not in line with ILS and OSH. Target: Better inspection system with 80% of inspection reports containing relevant data in compliance with ILS. Indicator: No. of labour inspection reports produced and published containing relevant data in compliance with ILS. Output 4.1:Enforcement Priorities established and Enforcement Plan developed. Basline: 1- No training of a leadership team 2- No enforcement priorities and no existing plan Target: 1-A leadership team of employees of Public Authority of Manpower trained. 2- Needed Enforcement Priorities established and enforcement Plan developed for 24 month period. Indicator: 1- Number of Employees of Public Authority of Manpower leadership team trained. 2-Number of Enforcement Priorities established & Enforcement Plan developed | Activity 4.1.1: Training of Public Authority of Manpower leadership team . Activity 4.1.2: Meeting of Public Authority of Manpower leadership team to establish Enforcement Priorities and to develop Enforcement Plan (including OSH) | bar: Q1 Jan to Q2 Jun
Output 4.2: Labor Inspection Assessment and Recommendations issued Baseline:No existing Labour inspection assessment Target: Assessment and recommendations completed Indicator: % of assessment and recommendations completed | Activity 4.2.2: Prepare assessment and make recommendations on actions | bar: Q1 Jan to Q2 Jun
Output 4.3: Action Plan developed based on assessment’s findings. Baseline: No action plan Target: Action Plan developed based on Assessment and in support of Enforcement Plan. Indicator: % of Action Plan developed | Activity 4.3.1: Action Plan for implementing the recommendations of the assessment is drafted and presented to the Public Authority of Manpower. | bar: Q2 Apr to Q3 Sep
Output 4.4: Actions Plan is Implemented as agreed to by PAM Baseline: No action plan Target: 75% of Enforcement Plan implemented. Indicator: % of Enforcement Plan implemented. | Activity 4.4.1: Actions included in Action Plan are completed consistent with stated timelines and deadlines
Output 4.5: National Occupational Safety and Health Policy, Profile and Programme is produced. Baseline: No existing national OSH profile. Target: OSH Profile and policy produced by PAM. Indicator: % of national OSH policy and profile produced | Activity 4.5.1: Technical Assistance and Advisory Services for the preparation of a national OSH policy, profile and programme in full participation of Public Authority of Manpower, social partners and other stakeholders | bar: Q2 Apr to Q4 Dec
Output 4.6: Labor inspectors trained on basic Occupational Safety and Health and risk assessment. (consistent with Enforcement Priorities and in support of Enforcement Plan and Action Plan). Baseline: Not enough training of inspectors on OSH. Target: PAM inspectors trained on basic OSH and risk assessment Indicator: Number of training courses are conducted on basic OSH and risk assessment | Training courses on the basic occupational safety and health knowledge targeting labor inspectors. (Consistent with Enforcement Priorities and in support of Enforcement Plan and Action Plan).
Output 4.7: Technical capacity of OSH inspectors for monitoring the environmental pollutants in the workplace and using related equipment and facilities are developed. (consistent with Enforcement Priorities and in support of Enforcement Plan and Action Plan). Baseline: No technical capacity of inspectors for monitoring environmental pollutants in the workplace. Target: Six OSH specialists (including women, and potential trainers) receive specialized training on the use of OSH equipment. Indicator: # of OSH specialists (including women, and potential trainers) receive specialized training on the use of OSH equipment. | Activity 4.7.1: Advanced OSH training, including monitoring environmental pollutants in the workplace, and use of relevant equipment, targeting labor inspectors, in collaboration with ITC-Turin, or some specialized centers or institutes in other countries. (consistent with Enforcement Priorities and support of Enforcement Plan and Action Plan) | bar: Q2 Apr to Q4 Dec
Output 4.8: Workers and Employers Representatives’ capacities on LI and OSH issues and relevant ILS developed. (Consistent with Enforcement Priorities and in support of Enforcement Plan.) Baseline: Weak capacity of employers’ and workers’ representatives on LI and OSH. Target: One training course for Workers’ Reps and one for Employers’ Reps are implemented, including 2 women (one from employers’ reps, and one from workers’ reps). Indicator: # of training course for Workers’ Reps and one for Employers’ Reps are implemented, including 2 women (one from employers’ reps, and one from workers’ reps). | Activity 4.8.1: Specific courses for W&E Reps on LI and OSH issues and relevant ILS are developed and implemented. | bar: Q3 Jul to Q4 Dec
Output 4.9: Tools for educating workers and employers’ reps on LI and OSH issues are developed and used. (Consistent with Enforcement Priorities and in support of Enforcement Plan.) Baseline: No existing tools Target: One workers and employers brochure developed on LI and OSH. Indicator: Number of workers and employers brochure developed on LI and OSH. | bar: Q4 Oct to Q4 Dec
Total Budget Output 4 | [25 empty] | 618293.5
Total ILO Budget | [25 empty] | 816827
UNDP
Outcome 3: Kuwait CPD 2015-2018 outcome 3: Governance and institutional management is efficient, transparent, accessible, competitive and accountable
Output 5.1: Gap analysis report performed and disseminated between programme team and PAM members Baselines: 1- No team assembled for the data gathering 2- Random process for gathering data. 3- Corrupted database for gathering and storing data (reading from different databases). 4- No corrective measures taken for feedback on corrupted data form external stakeholders. 5- Random and repeated measurement indicators. 6- Outdated versions of job and economic sectors categorization Targets: 1- Data gathering team established 2- A. Report on current process for gathering data and its effectiveness is issued. 2-B. Process for data gathering and tools is established taking into consideration report generated in 2.A. 3- Database relational design is conducted and data is gathered and stored in one place. 4- Corrupted data is rectified based on feedback from external stakeholders. 5- List of measurement indicators identified and linked to sources. 6- 2014 GCC job classification and ISIC 4 classification of economic sectors is introduced and staff trained. Indicators: 1- Data gathering team established (Y/N) 2-A. Report on current process for gathering data and its effectiveness is issued (Y/N) 2-B % of process implementation. 3-Database relational design is conducted and data is gathered and stored in one place (Y/N) 4- % of rectified corrupted data based on feedback from external stakeholders. 5- # of measurement indicators identified and linked to sources. 6- # of staff trained and using GCC job classification and ISIC 4 classification of economic sectors is introduced and staff trained. | Activities (as per Atlas AWP) | Sub activity | Status/Progress | Action | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4 | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
| 5.1.1: Establish the team from each department in the PAM | [24 empty] | 0 | bar: Q1 Feb to Q1 Mar
| 5.1.2 :Survey of PAM capabilities and review internal process for establishment of report issuance effectiveness | [24 empty] | 0 | bar: Q2 Apr to Q2 May
| 5.1.3 Prepare a TOR for Oracle Database Developer and select candidates. | [24 empty] | 110000 | bar: Q1 Feb to Q2 Apr
| 5.1.4 Collect feedback from outside counterparts on data generated by PAM | [24 empty] | 0 | bar: Q1 Jan to Q1 Feb
| 5.1.5: Team to gather all the data available at all departments to be analyzed for the report | [24 empty] | 0 | bar: Q2 Apr to Q2 Jun
| 5.1.6: Determine the data entry required for digitizing the data | [24 empty] | 0 | bar: Q2 Jun to Q3 Aug
| 5.1.7: Establish a list of all the data sources and formats | [24 empty] | 0 | bar: Q2 Jun to Q3 Aug
| 5.1.8: Establish process of data gathering and tools needed for the monthly process | [24 empty] | 0 | bar: Q3 Sep to Q4 Oct
| 5.1.9: Gather data from IOM and ILO programs to be consolidated in the monthly performance report | [24 empty] | 0 | bar: Q4 Oct
| 5.1.10: Compile a list of all possible measurement indicators | [24 empty] | 0 | bar: Q4 Oct to Q4 Nov
| 5.1.11 Define all data sources | [24 empty] | 0 | bar: Q4 Oct to Q4 Dec
| 5.1.12: Standardize data retrieval at the PAM | [24 empty] | 0 | bar: Q4 Oct to Q4 Dec
| 5.1.13: Data quality and clean up conducted on phases using feedback from outside counterparts and conducted by a task force of PAM staff. | [24 empty] | 0
| 5.1.14: Establish connection with Ministry of Commerce to reflect new economic sector categorization within PAM. | [24 empty] | 0 | bar: Q2 May to Q2 Jun
| 5.1.15: Establish a team withn PAM to link jobs (as per GCC categorization) with economic sectors and deploy on the system. | [24 empty] | 0 | bar: Q3 Jul to Q3 Sep
| 5.1.16: Conduct training for data entry employees on new job categorization linked to economic sectors | [24 empty] | 40000 | bar: Q4 Nov to Q4 Dec
Total Output 5.1 | [25 empty] | 150000
Output 5.2: Indicators established and monthly report produced Baselines: 1- No process for reporting formulated at PAM 2- No reporting team established 3- No statistical tools used to process data 4- No Key Performance Indicators established. 5- No monthly report issued. Targets: 1- Process for reporting formulated and implemented at PAM 2- Reporting team established 3-Statistical tools used to process data are identified and implemented 4-Key Performance Indicators established for Recruitment and Employment Sector. 5- Accurate and timely monthly report is issued Indicators: 1- Process for reporting formulated and implemented at PAM (Y/N). 2- Reporting team established (Y/N) 3-Statistical tools used to process data are identified and implemented (Y/N) 4- Key Performance Indicators established for Recruitment and Employment Sector. (Y/N) 5- A # of errors in data issued in reports 5- B date of issuing every report (by the second week of each following month) 5- C % of satisfaction of management and third parties of issued reports | Activity 5.2.1: determine the methods of reporting, i.e.: dashboards, report cards, biweekly, monthly and yearly, month on month, and year to date. Categorization of the data. | [24 empty] | 0 | bar: Q2 Apr
| Activity 5.2.2: establish departmental reports addressing information in each department. | [24 empty] | 0 | bar: Q2 May to Q2 Jun
| Activity 5.2.3: establish the team that will be trained on compiling of data and issuing of the report. | [24 empty] | 0 | bar: Q2 Apr
| Activity 5.2.4: develop a TOR for a statistician and select candidates | [24 empty] | 60000 | bar: Q1 Feb to Q2 Apr
| Activity 5.2.5: establish who will review the reports, and the decisions to be taken from using the report. | [24 empty] | 10000 | bar: Q2 May to Q2 Jun
| Activity 5.2.6: determine the key performance indicators for the “recruitment and employment sector” that drive performance at the PAM in coordination with Equate CSR program to support the PAM. | [24 empty] | 20000 | bar: Q1 Mar to Q3 Sep; Q4 Dec
Total Output 5.2 | [25 empty] | 90000
Output 5.3: Tools for empowering PAM staff to issue report and capacity building on report issued Baselines: 1- No clear accountabilities and responsibilities established for interpreting data and generating reports 2- No technical competency profiles for the reporting PAM team 3-No training conducted on PAM staff based on competency gaps 4- No training conducted for remaining PAM staff to understand and analyze reports 5- No research roadmap based on reported indicators. Targets: 1- Accountabilities and responsibilities Matrix for the reporting team and Labor Market Research department identified and implemented. 2- Technical competency profiles for the reporting PAM team identified and approved. 3- Training plans are implemented based on competency gaps of staff. 4- 3 Training sessions conducted for remaining PAM staff on analyzing the reports. 5- Research roadmap in place with 1 pilot research implemented based on reported indicators. Indicators: 1-Accountabilities and responsibilities Matrix for the reporting team and Labor Market Research department identified and implemented. (Y/N) 2- Technical competency profiles for the reporting PAM team identified and approved (Y/N) 3- # of reporting staff engaged in training plans based on competency gaps 4- # of training sessions conducted for remaining PAM staff on analyzing the reports. 5- # of pilot research implemented based on reported indicators. 1- No clear accountabilities and responsibilities established for interpreting data and generating reports 2- No technical competency profiles for the reporting PAM team 3-No training conducted on PAM staff based on competency gaps 4- No training conducted for remaining PAM staff to understand and analyze reports 5- No research roadmap based on reported indicators. | Activity 5.3.1: establish a TOR and identify consultants to: | 5.3.1.1 Conduct an assessment to define accountabilities, responsibilities, needed staff, and evaluation of statistical packages needed of the market research department. | [23 empty] | 90000 | bar: Q1 Mar to Q2 Apr
5.3.1.2 Develop technical competency profiles for various positions within identified reporting team. | bar: Q2 May
5.3.1.3 Establish needed training plan for all concerned staff based on competency gaps | bar: Q2 Jun to Q3 Sep
5.3.1.4 Develop a research roadmap and run one pilot study with concerned PAM staff. | bar: Q4 Oct to Q4 Nov
5.3.1.5 Develop linkages with regional and international labor research institutes. | bar: Q4 Dec
Activity 5.3.2: Establish training plan for all staff receiving the reports on how to analyze them and take decisions based upon it. | bar: Q4 Nov to Q4 Dec
Activity 5.3.3: Train PAM staff handling the reporting to issue reports in monthly, and yearly basis | bar: Q4 Oct to Q4 Dec
Total Output 5.3 | [25 empty] | 90000
Total Output 5 Budget | [25 empty] | 330000
Total UNDP Project Cost (including output 1) | [25 empty] | 540000
UNDP GMS 7% | [25 empty] | 37800
Total UNDP | [25 empty] | 577800
Total ILO Cost Including 10% GMS | [25 empty] | 816827
IOM Project Cost | [25 empty] | 523000
IOM GMS 7% | [25 empty] | 36610
Total IOM | [25 empty] | 559610
Total Costs 2016 | [25 empty] | 1954237

## Sheet1
| Initial budget | 2015 Expenditures | 2015 Utilisation % | 2016 Starting Balance | 2016 Expexted Expenditures
IOM | 866700 | 108000 | 12.4611 | 758700 | 523000
ILO | 870040 | 53213 | 6.1162 | 816827 | 816827
UNDP | 642000 | 20312 | 3.1639 | 621688 | 540000
Evaluation | 10000 | 0 | 0 | 0 | 0
AA & AC | 23887 | 0 | 0 | 0 | 0
Total Budget | 2412627 | 181525 | 7.524 |  | 1879827

## Sheet2
Why KISR
• It is a national government institution with good exposure to similar projects with other governmental entities such as the MGRP program in collaboration with World Bank. They also developed the strategy for the public authority for industry and research center. • They have a training center that we can use to run learning solutions identified for all PAM staff covered under the program. This will save the hassle and cost of running needed training programs at hotels and other venues. • Enjoy established international and regional networks of research that can enhance the interpretation of data generated through PAM. • They have a good technical team that enjoy statistical expertise aligned with economy awareness. This is crucial for the success of reporting. • UNDP enjoys a good relationship with KISR as they are involved in many of our projects. • UNDP visited similar institution in Kuwait, however, they provide similar services but might not be detailed enough to cover Kuwaiti Labor Market as they have regional exposure • UNDP had a recommendation from the Central Statistical Bureau on their outputs and deliverables. • The cost might be less than commercial companies providing the same services • Considerable time will be saved if direct contracting process is followed.