## 2018 AWP
Project Title: | Implementation of National Traffic and Transport Sector Strategy |  |  |  |  | Award Number: |  |  |  | 00058316 | [6 empty] | Total Budget |  | 11209215.46 | [5 empty] | Prepared by: | Osama Matri
Project Number: | 00072396 |  |  |  |  | Year: |  |  |  | 2018 | [6 empty] | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | Policy and regulatory economic, social and environmental frameworks are in place to build resilience for inclusive, sustainable growth and development.
Indicative Output(s): | Policies and measures approved and implemented to improve the efficiency and quality of the welfare system..
2018
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1 Capacity of GDT to manage national traffic informaiton developed Indicators: 1.1 Level of Progress in achieving Kuwait Road Accident Data Management System (KRADMS) 1.2 Number of users and and administrators trained on use and integration/configuration of the system Baseline: 1.1 Successful operation/full funcitoing of KRADMS 1.2 35 of GDT cadre trained on use of KRADMS Targets: 1.1 Continued Maintenance and Support for 2 years 1.2 Addtional training for 20 GDTcadre | Complete Maintenance and Training (20% of Training Milestone and 30% of Installation and Maintenance) |  | Ongoing | Provision of Maintenance and Training Services | [12 empty] | 1 | 198549 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 198549 | Professional services | MOI/UNDP | bar: Q1 Jan to Q1 Mar
| Sub Total | [24 empty] | 198549
| 1.3 Manage Maintenance and Support services for server room (Activity 2 MOI) |  | Ongoing | Provision of maintenance and support for the infrastrcutre hosting KRADMS, correspondence, archiving and training programme applications | [12 empty] | 1 | 66000 |  |  | ITB | Milestone in Contarct |  | 72140 | Contractual Services Companies | 66000 | Professional services | MOI/UNDP | bar: Q1 Jan to Q4 Dec
| 1.4 Procure Additional Servers/Capacity to Server Room (Activity 2 MOI) |  | Ongoing | Procurement of Additional Server(2) and Storage (1) including professional services | [12 empty] | 1 | 33805 |  |  | ITB | Milestone in Contarct |  | 72140 | Contractual Services Companies | 33805 | Goods/IT Equipment | MOI/UNDP | bar: Q1 Jan to Q4 Dec
| Sub total | [16 empty] | 99805 | [7 empty] | 99805
Total Output1 | [17 empty] | #REF! | [7 empty] | 298354
Output 2 Technical and Administrative Capcities and Processes of GDT to Support Professional Development and Transition to E Government Enhanced Indicators: 2.1 Level of Progress Achieved in Fully Functioming Correspondence System 2.2 Number of Users Trained in Implementing Correspondence System 2.3 Level of Progress in Achieving Fully Functional Electronic Document Management System (Archiving) 2.4 Number of Users Trained in Implementing Electronic Document Management System (Archiving) 2.5 Level of Progress in Achieving Fully Functioning Electronic Driving License Issuance System 2.6 Number of Users trained on Implementing Electronic Driving License Issuance System 2.7 Electronic Platform/Programme to Manage Training Activities of GDT updated 2.8 Two International Conferences/Exchange of Experience Events attende Baseline: 2.1 Electronic Correspondece System is fully functional 2.2 15 people trained on Electrconic Correspondence System 2.3 Completion of Testing/Piloting Phase of Electronic Document Management System (Archiving) 2.4 4 cadre of GDT receiving general training 2.5 Identification and deployment of Electronic Driving License Issuance System 2.6 0 trained on Electronic Driving License Issuance System 2.7 Completion of testing/piloting phase of Electronic Platform/Programme to Manage Training Activities of GDT 2.8 0 International Conference/Exchange of Exerience Events Identified Targets: 2.1 Electronic Correspondence is fully functional in 45 Offices 2.2 120 cadre of GDT trained in implementation of Electronic Correspondence System 2.3 Fully Functional Electronic Document Management System (Archiving) in all 6 governorates of GDT (14 locations) 2.4 25 cadre of GDT trained on Electronic Document Management System (Archiving) 2.5 Fully Functional Electronic Correspondence System to provide services for citizens and noncitizens 2.6 50 cadre of MOI and GDT trained on implementation of Electronic Driving License Issuance System 2.7 Electronic Platform programme to Manage Training Activities of GDT Implemented 2.8 Particiaption in 1 International Conferences/Exchange of Experience | 2.1 Manage Maintenance and Support Services for electronic correspondence including training of 120 cadre of GDT (Activity 2 MOI) |  | Ongoing | Provision of training, maintenance and support | [12 empty] | 4 | 20200 |  |  | RFQ | Milestone in Contract |  | 72140 | Contractual Services Companies | 80800 | Professional services | MOI/UNDP | bar: Q1 Jan to Q4 Dec
| 2.2 Provision of Correspondence Equipment to 45 offices within GDT locations in all governorates (Activity 2 MOI) |  | Not Started | Provision of Pcs, Scanners, Barcode Printers and Barcode Scanners | [12 empty] | 1 | 87000 |  |  | RFQ | Milestone in Contract |  | 72140 | Contractual Services Companies | 87000 | Goods/IT Equipment | MOI/UNDP | bar: Q1 Jan to Q4 Dec
| Sub total | [16 empty] | 107200 | [7 empty] | 167800
| 2.3 Conducting Confiugration, Testing and Installation of Electronic Document Management System (Archiving) in 14 locations including training (Activity 2 MOI) |  | Ongoing | Provision of testing, configuration, installation and training services | [12 empty] | 1 | 70164 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 70164 | Professional services | MOI/UNDP | bar: Q1 Jan to Q1 Feb
| 2.4 Manage Maintenance and Support services for Electronic Document Management System (Archiving) (Activity 2 MOI) |  | Not Started | Provision of Maintenance and Suppor Services | [12 empty] | 1 | 70164 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 70164 | Professional services | MOI/UNDP | bar: Q1 Mar to Q4 Dec
| 2.5 Procurement of Infrastrcutre for Archiving i.e.20 Scanners for offices in 14 Locations (6 governorates)(Activity 2 MOI) |  | Not Started | Provision of Goods/IT equipment | [12 empty] | 1 | 50000 |  |  | RFQ | Milestone in Contract |  | 72140 | Contractual Services Companies | 50000 | Goods/IT Equipment | MOI/UNDP | bar: Q1 Jan to Q1 Mar
| Sub total | [16 empty] | 190328 | [7 empty] | 190328 | bar: Q1 Jan to Q4 Dec
| 2.5 Install, Configure, Customize and Launch of Beta Version of Electronic Driving License that includes one printer, one kiosk, web portal and mobile (Activity 2 MOI) |  | Ongoing | Provision of IT Services (Configuration, Custmization, and Developmet of Beta Version) | [12 empty] | 1 | 363456 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 363456 | Professional services | MOI/UNDP | bar: Q1 Jan
| 2.6 Operationalize Electronic Driving License System inlcuding operationalization of 15 kiosks, 70 printers and launch of web portal and mobile app(Activity 2 MOI) |  | Not Started | Provision of IT Services to Operationalize eDL system | [12 empty] | 1 | 726912 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 726912 | Professional services | MOI/UNDP | bar: Q1 Feb to Q1 Mar
| 2.7 Provide Onsite Maintenance and Support for Electronic Driving License Issuance System (Activity 2 MOI) |  | Not Started | Provision of Maintenance | [12 empty] | 1 | 363456 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 363456 | Professional services | MOI/UNDP | bar: Q2 Apr to Q4 Dec
| 2.8 Provide IT Infrastrcutre Requirements for Electronic Driving License Issuance System including Warranty and Maintenance |  | Not Started | Provision of IT Goods | [12 empty] | 1 | 750000 |  |  | ITB | Milestone in Contract |  | 72140 | Contractual Services Companies | 750000 | Goods/IT Equipment | MOI/UNDP | bar: Q2 Apr to Q4 Dec
| 2.9 Lease Infrastrutre Requirements for 6 months for Electronic Driving License Issuance System (Activity 2 MOI) |  | Not Started | Provision of IT Goods | [12 empty] | 1 | 150000 |  |  | RFP | Milestone in Contract |  | 72140 | Contractual Services Companies | 150000 | Goods/IT Equipment | MOI/UNDP | bar: Q1 Feb to Q2 Jun; Q3 Aug to Q4 Dec
| Sub total | [16 empty] | 2353824 | [7 empty] | 2353824 | Professional services | MOI/UNDP
| 2.8 Provide Maintenance, Support and Continuous Modification and Training on Electronic Platform for managing GDT Training Activities (Activity 2 MOI) |  | Ongoing | Provide Maintenance, Support and Training | [12 empty] | 1 | 12125 |  |  | RFP | Milestone in Contract |  | 72140 |  | 12125 | Professional services | MOI/UNDP | bar: Q1 Jan to Q2 Jun
| Sub total | [16 empty] | 12125 | [7 empty] | 12125
| 2.9 Participation in International Conferences/Exchange of Experiences (Activity 2 MOI) |  | Not started | [14 empty] | 0 | [7 empty] | 0
| Sub total | [16 empty] | 0 | [7 empty] | 0
Total Output 2 | [17 empty] | 2663477 | [7 empty] | 2724077
| Project Staff (Acitivity 2 MOI) |  |  | Project Staff | [13 empty] | 300000 | [5 empty] | 71405 |  | 300000 | bar: Q1 Jan to Q4 Dec
| Miscellaneous (Activity 2 MOI) |  |  | Sundry | [13 empty] | 20000 | [5 empty] | 74525 |  | 20000 | bar: Q1 Jan to Q4 Dec
| Translator-Northwestern Training Materials |  |  | Short Term Consultant | [13 empty] | 20000 | [5 empty] | 71305 |  | 20000 | bar: Q1 Jan to Q2 Apr
| Mid Term Evaluation (Activity 1) |  |  | Evaluation | [13 empty] | 20000 | [5 empty] | 71205 |  | 20000 | bar: Q1 Jan to Q1 Mar
| Sub Total | [16 empty] | 360000 | [7 empty] | 360000
Total Budget | [25 empty] | 3382431
Total Budget including 3% GMS | [25 empty] | 3483903.93
|  |  |  | Current Contract | [15 empty] | Advertised | bar: Q3 Aug to Q4 Dec
*Proposed Activities |  |  |  | Under hiring process | bar: Q3 Aug to Q4 Dec