## 2018 AWP
Project Title: | Kuwait Environmental Governance Initiative |  |  |  | Award Number: | [10 empty] | Total Budget |  | 2000000 | [5 empty] | Prepared by:
Project Number: | 00091766 |  |  |  | Year: |  |  |  | 2018 | [6 empty] | Fund Number: |  |  |  |  | Donor Number: |  |  | Certified by:
Contributing Outcome (CPD) | Policy and regulatory economic, social and environmental frameworks are in place to build resilience for inclusive, sustainable growth and development
Indicative Output(s): | legal and regulatory capacity developmennt, including on issues of environment
2018
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1: Participation in Multilateral Environmental Agreements and internationally agreed development goals strengthened. Indicators: 1.2 Number of capacity development measures designed for meweting obligations under signed and ratified MEAs for Kuwait 1.4 Number of SDGs with nationally appropriate indictors measured to assess progress on SDGs environment pillars. Baseline: 1/0 Targets: 3/7 | 1.1 Conduct capacity sefl-assessment (NCSA) to identify capacity building needs relating to MEAs, including national and local needs and cross cutting thematic issues | International consultant recuited to conduct prepare detailed workplan and TORs for local consultants | Establish project NCSA operational working group | [12 empty] | 1 |  | IC | 12 months |  |  |  |  | International consultant | 28000 | Reports on three thematic profiles pertaining to the NCSA | UNEP | bar: Q1 Jan
[24 empty] | Travel | 3000
|  |  | Prepare detailed workplan and TORs for consultants | [12 empty] | 3 |  | IC | 6 months |  |  |  |  | Local consultants | 105000 | bar: Q1 Jan to Q1 Feb
[24 empty] | Miscellaneous | 70000
| Sub Total | [23 empty] | 206000
| 1.2 Develop National MEA action plan with measures to address achievement gaps including UNFCCC, UNCBD, UNCCD | Stocktaking and thematic profiles developed | Recriutement of local consultants | [13 empty] | 52500 | IC | [5 empty] | Local consultants | 11200 | Draft National Report | UNEP | bar: Q1 Jan to Q1 Mar
|  |  | national consultation and in depth analysis pf priority areas | [21 empty] | 0 | bar: Q2 Apr to Q2 Jun
| Sub total | [23 empty] | 11200
| 1.3 Organize natioinal capacity building workshops on MEA implementation and readiness for new intiatives to implement the SDG environmental pillars including SDG 13 |  | Workshops on the three conventions | [12 empty] | 3 | [7 empty] | Miscellaneous | 150000 | National workshops on the three convensions | UNEP | bar: Q2 May; Q3 Sep; Q4 Nov
0
| Sub total | [23 empty] | 150000
| 1.4 Support for designing National Adaptation Plan and related intiatives linkied to water, city planning and other sectors |  | technical support provided based on the outcomes of NCSA and 2nd communication assessment | [21 empty] | 0 |  | UNEP | bar: Q3 Jul to Q4 Dec
|  |  | TORs prepared for internatonal consultan | [14 empty] | IC | [5 empty] | International consultant | 150000 | Report on a national adaptation plan.
| Sub Total | [23 empty] | 150000
| 1.5 Undertake assessment of challenges and opportunities for achievement of the SDG environmental pillars in Kuwait and prepare national SDG reporting | International consultant recuited to conduct assessment and intial SDG indicators workshop underway | activity under implementation. first mission in february, first draft of assessment report end of march | [12 empty] | 1 | 63300 | IC | 6 months |  | Report on localized SDG environmental indicators for Kuwait |  |  |  | 63300 | Report on indicator development and national reporting of SDGs | UNDP | bar: Q1 Jan to Q3 Jul
|  | First workshop to be completed on environmental SDGs | Workshop organized with the support of the regional hub on the environmental SDGs | [12 empty] | 1 | 14500 | Regional team support | 3 days | [5 empty] | 14500 | bar: Q1 Feb
|  |  | SDG data portal to be prepared and integrated in Emisk | [13 empty] | 50000 | RFP | 6 months | [5 empty] | 50000 | Application integrated within Emisk for SDG data reporting | bar: Q3 Aug to Q4 Dec
| Sub total | [15 empty] | 120800 | [7 empty] | 77800
| 1.6 Design and implement awareness raising progranne on priority environmental issues includng through proper campaigns, workshops and media outreach | RFP prepared for local media ffirms | contracting of firm | [12 empty] | 1 | 100,00 | RFP | 9 months |  | Media campaign |  |  |  | 100000 | awareness material ( vidoe and radio ads) on the environment law of Kuwait | UNDP | bar: Q1 Jan to Q4 Dec
0
| Sub total | [15 empty] | 100,00 | [7 empty] | 100000
Total Output1 | [24 empty] | 695000
Output 2: Environmental Information Systems Enhanced Indicators: Number of sectoral environmental databases supported and aligned to KEPA's Emisk Baseline: 3 Targets: 6 | 2.1 Conduct gap analysis and user survey to assess the state and usage of existing EIS plartforms for decision making processes to implement EPL | Gap analysis underway to identify data and software usage within KEPA and key stakeholders | Activity under implementation | [13 empty] | 28500 | IC | 3 months | [5 empty] | 28500 | Report on gaps and recommedations for enhancement of EIS | UNDP | bar: Q1 Jan to Q1 Feb
|  |  | Workshop | [12 empty] | 1 | 4000 | [7 empty] | 4000 | bar: Q1 Feb
| Sub total | [15 empty] | 32500 | [7 empty] | 32500
| 2.2 Identify bottlenecks and recommend system enhancements to current EIS infrastructure, system administration and security requirements, and connectivity. | To completed as part of the gap analysis | Activity under implementation under one contract with activity 2.1 | [21 empty] | 0 | Same as above | UNDP | bar: Q1 Jan to Q1 Feb
0
| Sub total | [23 empty] | 0
| 2.3 Enhance Emisk IT capacity to support required EIS infrastructure, system administration and security requirements and connectivity | Builds on the findings of the gap analysis and providing road map for enhancing EIS | Prepare TORs for consultant and contract | [13 empty] | 70000 | IC | 6 months | [5 empty] | 70000 | Same as above | UNDP | bar: Q1 Mar to Q4 Dec
| Sub Total | [15 empty] | 70000 | [7 empty] | 70000
| 2.4 Identify and put in place new metrics and indicators for tracking perforamce on EPL | International goverance specialist recruited to develop enforcement and compliance indicators | Conduct detailed analysis of reglulatory framework | [13 empty] | 100000 | IC | 5 months | [5 empty] | 100000 | Report on indictors for tracking EPL implementaion (enforcement and compliance) | UNDP | bar: Q1 Feb to Q3 Jul
|  |  | Provide capacity building for monitoring enforcement and compliance and implementation of action plan | [13 empty] | 50000 | IC | 4 months | [5 empty] | 50000 | workshops and training for key stakeholders | bar: Q3 Sep to Q4 Dec
|  |  | Workshops | [12 empty] | 2 | 9000 | [7 empty] | 9000 | workshops | bar: Q2 May; Q4 Oct
| Sub Total | [15 empty] | 159000 | [7 empty] | 159000
| 2.5 Train KEPA, Central Statistics Bureau and stakeholders on data collection including data validity and reliability and statistical analysis related to environmental indicators | To be completed in the second half of the year | Activity will be part of the TORs for 2.3 | [13 empty] | 30000 | IC | 6 months | [5 empty] | 30000 | On the job training and material | UNDP | bar: Q3 Aug to Q4 Dec
|  |  | Workshops | [12 empty] | 2 | 9000 | [7 empty] | 9000 | bar: Q3 Sep; Q4 Nov
| Sub Total | [15 empty] | 39000 | [7 empty] | 39000
| 2.6 Document and share success stories and good practice in national indicators systems for tracking achieving SDG environmental pillars. | Part of the SDG activity identified in output 1 | activity is part of the TORs for 1.5 | [22 empty] | Same as 1.5 | UNDP | bar: Q1 Jan to Q2 Jun
|  |  | workshops | [12 empty] | 1 | 5000 | [7 empty] | 5000 | bar: Q2 May
| Sub total | [15 empty] | 5000 | [7 empty] | 5000
Total Output 2 | [24 empty] | 306000
Output 3 Indicators: Baseline: Targets: | [24 empty] | 0
0
| sub total | [23 empty] | 0
0
0
0
| Sub total | [23 empty] | 0
0
0
| Sub total | [23 empty] | 0
0
0
| Sub total | [23 empty] | 0
Total Output 3 | [24 empty] | 0
Output 4 Indicators: Baseline: Targets: | [24 empty] | 0
0
0
0
0
0
Total Output 4 | [24 empty] | 0
|  |  | Project Manager | [13 empty] | 113000 | [7 empty] | 0 | bar: Q1 Jan to Q4 Dec
|  |  | Project Assistant | [13 empty] | 28000 | [7 empty] | 0 | bar: Q1 Jan to Q4 Dec
|  |  | Evaluation | [13 empty] | 20000
| Project Administration Costs |  | GMS 0.3% | [13 empty] | 60000 | [7 empty] | 30030 |  |  | x x
| Sub Total | [15 empty] | 221000 | [7 empty] | 30030
Total Output 5 excluding GMS and Evaluation | [24 empty] | 0
Total Budget | [24 empty] | 1001000
Total Budget including 3% GMS | [24 empty] | 1031030
|  |  | current consultant | [15 empty] | Advertised | bar: Q3 Aug to Q4 Dec
Under hiring process | bar: Q3 Aug to Q4 Dec