## 2018 AWP
Project Title: | Support the State Audit Bureau to Develop a Performance Management Framework |  |  |  |  | Award Number: |  |  |  | 66516 | [6 empty] | Total Budget |  | 1223566.87 | [5 empty] | Prepared by: | Bashar Marafie - Programme Associate
Project Number: | 00082681 |  |  |  |  | Year: |  |  |  | 2018 | [6 empty] | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | Human development accelerated through high-caliber human capital and increased social empowerment.
Indicative Output(s): | Strategic plans for strengthening human capital developed with focus on building capacity and career advancement, with special attention to women and youth.
2018
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1 Improved legal and institutinal framework to facilitate performance effectiveness Indicators: 1.1 Statuts of the development and implementation of performance management framework (Scale 0: no framework plan in place - 1: avalability of an operational performance management framework) 1.2 Number of government sectors adopting performance management and monitoring systems 1.3 Number of agreed KPIs with targets and owners for each sector Baseline: 1.1 :0 1.2 :0 1.3 :0 Targets: 1.1 :1 1.2 :3 1.3 :15 | 1.1 Assess the "As-is" situation of the Performance Management, monitoring and control mechanisims at the State Audit Bureau and the selected "Pilot" Government sectors/entities from a people process and technology perspective | 1.1.1 Conduct a review of the currect SAB and Government entity strategic plans and capabilities | Complete | [24 empty] | PWC
|  | 1.1.2 Provide analysis on linkages and gaps between the strategic plans/capacities and performance management for the Kuwait Vision 2035 and the Kuwait National Development Plan (KNDP) 2015-16/-2018/2019. | Complete | [24 empty] | PWC
|  | 1.1.3 Evaluation of international best practices, which could be applied to the Kuwaiti context. | Complete | [24 empty] | PWC
| Sub Total | [24 empty] | 0
| 1.2 Design a Balanced Scorecard-Based Performance Management Framework | 1.2.1 Develop a work-plan for the subsequent development process of a responsive Performance Management Framework | Complete | [24 empty] | PWC
|  | 1.2.2 Create a Performance Management Framework | Complete | [24 empty] | PWC
| Sub total | [24 empty] | 0
| 1.3 Develop the Key Performance Indicators (KPIs) and Reporting Framework | 1.3.1 Develop KPIs and for three key sectors (education, health and oil) | ongoing | [13 empty] | 1 | 246945 | [7 empty] | 246945 |  | PWC | bar: Q1 Jan to Q1 Mar
|  | 1.3.2 Organize workshops around the development | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q1 Mar
|  | 1.3.3 Develop baseline reporting and performance management mechanisms | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q1 Mar
| Sub total | [24 empty] | 246945
| 1.4 Support the implementation and operation of the new National Performance Management Operating Model and System at the State Audit Bureau and Train Staff | 1.4.1 Conduct training awareness orientation for State Audit Bureau employees about performance monitoring processes and values | ongoing | [13 empty] | 1 | 197694 | [7 empty] | 197694 |  | PWC | bar: Q1 Jan to Q2 Jun
|  | 1.4.2 Develop the system within the state Audit Bureau. | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q2 Jun
|  | 1.4.3 Prepare training material/schedules to train State Audit Bureau’s personnel on how to use the tool | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q2 Jun
|  | 1.4.4 Conduct the training programme for SAB | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q2 Jun
| Sub Total | [24 empty] | 197694
| 1.5 Support the implementation and operation of the new National Performance Management Operating Model and System at the selected pilot sectors (Education, Health and Oil and Gas) and train staff | 1.5.1 Provide required awareness and orientation for the pilot entities employees about performance monitoring processes and value | ongoing | [14 empty] | 0 | [7 empty] | 0 |  | PWC | bar: Q1 Jan to Q2 Jun
|  | 1.5.2 Develop and rollout the system within the entities | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q2 Jun
|  | 1.5.3 Conduct training (along with the implementing partner if applicable) | ongoing | [24 empty] | PWC | bar: Q1 Jan to Q2 Jun
| Sub total | [24 empty] | 0
Total Output1 | [25 empty] | 444639
Output 2: Improved internal audit standards for bringing a systematic disciplined approach to evaluate and improve the effectiveness of risk management control and government processes Indicators: 2.1 Status of the developement of "The Internal Auditors Guides" manual(s) (0: no manual - 1: manual is developed) 2.2 Status of the developement of "The Auditors Quality Assurance and Monitoring and Evaluatation System Guides" manual(s) (0: no manual - 1: manual is developed) 2.3 Number of persons with enhance capacities for the implementation of the internal audit process 2.4 Number of persons with enhance capacities for the implementation of the monitoring and evaluation system of the internal audit process 2.5 Number of persons with enhance capacities of train-the-trainer for the implementation, monitoring and evaluation system of the internal audit process Baseline: 2.1 : 0 2.2 : 0 2.3 : 0 2.4 : 0 2.5 : 0 2.1 : 1 2.2 : 1 2.3 : 300 2.4 : 300 2.5 : 35 | 2.1 Conduct Gap analysis assessment and develop action plans | 2.1.1 Identify and prioritize governmental entities based on their functional activities and pressing needs for internal audit and control and select pilot entities of approximate 35 governmental entities | [14 empty] | 1 | 131270.4 | [7 empty] | 131270.4 |  | LTA | bar: Q1 Mar to Q2 Apr
|  | 2.1.2 Conduct Gap analysis assessment and development of action plans for the identified pilot governmental entities | [23 empty] | 0 |  | LTA | bar: Q1 Mar to Q2 Apr
| Sub total | [24 empty] | 131270.4
| 2.2 Conduct Risk analysis and revision of the existing practice and regulations of Internal Audit mechanisms | [15 empty] | 1 | 131270.4 | [7 empty] | 131270.4 |  | LTA | bar: Q1 Mar to Q2 Jun
| Sub total | [24 empty] | 131270.4
| 2.3 Develop and implement a Monitoring and evaluation mechanism | 2.3.1 Design a monitoring and evaluation system that enables SAB to ensure quality of governmental operational procedures. | [23 empty] | 0 |  | LTA | bar: Q1 Mar to Q2 Jun
|  | 3.3.2 Develop an action plan and support the implementation of the monitoring and evaluation designed system | [23 empty] | 0 |  | LTA | bar: Q1 Mar to Q2 Jun
| Sub total | [24 empty] | 0
| 2.4 Implement Internal audit and its permanent development based on the International standards | [26 empty] | LTA | bar: Q1 Mar to Q2 Jun
| Sub total | [24 empty] | 0
| 2.5 Produce Internal Audit manuals and guidelines for Auditors | 2.5.1 Develop "The Internal Auditors Guides” for GAAIA Auditors | [14 empty] | 1 | 196905.6 | [7 empty] | 196905.6 |  | LTA | bar: Q1 Mar to Q2 Jun
|  | 2.5.2 Develop “The Auditors Quality Assurance and Monitoring and Evaluation System Guide” for SAB Auditors. | [25 empty] | LTA | bar: Q1 Mar to Q2 Jun
| Sub total | [24 empty] | 196905.6
| 2.6 Develop and implement Capacity building plan for the development, implementation, monitoring and evaluation internal audit system including the production of required manuals and reporting templates. | 2.6.1 Conduct Capacity building trainings and workshops for Auditors on Internal Audit SOPs | [14 empty] | 1 | 196905.6 | [7 empty] | 196905.6 |  | LTA | bar: Q3 Sep to Q4 Dec
|  | 2.6.2 Conduct Capacity building trainings and workshops for Auditors on Internal Audit Quality Assurance and monitoring and evaluation system | [25 empty] | LTA | bar: Q3 Sep to Q4 Dec
|  | 2.6.3 Conduct train-the-trainer Auditors on Internal Audit SOPs and the Internal Audit Quality Assurance and monitoring and evaluation system | [25 empty] | LTA | bar: Q3 Sep to Q4 Dec
| Sub total | [24 empty] | 196905.6
Total Output 2 | [25 empty] | 656352
Output 3: Project Administration | Project Administration Costs |  |  | Project Staff | [13 empty] | 7300 |  | 9 | [5 empty] | 65700 | bar: Q2 May to Q4 Dec
|  |  |  | Miscellaneous | [13 empty] | 2000 |  | 1 | [5 empty] | 1238
|  |  |  | Evaluation | [13 empty] | 20000 |  | 1 | [5 empty] | 20000
|  |  |  | GMS | [13 empty] | 0.03 | [7 empty] | 35637.87 |  |  | x x
| Sub Total | [24 empty] | 86938
Total Output 3 excluding GMS | [25 empty] | 86938
Total Budget | [25 empty] | 1187929
Total Budget including 3% GMS | [25 empty] | 1223566.87
|  |  |  | current consultant | Q2 Jun: Contract to be renewed |  |  |  | Advertised
|  |  |  | Under hiring process | Q2 Jun: prospective consultant
| On Behalf of GSSCPD |  | Dr. Khalid Mahdi |  | Q2 Jun: On Behalf of SAB:; Q4 Oct: Dr. Adel Sarawi |  |  |  |  | On Behalf of UNDP_Kuwait: |  | Dima Al-Khatib
|  |  | Secretery General of the Supreme Council of Planning and Develoment |  | Q1 Jan: Signature:; Q4 Oct: Acting Chairman of the State Audit Bureau |  |  | Signature |  |  |  | Deputy Resident Representative |  |  | Signature: