## 2018 AWP
Project Title: | Youth Empowerment in Kuwait |  |  |  |  | Award Number: |  |  |  | 100028 | [6 empty] | Total Budget |  | 787950.00 $ | [5 empty] | Prepared by: | Najat AlSayegh - Project Coordinator
Project Number: | 00103195 |  |  |  |  | Year: |  |  |  | 2018 | [6 empty] | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | Human development accelerated through high-caliber human capital and increased social empowerment.
Indicative Output(s): | Strategic plans for strengthening human capital developed with focus on building capacity and career advancement, with special attention to women and youth.
2018
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1 Young Kuwaiti men and women empowered to be positive and active agents of change at the national, regional and international levels Indicators: 1.1 A national policy for youth approved and adopted by government 1.2 Level of involvement of youth and partners in the formulation of the national youth policy 1.3 Communication and outreach strategy for the implementation of the youth policy developed and staff trained on translating it into action.7 Baseline: 1.1 :0 1.2 :0 1.3 :0 Targets: 1.1 :2 1.2 :80% 1.3 :2 | 1.1 Support the development and formulation of national youth policy in line with the Kuwait National Development Plan (KNDP) priorities and aligned with the respective SDGs | Review other counties’ National Youth Policies and international best practices including UN guidelines, considering some reference instruments as WPAY and the recommendations of the Global Initiative for Decent Jobs for Youth, the Convention on the Rights of Persons with Disabilities, UNFPA best practices among others. | Ongoing | [13 empty] | 1 | 51421.2 | UN to UN | [6 empty] | 51421.2 |  | UNFPA | bar: Q1 Feb to Q2 Jun
|  | Youth segmentation and stakeholders analysis | Ongoing | [13 empty] | 1 | 10500 | UN to UN | [8 empty] | UNFPA | bar: Q1 Feb to Q2 May
| Sub Total | [24 empty] | 51421.2
| 1.2 Support in identification of key interventions in the form of UN system wide review of the drafting of the national youth policy including based on its best practices and lessons learned | Map out different stakeholders, including youth organizations and NGOs to ensure inclusion in the youth policy and all social population groups. | Ongoing | [13 empty] | 1 | 51421.2 | UN to UN | [6 empty] | 51421.2 |  | UNFPA | bar: Q1 Feb to Q2 Jun
| Sub total | [24 empty] | 51421.2
| 1.3 Prepare a communication strategy and action plan to enhance networking for the implementation of the national youth policy. |  | Planned | [13 empty] | 2 | 35000 | [7 empty] | 70000 | bar: Q3 Jul to Q3 Aug
| Sub total | [24 empty] | 70000
| 1.4 Establish a multi-stakeholder guidance and oversight board to manage implementation of the action plan and communication strategy |  | Planned | [13 empty] | 2 | 20000 | [7 empty] | 40000 | bar: Q3 Jul to Q3 Aug
| Sub Total | [24 empty] | 40000
| 1.5 Train the staff of the Ministry on communications and networking skills |  | Planned | [13 empty] | 2 | 35000 | [7 empty] | 70000 | bar: Q3 Sep to Q4 Oct
| Sub total | [24 empty] | 70000
| 1.6 Set up a detailed database of partners and donors |  | Planned | [13 empty] | 1 | 10000 | [7 empty] | 10000 | bar: Q2 May to Q3 Jul
| Sub total | [24 empty] | 10000
Total Output1 | [25 empty] | 292842.4
Output 2: Capacity of MoSYA and PAY is strengthened to deliver services in a timely, efficient and effective manner Indicators: 2.1 Institutional and individual gaps identified within the MoSYA and YPA to effectively engage with youth and respond to their needs and priorities. Baseline: 2.1 : 0 Targets: 2.1 :2 | 2.1 Conduct capacity assessment of the MoSYA and YPA and Formulate a capacity development implementation plan based on the results of the assessment |  | Ongoing | [13 empty] | 1 | 92821 | UN to UN | [6 empty] | 92821 |  | UNFPA | bar: Q1 Mar to Q2 Apr
| Sub total | [24 empty] | 92821
| 2.2 Implement the plan based on the results of the assessment |  | Planned | [13 empty] | 1 | 25000 | UN to UN | [6 empty] | 25000 | bar: Q2 May to Q3 Jul
| Sub total | [24 empty] | 25000
| 2.3 Support development of an expertise and talent roster on youth development to advance efforts in the field of youth development in Kuwait |  | Ongoing | [13 empty] | 1 | 25000 | [7 empty] | 25000 |  | UNDP | bar: Q1 Jan to Q1 Mar
| Sub total | [24 empty] | 25000
Total Output 2 | [25 empty] | 142821
Output 3: Innovative approaches at MoSYA and PAY are in place to respond to the needs and priorities of young Kuwaiti men and women Indicators: 3.1 Number of innovative programmes launched. 3.2 Age and Gender-disaggregate data and indicators 1- developed and 2- published 3.3 Institutionalized volunteerism and leadership programmes initiated. Baseline: 3.1 :0 3.2 :0 3.3 :0 Targets: 3.1 : 1 3.2 : 1 3.3 : 2 | 3.1 Two technical papers to support the Kuwaiti government as they integrate the youth related SDGs into the national and local strategies and policies. |  | Ongoing | [13 empty] | 1 | 57370.4 | UN to UN | [6 empty] | 57370.4 |  | UNFPA | bar: Q1 Feb to Q3 Aug
| sub total | [24 empty] | 57370.4
| 3.2 Provide two effective, demand-driven, content-specific and evidence-based studies informing Kuwaiti policy and advise on the linkages between the State Vision Kuwait 2035, the Five- year reform program to improve the quality of General Education (2015-2020) and respective SDG's. |  | Ongoing | [13 empty] | 1 | 57366.4 | UN to UN | [6 empty] | 57366.4 |  | UNFPA | bar: Q1 Feb to Q3 Aug
| Sub total | [24 empty] | 57366.4
| 3.4 provide technical expertise for the establishment of a national youth volunteer scheme to be implemented through the Ministry |  | Ongoing | [13 empty] | 1 | 30000 | UN to UN | [6 empty] | 30000 |  | UNV | bar: Q1 Jan to Q2 May
| Sub total | [24 empty] | 30000
Total Output 3 | [25 empty] | 144736.8
Output 4: Kuwait is well positioned as a regional and global leader on youth development Indicators: 4.1 Participation in Number of UN youth related regional and global events 4.2 Number of events and activities positioning Kuwait regionally and globally. Baseline: 4.1 : 0 4.2 : 0 Targets: 4.1 : TBD 4.2 : 11 | 4.1 Support positioning Kuwait globally through establishing UN youth delegates program | Membership in the UN Youth assembly as an active state member, participation in youth related events | Planned | [13 empty] | 2 | 35300 | [7 empty] | 70600 | bar: Q3 Aug to Q4 Dec
70600
Total Output 4
|  |  | Ongoing | Project Coordinator | [13 empty] | 7000 |  | 12 | [5 empty] | 84000
|  |  |  | Miscellaneous | [13 empty] | 10000 |  | 1 | [5 empty] | 10000
|  |  |  | Evaluation | [13 empty] | 20000 |  | 1 | [5 empty] | 20000
| Project Administration Costs |  |  | GMS | [13 empty] | 0.03 | [7 empty] | 22950.006 |  |  | x x
| Sub Total | [24 empty] | 114000
Total Output 5 excluding GMS and Evaluation | [25 empty] | 114000
Total Budget | [25 empty] | 765000.2
Total Budget including 3% GMS | [25 empty] | 787950.206
|  |  |  | current consultant | [15 empty] | Advertised | bar: Q3 Aug to Q4 Dec
Under hiring process | bar: Q3 Aug to Q4 Dec