# Fostering Youth Resiliency - Annual Work Plan

Year: 2014

| EXPECTED OUTPUTS And baseline, associated indicatorsand annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1 Civil Society Organizations strengthened and their role expanded | 1. Project Evaluation to assess project activities in previous phase - Recruit Project Evaluator - Draft Evaluation Report |  | x |  |  | Kuwait Red Crescent Society and UNDP (Project Evaluation Specialist) | KNPC and UNDP Cost Sharing Agreement | Consultant fees | $6,000 |
|  | 2. Develop a violence prevention and resilience based intervention training program (theoretical and practical) - Recruit Psychologist - Psychology and Sociologist to develop a training kit for the intervention mechanism |  | x |  |  | Kuwait Red Crescent Society and UNDP (Sociologist and Psychologist) | KNPC and UNDP Cost Sharing Agreement | Psychologist Consultant Fees Sociologist Consultant Fees | $7,100 $8,875 |
|  | 3. Train 30 social workers from the Ministry of Education, to be youth resilience professional trainers - Identify schools with the Ministry of Education for trainees and student cases - Conduct 2 training of trainers (ToT) workshops for specialized social workers and psychologists from the Ministry of Education |  | x | x |  | Kuwait Red Crescent Society and UNDP | KNPC and UNDP Cost Sharing Agreement | Workshop Costs (Consultancy costs and catering) | Each workshop $12,425 Total cost of two workshops = $24,850 |
|  | 4. Pilot implementation & Assessment of the planned intervention Model - Resilience intervention implemented in at least 4 schools - Implementation assessment report developed |  |  | x | x | Kuwait Red Crescent Society and UNDP (Sociologist) | KNPC and UNDP Cost Sharing Agreement | Sociologist Costs (final deliverable) Intervention Misc. costs | $8,875 $12,425 |
| Output 2 Specialized awareness campaigns and programmes developed Baseline: Public awareness level is low, increasing incidence of violence in schools Indicators: Number of schools visited, Number of students reached, Number of materials printed Targets: Decrease the level of violence and risk behaviour by 50% | 1. Organize a minimum of 4 awareness raising sessions against violence in selected schools | x | x | x | x | Kuwait Red Crescent Society and UNDP | KNPC and UNDP Cost Sharing Agreement |  | Fully funded by the donor separately |
|  | 2. Materials printed and disseminated - pamphlets printed - banners and certificates of participation printed - 10 media interviews by KNPC 3. Organize National Youth Day event. | x | x | x x | x | Kuwait Red Crescent Society and UNDP Kuwait Red Crescent Society, Kuwait National Petroleum Company and the UNDP | KNPC direct billing for the entire duration of the project. KNPC and UNDP Cost Sharing Agreement | Event Fees | Fully funded by the donor separately To be decided |
| Project Coordinator |  |  |  |  |  |  |  |  | $61,887 |
| Misc. |  |  |  |  |  |  |  |  | $5,677 |
| Project Direct Costs |  |  |  |  |  |  |  |  | $135,689 |
| GMS (7%) |  |  |  |  |  |  |  |  | $9,498.23 |
| TOTAL |  |  |  |  |  |  |  |  | $145,187.23 |