# Annual Work Plan for The “Support To The CSB” Project

Year: 2014

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: National statistical tools and information systems developed Baseline: basic information infrastructure exists and needs maintenance and upgrading Indicators: 1-Statistical information infrastructure capacity, reliability, efficiency and results enhanced 2- Road map to enhance statistical data flow between CSB & national institutions developed to inform the development of relevant policies Targets: To upgrade the CSB Statistical information infra-structure Related CP outcome: KWT_OUTCOME1.5 National planning institutions capable of fulfilling the strategic planning role | Activity result 1.1: Information technology infrastructure of the CSB developed -Action 4: The expert in Global Geospatial Information Management (GIS) to continue developing a statistical-spatial framework in national statistical systems | X | X | X X X X | X X X X | CSB with close consultation with GSSCPD | GSSCPD | Consultant (Software engineer)= =7,000*2 months =14,000 Consultant (Information system)= 8,000*2 months = 16,000 Information Specialist (GIS) (Jasim ) = 9,800*12 months= 117,600 | $14,000 $16,000 $117,600 |
|  |  |  |  | X X | X X | National Institutions and CSB with close consultation with GSSCPD | GSSCPD | Consultant (Statistical.A&M)= 9,000*2 months= 18,000 | $18,000 |
|  | Activity result 1.2: Transition from SNA 1993 to SNA 2008. The development of the SAM for national accounts for the period 2007-2012 -Action 1: The expert in national accounts is to Identify National Accounts and other economic data between 2007-2012 for the SAM -Action 2: review, update and advertise the SAM RFP -Action 3:Develop the institutional agreements needed for the SAM with KISR & GSSCPD - Action 4: An expert in statistical quality assurance of National Accounts to ensure the quality of the statistical data produced | X X | X X | X X X X | X X X X | CSB with close consultation with GSSCPD | GSSCPD | Consultant (N. Acc.) (Kevin) 13,000*12 months = 156,000 Consultant (N. Acc QA) (Khalid) = 14,000*12 months= 168,,000 | $156,000 $168,000 |
|  | Activity result 2.3: develop new and enhance existing national development indicators to provide better quality support to the new national development plan - Action 2: The 2 experts in International trade are to review, update, upgrade and report on national accounts -Action 4: The expert in ICT is review, enhance and report on the national indicators of ICT | X X | X X | X X X X | X X X X | CSB with relevant Ministries and institutions, in close consultation with GSSCPD | GSSCPD | Consultant (House hold expenditures) = 8,000*2 months= 16,000 Consultant (Inter. Trade1) 13,000*12 months = 156,000 (Abdessalam) Consultant (Inter. Trade2) 12,000*12 months = 144,000 (Bulent) Consultant (Labour1)= 9,750*12 months = 117,000 (Salaheddin) Consultant (Labour2)= 9,000*2 months = 18,000 Consultant (ICT)= 8,500*12 Months = 120,000 (Emad) | $16,000 $156,000 $144,000 $117,000 $18,000 $102,000 |
|  | -Action 5: The expert in sampling is to ensure the enhancement of the quality of sampling processes and conduct surveys -Action 6: The expert in Demography is to enhance the processes of and conduct the national census and to review of the 2010 assessment of government entities focus groups | X X | X X | X X X X | X X X X | CSB with close consultation with GSSCPD | GSSCPD | Consultant (Sampling)= 14,000*12 months= 153,500 (Hassan) Consultant (Demography)= 12,000*12 months= 144,000 (Yosr) Consultant (Gender)= 7,000*2 months= 14,000 Consultant (Environment)= 9,000*2 months= 18,000 | $168,000 $144,000 $14,000 $18,000 |
| Output 2: Capacity of the Central Statistics Office developed Baseline: Indicators: 1-Outcome evaluation conducted 2- New project document developed and signed Targets: To enhance the support provided to the development of CSB capacity to realize its mandate Related CP outcome: KWT_OUTCOME1.5 National planning institutions capable of fulfilling the strategic planning role Related CP outcome: KWT_OUTCOME1.5 National planning institutions capable of fulfilling the strategic planning role | Activity result 2.1: Assess the impact and efficiency of the project and to redirect it strategically -Action1: cost sharing the recruitment of an expert in programme evaluation To undertake an independent evaluation of the overall democratic governance portfolio impact -Action2: Recruit a project manager to manage the day to day project implementation activities and To develop new project document in alignment with NMRDP, CPD, UNDPSP and CSB’s national, regional and international commitments -Action 3: Undertake an overall staff capacity assessment and develop and initiate the implementation of a full capacity building plan for CSB staff with special focus on use of technical tools, strategic planning and mentoring and evaluation for results -Action 4: Provide on the job technical training to relevant CSB staff | X | X | X X X X | X X X X X | CSB with close consultation with PM & CSB with close consultation with GSSCPD PM & CSB with close consultation with relevant project consultants | GSSCPD | Contract for Outcome evaluation (Shared cost) Consultant (evaluation)= =8,000*1 month =8, 000 Consultant (PM = 9,000*2 months = 18,000 | $8,000 $18,000 |
| Conferences, Workshops & Events |  |  |  |  |  |  |  |  | $20,000 |
| Total Direct Costs |  |  |  |  |  |  |  |  | $1,432,600 |
| GMS cost |  |  |  |  |  |  |  | 3% of direct costs | $42,978 |
| TOTAL |  |  |  |  |  |  |  |  | 1,475,578 |