# Annual Work Plan

Project: “Support the capacity development of the General Secretariat of the Supreme Council for Planning and Development to direct the strategic planning priorities of the State of Kuwait”

ATLAS ID: 79950

Year: January – December 2014

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Organizational structure of GSSCPD strengthened and improved leading to more efficient and effective organization |
| Baseline: ( ) Indicators: - Project evaluation conducted - Corporation framework between UNDP and GSSCPD developed and implemented - Internal management framework for GSSCPD developed -Number and nature of GSSCPD staff trainings - Number of GSSCPD staff and junior Kuwaiti professionals trained Targets: - To assess the effectiveness and impact of the project’s support to GSSPD - improve the efficiency and effectiveness of the administrative structure and financial operations of GSSCPD - to enhance the capacities of GSSCPD staff and junior Kuwaiti provisional to support the development and implementation of the national development plans Related CP outcome: KWT_OUTCOME1.5 National planning institutions capable of fulfilling the strategic planning role | 1.1 Activity Result Undertake an independent project evaluation - Action recruit project evaluation specialist |  |  | X | X | GSSCPD | GSSCPD | Consultant ($600/day x 20 working days) Travel | $12,000 $1,000 |
|  | 1.2 Activity Result: Improving GSSCPD performance, providing quality control, and supporting decision makers at GSSCPD on key development issues - Action: 2 consultants providing support to the Office of the Secretary General of GSSCPD in global development reports (HDR, MDGs) and coordination with various national, regional and international development partners. - Action: 2 consultants providing support to the Office of the Minister of State for Development Affairs to increase efficiency and organizational development of the GSSCPD. | X | X | X | X | GSSCPD and UNDP Consultants: Faris Al-Obaid, Hala Ali, Mohamad Al-Duwaihees, Hasan Merza | GSSCPD | Consultants: $242,400 | $242,400 |
|  | 1.3 Activity Result: Providing advice and internal reviews on financial matters related to GSSCPD, CSB and the Consultants Selection Committee - Action: Recruit (1) Financial Expert for the Office of the State Minister for Planning and Development Affairs - Action: Review all of GSSCPD, CSB and CSC’s financial matters, decisions, contracts, committee appointments, and recruitments to ensure their alignment with national laws and financial regulations. |  |  | X | X | GSSCPD Consultant: Mohamad Ismail | GSSCPD | Consultant ($8,000 x 6 months) Travel | $48,000 $1,000 |
|  | 1.4 Activity Result: Improve the GSSCPD administrative and financial structure and processes to ensure its efficiency and effectiveness -Action: Recruit (1) administration expert -Action: develop internal management framework for GSSCPD - Action: Develop internal TORs for GSSCPSD staff per role and function -Action: Develop training programmes and models for GSSCPD staff per role and function |  |  | X X X | X X | GSSCPD (Administrative Development and Training Department) Consultant: Executive Administration Consultant | GSSCPD | Consultant ($11000x3.5months) Travel | $38,500 $1,000 |
|  | 1.5 Activity Result: Recruit Project Manager - Action: Develop a clearing house mechanism at GSSCPD to review consultancy requests alignment with national development priorities - Action: Recruit a Development Expert for the clearing house mechanism - Action: Develop SOPs for cooperation between UNDP and GSSCPD for the years 2015-2018 - Action: Develop new project document in light of new National Mid-Range Development Plan (MRDP), new CPD and evaluation outcomes. |  |  | X | X | Project Manager, GSSCPD and UNDP Consultant: Development Expert | GSSCPD | Project Manager ($11,000x3months) 1 Consultant ($11,000 x x 2 months) Travel | $33,000 $22,000 $2,000 |
|  | 1.6 Activity Result: To build the capacity of junior Kuwaiti professionals in various areas to support the implementation of the national development plan -Action: Continue support to the first batch of JPOs -Action: Recruit second patch of JPO programme | X | X X X | X X | X X | GSSCPD, UNDP and JPOSC | GSSCPD | JPO Service Center | $1,920,000 |
| Output 2: National planning and implementation systems developed and GSSCPD role in economic management national recourses enhanced |
| Baseline: 1. National development plan and med-range national plan developed Indicators: 1.GSSCPD framework for M&E of the implementation of the development plan developed and implemented 2. Number of experts recruited to support various GSSCPD departments 4. Number of GSSCPD staff trained in planning, monitoring and evaluation processes and techniques Targets: - To improve GSSCPD output to the development of the new national development plan -To enable GSSCPD to fulfil its national oversight role in monitoring and evaluating the implementation of the development plans Related CP outcome: KWT_OUTCOME1.5 National planning institutions capable of fulfilling the strategic planning role | 2.1 Activity Result: Upgrade GSSCPD processes in planning, monitoring and implementing the new MRDP, specifically in the areas of financial planning, economic development, macro-economic policy and modelling, and education. - Action: 8 Consultants providing support to the Office of the Minister and the Planning Sector on the MRDP | X | X | X | X | UNDP and GSSCPD (Office of Minister and Planning Sector) Consultants: Ahmed Hakro, Khaled Hassan, Bechir Talbi, Dalal Mostafa, Siddig Salih, Expert in Economic Financial Planning, Expert in Human Development: General and Higher Education | GSSCPD | Consultants Ongoing - 5 Consultants: $469,500 New – 2 consultancies: 2 x ($11,000x 2 months) Travel | $469,500 $44,000 $2,000 |
|  | 2.2 Activity Result: Upgrade GSSCPD monitoring and evaluation mechanisms for the implementation of the development plan - Action recruit (1) M&E expert to develop GSSCPD framework for monitoring and evaluation - Action: Assess M&E capacity gaps in national entities and develop an M&E capacity building programme for national entities relevant technical staff - Action develop and implement M&E capacity building programme for GSSCPD relevant staff - Action: Improve and develop new databases, systems and tools |  |  | X X | X X | GSSCPD (Future Studies and Follow-up Sector) Consultant: Planning, Monitoring and Evaluation Expert (with special emphasis on Economic Development) | GSSCPD | Consultant ($11,000 x 2 months) Travel | $22,000 $1,000 |
|  | 2.3 Activity Result: Support GSSCPD in evaluating and exploring potential future scenarios for the State of Kuwait - Action: Recruit (1) Future Studies Expert to support researchers - Provide researchers with a set of methods and skills in formulating long-term strategies and policies. |  |  |  |  | GSSCPD (Future Studies and Follow-up Sector) Consultant: Future Studies Expert |  | Consultant ($11,000 x 2 months) Travel | $22,000 $1,000 |
|  | 2.4 Activity Result: Upgrade planning capacities and processes at GSSCPD - Action: Recruit (1) Strategic Planning Expert -Action: Assess the planning capacities and process at GSSCPD - Action: Provide technical support to enhance planning capacities - Action: Assess the capacity gaps of other national entities |  |  |  |  | GSSCPD (Planning Sector) Consultant: Expert in Strategic Planning |  | Consultant ($11,000 x 2 months) Travel | $22,000 $1,000 |
|  | 2.5 Activity Result: Design and upgrade efficient IT systems for efficient monitoring of the development plan - Action: 1 Consultant providing support to the IT department of GSSCPD | X | X | X | X | GSSCPD Consultant: Eslam Farag |  | Consultant ($4,000 x 12 months) | $48,000 |
|  | 2.6 Activity Result : Develop a communication strategy for GSSCPD and strengthen advocacy efforts as part of the national development process - Action: Team of (3) consultants working on media, communications and public awareness | X | X | X |  | GSSCPD and UNDP Consultant: Henrietta Asswad, Ahmad Al-Ebrahim, Adly Bseiso |  | Consultants 1 Media expert = $108,000 1 Communication and Public Awareness Consultant = $59,000 1 communication and Public Awareness Consultant = 121,500 | $288,500 |
| Output 3: Planning departments in line ministries conduct their functions more efficiently and effectively |
| Baseline: 1. Inadequate national planning system Indicators: 1. # of experts recruited to support national line ministries 2. Clearing house mechanism 3- # of line ministries staff trained in planning, monitoring and evaluation. Targets: - To enhance GSSCPD capacity to perform its oversight roll - To build line ministries capacities in planning, monitoring & evaluation to enhance their input in the national development plan Related CP outcome: KWT_OUTCOME1.5 National planning institutions capable of fulfilling the strategic planning role | 3.1 Activity Result: Assess the capacity gaps in the Consultants Selection Committee and develop mechanisms to improve qualifying, selection and contracting criteria and procedures for consultancy firms to ensure its alignment with national standards Action: (3) Consultants providing technical support to the Consultants Selection Committee |  |  |  |  | GSSCPD, UNDP , Consultants Selection Committee Consultant: Issam Hage Ali, Mohamad Moudares, Expert in Civil Engineering |  | Consultants 1 Expert in Project Evaluation and Construction Management = $37,600 1 Expert in Engineering and PM = $87,700 1 Civil Engineering Expert: ($11,000x2 months) Travel | $125,000 $22,000 $2,000 |
|  | 3.4 Activity Result support national entities in developing sectoral plans based on the national development plan. National entities include Ministry of Finance, Public Authority for Industry, Ministry of Communications, Kuwait Anti-Corruption Authority, Ministry of National Assembly Affairs, General Secretariat for Awqaf, the National SME Fund, MILSET. - Action recruit (17) technical experts in different fields as needed | X | X | X | X | National Entities and GSSCPD Consultants: Ministry of Finance: Fahad Al-Fuhaid and Sayed Al-Hunayan, MILSET: Expert in Science and Technology Educational Training Programmes Development PAI: Advisor on WTO Issues, Industrial Strategy formulation Anti-Corruption Authority: Media and Communication Expert, Administration Expert Ministry of Communication: Railway Consultant, Metro Consultant Ministry of National Assembly: Statistics Expert, Political Expert Awqaf Foundation: Engineering expert Other Urgent Requests (5) | GSSCPD | Consultants 1 consultant ($9600x8months) = $76,800 1 local consultant ($9000x12months) = $108,000 15 consultants ($9000x3months) = $405,000 Travel 15 tickets | $589,800 $15,000 |
| Project assistant/ translator |  |  |  |  |  |  |  | Admin ($4000x2months) | $8,000 |
| NIM Audit Costs |  |  |  |  |  |  |  | Audit firm | $40,000 |
| Outcome Evaluation Costs |  |  |  |  |  |  |  | Consultant | $20,000 |
| Miscellaneous (visas, travel, other costs) |  |  |  |  |  |  |  |  | $20,000 |
| Total Direct Costs |  |  |  |  |  |  |  |  | $4,083,700 |
| GMS |  |  |  |  |  |  |  |  | $122,511 |
| TOTAL |  |  |  |  |  |  |  |  | $4,206,211 |

Total Available Resources for 2014: $6,581,946.02