## Sheet1
EXPECTED OUTPUTS | PLANNED ACTIVITIES | RESPONSIBLE PARTY | PLANNED BUDGET |  | Planned Budget by Year (NEW) |  |  |  | Planned Budget by Year (ORIGINAL)
|  |  | Funding Source | Budget Description | 2017 | 2018 | Sub-Amount | Amount | 2017 | 2018 | Amount
1. Output Participation in Multilateral Environmental Agreements (MEAs) and Internationally Agreed Development Goals (IADGs) Strengthened | 1.1 Activity) Conduct capacity self-assessment (NCSA) to identify capacity building needs relating to MEAs, including national and local needs and cross-thematic issues | KEPA / UNEP | GOVT | International Consultants | 10000 | 40000 | 50000 | 140000 | 110000 | 80000 | 280000
|  |  |  | Regional Team Support |  | 40000 | 40000 |  | 20000 | 20000
|  |  |  | Travel | 10000 | 10000 | 20000 |  | 10000 | 10000
|  |  |  | Miscellaneous |  | 30000 | 30000 |  | 15000 | 15000
| 1.2 Activity) Develop National MEA Action Plan with measures to address achievement gaps including UNFCCC, UNCBD, and UNCCD | KEPA / UNEP | GOVT | International Consultants | 0 | 195000 | 195000 | 255000 | 30000 | 20000 | 70000
|  |  |  | Regional Team Support |  |  |  |  | 10000 | 10000
|  |  |  | Travel | 0 | 20000 | 20000
|  |  |  | Workshops | 0 | 20000 | 20000
|  |  |  | Miscellaneous | 0 | 20000 | 20000
| 1.3 Activity) Organize national capacity building workshops on MEA implementation and readiness for new initiatives to implement the EPL | KEPA / UNEP | GOVT | International Consultants |  | 70000 | 70000 | 130000 | 30000 | 20000 | 130000
|  |  |  | Regional Team Support |  |  |  |  | 30000 | 20000
|  |  |  | Travel |  | 10000 | 10000
|  |  |  | Workshops |  | 50000 | 50000 |  | 20000 | 10000
| 1.4 Activity) Support for designing National Adaptation Plan (NAP) and related initiatives linked to water, city planning and other sectors | KEPA / UNEP | GOVT | International Consultants | 0 | 200000 | 200000 | 280000 | 150000 | 50000 | 390000
|  |  |  | Regional Team Support |  |  |  |  | 50000 | 50000
|  |  |  | Workshops |  | 30000 | 30000 |  | 20000 | 10000
|  |  |  | Travel |  | 30000 | 30000 |  | 20000 | 10000
|  |  |  | Miscellaneous |  | 20000 | 20000 |  | 15000 | 15000
| 1.5 Activity) Undertake assessment of challenges and opportunities for achievement of the SDG environmental pillars in Kuwait, and prepare National SDG Reporting | KEPA / UNDP | GOVT | International Consultants | 0 | 50000 | 50000 | 120000 | 30000 | 20000 | 120000
|  | (UN Environment will support this activity through technical staff time) |  | Regional Team Support | 0 | 40000 | 40000 |  | 20000 | 20000
|  |  |  | Workshops | 0 | 30000 | 30000 |  | 20000 | 10000
| 1.6 Activity) Design and implement awareness raising programme on priority environmental issues including through proper campaigns, workshops and media outreach | KEPA / UNDP | GOVT | local Consultants | 0 | 0 | 30000 | 105000 | 20000 | 10000 | 105000
|  |  |  | Regional Team Support | 0 | 10000 | 10000 |  | 10000
|  |  |  | Audio Visual & Print Prod Cost | 0 | 35000 | 35000 |  | 20000 | 15000
|  |  |  | Miscellaneous | 0 | 30000 | 30000 |  | 15000 | 15000
| Sub-Total for Output 1 (UNEP) incl. project management support (8%) |  |  |  | 20000 | 785000 |  | 805000
| Sub-Total for Output 1 (UNDP) |  |  |  | 0 | 315000 |  | 365000
| Sub-Total for Output 1 | [6 empty] | 1170000 | 665000 | 430000 | 1095000
Output 2 Environmental Information Systems Enhanced | 2.1 Activity) Conduct gap analysis and user survey to assess the state and usage of existing EIS platforms for decision-making processes to implement EPL | KEPA / UNDP | GOVT | International Consultants | 5000 | 45000 | 50000 | 60000 | 30000 | 20000 | 60000
|  |  |  | Miscellaneous | 0 | 10000 | 10000 |  | 5000 | 5000
| 2.2 Activity) Identify bottlenecks and recommend system enhancements to current EIS functions and services so as to be fit for purpose to implement EPL | KEPA / UNDP | GOVT | International Consultants | 0 | 50000 | 50000 | 90000 | 30000 | 20000 | 90000
|  |  |  | Workshops | 0 | 20000 | 20000 |  | 10000 | 10000
|  |  |  | Regional Team Support | 0 | 20000 | 20000 |  | 10000 | 10000
| 2.3 Activity) Enhance EMISK IT capacity to support required EIS infrastructure, system administration and security requirements, and connectivity | KEPA / UNDP | GOVT | International Consultants | 0 | 90000 | 90000 | 90000 | 50000 | 20000 | 90000
|  |  |  | Travel | 0 | 10000 | 10000 |  | 5000 | 5000
|  |  |  | Miscellaneous | 0 | 20000 | 20000 |  | 5000 | 5000
| 2.4 Activity) Identify and put in place new metrics and indicators for tracking performance on EPL | KEPA / UNDP | GOVT | International Consultants | 0 | 50000 | 50000 | 80000 | 30000 | 20000 | 80000
|  |  |  | Regional Team Support | 0 | 30000 | 30000 |  | 15000 | 15000
| 2.5 Activity) Train KEPA, Central Statistical Bureau and stakeholders on data collection, quality control including data validity and reliability and statistical analysis related to environmental indicators | KEPA / UNEP | GOVT | International Consultants | 0 | 60000 | 60000 | 130000 | 15000 | 20000 | 75000
|  |  |  | Travel | 0 | 30000 | 30000 |  | 10000 | 10000
|  |  |  | Workshops | 0 | 40000 | 40000 |  | 10000 | 10000
| 2.6 Activity) Document and share success stories and good practices in national indicators systems for tracking achieving SDG environmental pillars | KEPA / UNDP | GOVT | Regional Team Support | 0 | 30000 | 30000 | 70000 | 20000 | 10000 | 70000
|  |  |  | Workshops | 0 | 40000 | 20000 |  | 10000 | 10000
|  |  |  | Miscellaneous | 0 | 20000 | 20000 |  | 10000 | 10000
| Sub-Total for Output 2 |  |  |  | 5000 | 565000 |  | 520000 | 0 | 0 | 465000
Project Management |  | UNDP | GOVT | Project Manager | 60000 | 113000 | 173000 |  | 120000 | 120000 | 240000
|  |  |  | Project Assistant | 14000 | 28000 | 42000 |  | 65000 | 65000 | 130000
Monitoring & Evaluation | Mid-Term and Final Evaluations | KEPA | GOVT |  |  | 20000 | 20000 |  |  | 20000 | 20000
General Management Support |  | UNDP | GOVT | GMS (3%) |  |  | 60000 |  | 60000 |  | 60000
TOTAL |  |  |  |  | 99000 | 1706000 | 1875000 |  | 930000 | 630000 | 2010000