## 2018 AWP
Project Title: | Kuwait Annual National Energy Outlook (KNEO) Project |  |  |  |  | Award Number: |  |  |  | 91765 | [6 empty] | Total Budget |  | 900000 | [5 empty] | Prepared by:
Project Number: | 00096803 |  |  |  |  | Year: |  |  |  | 2018 | [6 empty] | Fund Number: |  | 30071 |  |  | Donor Number: |  | 145 | Certified by:
Contributing Outcome (CPD) | Human development accelerated through high-caliber human capital and increased social empowerment.
Indicative Output(s): | Strategic plans for strengthening human capital developed with focus on building capacity and career advancement, with special attention to women and youth.
2018
Output Indicatirs, Baseline, Targets | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1 Annual Kuwait National Energy Outlook (KNEO) report initiated Indicators: Annual production of a national energy outlook report Baseline: 0 -- no existing annual national energy outlook report. Targets: Publication of a national energy outlook report every year from 2018. | 1.1 Estabilishment of editorial and production committees; 1.11 Data collection and indicators Formulation; 1.12 Data analysis, and formulation of baselines; 1.13 Development of processing protocols and development of scenarios. | Steering Committee (GSSCPD/UNDP/KISR) for project oversight | Proposed committee needs approval | Decide this meeting
|  | Technical Working Group (GSSCPD,UNDP,KISR,CSB,KPC/KOC/KNPC) data collection and verificartion | Proposed needs approval | Decide this meeting
|  | KISR editorial and production team and consultant (proposed: Dr. Seth Blumsack) | Proposed needs approval | Decide this meeting
| Sub Total | [24 empty] | 240000
| 1.2 Engagement with regional and international partners. | SEI-US (Dr. Charlie Heaps) - LEAP software was purchased by KISR | Intiated contact through KISR and now liasoning with UNDP | Partner to develop a bottom-up energy model for the State of Kuwait
|  | WEO finalize TOR | UNDP has initiated contact; TOR finalized | Setup workshops to learn methods from IEA and adapt WEM for Kuwait
| Sub total | [24 empty] | 60000
| 1.3 Data management platform development, 1.31 Data collection, analysis, scenarios forecasting, processing, writing, production and publication of the reports. | Data collection and analysis and top-down approach forecasting | Initiated | Top-down approach requires more data. Tier 1 data is being collected and analyzed. Tier 2 data (OAPEC) available but data refinement shows inconsistencies.
|  | Writing and pubilication of KNEO | Initiated | Collecting literature; partnership with WEO to learn their publication methods
| Sub total | [24 empty] | 200000
| 1.4 Annual launch events within the country, dissemination, promotion and national and regional advocacy | Setting up calendar of events | Pending | Needs to be discussed amoungst project team and coordinator
|  | Promotion and advocacy to sustain the production of future KNEO publications | Pending | Needs to be discussed amoung stakeholders; Holding local events and seeking sponsorship from private sector (e.g. EQUATE)
| Sub Total | [24 empty] | 100000
Total Output1 | [25 empty] | 600000
Output 2 Institutional capacity of KISR for production of KNEO strengthened Indicators: Number of KISR staff benefited from capacity development, exchange visits, and training. Baseline: Existing capacity development activities at KISR Targets: 10 people benefit from capacity development activities. | 2.1 Institutional capacity assessment process initiated | Capacity assessment (gap analysis to be conducted by WEO - include within TOR) | Initial team formed and will add new professionals; WEO will highlight technical requirements | Current KISR project team includes 4 researchers and 7 professionals
|  | Capacity building with KISR staff | Identification of knowledge gaps and training with SEI and WEO | Discussed with UNDP and now coordinating timing of workshops
| Sub total | [24 empty] | 143000
| 2.2 Facilitation of exchange of lessons and knowledge with OECD's IEA World Energy Outlook. | Establish relation with WEO through UNDP | Initiated | UNDP has initiated contact
|  | KISR staff participate in workshops with WEO & SEI | Pending | Coordinating through UNDP
| Sub total | [24 empty] | 10000
| 2.3 Institutional capacity building acitivities for structure production, advocacy and presntations and for linking KNEO to Policy Center at GSSCPD | Knowledge sharing through workshops with SEI and WEO | Initiated | UNDP has initiated contact
|  | Select local and regional events to advocate KNEO report | Pending | Needs to be discussed amoung stakeholders
Sub total
Total Output 2 | [25 empty] | 143000
| Project Coordinator | [24 empty] | 100000
| Miscellaneous | [24 empty] | 10000
| Evaluation | [24 empty] | 20000
x x
| Sub Total | [24 empty] | 130000
Total Budget | [25 empty] | 873000
GMS 3% | [25 empty] | 27000
Total Budget including 3% GMS | [25 empty] | 900000
|  |  |  | current consultant | [15 empty] | Advertised | bar: Q3 Aug to Q4 Dec
Under hiring process | bar: Q3 Aug to Q4 Dec