## 2017 AWP Budget Revision Aug 6
Project Title: | The Institutional and Technical support for the establishment of Kuwait Public Policy Centre (KPPC) | [7 empty] | Award Number: |  |  |  | 00098909 |  |  |  | Total Budget |  |  |  |  | 2401090 |  |  | Prepared by: | Fatima Keaik
Project Number: | 00102106 | [7 empty] | Year: |  |  |  | 2018 |  |  |  | Date |  | 2018-01-01 |  |  | Donor Number: |  | 00145 | Certified by: | Dima Al-Khatib
Outcome: Governance and institutional management is efficient, transparent, accessible, competitive and accountable
Output 1. Institutional and technical preparation for the establishment of KPPC supported. Indicators : 1.1 Political Economy analysis or Institutional Context analysis conducted. 1.2 Business model of engagement and staff structure plan developed following the results of the PEA or ICA 1.3 recruited KPPC staff 1.4 Launch event establishing KPPC Baselines: • 0 • 0 • 0 • 0 Targets (Year 2018): • 1 • 1 • 1 • 1 | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Budget
| Activity 1.1 : Conduct a political economy analysis of the KPPC | Conduct PEA and ICA for the KPPC to have a baseline assessment of the current policymaking situation in Kuwait |  | Consultancy services on conducting Political Economy Assessment (PEA) and Institutional Context Assessment (ICA) | [12 empty] | 1 | 34500 | - | - | IC |  |  | 71200 |  | 34500 | Claudia Melim | bar: Q1 Jan
|  |  |  | Workshop presenting the findings of the assessment and suggested ways forward | [12 empty] | 1 |  |  |  | IC |  |  | 71200 |  | 0 | Claudia Melim | bar: Q1 Jan
| Sub total | [24 empty] | 34500
| Activity 1.2: Develop an institutional organizational structure and strategy for KPPC | Set up institutional skills diagram, functional job categorization, executive plan, SOPs and staff capacity development plan, a risk management plan with the key performance indicators (KPIs) |  | Propose the setup of an Executive Board for KPPC | [12 empty] | 1 | 67890 |  |  | IC |  |  | 71200 |  | 67890 | Mazen Choaib | bar: Q1 Jan to Q1 Feb
|  |  |  | Set profiles and criteria to recruit staff to KPPC from the GSSCPD | [12 empty] | 1 | [9 empty] | Mazen Choaib | bar: Q1 Jan to Q1 Feb
|  |  |  | Develop Governance framework, operating model, and bylaws for the KPPC | [12 empty] | 1 | [9 empty] | Mazen Choaib | bar: Q1 Jan to Q1 Feb
|  |  |  | Develop business flow process, risk management plan, and SOPs | [12 empty] | 1 | [9 empty] | Mazen Choaib | bar: Q1 Jan to Q1 Feb
| Sub Total | [24 empty] | 67890
Total Output1 | [25 empty] | 102390
Output 2: KPPC knowledge and behavioural insight (nudge) capacity-building established Indicators: 2.1 Nudge unit / mechanism established including the experts on behavioural insight recruited 2.2 Number of policy experimentations run by the Nudge unit 2.3 Public Policy Capacity building on evidence-based policy planning Baseline: • 0 • 0 • 0 Targets (2017): • 1 • 1 • 1 | Activity 2.1: Establish KPPC Knowledge base | Establishment of a Knowledge Base |  | Provision of policy advisor for each of the KNDP pillar on Health to provide technical advice and develop health white paper for KPPC. | [12 empty] | 1 | 50000 | - | - | IC |  |  | 71200 |  | 50000 | Sungsoo Chun | bar: Q1 Jan to Q3 Jul
|  |  |  | Provision of policy advisor for each of the KNDP pillar on Economic Growth to provide technical advice and develop economic white paper for KPPC. | [12 empty] | 1 | 122756 | - | - | IC |  |  | 71200 |  | 207000 | Arif Mahmoud | bar: Q1 Jan to Q3 Jul
|  |  |  | Provision of policy advisor for each of the KNDP pillar on Human Capital and Public Administration Pillars to provide technical advice and develop white papers for KPPC. | [12 empty] | 1 | 298600 | - | - | IC |  |  | 71200 |  | 298600 | Wafa Saad
|  |  |  | Provision of consultancy services to develop customized macro-economic model for Kuwait. | [12 empty] | 1 | 938800 |  |  | RFP |  |  | 72100 |  | 938800 | Oxford Economics | bar: Q1 Jan to Q3 Sep
|  |  |  | Provision of policy advisor to develop economic outlook and forecast on both the global and local economy with focus on financial sector. | [12 empty] | 1 | 50000 |  |  | IC |  |  | 71300 |  | 50000 | TBD | bar: Q2 Jun to Q4 Dec
|  |  |  | Development of Health System Review and overall assessment of the current public health system in Kuwait based on national consultations and data collection. | [12 empty] | 1 | 135000 |  |  | KFAS (IP) |  |  |  |  | 135000 | KFAS, LSE | bar: Q1 Jan to Q3 Sep
|  |  |  | Review of the current STI in Kuwait with recommendations on policy reforms to improve the competitiveness of the country in the innovation and technology | [12 empty] | 1 | 300000 |  |  | KFAS (IP) |  |  |  |  | 300000 | KFAS, OECD | bar: Q1 Jan to Q3 Sep
|  |  |  | Development of Computable General Equilibrium (CGE) Model to quantify the impact of various fiscal, energy, and competition policies on the Kuwait Economy. | [12 empty] | 1 | 125000 |  |  | KFAS (IP) |  |  |  |  | 125000 | KFAS, OIES | bar: Q1 Jan to Q3 Sep
|  | Establishment of a Nudge Unit |  | Set policy agenda for each policy area with ideas for experimentation, conduct capacity building workshops and courses | [12 empty] | 1 | 50000 |  |  | IC |  |  |  |  | 50000 | bar: Q2 May to Q4 Dec
| Sub total | [24 empty] | 2154400
Total Output 2 | [25 empty] | 2154400
Output 3: KPPC advocacy, outreach and partnership development reinforced. Indicators: 3.1 A communication strategy developed 3.2 Community of Practice developed 3.3 Regional Conference on Policy Planning Challenges and Solutions Pathways (e.g. nudge units) 3.4 Youth and public policy making Initiative 2020 Baseline: • 0 • 0 • 0 • 0 Targets (2017): • 1 • 1 • 1 • 1 | Activity 3.1: Build strategies for advocating and outreaching KPPC partners | Develop a communication strategy for the KPPC |  | Create KPPC logo, brochure and other branding materials | [12 empty] | 1 | 4300 | [5 empty] | 74200 |  | 4300 | bar: Q1 Jan to Q1 Feb
| sub total | [24 empty] | 4300
| Activity 3.2. Training on Policy development and formulation | Capacity building activities on public policymaking |  | Conduct monthly lectures and roundtable discussions on various public policy issues and key related trends | [12 empty] | 5 | 1000 | [5 empty] | 71600 |  | 5000 | bar: Q1 Jan to Q2 May; Q4 Oct to Q4 Dec
[17 empty] | 12 | 850 | [5 empty] | 74200 |  | 10200 | bar: Q1 Jan to Q2 May; Q4 Oct to Q4 Dec
[17 empty] | 1 | 500 | [5 empty] | 75700 |  | 500 | bar: Q1 Jan to Q2 May; Q4 Oct to Q4 Dec
| Sub total | [24 empty] | 15700
| Activity 3.3: Develop new partnerships for KPPC | Develop national and regional Partnerships |  | Create partnership with regional policy and research centres in the GCC and the MENA region | [21 empty] | 0
|  | Develop strategic collaborations (MOUs) with regional and international policy centres, corporations and businesses. |  | Create MOUs with regional and international policy centres | [21 empty] | 0
| Sub Total | [24 empty] | 0
Total Output 3 | [25 empty] | 20000
| Project Coordinator | [15 empty] | 12 | 7000 | [5 empty] | 71400 |  | 84000
| Project Assistant | [15 empty] | 8 | 5000 | [5 empty] | 71400 |  | 40000 | bar: Q2 May to Q4 Dec
| Miscellaneous | [16 empty] | 300 | [5 empty] | 72400 |  | 300
| Sub Total | [24 empty] | 124300
Total Output 4 excluding GMS | [25 empty] | 124300
Total Budget | [25 empty] | 2401090
Total Budget including 3% GMS | [25 empty] | 2473122.7
| Dr. Khaled Mahdi | [18 empty] | Ms. Dima Al Khatib
| Secretary General | [18 empty] | Deputy Resident Representative
| Supreme Council for Planning and Development (SCPD) | [18 empty] | United Nations Development Programme (UNDP)