## 2017 AWP-Quarter Budget Details
Project Title: | The Institutional and Technical support for the establishment of Kuwait Public Policy Centre (KPPC) | [7 empty] | Award Number: |  |  |  | 00098909 |  |  |  | Total Budget |  |  |  |  | 667500 |  |  | Prepared by: | Fatima Keaik
Project Number: | 00102106 | [7 empty] | Year: |  |  |  | 2017 |  |  |  | Fund Number: |  | 30071 |  |  | Donor Number: |  | 00145 | Certified by: | Dima Al-Khatib
Outcome: Governance and institutional management is efficient, transparent, accessible, competitive and accountable
Output 1. Institutional and technical preparation for the establishment of KPPC supported. Indicators : 1.1 Political Economy analysis or Institutional Context analysis conducted. 1.2 Business model of engagement and staff structure plan developed following the results of the PEA or ICA 1.3 recruited KPPC staff 1.4 Launch event establishing KPPC Baselines: • 0 • 0 • 0 • 0 Targets (Year 2017): • 1 • 1 • 1 • 1 | Activities (as per Atlas AWP) | Sub activity | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Budget
| Activity 1.1 : Conduct a political economy analysis of the KPPC | Conduct PEA and ICA for the KPPC to have a baseline assessment of the current policymaking situation in Kuwait |  | Consultancy services on conducting Political Economy Assessment (PEA) and Institutional Context Assessment (ICA) | [12 empty] | 1 | 35000 | - | - | IC |  |  |  |  | 35000 | bar: Q4 Oct to Q4 Dec
|  |  |  | Workshop presenting the findings of the assessment and suggested ways forward | [12 empty] | 1 | 5000 | [7 empty] | 5000 | bar: Q4 Dec
| Sub total | [24 empty] | 40000
| Activity 1.2: Develop an institutional organizational structure and strategy for KPPC | Set up institutional skills diagram, functional job categorization, executive plan, SOPs and staff capacity development plan, a risk management plan with the key performance indicators (KPIs) |  | Propose the setup of an Executive Board for KPPC | [12 empty] | 1 | 10000 |  |  | IC |  |  |  |  | 10000 | bar: Q3 Sep to Q4 Dec
|  |  |  | Set profiles and criteria to recruit staff to KPPC from the GSSCPD | [12 empty] | 1 | 5000 |  |  | IC |  |  |  |  | 5000 | bar: Q3 Sep to Q4 Oct
|  |  |  | Develop Governance framework, operating model, and bylaws for the KPPC | [12 empty] | 1 | 10000 |  |  | IC |  |  |  |  | 10000 | bar: Q3 Sep to Q4 Dec
|  |  |  | Develop business flow process, risk management plan, and SOPs | [12 empty] | 1 | 10000 |  |  | IC |  |  |  |  | 10000 | bar: Q3 Sep to Q4 Oct
| Sub Total | [24 empty] | 35000
| Activity 1.3 Develop Strategy for KPPC including a technical capacity plan for KPPC | Establish an executive committee/ advisory board |  | Develop ToR for the executive committee, define mandate, target potential members from international research institutions and academia, private sector, and public entities | [21 empty] | 0 | bar: Q1 Mar to Q2 Jun
|  |  |  | Develop clear strategy with mission and vision outlined | [21 empty] | 0 | bar: Q3 Jul to Q4 Dec
|  | Provide operational support to the KPPC |  | Mapping out all research institutions and think tanks relevant to the KPPC work | [21 empty] | 0 | bar: Q3 Jul to Q3 Aug
| Sub total | [24 empty] | 0
Total Output1 | [25 empty] | 75000
Output 2: KPPC knowledge and behavioural insight (nudge) capacity-building established Indicators: 2.1 Nudge unit / mechanism established including the experts on behavioural insight recruited 2.2 Number of policy experimentations run by the Nudge unit 2.3 Public Policy Capacity building on evidence-based policy planning Baseline: • 0 • 0 • 0 Targets (2017): • 1 • 1 • 1 | Activity 2.1: Establish KPPC Knowledge base | Establishment of a Knowledge Base |  | Provision of policy advisors for each of the KNDP main pillar: Governance, Economic Growth, Human Capital, Environment, Health and Social Policy | [12 empty] | 3 | 60000 | - | - | IC |  |  |  |  | 180000 | bar: Q3 Jul to Q4 Dec
|  |  |  | Issuance of policy white papers on public health policy and future energy policy through KFAS partnership with leading universities | [12 empty] | 1 | 120000 |  |  | RPA |  |  |  |  | 120000 | bar: Q3 Jul to Q4 Dec
|  |  |  | Provision of consultancy services to develop customized macro-economic model for Kuwait. | [12 empty] | 1 | 50000 |  |  | RFP |  |  |  |  | 50000 | bar: Q4 Nov to Q4 Dec
|  |  |  | Provision of ready-made economic model that is compatible with Kuwait Industry model with different scenarios for planning | [12 empty] | 1 | 59000 |  |  | RFQ |  |  |  |  | 59000 | bar: Q4 Oct to Q4 Dec
|  | Establishment of a Nudge Unit |  | Set operating model, structure, lessons learned, and detailed design and positioning of the nudge unit | [12 empty] | 1 | 100000 |  |  | IC |  |  |  |  | 100000 | bar: Q3 Sep to Q4 Dec
| Sub total | [24 empty] | 509000
Total Output 2 | [25 empty] | 509000
Output 3: KPPC advocacy, outreach and partnership development reinforced. Indicators: 3.1 A communication strategy developed 3.2 Community of Practice developed 3.3 Regional Conference on Policy Planning Challenges and Solutions Pathways (e.g. nudge units) 3.4 Youth and public policy making Initiative 2020 Baseline: • 0 • 0 • 0 • 0 Targets (2017): • 1 • 1 • 1 • 1 | Activity 3.1: Build strategies for advocating and outreaching KPPC partners | Develop a communication strategy for the KPPC |  | Create KPPC logo, brochure and other branding materials | [12 empty] | 1 | 10000 | [7 empty] | 10000 | bar: Q1 Feb to Q2 Apr
| sub total | [24 empty] | 10000
| Activity 3.2. Training on Policy development and formulation | Capacity building activities on public policymaking |  | Conduct monthly lectures and sessions on various public policy issues and key related trends | [12 empty] | 6 | 2500 | [7 empty] | 15000 | bar: Q1 Mar to Q2 May; Q4 Oct to Q4 Dec
| Sub total | [24 empty] | 15000
| Activity 3.3: Develop new partnerships for KPPC | Develop national and regional Partnerships |  | Create partnership with regional policy and research centres in the GCC and the MENA region | [21 empty] | 0 | bar: Q2 Apr to Q4 Dec
|  | Develop strategic collaborations (MOUs) with regional and international policy centres, corporations and businesses. |  | Create MOUs with regional and international policy centres | [21 empty] | 0 | bar: Q2 Apr to Q4 Dec
| Sub Total | [24 empty] | 0
Total Output 3 | [25 empty] | 25000
| Project Coordinator | [15 empty] | 9 | 6500 | [7 empty] | 58500 | bar: Q2 Apr to Q4 Dec
| Sub Total | [24 empty] | 58500
Total Output 4 excluding GMS | [25 empty] | 58500
Total Budget | [25 empty] | 667500
Total Budget including 3% GMS | [25 empty] | 687525
| Dr. Khaled Mahdi | [18 empty] | Ms. Dima Al Khatib
| Secretary General | [18 empty] | Deputy Resident Representative
| Supreme Council for Planning and Development (SCPD) | [18 empty] | United Nations Development Programme (UNDP)