## 2018 AWP
Project Title: | Preservation and Promotion of Kuwait's Cultural Heritage |  |  |  |  | Award Number: | [10 empty] | Total Budget | [7 empty] | Prepared by:
Project Number: | 102378 |  |  |  |  | Year: |  |  |  | 2018 | [6 empty] | Fund Number: |  |  |  |  | Donor Number: |  |  | Certified by:
Contributing Outcome (CPD) | Strategic Multilateral partnership at the global and regional levels established, including through South-South and Triangular cooperation, to advise the post 2015 development agenda
Indicative Output(s): | A clear framework for the development of culture.
2018
Output Indicators, Baseline, Targets | Activities (as per Atlas AWP) | Subactivities | Status/ Progress | Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender | Account Code | Budget Description | Amount USD $ | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable
Output 1 NCCAL strengthened through cultural policy development and institutional restructuring Indicators: 1.1 NCCAL cultural policy framework developed Baseline: 1.1 0 Targets: 1.1 1 | Develop Cultural Policy | Elaborate public cultural policy based on themes, topics, tendencies and trends identified and disseminate/publicize the policy document |  | 6 x Round table discussions with national specialists (up to 15 pax per round table) | [14 empty] | SC |  |  | UNESCO staff time |  |  |  | 30000 | bar: Q1 Mar to Q4 Dec
|  |  |  | 4 x Focus group sessions - Stakeholder assessment about people’s attitudes towards culture (15 pax per focus group) | [14 empty] | SC |  |  | UNESCO staff time |  |  |  | 15000
|  | Develop a framework for enhancing the culture of cooperation with the private sector. |  | Mapping cultural services, institutions and actors assisted by 4 x Staff from NCCAL (as part of capacity devleopment programme) | [14 empty] | SC |  |  | UNESCO staff time |  |  |  | 20000 | bar: Q2 Apr to Q4 Dec
| Review legal framework for culture | Review laws towards movable and immovable cultural heritage |  | Review of laws that affect culture and antiquities (access to all legal documents is facilitated through NCCAL); | [14 empty] | IC | 2 | CV |  |  |  |  | 17360 | bar: Q1 Mar to Q2 Jun
2 x round table discussions with national experts to identify what's missing in the law (up to 15 pax per round table) | bar: Q1 Mar to Q2 Jun
1 x International Consultant in Kuwait for 2 months to lead on review of law and propose re-drafting | bar: Q1 Mar to Q2 Jun
|  | Create mechanism towards implementation |  | 1 x International Consultant in Kuwait for 1 month to develop mechanism and draft law in Arabic | [14 empty] | IC | 1 | CV |  |  |  |  | 8680 | bar: Q2 Apr to Q4 Oct
3 x round table discussions with national experts to review the mechanism and the proposed Arabic law (up to 15 pax per round table) | bar: Q2 Apr to Q4 Oct
| Sub Total | [24 empty] | 91040
| Revise NCCAL Strategy | Review and develop an updated NCCAL Strategy in the framework of the proposed Policy Document |  | Introductory workshop for all NCCAL staff for introducing the project aims and activities, the importance of a cultural policy, and an overview of the plan of action | [14 empty] | SC and IC | 2 | CV |  |  |  |  | 27360 | bar: Q2 Apr to Q4 Dec
1 x International Consultant in Kuwait for 2 months to review NCCAL strategy, governance structure, HR policies and draft recommendations for revision. | bar: Q2 Apr to Q4 Dec
|  | Review existing institutional assessments of museum division as part of the overall NCCAL Strategy |  | 1 x International Consultant in Kuwait for 2 months to review structure and mechanism for operating the museum division within the NCCAL strategy, | [14 empty] | IC | 2 | CV |  |  |  |  | 17360 | bar: Q2 Apr to Q3 Sep
| Sub total | [24 empty] | 44720
Total Output1 | [25 empty] | 135760
Output 2 Institutional strengthening for NCCAL with focus on Museums Division Indicators: 2.1 KNM and MoMA services and departments are assessed and recommendations made. 2.2 KNM collection surveyed and action plan drafted. Baseline: 2.1 0 2.2 0 Targets: 2.1: 2 2.2: 2 | Evaluate KNM and MoMA services and departments | Improve storage and inventory systems |  | Assessment visits to all storage depots and assessments of the inventory system is conducted. | [14 empty] | SC |  |  | UNESCO staff time |  |  |  | 35000
|  | Undertake the condition survey of the KNM collection and develop conservation strategies |  | A support team at the core of KNM is formed consisting of KNM staff who will be invovled in all capacity development at a later stage to undertake a survey of the condition of the collection. | [14 empty] | SC |  |  | UNESCO staff time |  |  |  | 20000 | bar: Q2 Apr to Q3 Sep
| Sub total | [24 empty] | 55000
| Develop Studies and programmes for NCCAL museums | Conduct analysis for potential services, programmes, and exhibitions |  | 1 x international consultant in Kuwait for 2 months to develop a feasibility study for expanding the KNM museum services to include gift shops, cafeteria, guided tours, etc | [14 empty] | IC | 2 | CV |  |  |  |  | 17360 | bar: Q2 Apr to Q3 Sep
|  |  |  | Study the feasibility of a new programme for the display of the Al-Sabah pre-Islamic collection in Building 17 | [14 empty] | SC |  |  | Internal UNESCO staff time |  |  |  | 10000 | bar: Q3 Jul to Q4 Dec
|  |  |  | 1 x international consultant in Kuwait for 4 months to develop a museological programme of the “History of Kuwait” exhibition | [14 empty] | IC | 4 | CV |  |  |  |  | 34720 | bar: Q4 Oct to Q4 Dec
|  |  |  | Following up on the Exhibition of DAI's collection in Buildings 3 and 4, up to installation of the display in the galleries | [14 empty] | SC |  |  | Internal UNESCO staff time |  |  |  | 25000 | bar: Q3 Jul to Q4 Dec
| Sub total | [24 empty] | 87080
142080
Output 3 Capacity development plan for NCCAL implemented and handicrafts and creative industries framework established and capacities enhanced Indicators: 3.1 Training of NCCAL staff undertaken 3.2 Handicrafts framework developed Baseline: 3.1 0 3.2 0 Targets: 3.1 8 3.2 1 | Organize specialized training of NCCAL staff | Conduct capacity assessment for NCCAL staff |  | Review of the current staffing capacities through NCCAL HR/Administration department giving access to all current staff specialisations, ongoing or upcoming training programmmes, and full organisation chart. | [14 empty] | SC |  |  | Internal UNESCO staff time |  |  |  | 10000 | bar: Q1 Feb to Q2 Jun
|  | Develop implementation plan |  | Identify gaps in training or specialisation in light of newly proposed structure, and draw up long-term training plan for NCCAL departments. | [14 empty] | SC |  |  | Internal UNESCO staff time |  |  |  | 20000 | bar: Q2 Apr to Q2 Jun
|  | Implement specialized training of NCCAL staff |  | 4 x workshops in UNESCO conventions led by 2 x international consultants for each workshop, approx 3 days each (see training programme for number of attendees, number of trainers, and proposed dates) | [14 empty] | IC and contract for services |  | CV and RFP |  |  |  |  | 155000 | bar: Q2 Apr to Q4 Dec
9 x conservation workshops (up to 20 pax) and 2 x wrap-up/revision workshops led by Internal UNESCO staff. (approx 1 - 3 days each - see training programme for more information) Materials & equipment to be purcahsed through NCCAL | bar: Q2 Apr to Q4 Dec
2 x international trainers in Kuwait for 2 weeks for RE-ORG training. Materials & equipment to be purcahsed through NCCAL | bar: Q2 Apr to Q4 Dec
10 x international specialist conservators (materials) in Kuwait for 2 weeks each training. | bar: Q2 Apr to Q4 Dec
| sub total | [24 empty] | 185000
| Develop a framework for crafts development in the NCCAL Strategic Plan 2015-2020, specifically under Axis 6 of the Sectors Strategic Objectives (“Supporting, encouraging and developing Fine Arts”); | Undertake a feasibility study for the establishment of an Arts and Crafts District in Kuwait |  | 1 x international consultant in Kuwait for 2 months to develop a feasibility study | [14 empty] | IC | 2 | CV |  |  |  |  | 17360 | bar: Q3 Jul to Q4 Dec
|  | Organize a product development course |  | 1 x international consultant in Kuwait for 2 months to develop the course | [14 empty] | IC | 2 | CV |  |  |  |  | 17360 | bar: Q3 Jul to Q4 Dec
| Sub total | [24 empty] | 34720
Total Output 3 | [25 empty] | 219720
Output 4 NCCAL undertakings widely disseminated Indicators: 4.1 Communication and outreach strategy developed Baseline: 4.1 0 Targets: 4.1 1 | Develop communications strategies | Develop a communication and outreach strategy for NCCAL & the Cultural Heritage project, and implement the Cultural Heritage strategy |  | 1 x international consultant in Kuwait for 5 months to develop the comms and outreach strategy | [14 empty] | IC | 5 | CV |  |  |  |  | 43400 | bar: Q1 Mar to Q4 Dec
|  | Develop NCCAL’s rebranding and repositioning strategy |  | Open competition through partner organisation or university. Submissions to be judged by a panel engaged by NCCAL and prize to be awarded by NCCAL | [14 empty] | Contract for services | 3 | RFP |  |  |  |  | 15000 | bar: Q2 May to Q3 Sep
| Sub total | [24 empty] | 58400
Total Output 4 | [25 empty] | 58400
Output 5 SSC/TRc enacted through benchmarking, knowledge sharing and international positioning Indicators: 5.1 International conference on Cultural Heritage organized Baseline: 5.1 0 Targets: 5.1 1 | Build on the successful experience of DAI, explore international cooperation through a range of activities including scholarships and artists in residence programmes | Prepare and present programmes for potential cooperation |  | Review of possible international and regional avenues for cooperation. Develop and present a timetable of cooperation. | [14 empty] | SC |  |  | Internal UNESCO staff time |  |  |  | 9768 | bar: Q1 Mar to Q4 Dec
|  | Organize a regional Cultural Heritage Conference |  | 1 x regional conference of up to 150 persons. | [17 empty] | direct procurement |  |  |  | 25000 | bar: Q4 Oct to Q4 Dec
| Sub total | [24 empty] | 34768
Total Output 5 | [25 empty] | 34768
|  |  |  | Project Manager | [21 empty] | 98500
|  |  |  | Lead conservator | [21 empty] | 80520
|  |  |  | Project Assistant | [21 empty] | 72000
|  |  |  | Project Coordinator | [21 empty] | 80000
|  |  |  | Miscellaneous | [21 empty] | 5000
|  |  |  | Evaluation | [21 empty] | 15000
| Project Administration Costs |  |  | GMS | [13 empty] | 0.03 | [7 empty] | 28252.44 |  |  | x x
| Sub Total | [24 empty] | 379272.44
Total Output 5 excluding GMS and Evaluation | [25 empty] | 351020
Total Budget | [25 empty] | 941748
Total Budget including 3% GMS | [25 empty] | 970000.44
|  |  |  | current consultant | [15 empty] | Advertised | bar: Q3 Aug to Q4 Dec
Under hiring process | bar: Q3 Aug to Q4 Dec