## 2018 AWP
Project Title: | Achieving Kuwait 2035 Vision Towards Persons with Disability (00096747) | [15 empty] | Award Number: |  |  |  | 00091631 | [7 empty] | Total Budget: | [7 empty] | US$ 2,000,000 |  |  | Prepared by: | Ahmed Ghanem
Project Number: | 00096747 | [15 empty] | Year: |  |  |  | 2017 & 2018 | [7 empty] | Fund Number: |  |  |  |  | 30071 |  |  | Donor Number: |  | 00145 | Certified by:
Outcome #1 Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded. Output 1.2. Options enabled and facilitated for inclusive and sustainable social protection |  |  |  |  | 2017 | [11 empty] | 2018
Activities (as per Atlas AWP) | Output | Action | Status/ Progress | Detailed Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit |  |  |  | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | 2016 | 2017 | 2018 | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
Output 1. Enhanced human capacities and institutional effectiveness for early detection, diagnosis and rehabilitation of disabilities. Indicator 1.1: PADA Institutional and Business Operations infrastructure in place (scale of 0-4 ) Baseline (2016): 1 Target (2018): 4 Indicator 1.2: PADA gender sensitive human resources and capacities performance (scale of 0-4 ) Baseline (2016): 1 Target (2018): 4 Indicator 1.3: Level of implementation of PADA Strategic Plan for prevention/early detection and diagnosis Baseline (2016): 2 ongoing projects on early detection and intervention Target (2018): International standards (ICF) in diagnosis applied and staff trained Indicator 1.4: Efficient and effective gender sensitive M&E for PADA projects Baseline (2016): No M&E system exists Target (2018): M&E system in place and staff trained | 1.1 Develop an institutional organizational structure efficient to deliver disability diagnostic services, and prevention strategy at all levels of prevention (i.e. primary, secondary and tertiary prevention levels ) Results Indicator 1.1 • PADA Institutional and Business Operations infrastructure in place (scale of 0-4 ) • PADA gender sensitive human resources and capacities performance (scale of 0-4 ) Data Source: PADA internal documentation and project documentation Frequency: annually Baseline (2016): 1 (Women: Men: ) 2:1 Target (2018): 4 Baseline (2016): 1 (Women: Men: ) 2:1 Target (2018): 4 | Conduct an institutional and skills analysis for all PADA in relation to its mandate and strategy and workflow with MOH, MOE and other stakeholders. |  | Develop TORs for a consultancy firm specifying the gender approach as a requirement | [36 empty] | 0 |  | Project Manager/PADA | bar: Q1 Mar
|  | Propose new PADA organogram/structure with delegations of authorities and defined lines of reporting |  | Solicit proposals, select and contract | [24 empty] | 1 | 489637 |  | 97927.4 | 391709.6 |  |  | LTA - Institutional Contract |  |  |  | Institutional Development Consulting Firm | 489637 | Revised Organogram, operational procedures, job descriptions | PADA /UNDP | bar: Q2 Apr to Q2 May
|  | Suggest a structure for the Diagnosis Center in PADA |  | Conduct the analysis | [36 empty] | 0 |  | Consulting Firm | bar: Q3 Sep; Q4 Dec
|  |  |  | Develop the organogram | [36 empty] | 0 |  | Consulting Firm | bar: Q3 Sep to Q4 Oct; Q4 Dec to Q1 Jan
|  | Develop standard operating procedures, administrative processes and systems improvements including with units in MOH, MOE and others. |  | Approve the organogram | [36 empty] | 0 |  | Consulting Firm | bar: Q4 Nov; Q1 Feb
|  | Build and implement a system and procedures for referral of cases between MOH and PADA (including e-medical reporting if possible) |  | Develop the SOPs and job descriptions | [36 empty] | 0 |  | Consulting Firm | bar: Q4 Dec to Q1 Jan; Q1 Mar to Q2 Apr
|  | Develop job descriptions to create functional job categorization and descriptions |  | Approve the SOPs and job descriptions | [36 empty] | 0 |  | Consulting Firm | bar: Q1 Feb; Q2 May
|  |  |  | Launch the organogram and administrative procedures | [36 empty] | 0 |  | PADA | bar: Q1 Mar; Q2 Jun
|  | Develop and implement a gender sensitive Human Resources Strategy 2016-2020 for PADA aligned with the new PADA- organogram and informed by the institutional skills audit. |  | Develop the human resources strategy in a gender sensitive manner | [36 empty] | 0 | Human Resources Strategy, Capacity development plan and performance management system | Consulting Firm | bar: Q4 Dec; Q1 Mar
|  | Conduct gender sensitive staff capacity needs assessment and create capacity development plan including design of skills and mentoring program |  | Develop the gender sensitive capacity development plan | [36 empty] | 0 |  | Consulting Firm | bar: Q4 Dec; Q1 Mar
|  | Pilot a Performance Management System for merit based assessment of staff delivering preventions services. |  | Develop the performance management system | [36 empty] | 0 |  | Consulting Firm | bar: Q1 Jan; Q2 Apr
|  |  |  | Pilot the performance management system and share lessons | [36 empty] | 0 |  | PADA | bar: Q1 Jan to Q2 Jun
|  |  |  | Consultative internal workshops and roll out structure and induction plan | [24 empty] | 1 |  |  |  | 363 | [6 empty] | Roll out/induction of new SOPs | 363 |  | PADA | bar: Q3 Sep to Q2 Jun
|  | Develop a communication strategy and plan for PADA internal administration and with external institutions (e.g. MOH departments and centers). | [38 empty] | 0 |  | Media company | bar: Q2 Apr
| Sub total | [30 empty] | 97927.4 | 392072.6 | [7 empty] | 490000
| 1.2 Support the implementation of PADA’s Strategic Plan in early detection, intervention and diagnosis of disability Results Indicator 1.2 Level of implementation of PADA Strategic Plan for early intervention and diagnosis. Data Source: PADA internal documentation Frequency: annually Baseline (2016): 2 ongoing projects on early detection and intervention Target (2018): International standards (ICF) in diagnosis introduced and staff trained - standard model for Kuwait Early Intervention Centers in place | Operationalize disability diagnosis center for research and knowledge of disability evaluation, classification. |  | Liaise with WHO (WHO Kuwait Regional Center WHO-FIC) experts for information about the International Standards (ICF) | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Jul
|  | Prepare training materials on techniques for detection, evaluation and classification of disabilities based on international standards and conduct training for medical staff |  | Develop TORs for a Health/Medical national expert to support implementation of ICF and ensure equal opportunities for men and women in hiring | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Oct
|  | Define and deploy audit and quality control protocols |  | Solicit proposals, hire and contract | [24 empty] | 1 | 30000 |  | 0 | 30000 |  |  | IC |  |  |  | ICF Specialists (WHO) | 30000 | Training material on ICF | PADA /UNDP | bar: Q4 Nov to Q1 Feb
|  |  |  | Conduct an assessment of PADA in relation to ICF implementation | [36 empty] | 0 |  | Consultant | bar: Q1 Jan; Q1 Mar
|  |  |  | Develop training material and quality control protocols | [36 empty] | 0 |  | Consultant | bar: Q1 Feb to Q2 May
|  |  |  | Print material | [24 empty] | 1 | 1000 |  |  | 1000 | [6 empty] | Training workshop costs | 1000 | bar: Q1 Mar; Q2 May
|  |  |  | Conduct trainings for male and female medical staff selected from committees or those hired in the diagnosis center when applicable | [24 empty] | 1 | 1000 |  |  | 1000 |  |  | Catering /Stationary |  |  |  | Training workshop costs | 1000 | Training reports | Consultant | bar: Q2 Apr; Q2 Jun
|  |  |  | Provide (remote) mentoring support during implementation of the ICF | [36 empty] | 0 |  | Consultant | bar: Q2 Apr; Q2 Jun to Q3 Jul; Q4 Oct
|  |  |  | Provide a refresher training one year after | [24 empty] | 1 | 1000 |  |  | 1000 | [6 empty] | Training workshop costs | 1000 |  | Consultant | bar: Q4 Oct
|  | Conduct a gender sensitive analysis of the situation of the 3 intervention centers in Kuwait and provide recommendations based on best practice |  | Develop a gender sensitive TORs for an International expert in Early Intervention and ensure equal opportunities for men and women in hiring | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 Apr
|  |  |  | Solicit proposals, hire and contract | [24 empty] | 1 | 53000 |  | 53000 | 0 |  |  | IC |  |  |  | Early Intervention Specialists | 53000 | Assessment and Recommendations Report | PADA /UNDP | bar: Q1 Mar to Q2 Apr
|  |  |  | Conduct the gender sensitive analysis and recommend best practices | [36 empty] | 0 |  | Consultants | bar: Q2 Jun to Q3 Jul
|  |  |  | Provide concrete recommendations for improving the early intervention centers in Kuwait | [36 empty] | 0 |  | Consultants | bar: Q3 Aug
Develop a standard model for Early Intervention Centers for PADA in Kuwait | bar: Q3 Aug to Q4 Oct
|  | Development of a triangular co-operation protocol i.e. South-South Exchange in development of Early Intervention prevention protocols and screening programs. |  | Organize exchange visit to Kuwait in relation to diagnosis and early intervention to share and learn from their experiences | [24 empty] | 1 | 11000 |  |  | 22000 |  |  | Travel tickets/DSA |  |  |  | South Exchange visits | 22000 | Visit reference material | Project Manager/PADA | bar: Q4 Oct to Q4 Dec; Q1 Mar to Q2 May
| Sub Total | [30 empty] | 53000 | 55000 | [7 empty] | 108000
| 1.3 Upgrade PADA monitoring and evaluation mechanisms for the PADA strategy and development projects Results Indicator 1.3 • Efficient and effective gender sensitive M&E for PADA projects Data Source: PADA internal documentation Frequency: annually Baseline (2016): No M&E system (Women : Men: ) 2:1 Target (2018): M&E system in place and staff trained | Apply improvements to M&E mechanism based on an assessment, gaps analysis that includes necessary, systems or tools. |  | Develop TORs for a gender sensitive RBM/M&E expert | [36 empty] | 0 |  | Project Manager/PADA | bar: Q1 Feb
|  | Put in place a framework using results oriented and evidence based indicators. |  | Solicit CVs, hire and contract and ensure equal opportunities for men and women in hiring | [24 empty] | 1 | 42550 |  | 42550 |  |  |  | IC |  |  |  | RMB/M&E specialist | 42550 | RBM and M&E framework | PADA /UNDP | bar: Q1 Mar to Q2 Apr
|  | Develop and implement an M&E capacity development program for national relevant technical staff |  | Conduct a mid-term review of development projects at PADA and provide recommendations including RBM and gender indicators | [36 empty] | 0 |  | Consultant | bar: Q2 May to Q2 Jun
|  | Ensure inclusion of gender sensitive indicators |  | Develop M&E framework for the projects in discussion with project staff | [36 empty] | 0 |  | Consultant | bar: Q3 Jul to Q3 Aug
|  | Develop and improve accessible customer services for PADA frontlines staff |  | Capcity Building for customer services for PADA frontlines staff | [24 empty] | 1 | 8505 |  | 8505 |  |  |  | IC |  |  |  | Workshops | 8505 |  | Consultant | bar: Q3 Aug to Q4 Nov
| Sub total | [30 empty] | 51055 | 0 | [7 empty] | 51055
Total Output1 | [31 empty] | 201982.4 | 447072.6 | [7 empty] | 649055
Output 2: Coordinated and well organized efficient efforts towards removal of barriers to the inclusion of persons with disabilities Indicator 2.1: Accessible guides and curricula are available for schools and VTCs Baseline (2016): No guides are available and curricula is general Target (2018): Guides and enhanced curricula in place and staff trained Indicator 2.2: Number of collaborative gender sensitive initiatives implemented with CSOs and PAYS that have direct impact on disabled inclusion Baseline (2016): a number of workshops was implemented with CSOs by PADA Target (2018): At least 2 initiatives implemented by 2018 | 2.1 Access to all types and degrees of disabilities at education or vocational training. Results Indicator 2.1: Accessible guides and curricula are available for schools and VTCs Educational Support Criteria & Guidelines Data Source: Project Documentation Frequency: annually Baseline (2016): No guides are available and curricula is general Target (2018): Guides and enhanced curricula in place and staff trained Guideline and criteria to determine Educational Support for student with disabilities in place | Through a consultative process, select pilot schools and vocational centers based on criteria and determine targeted types of disabilities |  | Conduct a consultation with stakeholders in PADA, MOE and building on the available MOE study define the support required for schools and VT sector for educational inclusion | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Sep
|  | Ensure the selected schools/VT centers targeting both girls and boys/women and men |  | Develop criteria to select the most relevant schools and VT centers and types of disabilities if needed | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Sep
|  | Develop a gender sensitive guide for school teachers based on "universal design" standards and train teachers in the selected schools |  | Develop the TORs for the development of the guide and curricula review to encompass universal standards for learning ensuring gender considerations | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Oct; Q4 Dec
|  | Develop a gender sensitive curriculum in co-ordination with ILO and KISR for vocational training |  | Identify relevant institutions (ILO/KISR/Universities) and invite them to submit proposals | [38 empty] | Project Manager/PADA | bar: Q4 Nov to Q1 Feb
|  | Train male and female teachers and caregivers in the selected vocational training centers. |  | Select and contract the selected institution | [24 empty] | 1 | 115000 |  |  | 115000 |  |  | RFP (Institutional Contract) |  |  |  |  | 115000 | Teachers Guide and Enhanced vocational curricula, Training Reports | PADA /UNDP | bar: Q4 Dec to Q1 Mar
|  |  |  | Develop the guide for the selected types of disabilities | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Feb; Q2 Apr
|  |  |  | Train the school teachers on basic concepts of inclusion of PWDs and on using the guides | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Mar to Q2 Jun
|  |  |  | Facilitate networking and information exchange among the teachers | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Feb to Q3 Jul
|  |  |  | Conduct an assessment of the selected VT centers existing curricula | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Mar; Q2 May
|  |  |  | Enhance the curricula by adding accessibility components and guidance | [36 empty] | 0 |  | Consultant Institution | bar: Q2 Apr to Q3 Jul
|  |  |  | Train the teachers and caregivers on basic concepts of inclusion of PWDs and on using the guides | [28 empty] | 0 | [7 empty] | 0 |  | Consultant Institution | bar: Q2 Jun; Q3 Aug
|  | Improve employment assistance and job opportunities and launch initiatives to encourage employers to hire both men and women with disabilities |  | Seek partnerships with private sector firms (>50 employees) to hire PWDs and identify needed skills | [36 empty] | 0 |  | Project Manager/PADA | bar: Q1 Jan; Q1 Mar; Q2 May; Q3 Jul
|  |  |  | Conduct a job fair for private sector and PWDs seeking employment and/or webpage at PADA for jobs where PWDs can apply/Collaborate with CSOs for products as example | [24 empty] | 1 | 30000 |  |  | 30000 |  |  | Venue/Catering |  |  |  |  | 30000 |  | Project Manager/PADA | bar: Q2 May; Q3 Jul
|  |  |  | Identify and conduct south-south visit from best practices on employment of PWDs | [24 empty] | 1 | 15000 |  |  | 15000 |  |  | Travel/DSA |  |  |  |  | 15000 |  | Project Manager/PADA | bar: Q2 May; Q3 Jul
|  | Develop Guideline and criteria to determine Educational Support for student with disabilities |  | Develop TORs for Educational Support expert | [36 empty] | 0 | bar: Q3 Jul to Q3 Aug
|  |  |  | Solicit CVs, hire and contract and ensure equal opportunities for men and women in hiring | [36 empty] | 0 | bar: Q4 Oct to Q4 Nov
|  |  |  | Conduct an assessment of the current PADA system for Educational Support for student with disabilities including school fees | [24 empty] | 1 | 60000 |  | 16678.05 | 38915.45 |  |  | IC |  |  |  |  | 60000 | bar: Q4 Dec to Q1 Jan
Development of a guideline and criteria to determine Educational Support for student with disabilities | bar: Q1 Jan to Q1 Feb
[32 empty] | 16678.05 | 198915.45 | [7 empty] | 220000
| 2.2 Coordinate and Build capacity of civil society organizations (CSOs) working with persons with disabilities. Results Indicator 2.2: Number of collaborative gender sensitive initiatives implemented with CSOs and PAYS that have direct impact on disabled inclusion. Data Source: Project Documentation Frequency: annually Baseline (2016): a number of workshops implemented by PADA . Target (2018): At least two collaborative initiatives/year PADA partnership strategy and framework in place | Initiate a network for CSOs working with persons with disabilities. |  | Develop TORs for CSOs capacity building | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Aug to Q3 Sep
|  |  |  | Solicit CVs, hire and contract and ensure equal opportunities for men and women in hiring | [24 empty] | 1 | 100000 |  |  | 100000 |  |  | ICS |  |  |  |  | 100000 |  | Project Manager/PADA | bar: Q1 Jan to Q1 Feb
Support strengthen the dialogue and consultation among CSOs to promote removal of barriers and inclusion of persons with disability | bar: Q1 Mar to Q2 Apr
|  | Develop a joint action plan in consultation with CSOs for inclusion of PWDs |  | Identify of capacity building needs of CSOs (CSOs joined the network in phase two) by developing a self-assessment tools and encourage CSOs to voluntary apply self-assessment | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 Apr
|  | Support CSOs to develop internal improvement plan based on the above results |  | Review the improvement plan from CSOs and PAYS | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 May
|  |  |  | Support implementation | [24 empty] | 1 | 55000 |  |  | 55000 |  |  | IC/ Venue/Catering |  |  |  |  | 55000 | bar: Q2 May to Q2 Jun
|  | Enhance PADA partnership strategy and framework |  | Develop TORs for partnership strategy | [24 empty] | 1 | 100000 |  |  | 100000 |  |  | IC |  |  |  |  | 100000 |  | Project Manager/PADA | bar: Q3 Jul
|  |  |  | Solicit CVs, select, hire 4 local trainers | [36 empty] | 0 | bar: Q3 Sep to Q4 Oct
Conduct participatory assessment of current partnership and cooperation practices within PADA | bar: Q4 Nov to Q4 Dec
|  |  |  | Develop PADA partnership strategy | [36 empty] | 0 | bar: Q4 Dec to Q1 Mar
|  | Develop and launch a gender sensitive advocacy campaign on inclusion in education, labor market, the physical environment and social life for Kuwaitis and non-Kuwaiti disabled population in collaboration with CSOs and other stakeholders |  | Develop TORs for a media consultancy firm | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 May to Q2 Jun
|  |  |  | Solicit proposals, hire and contract | [24 empty] | 1 | 175000 |  | 0 | 175000 |  |  | RFP |  |  |  |  | 175000 | Design of PADA communication strategy and plan/Design of public campaign on inclusion of PWDs | UNDP/PADA | bar: Q3 Aug to Q3 Sep
|  |  |  | Discuss the messages and component with CSOs and develop the campaign with PADA | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Oct to Q4 Nov
|  |  |  | Implement the campaign | [36 empty] | 0 |  | Consultancy firm | bar: Q4 Nov to Q2 May
[32 empty] | 0 | 430000 | [7 empty] | 430000
Total Output 2 | [31 empty] | 16678.05 | 628915.45 | [7 empty] | 650000
Output 3: Enhanced technical expertise and organizational capacities for Universal Design and country-wide use of technology enablers for persons with disabilities Indicator 3.1: No. and type of Public Buildings included in the the universal design proposal. Baseline (2016): 0 Target (2018): TBD 285 by 2020? Indicator 3.2: Building code adopted and communicated to stakeholders Baseline (2016): Partially Target (2018): Fully 100% Indicator 3.3: No. of institutions who receive guides about/implement technology enablers and assistive adaptive strategies. Baseline (2016): TBD Target (2018): At lease 2 public website enabled and guides disseminated to at least 50 insitutions | 3.1 Issuance of Code and guidance for implementation of universal design within public government buildings (schools, health and social care buildings) Result indicator 3.1: Kuwait Universal Design code produced No. of Public Buildings included the universal design proposal Data Source: Project documentation Frequency: annually Baseline (2016): Limited design code not in compliance with UD principles Partial accessibility of PADA public building Target (2018): Kuwait national UD code in place PADA public building Universal Design adaptation in place | Finalize universal design code and submit to related authorities for approval |  | Hire short term consultant to review the Universal Design Code | [25 empty] | 36249 |  | 36249 |  |  |  |  | IC |  |  | Universal Design Code expert | 36249 | Universal Design Code | Project Manager/PADA | bar: Q2 May to Q3 Jul
Research and review the existing building code and any other existing codes related Universal Design in Kuwait. | bar: Q2 Jun to Q3 Jul
Consult and discuss with a wide range of stakeholders including PADA, Kuwait municipality, the National Committee on Codes, the Ministry of Public Works, the Public Authority of Housing Welfare | bar: Q3 Jul
Finalize universal design code in consultation with stockholders and submit to related authorities for approval | bar: Q3 Jul to Q3 Aug
Support and facilitate Issue regulations for upgrading | bar: Q3 Sep to Q4 Oct
|  | Inventory which public facilities and outdoor areas need to be upgraded and prioritize in consultation with stakeholders . |  | Develop TORs for an architectural/engineering firm with universal design experience e | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Sep to Q4 Oct
|  | Develop a design proposal for several models and provide specifications for adjustments compliant with the code |  | Solicit offers, select and hire | [24 empty] | 1 | 50751 |  |  | 50751 |  |  | RFP |  |  |  | Architectural/Engineering firm for Universal Design | 50751 | Design proposal with specification and execution plan | UNDP/PADA | bar: Q4 Oct to Q4 Dec
|  | Develop a phased execution plan for upgrading existing public buildings, facilities and outdoor areas through KNDP projects and funds. |  | Develop the design proposal and specs for adjustments and execution plan | [36 empty] | 0 |  | Engineering Firm | bar: Q1 Jan to Q1 Feb
|  | Issue Regulation for new buildings and upgrading | [38 empty] | 0 |  | PADA and Municipality | bar: Q2 Apr to Q2 Jun
| sub total | [30 empty] | 36249 | 50751 | [7 empty] | 87000
| 3.2 Ensure “new” buildings and facilities comply with universal design Result indicator 3.2: Indicator 3.2: Building code adopted and communicated to stakeholders Data Source: Municipality of Kuwait Frequency: annually Baseline (2016): Partially Target (2018): Fully 100% | Set up a Universal Design unit in PADA |  | Based on the organogram, PADA to hire/assign staff for the unit | [36 empty] | 0 |  | PADA | bar: Q4 Dec to Q1 Jan
|  | Build Staff capacity on Universal Design |  | Identify trainers from Universal Design Centers on the different specializations and train staff | [24 empty] | 1 | 31000 |  |  | 31000 |  |  | Cooperation agreements |  |  |  |  | 31000 | Training Reports | Project Manager/PADA | bar: Q4 Dec to Q2 Apr
|  | Introduce and promote universal design concept to the private and public sector, architects, engineers and planners |  | Organize the conference for private sector firms, architects, engineers and planners and present options, benefits, experiences and best practices in universal design from other countries | [24 empty] | 1 | 30000 |  | 1655 | 28345 |  |  | Venue/catering |  |  |  |  | 30000 |  | Project Manager/PADA | bar: Q4 Dec; Q3 Sep
|  |  |  | Announce criteria for private sector to qualify for symbolic award | [31 empty] | Catering |  |  |  |  | 0 |  | Project Manager/PADA | bar: Q3 Aug
|  |  |  | Select the most compliant private sector buildings based on the criteria | [36 empty] | 0 | bar: Q4 Oct to Q4 Nov
|  | Organize a national conference to prompt universal design concept and issue a symbolic award for best practice in cooperation with Municipality of Kuwait |  | Organize symbolic award ceremony on PWDs day on 3 December | [24 empty] | 1 | 2000 |  | 0 | 2000 | [7 empty] | 2000 | bar: Q4 Dec
|  | South exchange with Countries on Universal Design (e.g. Ireland) |  | Identify and liaise with institutions with Universal Design Centers in other countries and sign a cooperation agreement with one | [31 empty] | Cooperation agreements |  |  |  |  | 0 |  | UNDP/PADA | bar: Q1 Feb to Q1 Mar; Q3 Sep
| Sub total | [30 empty] | 1655 | 61345 | [7 empty] | 63000
| 3.3 Ensure implementation of technology enablers and adaptive strategies Result indicator 3.3: No. of institutions who receive guides and implement technology enablers and assistive adaptive strategies. Data Source: Project Documentation Frequency: annually Baseline (2016): 0 Target (2018): PADA public website and online services enabled & accessible and guides disseminated to at least 50 institutions | Identify needs and perform analysis based on best practices in accessible digital learning platforms, adaptive strategies and assistive devices. |  | Develop TORs for a specialized firm/institution in accessibility and adaptive strategies in digital platforms | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Nov to Q4 Dec
|  | Define requirements, policies and regulations and develop and disseminate guidelines and standards |  | Solicit proposals, hire and contract | [24 empty] | 1 | 50000 |  |  | 50000 |  |  | RFP |  |  |  |  | 50000 | Best practices, guide and websites | UNDP/PADA | bar: Q1 Jan to Q1 Feb
|  | Promote implementation in public and private sector |  | Develop need analysis based on best practices and guidelines and Standards | [36 empty] | 0 |  | Specialized firm | bar: Q1 Mar
|  | implement adaptive strategies in PADA websites and services including building the capacity of PADA IT staff on the guidelines and international standards |  | Disseminate by PADA to various public and private organizations | bar: Q1 Mar to Q2 Apr
|  |  |  | Implement adaptive strategies in selected websites (PADA and e-go and possibly others) | [36 empty] | 0 |  | Specialized firm | bar: Q2 Apr to Q2 May
| Sub Total | [30 empty] | 0 | 50000 | [7 empty] | 50000
Total Output 3 | [31 empty] | 37904 | 162096 | [7 empty] | 200000
Activity 4: Management | Project Manager (Acting) | Hire Acting Project Manager | [26 empty] | 1 | 60620 |  | 60620 | 0 | IC | 3.5 months | [5 empty] | 60620 | bar: Q1 Feb to Q2 May
| Project Manager (IC) | [27 empty] | 6 | 9333.3333 |  | 56000 |  |  | 6 months | [5 empty] | 56000 | bar: Q2 Jun to Q4 Dec
| Project Manager (SC) | Hire Project Manager | [26 empty] | 12.5 | 10000 |  |  | 125000 | IC | 12.5 months | [5 empty] | 125000 |  | UNDP/PADA | bar: Q1 Jan to Q4 Dec
| Project Assistant | Hire Project Assistant | [26 empty] | 20 | 5284.6 |  | 42536 | 63804 | SC | 20 months | [5 empty] | 106340 |  | UNDP/PADA | bar: Q2 May to Q4 Dec
| Advertisements, translation and Admin | [29 empty] | 1878 | 9686 | 5314 | [7 empty] | 16878 | bar: Q1 Mar to Q4 Dec
| Stationery & laptops | [30 empty] | 12037 | 4613 | [7 empty] | 16650 | bar: Q3 Jul
| Contingency | [31 empty] | 37138 | [7 empty] | 37138 | bar: Q3 Aug to Q4 Dec
| Evaluation | Hire and conduct the evaluation | [26 empty] | 1 | 25000 |  | 0 | 25000 |  |  | RFQ |  |  |  |  | 25000 |  | UNDP/PADA | bar: Q4 Oct to Q4 Dec
| Sub Total | [29 empty] | 1878 | 180879 | 260869 | [7 empty] | 443626
Total Output 4 excluding GMS | [30 empty] | 1878 | 180879 | 260869 | [7 empty] | 443626
Total Budget excluding GMS | [30 empty] | 1878 | 437443.45 | 1498953.05 | [7 empty] | 1942681
3% GMS | [30 empty] | 56.34 | 13123.3035 | 44968.5915 | [7 empty] | 58280.43
|  | Total Budget including 3% GMS | [28 empty] | 1934.34 | 450566.7535 | 1543921.6415 | [7 empty] | 2000961.43

## Project WP
Project Title: | Achieving Kuwait 2035 Vision Towards Persons with Disability (00096747) | [15 empty] | Award Number: |  |  |  | 00091631 | [7 empty] | Total Budget: | [7 empty] | US$ 2,000,000 |  |  | Prepared by: | Ahmed Ghanem
Project Number: | 00096747 | [15 empty] | Year: |  |  |  | 2017 & 2018 | [7 empty] | Fund Number: |  |  |  |  | 30071 |  |  | Donor Number: |  | 00145 | Certified by:
Outcome #1 Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded. Output 1.2. Options enabled and facilitated for inclusive and sustainable social protection |  |  |  |  | 2017 | [11 empty] | 2018
Activities (as per Atlas AWP) | Output | Action | Status/ Progress | Detailed Action | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Quantity | Cost / Unit |  |  |  | Recruitment Services |  | Procurement Services |  | % of budget allocated to Gender |  |  |  | Deliverable | Responsibility
[5 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  | 2016 | 2017 | 2018 | Type of contract | Duration | Type of Procurement | Nature of assignment/deliverable |  | Account Code | Budget Description | Amount USD $
Output 1. Enhanced human capacities and institutional effectiveness for early detection, diagnosis and rehabilitation of disabilities. Indicator 1.1: PADA Institutional and Business Operations infrastructure in place (scale of 0-4 ) Baseline (2016): 1 Target (2018): 4 Indicator 1.2: PADA gender sensitive human resources and capacities performance (scale of 0-4 ) Baseline (2016): 1 Target (2018): 4 Indicator 1.3: Level of implementation of PADA Strategic Plan for prevention/early detection and diagnosis Baseline (2016): 2 ongoing projects on early detection and intervention Target (2018): International standards (ICF) in diagnosis applied and staff trained Indicator 1.4: Efficient and effective gender sensitive M&E for PADA projects Baseline (2016): No M&E system exists Target (2018): M&E system in place and staff trained | 1.1 Develop an institutional organizational structure efficient to deliver disability diagnostic services, and prevention strategy at all levels of prevention (i.e. primary, secondary and tertiary prevention levels ) Results Indicator 1.1 • PADA Institutional and Business Operations infrastructure in place (scale of 0-4 ) • PADA gender sensitive human resources and capacities performance (scale of 0-4 ) Data Source: PADA internal documentation and project documentation Frequency: annually Baseline (2016): 1 (Women: Men: ) 2:1 Target (2018): 4 Baseline (2016): 1 (Women: Men: ) 2:1 Target (2018): 4 | Conduct an institutional and skills analysis for all PADA in relation to its mandate and strategy and workflow with MOH, MOE and other stakeholders. |  | Develop TORs for a consultancy firm specifying the gender approach as a requirement | [36 empty] | 0 |  | Project Manager/PADA | bar: Q1 Mar
|  | Propose new PADA organogram/structure with delegations of authorities and defined lines of reporting |  | Solicit proposals, select and contract | [24 empty] | 1 | 489637 |  | 97927.4 | 391709.6 |  |  | LTA - Institutional Contract |  |  |  | Institutional Development Consulting Firm | 489637 | Revised Organogram, operational procedures, job descriptions | PADA /UNDP | bar: Q2 Apr to Q2 May
|  | Suggest a structure for the Diagnosis Center in PADA |  | Conduct the analysis | [36 empty] | 0 |  | Consulting Firm | bar: Q3 Sep; Q4 Dec
|  |  |  | Develop the organogram | [36 empty] | 0 |  | Consulting Firm | bar: Q3 Sep to Q4 Oct; Q4 Dec to Q1 Jan
|  | Develop standard operating procedures, administrative processes and systems improvements including with units in MOH, MOE and others. |  | Approve the organogram | [36 empty] | 0 |  | Consulting Firm | bar: Q4 Nov; Q1 Feb
|  | Build and implement a system and procedures for referral of cases between MOH and PADA (including e-medical reporting if possible) |  | Develop the SOPs and job descriptions | [36 empty] | 0 |  | Consulting Firm | bar: Q4 Dec to Q1 Jan; Q1 Mar to Q2 Apr
|  | Develop job descriptions to create functional job categorization and descriptions |  | Approve the SOPs and job descriptions | [36 empty] | 0 |  | Consulting Firm | bar: Q1 Feb; Q2 May
|  |  |  | Launch the organogram and administrative procedures | [36 empty] | 0 |  | PADA | bar: Q1 Mar; Q2 Jun
|  | Develop and implement a gender sensitive Human Resources Strategy 2016-2020 for PADA aligned with the new PADA- organogram and informed by the institutional skills audit. |  | Develop the human resources strategy in a gender sensitive manner | [36 empty] | 0 | Human Resources Strategy, Capacity development plan and performance management system | Consulting Firm | bar: Q4 Dec; Q1 Mar
|  | Conduct gender sensitive staff capacity needs assessment and create capacity development plan including design of skills and mentoring program |  | Develop the gender sensitive capacity development plan | [36 empty] | 0 |  | Consulting Firm | bar: Q4 Dec; Q1 Mar
|  | Pilot a Performance Management System for merit based assessment of staff delivering preventions services. |  | Develop the performance management system | [36 empty] | 0 |  | Consulting Firm | bar: Q1 Jan; Q2 Apr
|  |  |  | Pilot the performance management system and share lessons | [36 empty] | 0 |  | PADA | bar: Q1 Jan to Q2 Jun
|  |  |  | Consultative internal workshops and roll out structure and induction plan | [24 empty] | 1 |  |  |  | 363 | [6 empty] | Roll out/induction of new SOPs | 363 |  | PADA | bar: Q3 Sep to Q2 Jun
|  | Develop a communication strategy and plan for PADA internal administration and with external institutions (e.g. MOH departments and centers). | [38 empty] | 0 |  | Media company | bar: Q2 Apr
| Sub total | [30 empty] | 97927.4 | 392072.6 | [7 empty] | 490000
| 1.2 Support the implementation of PADA’s Strategic Plan in early detection, intervention and diagnosis of disability Results Indicator 1.2 Level of implementation of PADA Strategic Plan for early intervention and diagnosis. Data Source: PADA internal documentation Frequency: annually Baseline (2016): 2 ongoing projects on early detection and intervention Target (2018): International standards (ICF) in diagnosis introduced and staff trained - standard model for Kuwait Early Intervention Centers in place | Operationalize disability diagnosis center for research and knowledge of disability evaluation, classification. |  | Liaise with WHO (WHO Kuwait Regional Center WHO-FIC) experts for information about the International Standards (ICF) | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Jul
|  | Prepare training materials on techniques for detection, evaluation and classification of disabilities based on international standards and conduct training for medical staff |  | Develop TORs for a Health/Medical national expert to support implementation of ICF and ensure equal opportunities for men and women in hiring | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Oct
|  | Define and deploy audit and quality control protocols |  | Solicit proposals, hire and contract | [24 empty] | 1 | 30000 |  | 0 | 30000 |  |  | IC |  |  |  | ICF Specialists (WHO) | 30000 | Training material on ICF | PADA /UNDP | bar: Q4 Nov to Q1 Feb
|  |  |  | Conduct an assessment of PADA in relation to ICF implementation | [36 empty] | 0 |  | Consultant | bar: Q1 Jan; Q1 Mar
|  |  |  | Develop training material and quality control protocols | [36 empty] | 0 |  | Consultant | bar: Q1 Feb to Q2 May
|  |  |  | Print material | [24 empty] | 1 | 1000 |  |  | 1000 | [6 empty] | Training workshop costs | 1000 | bar: Q1 Mar; Q2 May
|  |  |  | Conduct trainings for male and female medical staff selected from committees or those hired in the diagnosis center when applicable | [24 empty] | 1 | 1000 |  |  | 1000 |  |  | Catering /Stationary |  |  |  | Training workshop costs | 1000 | Training reports | Consultant | bar: Q2 Apr; Q2 Jun
|  |  |  | Provide (remote) mentoring support during implementation of the ICF | [36 empty] | 0 |  | Consultant | bar: Q2 Apr; Q2 Jun to Q3 Jul; Q4 Oct
|  |  |  | Provide a refresher training one year after | [24 empty] | 1 | 1000 |  |  | 1000 | [6 empty] | Training workshop costs | 1000 |  | Consultant | bar: Q4 Oct
|  | Conduct a gender sensitive analysis of the situation of the 3 intervention centers in Kuwait and provide recommendations based on best practice |  | Develop a gender sensitive TORs for an International expert in Early Intervention and ensure equal opportunities for men and women in hiring | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 Apr
|  |  |  | Solicit proposals, hire and contract | [24 empty] | 1 | 53000 |  | 53000 | 0 |  |  | IC |  |  |  | Early Intervention Specialists | 53000 | Assessment and Recommendations Report | PADA /UNDP | bar: Q1 Mar to Q2 Apr
|  |  |  | Conduct the gender sensitive analysis and recommend best practices | [36 empty] | 0 |  | Consultants | bar: Q2 Jun to Q3 Jul
|  |  |  | Provide concrete recommendations for improving the early intervention centers in Kuwait | [36 empty] | 0 |  | Consultants | bar: Q3 Aug
Develop a standard model for Early Intervention Centers for PADA in Kuwait | bar: Q3 Aug to Q4 Oct
|  | Development of a triangular co-operation protocol i.e. South-South Exchange in development of Early Intervention prevention protocols and screening programs. |  | Organize exchange visit to Kuwait in relation to diagnosis and early intervention to share and learn from their experiences | [24 empty] | 1 | 11000 |  |  | 22000 |  |  | Travel tickets/DSA |  |  |  | South Exchange visits | 22000 | Visit reference material | Project Manager/PADA | bar: Q4 Oct to Q4 Dec; Q1 Mar to Q2 May
| Sub Total | [30 empty] | 53000 | 55000 | [7 empty] | 108000
| 1.3 Upgrade PADA monitoring and evaluation mechanisms for the PADA strategy and development projects Results Indicator 1.3 • Efficient and effective gender sensitive M&E for PADA projects Data Source: PADA internal documentation Frequency: annually Baseline (2016): No M&E system (Women : Men: ) 2:1 Target (2018): M&E system in place and staff trained | Apply improvements to M&E mechanism based on an assessment, gaps analysis that includes necessary, systems or tools. |  | Develop TORs for a gender sensitive RBM/M&E expert | [36 empty] | 0 |  | Project Manager/PADA | bar: Q1 Feb
|  | Put in place a framework using results oriented and evidence based indicators. |  | Solicit CVs, hire and contract and ensure equal opportunities for men and women in hiring | [24 empty] | 1 | 42550 |  | 42550 |  |  |  | IC |  |  |  | RMB/M&E specialist | 42550 | RBM and M&E framework | PADA /UNDP | bar: Q1 Mar to Q2 Apr
|  | Develop and implement an M&E capacity development program for national relevant technical staff |  | Conduct a mid-term review of development projects at PADA and provide recommendations including RBM and gender indicators | [36 empty] | 0 |  | Consultant | bar: Q2 May to Q2 Jun
|  | Ensure inclusion of gender sensitive indicators |  | Develop M&E framework for the projects in discussion with project staff | [36 empty] | 0 |  | Consultant | bar: Q3 Jul to Q3 Aug
|  | Develop and improve accessible customer services for PADA frontlines staff |  | Capcity Building for customer services for PADA frontlines staff | [24 empty] | 1 | 8505 |  | 8505 |  |  |  | IC |  |  |  | Workshops | 8505 |  | Consultant | bar: Q3 Aug to Q4 Nov
| Sub total | [30 empty] | 51055 | 0 | [7 empty] | 51055
Total Output1 | [31 empty] | 201982.4 | 447072.6 | [7 empty] | 649055
Output 2: Coordinated and well organized efficient efforts towards removal of barriers to the inclusion of persons with disabilities Indicator 2.1: Accessible guides and curricula are available for schools and VTCs Baseline (2016): No guides are available and curricula is general Target (2018): Guides and enhanced curricula in place and staff trained Indicator 2.2: Number of collaborative gender sensitive initiatives implemented with CSOs and PAYS that have direct impact on disabled inclusion Baseline (2016): a number of workshops was implemented with CSOs by PADA Target (2018): At least 2 initiatives implemented by 2018 | 2.1 Access to all types and degrees of disabilities at education or vocational training. Results Indicator 2.1: Accessible guides and curricula are available for schools and VTCs Educational Support Criteria & Guidelines Data Source: Project Documentation Frequency: annually Baseline (2016): No guides are available and curricula is general Target (2018): Guides and enhanced curricula in place and staff trained Guideline and criteria to determine Educational Support for student with disabilities in place | Through a consultative process, select pilot schools and vocational centers based on criteria and determine targeted types of disabilities |  | Conduct a consultation with stakeholders in PADA, MOE and building on the available MOE study define the support required for schools and VT sector for educational inclusion | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Sep
|  | Ensure the selected schools/VT centers targeting both girls and boys/women and men |  | Develop criteria to select the most relevant schools and VT centers and types of disabilities if needed | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Sep
|  | Develop a gender sensitive guide for school teachers based on "universal design" standards and train teachers in the selected schools |  | Develop the TORs for the development of the guide and curricula review to encompass universal standards for learning ensuring gender considerations | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Oct; Q4 Dec
|  | Develop a gender sensitive curriculum in co-ordination with ILO and KISR for vocational training |  | Identify relevant institutions (ILO/KISR/Universities) and invite them to submit proposals | [38 empty] | Project Manager/PADA | bar: Q4 Nov to Q1 Feb
|  | Train male and female teachers and caregivers in the selected vocational training centers. |  | Select and contract the selected institution | [24 empty] | 1 | 115000 |  |  | 115000 |  |  | RFP (Institutional Contract) |  |  |  |  | 115000 | Teachers Guide and Enhanced vocational curricula, Training Reports | PADA /UNDP | bar: Q4 Dec to Q1 Mar
|  |  |  | Develop the guide for the selected types of disabilities | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Feb; Q2 Apr
|  |  |  | Train the school teachers on basic concepts of inclusion of PWDs and on using the guides | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Mar to Q2 Jun
|  |  |  | Facilitate networking and information exchange among the teachers | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Feb to Q3 Jul
|  |  |  | Conduct an assessment of the selected VT centers existing curricula | [36 empty] | 0 |  | Consultant Institution | bar: Q1 Mar; Q2 May
|  |  |  | Enhance the curricula by adding accessibility components and guidance | [36 empty] | 0 |  | Consultant Institution | bar: Q2 Apr to Q3 Jul
|  |  |  | Train the teachers and caregivers on basic concepts of inclusion of PWDs and on using the guides | [28 empty] | 0 | [7 empty] | 0 |  | Consultant Institution | bar: Q2 Jun; Q3 Aug
|  | Improve employment assistance and job opportunities and launch initiatives to encourage employers to hire both men and women with disabilities |  | Seek partnerships with private sector firms (>50 employees) to hire PWDs and identify needed skills | [36 empty] | 0 |  | Project Manager/PADA | bar: Q1 Jan; Q1 Mar; Q2 May; Q3 Jul
|  |  |  | Conduct a job fair for private sector and PWDs seeking employment and/or webpage at PADA for jobs where PWDs can apply/Collaborate with CSOs for products as example | [24 empty] | 1 | 30000 |  |  | 30000 |  |  | Venue/Catering |  |  |  |  | 30000 |  | Project Manager/PADA | bar: Q2 May; Q3 Jul
|  |  |  | Identify and conduct south-south visit from best practices on employment of PWDs | [24 empty] | 1 | 15000 |  |  | 15000 |  |  | Travel/DSA |  |  |  |  | 15000 |  | Project Manager/PADA | bar: Q2 May; Q3 Jul
|  | Develop Guideline and criteria to determine Educational Support for student with disabilities |  | Develop TORs for Educational Support expert | [36 empty] | 0 | bar: Q3 Jul to Q3 Aug
|  |  |  | Solicit CVs, hire and contract and ensure equal opportunities for men and women in hiring | [36 empty] | 0 | bar: Q4 Oct to Q4 Nov
|  |  |  | Conduct an assessment of the current PADA system for Educational Support for student with disabilities including school fees | [24 empty] | 1 | 60000 |  | 16678.05 | 38915.45 |  |  | IC |  |  |  |  | 60000 | bar: Q4 Dec to Q1 Jan
Development of a guideline and criteria to determine Educational Support for student with disabilities | bar: Q1 Jan to Q1 Feb
[32 empty] | 16678.05 | 198915.45 | [7 empty] | 220000
| 2.2 Coordinate and Build capacity of civil society organizations (CSOs) working with persons with disabilities. Results Indicator 2.2: Number of collaborative gender sensitive initiatives implemented with CSOs and PAYS that have direct impact on disabled inclusion. Data Source: Project Documentation Frequency: annually Baseline (2016): a number of workshops implemented by PADA . Target (2018): At least two collaborative initiatives/year PADA partnership strategy and framework in place | Initiate a network for CSOs working with persons with disabilities. |  | Develop TORs for CSOs capacity building | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Aug to Q3 Sep
|  |  |  | Solicit CVs, hire and contract and ensure equal opportunities for men and women in hiring | [24 empty] | 1 | 100000 |  |  | 100000 |  |  | ICS |  |  |  |  | 100000 |  | Project Manager/PADA | bar: Q1 Jan to Q1 Feb
Support strengthen the dialogue and consultation among CSOs to promote removal of barriers and inclusion of persons with disability | bar: Q1 Mar to Q2 Apr
|  | Develop a joint action plan in consultation with CSOs for inclusion of PWDs |  | Identify of capacity building needs of CSOs (CSOs joined the network in phase two) by developing a self-assessment tools and encourage CSOs to voluntary apply self-assessment | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 Apr
|  | Support CSOs to develop internal improvement plan based on the above results |  | Review the improvement plan from CSOs and PAYS | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 May
|  |  |  | Support implementation | [24 empty] | 1 | 55000 |  |  | 55000 |  |  | IC/ Venue/Catering |  |  |  |  | 55000 | bar: Q2 May to Q2 Jun
|  | Enhance PADA partnership strategy and framework |  | Develop TORs for partnership strategy | [24 empty] | 1 | 100000 |  |  | 100000 |  |  | IC |  |  |  |  | 100000 |  | Project Manager/PADA | bar: Q3 Jul
|  |  |  | Solicit CVs, select, hire 4 local trainers | [36 empty] | 0 | bar: Q3 Sep to Q4 Oct
Conduct participatory assessment of current partnership and cooperation practices within PADA | bar: Q4 Nov to Q4 Dec
|  |  |  | Develop PADA partnership strategy | [36 empty] | 0 | bar: Q4 Dec to Q1 Mar
|  | Develop and launch a gender sensitive advocacy campaign on inclusion in education, labor market, the physical environment and social life for Kuwaitis and non-Kuwaiti disabled population in collaboration with CSOs and other stakeholders |  | Develop TORs for a media consultancy firm | [36 empty] | 0 |  | Project Manager/PADA | bar: Q2 May to Q2 Jun
|  |  |  | Solicit proposals, hire and contract | [24 empty] | 1 | 175000 |  | 0 | 175000 |  |  | RFP |  |  |  |  | 175000 | Design of PADA communication strategy and plan/Design of public campaign on inclusion of PWDs | UNDP/PADA | bar: Q3 Aug to Q3 Sep
|  |  |  | Discuss the messages and component with CSOs and develop the campaign with PADA | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Oct to Q4 Nov
|  |  |  | Implement the campaign | [36 empty] | 0 |  | Consultancy firm | bar: Q4 Nov to Q2 May
[32 empty] | 0 | 430000 | [7 empty] | 430000
Total Output 2 | [31 empty] | 16678.05 | 628915.45 | [7 empty] | 650000
Output 3: Enhanced technical expertise and organizational capacities for Universal Design and country-wide use of technology enablers for persons with disabilities Indicator 3.1: No. and type of Public Buildings included in the the universal design proposal. Baseline (2016): 0 Target (2018): TBD 285 by 2020? Indicator 3.2: Building code adopted and communicated to stakeholders Baseline (2016): Partially Target (2018): Fully 100% Indicator 3.3: No. of institutions who receive guides about/implement technology enablers and assistive adaptive strategies. Baseline (2016): TBD Target (2018): At lease 2 public website enabled and guides disseminated to at least 50 insitutions | 3.1 Issuance of Code and guidance for implementation of universal design within public government buildings (schools, health and social care buildings) Result indicator 3.1: Kuwait Universal Design code produced No. of Public Buildings included the universal design proposal Data Source: Project documentation Frequency: annually Baseline (2016): Limited design code not in compliance with UD principles Partial accessibility of PADA public building Target (2018): Kuwait national UD code in place PADA public building Universal Design adaptation in place | Finalize universal design code and submit to related authorities for approval |  | Hire short term consultant to review the Universal Design Code | [25 empty] | 36249 |  | 36249 |  |  |  |  | IC |  |  | Universal Design Code expert | 36249 | Universal Design Code | Project Manager/PADA | bar: Q2 May to Q3 Jul
Research and review the existing building code and any other existing codes related Universal Design in Kuwait. | bar: Q2 Jun to Q3 Jul
Consult and discuss with a wide range of stakeholders including PADA, Kuwait municipality, the National Committee on Codes, the Ministry of Public Works, the Public Authority of Housing Welfare | bar: Q3 Jul
Finalize universal design code in consultation with stockholders and submit to related authorities for approval | bar: Q3 Jul to Q3 Aug
Support and facilitate Issue regulations for upgrading | bar: Q3 Sep to Q4 Oct
|  | Inventory which public facilities and outdoor areas need to be upgraded and prioritize in consultation with stakeholders . |  | Develop TORs for an architectural/engineering firm with universal design experience e | [36 empty] | 0 |  | Project Manager/PADA | bar: Q3 Sep to Q4 Oct
|  | Develop a design proposal for several models and provide specifications for adjustments compliant with the code |  | Solicit offers, select and hire | [24 empty] | 1 | 50751 |  |  | 50751 |  |  | RFP |  |  |  | Architectural/Engineering firm for Universal Design | 50751 | Design proposal with specification and execution plan | UNDP/PADA | bar: Q4 Oct to Q4 Dec
|  | Develop a phased execution plan for upgrading existing public buildings, facilities and outdoor areas through KNDP projects and funds. |  | Develop the design proposal and specs for adjustments and execution plan | [36 empty] | 0 |  | Engineering Firm | bar: Q1 Jan to Q1 Feb
|  | Issue Regulation for new buildings and upgrading | [38 empty] | 0 |  | PADA and Municipality | bar: Q2 Apr to Q2 Jun
| sub total | [30 empty] | 36249 | 50751 | [7 empty] | 87000
| 3.2 Ensure “new” buildings and facilities comply with universal design Result indicator 3.2: Indicator 3.2: Building code adopted and communicated to stakeholders Data Source: Municipality of Kuwait Frequency: annually Baseline (2016): Partially Target (2018): Fully 100% | Set up a Universal Design unit in PADA |  | Based on the organogram, PADA to hire/assign staff for the unit | [36 empty] | 0 |  | PADA | bar: Q4 Dec to Q1 Jan
|  | Build Staff capacity on Universal Design |  | Identify trainers from Universal Design Centers on the different specializations and train staff | [24 empty] | 1 | 31000 |  |  | 31000 |  |  | Cooperation agreements |  |  |  |  | 31000 | Training Reports | Project Manager/PADA | bar: Q4 Dec to Q2 Apr
|  | Introduce and promote universal design concept to the private and public sector, architects, engineers and planners |  | Organize the conference for private sector firms, architects, engineers and planners and present options, benefits, experiences and best practices in universal design from other countries | [24 empty] | 1 | 30000 |  | 1655 | 28345 |  |  | Venue/catering |  |  |  |  | 30000 |  | Project Manager/PADA | bar: Q4 Dec; Q3 Sep
|  |  |  | Announce criteria for private sector to qualify for symbolic award | [31 empty] | Catering |  |  |  |  | 0 |  | Project Manager/PADA | bar: Q3 Aug
|  |  |  | Select the most compliant private sector buildings based on the criteria | [36 empty] | 0 | bar: Q4 Oct to Q4 Nov
|  | Organize a national conference to prompt universal design concept and issue a symbolic award for best practice in cooperation with Municipality of Kuwait |  | Organize symbolic award ceremony on PWDs day on 3 December | [24 empty] | 1 | 2000 |  | 0 | 2000 | [7 empty] | 2000 | bar: Q4 Dec
|  | South exchange with Countries on Universal Design (e.g. Ireland) |  | Identify and liaise with institutions with Universal Design Centers in other countries and sign a cooperation agreement with one | [31 empty] | Cooperation agreements |  |  |  |  | 0 |  | UNDP/PADA | bar: Q1 Feb to Q1 Mar; Q3 Sep
| Sub total | [30 empty] | 1655 | 61345 | [7 empty] | 63000
| 3.3 Ensure implementation of technology enablers and adaptive strategies Result indicator 3.3: No. of institutions who receive guides and implement technology enablers and assistive adaptive strategies. Data Source: Project Documentation Frequency: annually Baseline (2016): 0 Target (2018): PADA public website and online services enabled & accessible and guides disseminated to at least 50 institutions | Identify needs and perform analysis based on best practices in accessible digital learning platforms, adaptive strategies and assistive devices. |  | Develop TORs for a specialized firm/institution in accessibility and adaptive strategies in digital platforms | [36 empty] | 0 |  | Project Manager/PADA | bar: Q4 Nov to Q4 Dec
|  | Define requirements, policies and regulations and develop and disseminate guidelines and standards |  | Solicit proposals, hire and contract | [24 empty] | 1 | 50000 |  |  | 50000 |  |  | RFP |  |  |  |  | 50000 | Best practices, guide and websites | UNDP/PADA | bar: Q1 Jan to Q1 Feb
|  | Promote implementation in public and private sector |  | Develop need analysis based on best practices and guidelines and Standards | [36 empty] | 0 |  | Specialized firm | bar: Q1 Mar
|  | implement adaptive strategies in PADA websites and services including building the capacity of PADA IT staff on the guidelines and international standards |  | Disseminate by PADA to various public and private organizations | bar: Q1 Mar to Q2 Apr
|  |  |  | Implement adaptive strategies in selected websites (PADA and e-go and possibly others) | [36 empty] | 0 |  | Specialized firm | bar: Q2 Apr to Q2 May
| Sub Total | [30 empty] | 0 | 50000 | [7 empty] | 50000
Total Output 3 | [31 empty] | 37904 | 162096 | [7 empty] | 200000
Activity 4: Management | Project Manager (Acting) | Hire Acting Project Manager | [26 empty] | 1 | 60620 |  | 60620 | 0 | IC | 3.5 months | [5 empty] | 60620 | bar: Q1 Feb to Q2 May
| Project Manager (IC) | [27 empty] | 6 | 9333.3333 |  | 56000 |  |  | 6 months | [5 empty] | 56000 | bar: Q2 Jun to Q4 Dec
| Project Manager (SC) | Hire Project Manager | [26 empty] | 12.5 | 10000 |  |  | 125000 | IC | 12.5 months | [5 empty] | 125000 |  | UNDP/PADA | bar: Q1 Jan to Q4 Dec
| Project Assistant | Hire Project Assistant | [26 empty] | 20 | 5284.6 |  | 42536 | 63804 | SC | 20 months | [5 empty] | 106340 |  | UNDP/PADA | bar: Q2 May to Q4 Dec
| Advertisements, translation and Admin | [29 empty] | 1878 | 9686 | 5314 | [7 empty] | 16878 | bar: Q1 Mar to Q4 Dec
| Stationery & laptops | [30 empty] | 12037 | 4613 | [7 empty] | 16650 | bar: Q3 Jul
| Contingency | [31 empty] | 37138 | [7 empty] | 37138 | bar: Q3 Aug to Q4 Dec
| Evaluation | Hire and conduct the evaluation | [26 empty] | 1 | 25000 |  | 0 | 25000 |  |  | RFQ |  |  |  |  | 25000 |  | UNDP/PADA | bar: Q4 Oct to Q4 Dec
| Sub Total | [29 empty] | 1878 | 180879 | 260869 | [7 empty] | 443626
Total Output 4 excluding GMS | [30 empty] | 1878 | 180879 | 260869 | [7 empty] | 443626
Total Budget excluding GMS | [30 empty] | 1878 | 437443.45 | 1498953.05 | [7 empty] | 1942681
3% GMS | [30 empty] | 56.34 | 13123.3035 | 44968.5915 | [7 empty] | 58280.43
|  | Total Budget including 3% GMS | [28 empty] | 1934.34 | 450566.7535 | 1543921.6415 | [7 empty] | 2000961.43