## Data
Project ID | Project Name | Category (IC, Service, Goods, Civil Works) | Description of goods, services or works | Unit of Measure | Quantity | Estimated Unit Price in USD | Estimated Total Price in USD | Available budget in USD | Method of Procurement | Evaluation criteria | Justification for non-competitive procurement, if any | Start of Activity | Completion of Activity | Responsible authorities | Requestor | Remarks/justification | Budget | Deadline
83838 | Fostering Youth Resiliency | IC | Project Evaluator | Consultant | 1 | 6000 | 6000 | 6000 | Advertisement | Technical and Financial | N/A | Q4 2014 | Q4 2014 | UNDP and KRSC | Governance Portfolio | N/A | 83838 | 2014-12-31
83838 | Fostering Youth Resiliency | IC | Project Sociologist | Consultant | 1 | 17750 | 17750 | 17750 | Already Recruited | Already Recruited | N/A | Q4 2013 | Q4 2014 | UNDP and KRSC | Governance Portfolio | N/A | 83838 | 2014-12-31
83838 | Fostering Youth Resiliency | IC | Project Social Worker | Consultant | 1 | 7100 | 7100 | 7100 | Advertisement | Technical and Financial | N/A | Q2 2014 | Q4 2014 | UNDP and KRSC | Governance Portfolio | N/A | 83838 | 2014-12-31
83838 | Fostering Youth Resiliency | Service | Workshop Costs (Catering, Printing, etc) | ea | 2 | 24850 | 24850 | 24850 | RFQ | Financial | N/A | q3 2014 | q4 2014 | UNDP and KRSC | Governance Portfolio | N/A | 83838 | 2014-12-31

## Summery
Sum of Estimated Total Price in USD
Description of goods, services or works | Requestor | Total
All in one, colored | Sahar Shawa | 300
Blind for security office at the entrance | Qaiser | 60
Dell Desktop - All-in-one | Omar | 1300
Dell Laptop | Omar | 4200
HP LaserJet P2055 | Saed Adam | 370
HP Laserjet Pro 200 colour MFP M276n (CF144A) | Asmae Aitssi | 370
| Qaiser | 370
| Qaiss Dashti | 370
Lamination Machine - HR | Summer | 200
Lamination Machine - Security office | Qaiser | 200
lamination sheet - HR | Omar | 200
multisheet scanner for multiple paper formats | Dalal | 900
Wireless keyboard & wireless mouse | Omar | 150
Grand Total |  | 8990