## RC-HC-DO and UNCT Workplan
2011 Annual Report and Performance Appraisal Planning
Please note that only those areas in bold are mandatory
State the UNDAF outcomes
Outcome 1:
Outcome 2:
Outcome 3:
Outcome 4:
Outcome 5:
Part 1: 2011 RC/HC/DO and UNCT Annual Report
KEY RESULT AREAS |  | Expected Output1 | Performance Indicators 2 | Actual Outputs at Year End | Funds required/ spent at end year | [8 empty] | Additional Support Needed from HQ or Regional Director's Team | Target Date
[5 empty] | SRC |  | UNCCF |  | Transition Funds | UN entities3 |  | Other
Result Area 1: Coordination for Results
UNCT Contribution to the National Development Plan/Poverty Reduction Strategy/MD and MDGs plan | UN support to formulation/implementation of relevant national strategies or plans e.g. JAS/NDP/PRSP | 1. UN designs, plans and develop implementing mechanism of UNDAF that is a response to the national plan of 7th NSEDP, using results-based management. | 1. Development of UNDAF Action Plan for the next cycle with M&E Framework that reflects corresponding indicators | 1. UN developed the UNDAF Action Plan 2012-2015 aligned with the national development agenda defined in the 7th NSEDP and the MDGs, with a strong M&E framework and common budgetary framework. UNDAF indicators were developed in a manner to optimally support monitoring of both the UNDAF and national development goal achievement simultaneously. When appropriate, UNDAF indicators are the same as for the 7th NSEDP and Sectoral Plans (e.g. Education, Health, HIV/AIDS) |  |  | 5000
|  | 2. UN effectively supports the Sector Working Group mechanism and promotes more integrated and streamlined national development work | 2. UNCT inter-agency working mechanisms operational and aligned to support the national development system | 2. UN Co-Chairs 5 SWGs and is the main counterpart for Gender Theme Group. This has helped strengthen SWG mechanism and the work of individual SWGs (particularly the SWG secretariat capacity both organizationally and substantively/technically), and provided strong support to develop SWGs' reports and feedback to sectoral plans in preparation for the Round Table Implementation Meeting
|  | 3. UN agencies co-chairs of Sector Working Group (SWGs) work towards developing/reviewing sectoral strategies for their sectors, which are aligned to the 7th NSEDP and UNDAF UN | 3. Respective UN agencies co-chairs the Sector Working Group and promotes streamlined working relationship between NSEDP and UNDAF | 3. UNDAF AP Outcome Groups are required to align as closely as possible and as relevant with existing national coordination mechanisms, including Sector Working Groups, technical working groups and other national coordinating mechanisms to ensure more integrated and streamlined national development process and work. UNCT decided to use the same monitoring tool for the UNDAF Action Plan as that used by the Government to monitor the 7th NSEDP, thus ensuring greater alignment between NSEDP and UNDAF
| UN plan to support the implementation of the Millennium Declaration, including scaling up IADG/MDG initiatives | 1. Strengthened UN support to national MDG strategy development and implementation. | 1. MDG strategy development reflected in the UNDAF Action Plan for alignment and operationalization | 1. UNDAF Action Plan was developed as an operational framework based on the tripartite relationship between the efforts on MDGs, NSEDP and UNDAF. The commitment of the UN to support Lao PDR to bring the MDGs in Lao PDR back on track, and to see them achieved by 2015, is reflected in the UNDAF: four UNDAF outcomes directly contribute to the achievement of the three most seriously off-track MDGs; three UNDAF outcomes directly contribute to the achievement of the four other off-track MDGs.
|  | 2. Increased UN coordination capacity on priority development areas to support scaling up NSEDP interventions - food security and nutrition, gender, HIV/AIDS, Climate Change, civil society/partnership. | 2. There is UN-wide inter agency mechanism that coordinates policy dialogue at multi-sectoral level on key NSEDP interventions (e.g. REACH, Gender Theme Group, etc) | 2. A UN-wide inter-agency mechanism coordinates policy dialogue on nutrition at the multi-sectoral level and supports the SUN movement in order to tackle more strategically the issue of undernutrition (seriously off-track MDG 1) in a concerted (i.e. inter-ministerial/inter-agency) manner.
|  | 3. Strengthened capacity of Department of Statistics to monitor and track the MDGs through LaoINFO. | 3. LaoINFO is operational and updated | 3. The Lao Statistics Bureau of MPI launched a new DevInfo project aiming to enhance the current LaoInfo database: the project aims at positioning LaoInfo as the central repository for development data in the country and establish tools to more effectively monitor the 7th National Socio-Economic Development Plan (NSEDP) 2011-2015.
UN support to capacity development strategies
| UN assistance to national authorities for the preparation of the national report on the implementation of the Brussels Programme of Action of LDCs 4 | 1. UN assists Government in further revision of the Brussels Programme of Action | 1. UN supports Government in preparation for the global reporting and dialogue on Brussels Programme of Action | 1. UN assisted the Government in preparation for the global reporting and dialogue on the Brussels Programme of Action during the Istanbul conference on Least Developed Countries in May 2011 | [5 empty] | 1000
Formulation/implementation of a transition plan or strategy 5
Other
Aid Coordination/ Management / Paris Declaration | Planned efforts to making use of national systems in the areas such as programme/project reporting, PRS/sectoral monitoring and evaluation systems, annual PRS/sectoral performance reviews, national procurement systems, etc | 1. UN actively participates in Aid Effective Task Force and delivers messages on as One UN to promote more harmonized, accountable and results oriented aid management | 1. UN actively participates in the Aid Effectiveness Task Force | 1. UN actively supported the Round Table Process and the RTIM was considered to be a success by the Government and many development partners. The central theme - “Pathway to the Achievement of 7th NSEDP/MDGs and 2020 LDC Graduation” - supported by UN successfully guided Government-led discussions with Development Partners on MDG-based growth, ensuring national ownership and leadership. | [5 empty] | 1000
|  | 2. UN delivers coordinated response in preparation for the Busan Aid Effectiveness conference 2011 (follow up to Accra) | 2. Survey is completed by the UN in a coherent and coordinated manner | 2. The UN provided coherent and coordinated input into the Paris Declaration Survey on Aid Effectiveness in preparation for the Busan Aid Effectiveness conference in 2011
| UN support to aid coordination/management | 1. UN facilitates development dialogue with Development Partners on a periodical basis to enhance donor coordination. | 1. Informal Quarterly Development Partner meetings are held to increase dialogues on key development issues surrounding, NSEDP, and other emerging issues | 1. Donor coordination was enhanced through regular and streamlined Informal Quarterly Development Partners (IQDP) meetings focusing on more efficient and effective support to the Round Table Process and other key emerging development issues. UN also convened several ad-hoc meetings to enhance donor coordination on key issues such as relief efforts after Typhoon Haima. UN furthermore supported the Government in analyzing national development planning processes, in particular focusing on the sector-working group relationship with the Round Table process, which is the ultimate platform for development dialogue. | [6 empty] | 3000
|  | 2. Non-traditional and non-resident donors development dialogue is better facilitated and improved. | 2. Non traditional donors are invited and participate to the informal Quarterly Development Partner meetings | 2. Active participation of non-traditional and non resident donors have been attained with the participation of India, Russia, Myanmar, Indonesia, etc, in the IQDP meetings. Regular briefings of non-resident donors on the Round Table Process were made by the UN Resident Coordinator to ensure wider development dialogue
|  | 3. UN supports evidence-based planning, budgeting and monitoring through LaoINFO | 3. LaoINFO is set up to monitor NSEDP and UNDAF Action Plan | 3. The Government of Lao PDR and the UNCT will use the same DevINFO technology to monitor the 7th NSEDP and the UNDAF Action Plan
Other
Other
UNDAF/Common Programming | Efforts to align UN programme cycle with national development cycle | 1. UNDAF Action Plan is aligned to the national cycle (7th NSEDP) | 1. UNDAF Action Plan is developed and aligned to the national development plan, 7th NSEDP, together with MDG Acceleration Framework | 1. The UNDAF Action Plan was developed as an operational framework based on the tripartite relationship between the efforts on MDGs, NSEDP and UNDAF and is fully aligned with the national cycle and supportive of national development priorities and goals.
| Preparation of Country Analysis/UNDAF/UNDAF Action Plan | 1.UNDAF Country Analysis and UNDAF Action Plan are developed in consultation with Government and stakeholders | 1. Number of key consultations held with Government and stakeholders per UNDAF road map | 1. The UNDAF Action Plan is the result of a series of consultations with Government counterparts both at the policy and technical level. | [5 empty] | 45000 | 46000
|  | 2.1 UNDAF Action Plan is developed to its full potential with a view to it being more operational with appropriate M&E framework and system in place | 2.1 UNDAF Action Plan is not only developed with solid results matrix and M&E framework but also contains implementation strategy including resource mobilization strategy | 2.1 The UNDAF Action Plan was developed to serve the following purposes: - To be a programming document for all UN agencies working in the Lao PDR describing the strategic priorities of the UN system and results planned to be achieved by 2015. - To be an operational document that describes how these priorities will be achieved. - T be a planning and monitoring tool with an indicator framework for implementing partners, donors and UN system agencies. - To be a common budgetary framework for the Government, implementing partners and UN system agencies, and for the information of donors and other partners, as well as more strategic planning by UNCT of resource mobilization efforts.
|  | 2.2 Appropriate inter-agency mechanism is reviewed, revised and developed to ensure effective and efficient UN working mechanism to better support implementation of national development as one UN | 2.2 UNDAF Action Plan is supported by clear operational plan containing inter-agency governance model and management mechanism for UNCT | 2.2 The UNDAF Action Plan contains an inter-agency governance model and programme management mechanism with a view to ensure greater coordination amongst the UNCT to better support implementation of national development goals.
Progress towards UNDAF outcomes (inputs provided by theme group chairs)
| Implementation of UNDAF M&E framework | 3. Programming and review process are better integrated to strengthen RBM of UNDAF. | 3. UNDAF Action Plan is developed with consideration for UNDAF annual reviews | 3. The UNDAF Action Plan Outcome Groups are responsible for substantive and detailed monitoring and the management of reviews and evaluations of UNDAF outcomes, outputs and the Common Resource Framework of the UNDAF Action Plan. The UNCT decided that the UNDAF Action Plan is a "living document" and that annual reviews can be the platform to make minor revisions to the Results Matrix through consensus and in consultation with partners and the Government in order to adapt to changing circumstances. UNDAF annual reviews and evaluations will inform the programming for the next UNDAF cycle.
| UNDAF Annual Review/ UNDAF Evaluation/SOF | 4. UNDAF evaluation for current cycle prepared with a view to link with next cycle UNDAF | 4. UNDAF evaluation is planned and organized | 4. Considering the high turn-over among UNCT members and deputies and the delay in the UNDAF process, as well as budgetary constraints, the evaluation of the current UNDAF could not be organized. |  |  | 7000
Joint planning initiatives with UN peacekeeping, peacebuilding, political and humanitarian actors (e.g. UNDAF plus, Integrated Strategic Framework) .
Other
Joint Programmes 6 | Preparation/ implementation of new Joint Programmes | 1. Increased UN coherence through endorsement of new joint programmes aligned to the next cycle UNDAF Action Plan | 1. Number of joint programmes that have been developed as results of UNDAF Action Plan development exercise | 1. The UNDAF Action Plan development process provided an opportunity to initiate the development of joint programmes proposals in the following areas, which are fully aligned with the UNDAF cycle and results framework: (1) recovery of natural disaster victims, (2) master planning of urban wetlands, and (3) integrated community-based development. Several ongoing Joint Programmes have continued implementation with two or more UN agencies working together through a common work plan and budgetary framework: (1) SELNA (Programme Support to an Effective Lao National Assembly) (with UNDP, UNICEF, UNFPA, UNAIDS, UN Women, UNODC) - managed through pooled funding; (2) Support for Integrated Management of Acute Malnutrition (WFP, WHO, UNICEF - designed as a pass through mechanism); (3) Strengthening Maternal, Neonatal and Child Health and Nutrition (MNCHN) (WFP, WHO, UNICEF and UNFPA - pass through mechanism); (4) Support for the Laos Social Indicator Survey (UNICEF, UNFPA and UNDP - parallel funding with a joint MOU with the Ministry of Health); (5) GPAR (UNDP/UNCDF); and (6) Enhanced sustainable tourism, clean production and export capacity (ITC, ILO, UNCTAD, UNIDO). The UN RC facilitated several joint programme opportunities that are and have been discussed by the UN development system in Laos as a whole and subsequently undertaken by respective UN agencies with particular comparative advantage such as: 1) urban wetland planning (FAO, UNDP, UN Habitat, UNESCO); and 2) disaster risk reduction (UNDP, Habitat, UN Women). Future joint programme opportunities will become clearer in consultation with the Government and Development Partners and aligned with the new UNDAF |  |  | 11000
| M&E of Joint Programmes | 2. Joint-Programme are better accounted for through appropriate M&E framework. | 2 Joint Programmes contain solid M&E framework | 2. Joint Programme contain solid M&E frameworks aligned with the UNDAF M&E framework
Other
HACT | Status of HACT implementation/compliance7 in the country | 1. Full implementation of HACT is pursued | 1. FACE is used by partners and new assurance framework is developed | 1. The FACE form is used by partners and assurance plan has been prepared
| Strengthening national systems/capacities through HACT | 2. Training and related capacity-building measures on public financial management provided by HACT team. | 2. Training designed, planned and implemented | 2. A workshop was organized to present overall results of the 2006 and 2009 micro-assessments and to serve as the basis for a brainstorming with NIPs to outline capacity developments strategies to further develop NIP capacity in financial management of UN assistance
Other
Gender Equality | UN support to incorporation of gender equality in national planning processes (such as National Development Strategies; PRSPs; SWAPs; Joint Assistance Strategies, etc.) | 1. UN supports gender initiatives as outlined in the 7th NSEDP sectoral plans (including education, health, agriculture, labour & legal sector) fully incorporate gender specific actions 2. UN supports national and sectoral plans that contain gender specific indicators and targets, and built-in mechanisms to ensure gathering of gender disaggregated data; and provide for gender specific budgetary actions. | 1. UN Gender Theme Working Group actively promotes women's empowerment initiatives to support women's machinery and law making body 2. UN supports Government in providing technical inputs on gender disaggregated data such as LSIS 3. UN Gender Theme Working Group is actively operational | 1.UN supported dialogue on implementation and monitoring approaches for the National Strategy for the Advancement of Women 2011-15, with a view to streamline the working relationships between the Sector Working Groups and the informal gender working group and better support incorporation of gender-specific actions in sectoral plans (including gender-disaggregated data, gender specific budgetary actions, gender specific indicators and targets, etc.). UN supported the National Assembly to strengthen legislation on GBV/VAW/DV. 2. UN also supported MoH and MPI in implementing LSIS which incorporates both women's and men's concerns 3. The Gender Theme Group contributed to the joint assessment exercise after Typhoon Haima and ensured that gender-sensitive tools were used to better support planning of the recovery efforts. The Gender Theme Group was also actively operational. The meetings, however, were held on the need basis to discuss on key gender related issues to support key UNCT efforts, such as inputs to UNDAF.
| Capacity development for gender theme groups to support UNCT to respond to national priorities for gender equality | 1. Gender Group is better able to focus, prioritize and harmonize as One UN to support national planning process. | 1. Gender Theme Group develops a work plan, reflecting initiatives to be carried out as one UN | 1. As per the UNDAF Action Plan, the existing UN gender theme group and the informal gender working group to some extent was used as a platform to discuss and ensure gender mainstreaming throughout all outcomes and in all stages of the UNDAF planning, programming, monitoring and evaluation, in close partnership with lead agencies of each outcome.
|  | 2. Strengthened UNCT capacity to respond to national priorities for gender equality through more systematic sharing of lessons learned, development of joint initiatives, and harmonization of existing programmes and activities. | 2. Gender Theme Group is operational and engages in active dialogue with women's machinery to support joint activities related to women's empowerment | 2. The Gender Theme Group engaged in active dialogue with LaoNCAw and LWU to ensure information sharing and joint support to the key activities organized by LaoNCAW and LWU, including the VAW/GBV campaign in 2011 during the 16-day activism.
| Other | 1. UN supports Government to respond to key CEDAW recommendations in a coordinated manner | 1. CEDAW reporting is supported by the UN | 1. UN supported Lao NCAW in drafting responses to the follow up recommendations in the concluding observations of the CEDAW committee on; 1) women migrant workers; and 2) violence against women.
HIV/AIDS | Establishment of Joint UN Team on AIDS and implementation of joint programme of support on AIDS | 1. UN is better able to advocate HIV/AIDS issues as One UN (internally / externally). | 1.1 Inter Agency AIDS Group develops Annual work plan to deliver as joint UN initiative on HIV/AIDS | 1.1 The Joint UN Programme of Support on AIDS 2011 (JUNP 11) - The development of the JUNP 11 was based on the UNAIDS Getting to Zero Strategy, integrated in the UNDAF and aligned with the National Strategy and Action Plan 2011-15. The JUNT 2011 management arrangements allowed for swift and flexible response to the rapidly changing environment faced by the HIV Response through the maximized involvement of the 25 Members that makes up the AIDS Team. - The JUNP 11 has positioned itself as the main provider of technical assistance and expertise and is the second largest contributor of financial resources in support to the HIV Response. Collective efforts have resulted in a number of breakthroughs in essential but under-resourced components of the national HIV Response. | [5 empty] | 1651084 | 1446449
|  |  | 1.2 World AIDS Day activities supported through inter-agency collaboration. | 1.2 The World AIDS Day 2011 Commemorations (WAD 11) The Centre for HIV/AIDS, the VTE Capital Heath Department, the Ministry of Education, civil society, and the media organized a one month HIV campaign with the theme “getting to zero – Taking the lead to protect young people”. As for previous edition of the WAD the JUNT 11 has worked with the campaign organizers to make this event a success. The World AIDS Day one month campaign provided more than 600 young people with a better understanding of the country HIV epidemic through a month of interactive debates with National HIV Programme Experts, UN and civil society partners and people living with HIV in the context of the new the Political Declaration on HIV/AIDS: Intensifying our Efforts to Eliminate HIV/AIDS” and the new UNAIDS Strategy: Getting to Zero. The events were reported on in national newspapers, radio broadcasts and television programmes.
|  |  | 1.3 IEC materials available in all UN offices. | 1.3: See reporting under point 3.
| UN support to the national response to AIDS through strengthening the Three Ones | 2. UN enhances support on policy support in HIV/AIDS. | 2. Policy support in HIV/AIDS provided by the UN. | 2. Policy and Programme Support to the National HIV Response The annual review of the JUNP 11 matrix indicated that out of a total of USD 1,760,000 mobilized this year significant resources were directed to collectively address strategic priority areas at policy and programme level. Some of the main interventions included: (1) A comprehensive research agenda to inform the HIV Response and advocate to address barriers to programme implementation; (2) A HIV Harm Reduction programme in two demonstration sites and an integrated PPTCT/MCH programme in 6 demonstration sites; (3) The development of a legal framework on HIV and for HIV Law related interventions; (4) A set of interventions to address the need of women and girls in the context of HIV; (5) The support to the Lao Network of People living with HIV to extend their network, to participate in policy dialogue and conduct the first ever National Stigma Index Survey; (6) Other interventions were also conducted within the framework of the JUNP 11 but implemented by individual agencies based on available expertise and resources.
| HIV/AIDS in the Workplace | 3. Progress in implementation of the UN Cares 10 Minimum Standards in Lao PDR. | 3.1 HR/operation managers follow code of conduct on HIV. 3.2 UN staff and dependants aware of HIV/AIDS related issues through implementation of the UN 2009 HIV Learning Plan. 3.3 Condoms are available on all UN premises. | 3. UN Cares Programme The UNCT made significant progress towards implementing the UN Cares 10 Minimum Standards in Lao PDR with regards to the following: - Information on HIV Transmission and Treatment - Learning that addresses Stigma and Discrimination - Condoms available at all UN premises - Access to Voluntary Counseling and Testing - Managerial commitment Further progress was achieved by establishing Dispensary Focal Points as UN Cares Focal Points and launching a UNCARE Survey. Moreover, HIV/AIDS awareness sessions have been organized by agencies | [7 empty] | 10000 | 10000
Other
Human Rights | Application of Human Right Based Approach | 1. Human Rights Based Approach is increasingly mainstreamed into UN Lao PDR development programming, in line with improved understanding of the HRBA among UN staff. | 1. UNDAF Action Plan is developed considering human rights as one of the 5 key principles | 1. The UNDAF Action Plan reflects a human rights based approach as one of the 5 key programming principles and is explicitly targeting the most vulnerable, women, children, young people and the disabled in the most remote areas
|  | 2. UN engages more with civil society in discussing human rights issues by creating opportunities for UN wide dialogues | 2. Civil Society Advisory Board meetings are held twice a year in lieu of the UNCT meetings | 2. UNRC and UNCT strongly advocated for increased involvement of civil society in the Round Table Process
|  | 3. Human rights issues are reflect in the next cycle UNDAF Action Plan as one of the 5 key principles of UNDAF | 3. UNDAF Action Plan is targeting the most vulnerable, women, children, young people and the disabled in disadvantaged areas | 3. See above
| Strengthening the capacity of UNCTs to support national human rights protection systems | 4. UN maintains strategic dialogue with respective development partners on emerging human rights issues | 4. UN participates in informal meetings with development partners on emerging issues | 4. UN has maintained strategic dialogue with development partners on key human rights issues, including through informal meetings.
5. The UN continued to support the implementation of the National Plan of Action on Human Trafficking and the COMMIT Sub-Regional Plan of Action II.
Other
Common Services and Premises | Status of initiatives to increase collaboration and cost-effectiveness of UN business operations in support of programme delivery (common services and premises) | 1. Good quality emergency medical care provided to 1,200 UN staff and dependents in Lao PDR by an adequately funded UN Dispensary. | 1. UN Dispensary is operational and providing basic medical treatment to UN staff and dependents | 1. The UN Dispensary has been fully funded by UN agencies and provided quality emergency medical care to approximately 60 patients on average (UN staff or dependents) per month and 31 evacuations to Thailand were carried out. Medical supplies have been secured, including vaccine for the avian influenza. Joint procurement has been ensured and vaccination has been deployed through the UN dispensary.
|  | 2. Appropriate DSA rates reflect 2011 reality in the different locations throughout Lao PDR. | 2. DSA rates are reviewed by OMT | 2. A DSA review by the OMT was carried out in consultation with other development partners, including the EU Delegation, and harmonized DSA rates were endorsed by UNCT and are now applicable
|  | 3. Increased cost-effectiveness of UN operations through conclusion of at least one new joint Long Term Agreement (LTA) and establishment of a joint UN vendor list. | 3. Number of LTA and joint UN Vendor List established | 3. A Long Term Agreements are in the process of being negotiated with key suppliers (internet provider, bank, guard, etc.). A bidding process is underway for the selection of a single internet services provider. Common banking fees are currently negotiated by the OMT Task Force on banking services.
|  | 4. Better staff retention and better attraction of talent through payment of more competitive salaries by UN agencies. | 4. Salary survey implemented through OMT | 4. A salary survey was carried out, and a review of Service Contract salary scale has been undertaken with the view to ensure the payment of a more competitive salary to retain talented staff.
| Other | 5. OMT capacity is enhanced to support better inter-agency common country programme (i.e. - UNDAF Action Plan) to deliver as one UN | 5. OMT meetings and mini retreats are held 5.1 OMT develops annual work plan | 5. OMT meetings are organized regularly and well attended. Under the UNDAF Action Plan, the OMT is acknowledged as key to support better the inter-agency common country programme to deliver as One UN. The OMT has thus continued to be responsible for overseeing progress in delivering common services and systems and to facilitate the standardization of operational mechanisms. 5.1 The OMT has an annual work plan supporting key UNCT efforts and regularly reports to UNCT on progress.
Other
Result Area 2: Coordination of Emergency Preparedness and Relief
Preparedness | Coordination of emergency preparedness efforts of UNCT members and relevant humanitarian actors | 1. UN supports more coherent and coordinated natural disaster risk reduction measures by strengthening Inter-Agency Standing Committee together with Government | 1. Inter Agency Standing Committee meetings occur consistently throughout the year 1.2 After Action Review matrix is reviewed and implemented | 1. The Inter Agency Standing Committee has met regularly throughout the year through regular meetings and workshops. 1.2 The Inter Agency Standing Committee work has been streamlined to ensure the implementation of the After Action Review Matrix. The TOR for IASC was reviewed to encompass Disaster Risk Reduction and was endorsed by Government. An Inter-Agency Contingency Plan technical working group is in the process of developing the Inter-Agency Contingency Plan, the draft framework for which was finalized in 2011. The plan is expected to be ready as a working document for trial during the 2012 rainy season. |  |  | 10000 | [5 empty] | 21846
|  | 2. UN supports government capacity building measures on natural disaster management through support of national disaster preparedness framework | 2. National disaster preparedness framework is developed | 2. UN supported the National Coordination Body on Disaster to develop national disaster preparedness framework and report.
|  | 3. UN supports government capacity building on business continuity planning including multi-sectoral pandemic preparedness of Government. | 3. Business continuity plans are developed for key line sectors 3.1 UN and Government discussion takes place at policy level on multi-sector business continuity plan | 3. Laos was recognized as a best practice country in the region for pioneering the development of BCPs within the public sector. The creation of the BCP Template and its use by trained Ministry BCP Teams was a groundbreaking process in the public sector in Asia and formed the basis for most of the BCP training, workshops and technical assistance between December 2009 and May 2011. Given the starting point of near zero awareness of Business Continuity Planning at the Government and ministry level in 2009, coupled with the absence of BCP resources and a roadmap, this should be seen as a significant achievement. Ten Key Ministry BCPs have been developed. In addition, five Ministries completed Operational BCPs: 1) Ministry of Industry and Commerce, 2) Ministry of Public Security, 3) Electricite Du Laos (EDL), 4) National Authority for Post and Telecommunication (NAPT) and 5) Vientiane Water Supply Authority (Nampapa Lao). | [8 empty] | 83780
Relief | Establishment of Humanitarian Country Team
Development of a response plan
Coordination of humanitarian operations
Advocacy
Resource mobilization
| Other |  |  | 1. Emergency response and recovery efforts were coordinated under the umbrella of IASC to ensure inter-agency coherence of emergency response and more effective contribution to the joint assessment of damage, loss and needs following Typhoon Haima. 2. an update on the emergency situation were developed by the RC Office and shared with OCHA and Development Partners.
Result Area 3: UN Advocacy and Resource Mobilization
Joint UNCT Advocacy and Communications | Development/implementation of the UNCT communications/advocacy strategy & plan | 1. UN as a partner and the UN’s work is better understood as a key contribution to development in Lao PDR by the government, donors, media, the public and other entities | 1. Develop a 4 year Communication Strategy and Plan of Action to build stakeholder and public understanding and support of the UNDAF. 1.1 Conduct a baseline survey of public awareness about UN in Lao PDR. 1.2 Design UNDAF Action Plan media package 1.3 UN Communications Group support number of key events such as UN Day, UNDAF consultations and donor meetings 1.4 UN Lao website is updated and contains latest information on UN collaboration 1.5 UN Newsletter and / or advocacy materials published at least two times annually | 1. The UNCG Strategy and 2-year action plan was drafted and approved by the UNCT. A baseline survey was completed and the results will be shared with UNCT. The UNDAF media package was not completed as the final UNDAF document is planned to be signed off in March 2012. UNCG provided support to UN Day and to two UNDAF consultations. The UN website was updated with agency stories, however additional work is needed to update background information. The One UN Newsletter was published in English in February 2011. | [5 empty] | 19000 | 23938 | 1.1 $3,850 1.3 UN Day $14,000 1.5 $1,650
|  | 2. UN Communications Group capacity is enhanced and more relevant to the work of the UN development system in Laos (UNCT) | 2. UN Communications Group is reorganized with a) solid governance model b) management mechanism c) budget d) annual work plan supporting key UNCT efforts | 2. The UNCG Terms of Reference was adopted and adhered to and is planned to be reviewed every two years. The UNCG Retreat was organized, which allowed for reporting and more strategic work planning supporting key UNCT efforts | [7 empty] | 2.2 $500
|  | 3. UN and media relationship strengthened through inter-agency mechanism (UN Communications Group) | 3. UN Communications Group organizes number of public relations events with Lao media for deepening understanding of each other | 3. A Lao media meet and greet event was held in July 2011. UNCG members contributed to two journalist training sessions. | [7 empty] | 3. $150
Other
Joint UNCT Resource Mobilization Strategy | Development/implementation of RM strategy | 1. UNCT develops strategic resource mobilization document in line with supporting the achievement of MDGs. | 1. 1 UNDAF Action Plan incorporates resource mobilization strategy 1.2 Number of donor meetings held 1.3 UNDAF Action Plan resource mobilization involves UN HQ | 1.1 The UNDAF Action Plan includes a common budgetary framework which is a comprehensive and results-based projection of financial resource requirements identifying funding gaps for the entire UNDAF Action Plan period 2012-2015. It will be used for planning, implementation and management of the financial aspects of the UNDAF Action Plan for Lao PDR. 1.2 Several informal development partners meetings served as the platform to discuss strategic issues including financial resources. |  |  | 5000
Other
Result Area 4: Security Management
Security | Duty station specific security risk assessment (SRA) for all locations in the country where UN staff are present | 1. All UN staff in Lao PDR are aware of the specific minimum operating security standards for their location. | 1. SRAs carried out for all locations and staff made aware. | 1. A comprehensive Security Risk Assessment (SRA) for the whole country has been developed and updated in 2011. Subsequently, a new MOSS was designed, all staff briefed about requirements and relevant documents placed on the shared drive of all UN Agencies. | [5 empty] | 21000
| Up to date security plan | 2. UN activities in Lao PDR carried out under an up to date Security Plan. | 2.1 Lao PDR Security Risk Assessment endorsed by SMT 2.2 Regular meetings of SMT. | 2.1 The updated Lao SRA was endorsed by SMT in 2011. 2.2 One SMT meeting was held during the year but covered an extensive and broad agenda with a range of issues discussed and agreed on, including the endorsement of the new Security Plan, SRA and MOSS.
| Security Management Team | 3. Active and well-trained SMT provides guidance and decision making in a context that is marked by increasing property crime. | 3.1 Recruitment of additional guard force supervisors. 3.2 Trainings of guard force. | 3.1 Contractual arrangements between various agencies and security service providers, which were dissimilar in content and requirements, are now streamlined with the same service requirements (financial penalties, minimum age of guards, extensive training, maximum duration of shift to 8 hours). The Guard Force Project continues to demonstrate sound performance. Guard Force Supervisors continuously patrol and randomly inspect office premises of all UN agencies, provide on duty training and guidance to the guards, ensure that they perform per established procedures and identify, record and address performance issues with the management of the service providers. 3.2 Training for guard force implemented.
| Implementation of security training for staff | 4. Improved security of UN offices and staff residences. | 4. Number of spot checks that deem performance satisfactory. | 4. With the implementation of Guard Force project, performance of security guards at UN offices has notably improved. Continuous patrolling and supervision ensures that a minimal performance level of security guards is achieved (on average each AFPOs office was inspected four times daily). Drivers attended a two days Drivers Development Training course held in 2011. UNDSS and the UN clinic delivered first aid training to all staff deployed in the southern provinces. UNDSS delivered training to all ASCs and DASs on the UN Security Management System and new Security Plan and MOSS. A number of new Wardens were identified and trained by UNDSS. All new staff attended security induction briefing.
Other
Result Area 5: Non-Resident UN Agencies
Special measures to integrate non-resident UN agencies in UNCT processes | Supporting the Involvement of non-resident UN agencies in the national strategic planning processes/ UN programming | 1. Greater involvement by non-resident agencies in UN Country Team particularly in the process for preparation of the UNDAF Action Plan | 1. Non resident agencies participate in key UNDAF consultation meetings with Government and stakeholders | 1. Non resident agencies actively participated in the UNDAF exercise through communication with the RCs Office, teleconferences and electronic communication. NRAs also participated in several UNDAF meetings in Vientiane throughout the year, as well as briefing meetings with the UNRC. The UNCT committed to ensure information-sharing and facilitate the involvement of non-resident agencies in the work of UNDAF outcome groups.
|  | 2. Information sharing between resident and non-resident UN offices are enhanced through inter-agency working group mechanism. | 2. Non resident agencies are involved in the development of UNDAF Action Plan through teleconferences and electronic communication | 2. Of the five UNDAF Priority Groups, NRAs were actively involved in three.
| Other | 3. Non-resident agencies partnership on human rights dialogue is streamlined and enhanced | 3. Frequency of information exchange between non resident agencies with human rights mandates on emerging human rights issues in Laos | 3. The Head of the RC Office regularly informed NRAs with human rights mandates on emerging human rights issues in Laos.
Coordination Capacity of the UNCT
Strengthening UNCT Coordination Capacity | RCO Staffing | 1. RCO is better able to function and respond strategically to respective inter-agency work. | 1. RCO participates in number of inter-agency group meetings | 1. RCO staff contributed to the work of UNDAF Deputies Group, the thematic groups for the development of the Country Analysis and UNDAF Action Plan, the Gender Theme Group, HACT, OMT, etc. | 100000 | 70442 |  |  |  | 90000 | 60258 |  | 49756
|  | 2. RCO is better staffed with longer-term and full-time staff. | 2. RCO is comprised of professional and general services staff with full time contract | 2. In 2011, the RCO was comprised of 2 international staff and 2 national staff, with three professional staff (P4, JPO and NOB) and one general services staff (G6), plus one part-time international staff supporting the communication portfolio Note: considering budget constraints and the drastic decrease of UNDOCO allocation, UNCT has decided to have a minimal RCO staffing structure in 2012 onwards and at the start of 2012 was composed of only one international UNV as head of office and one national coordination associate. | [6 empty] | 10594 |  | 27500
| Materials/Equipment | 3. Resident Coordinator's office is able to run smoothly through timely procurement of quality materials and equipment as needed. | 3. RCO is equipped with updated IT system and office space | 3. Office equipment and space, as well as stationary, have been made available throughout the year | [6 empty] | 5000
| Training of UN staff | 4. RCO staff is more aware about UN Reform, common country programme and related inter-agency programmes. | 4. RCO staff participates in number of training programmes (domestic and international) to increase knowledge and capacity on UN Reform | 4. RCO staff have participated in training programmes (JPO induction course, UNDAFinfo training, BCP, One Health), as well as relevant workshops providing on-the-job training experience (BCP workshop, IACP workshop, etc). RC Desktop Documents have been established, which acts as a quick guide on the key functions of the RCO |  |  | 5000
|  | 5. RCO staff are empowered to their respective technical and related professional skills. | 5. Clear division of labour (portfolios) are established for respective RCO staff | 5. RCO staff have developed their RCA. Throughout the year staff members discussed with their supervisor areas for further training and capacity building to hone their expertise.
|  | 6. Networking and exchange of experiences among RC offices in the sub-region and amongst other UNDAF roll-out countries enhanced. | 6. RCO established stronger network with DOCO 6.1 RCO takes part in regional coordination officers conference/workshop | 6. Throughout the year the RCO has been in communication with other RCOs within the region and outside of the region to exchange experience, especially related to the UNDAF exercise. In particular, the RCO has established communication with other DaO RCOs of Malawi, Bangladesh, Maldives and PNG for information sharing purposes. Furthermore, the RCO regularly liaised with the PSG on UNDAF-related issues, as well as with the UNDOCO/UNDAF Helpdesk.
| Other | 7. UNCT capacity to deliver as one is increased | 7. UNCT consistently holds number of meetings 7.1 UNCT retreat is held at least once with follow up mechanism | 7. Monthly regular UNCT meetings have been organized, including an annual UNCT retreat and working lunches to promote better teamwork and more streamlined UN work in Laos. |  |  | 17000 |  |  |  | 13210 |  | 5175
Total in USD: |  |  |  |  | 100000 | 70442 | 60000 | 0 |  | 1828084 | 1608449 | 10000 | 198057 | 0 | 0 | 0
1 Products or services, which result from the completion of activities within a development intervention
2 A quantitative or qualitative variable that allows the verification of changes produced by a development intervention relative to what was planned
3 Please name the agencies and the amounts
4 This reporting requirement applies only to LDCs
5 For post-conflict countries only
6 Please fill out also the information requested in the database on Joint Programmes (hyperlink)

## Performance Appraisal Planning
Part 2: 2012 UN Resident Coordinator/DO/HC Performance Appraisal Planning
Using the 2012 RC/UNCT Workplan (above), please insert the key planned results and performance indicators for which the RC/HC/DO will be appraised against for the year 2012. There should be one key planned result, per result area, and these should be drawn from and specifcally related to the 2012 workplan.
KEY RESULT AREAS | RC/HC/DO
| Key Planned Results | Performance Indicators
Result Area 1: Coordination for Results
Result Area 2: Coordination of Emergency Preparedness and Relief
Result Area 3: UN Advocacy and Resource Mobilization
Result Area 4: Security Management
Result Area 5: Non-Resident UN Agencies

## Sheet1
Part 2: 2012 UN Resident Coordinator/DO/HC Performance Appraisal Planning
Using the 2012 RC/UNCT Workplan (above), please insert the key planned results and performance indicators for which the RC/HC/DO will be appraised against for the year 2012. There should be one key planned result, per result area, and these should be drawn from and specifcally related to the 2012 workplan.
KEY RESULT AREAS |  | RC/HC/DO
|  | Key Planned Results | Performance Indicators
Result Area 1: Coordination for Results
1.1 UNCT Contribution to the National Development Plan/Poverty Reduction Strategy/MD and MDGs plan | UN support to formulation/implementation of relevant national strategies or plans e.g. JAS/NDP/PRSP
UN plan to support the implementation of the Millennium Declaration, including scaling up IADG/MDG initiatives
UN support to capacity development strategies
UN assistance to national authorities for the preparation of the national report on the implementation of the Brussels Programme of Action of LDCs 4
Formulation/implementation of a transition plan or strategy 5
Other
1.2 Aid Coordination/ Management / Paris Declaration | Planned efforts to making use of national systems in the areas such as programme/project reporting, PRS/sectoral monitoring and evaluation systems, annual PRS/sectoral performance reviews, national procurement systems, etc
UN support to aid coordination/management
Other
1.3 UNDAF/Common Programming | Efforts to align UN programme cycle with national development cycle
Preparation of Country Analysis/UNDAF/UNDAF Action Plan
Progress towards UNDAF outcomes (inputs provided by theme group chairs)
Implementation of UNDAF M&E framework
UNDAF Annual Review/ UNDAF Evaluation/SOF
Joint planning initiatives with UN peacekeeping, peacebuilding, political and humanitarian actors (e.g. UNDAF plus, Integrated Strategic Framework) .
1.4 Joint Programmes 6 | Preparation/ implementation of new Joint Programmes
M&E of Joint Programmes
Other
1.5 HACT | Status of HACT implementation/compliance7 in the country
Strengthening national systems/capacities through HACT
Other
1.6 Gender Equality | UN support to incorporation of gender equality in national planning processes (such as National Development Strategies; PRSPs; SWAPs; Joint Assistance Strategies, etc.)
Capacity development for gender theme groups to support UNCT to respond to national priorities for gender equality
Other
1.7 HIV/AIDS | Establishment of Joint UN Team on AIDS and implementation of joint programme of support on AIDS
UN support to the national response to AIDS through strengthening the Three Ones
HIV/AIDS in the Workplace
Other
1.8 Human Rights | Application of Human Right Based Approach
Strengthening the capacity of UNCTs to support national human rights protection systems
Other
1.9 Common Services and Premises | Status of initiatives to increase collaboration and cost-effectiveness of UN business operations in support of programme delivery (common services and premises)
Result Area 2: Coordination of Emergency Preparedness and Relief
2.1 Preparedness | Coordination of emergency preparedness efforts of UNCT members and relevant humanitarian actors
2.2 Relief | Establishment of Humanitarian Country Team
Development of a response plan
Coordination of humanitarian operations
Advocacy
Resource mobilization
Other
Result Area 3: UN Advocacy and Resource Mobilization
3.1 Joint UNCT Advocacy and Communications | Development/implementation of the UNCT communications/advocacy strategy & plan
Other
3.2 Joint UNCT Resource Mobilization Strategy | Development/implementation of RM strategy
Other
Result Area 4: Security Management
Security | Duty station specific security risk assessment (SRA) for all locations in the country where UN staff are present
Implementation of mitigating measures as identified in SRA
Up to date security plan
Security Management Team
Implementation of security training for staff
Other
Result Area 5: Non-Resident UN Agencies
Special measures to integrate non-resident UN agencies in UNCT processes | Supporting the Involvement of non-resident UN agencies in the national strategic planning processes/ UN programming