Lao People’s Democratic Republic

Peace Independence Democracy Unity Prosperity

Government of the Lao People’s Democratic Republic

United Nations Development Programme

##### PROJECT DOCUMENT

Support For Implementation of the Sixth Five-Year Plan (2006-2010)

The present project will assist the Government in the implementation of the Sixth Plan (2006-2010) including the constituent poverty reduction strategy and the MDGs; and in monitoring and evaluating the results. Specifically, the project will help the Government of the Lao PDR in achieving three outcomes: (i) incorporation of the poverty reduction and MDG priorities and programmes of the Sixth Plan (2006-2010) in the annual plans and budgets of selected Ministries and three pilot provinces and implementing them; (ii) enhanced capacities of CPI, selected Ministries and three pilot provinces for improved implementation monitoring, evaluation and reporting; and (iii) establishment of a research network comprising the National Economic Research Institute (NERI) and selected Ministries and Agencies to undertake policy research to support planning, monitoring and evaluation. The Department of General Planning in CPI will be the implementing partner for the project.

August 2006

Section I.

###### Part 1. Situation Analysis

- General Background

The Lao PDR is a landlocked Least Developed Country (LDC) that has been making steady progress in reducing poverty incidence from 46.0 percent in 1992/93 to 39.1 percent in 1997/98 and 33.5 percent in 2002/03. Disparities in income distribution have increased during the 1990s (the Gini index rose from 28.6 in 1992 to 35.7 in 1997), but stabilized thereafter. According to the third Lao Expenditure and Consumption Surveys (LECS III) conducted in 2002/03, the poorest of the poor seemed to have benefited more during the period 1997/98 and 2002/03. The declining trend in poverty incidence, if continued, would enable the country to achieve the MDG target of reducing the proportion of people below the poverty line by half well before 2015. Like income poverty, other dimensions of poverty have shown considerable improvements. However, the country may have difficulty in meeting some of the MDG targets such as that on maternal mortality, if the past trend continues. The country faces unique development challenges including limited human resource capacities, inadequate infrastructure and unexploded ordnance from the Indo-China War.

The economy of the Lao PDR has grown impressively at an average of more than 6.5 percent per annum over the period 2001-2005. The Sixth five-year Socio-Economic Development Plan (2006–2010) sets out specific objectives and targets including an economic growth rate of 7.5 to 8.0 percent per annum and further significant reduction in poverty. It is based on the ten-year Socio Economic Development Strategy (2001–2010) and longer term (2000– 2020) sector development strategies. The Government’s overall development goal is to lift the country from the ranks of LDCs by 2020 through a strategy of growth with equity and poverty reduction in a sustainable development framework.

Until recently, poverty eradication was seen to be achieved through the regular Annual Plans of the Ministries, provinces and districts within the framework of the five-year plans. At the same time, a few pilot targeted interventions have been implemented under various externally funded projects including the Poverty Reduction Fund (supported by IDA/WB). Formulated during 1999-2003 and approved in 2003, the NGPES introduced greater focus on the poor, particularly in the four priority sectors (Agriculture and Forestry, Education, Health and Infrastructure) and in the 47 poorest and 25 poor districts. Also, it presented strategies and programmes in such cross-cutting areas as governance, gender mainstreaming, environment and private sector development, as well as a few poverty-focused National Programmes (UXO, Drug Control and HIV.AIDS). The NGPES was seen to be the main vehicle for achieving the MDGs.

- Situation on Monitoring and Evaluation

Monitoring and evaluation are integral elements of the NGPES and the five-year and annual plans of the Lao PDR. Monitoring and evaluation of poverty in its multiple qualitative and quantitative dimensions is an important part of this process.  All levels of the Government have agreed that monitoring and evaluation are essential. Also, progress in achieving the MDGs will provide the ultimate test of the success of the NGPES. Monitoring and evaluation can be seen at two broad levels: (i) monitoring and evaluation of inputs and outputs or implementation monitoring and evaluation, and (ii) monitoring and evaluation of outcomes and impacts or impact monitoring and evaluation.

Implementation Monitoring and Evaluation: The Ministries and Agencies at the centre, the provinces, districts and villages, and other actors including the private sector are responsible for implementation of the development activities including the NGPES and the five-year and annual Plans. An important purpose of monitoring and evaluation of implementation is to utilise the information to improve future implementation. The CPI is responsible for the coordination and formulation of the Development Plans and the Public Investment Programmes (PIPs). The CPI is assigned as the focal point to coordinate the activities among the ministries and sectors to prepare the monthly, periodic and annual progress reports on the implementation of the five-year and annual plans, which are presented to the monthly meetings of the Government. The CPI through its Department of General Planning (DGP) has been undertaking the monitoring and evaluation of the progress on implementation of the plans. The Department relies on periodic reports (monthly, quarterly, semi-annual and annual) from the line Ministries, Agencies, provinces, districts and villages to gather information on progress on plan implementation. Drawing upon these, the CPI compiles summary reports for submission to the Government and the National Assembly.

The present system of implementation monitoring and evaluation is faced with a number of challenges. The provision of information (reports) by the line Ministries, Agencies and provinces, districts and villages is patchy. The bulk of the information, which is often incomplete, is descriptive; and the coverage of the reports and the quality of the information vary widely. Capacity limitations are significant at all levels. The communications systems too need improvement. It is necessary to improve the implementation monitoring and evaluation system, building upon the existing mechanisms, and strengthening the capacities and links (both skills and equipment including communications and computer facilities) at the CPI, in the line Ministries, Agencies and the provinces, districts and villages.

Impact Monitoring and Evaluation: The National Statistics Centre (NSC) in the CPI undertakes the monitoring and evaluation of the outcomes and impacts of the plans. The NSC has begun to take steps to establish a uniform and consistent national database on economic and social indicators. In consultation with relevant Government agencies, it has facilitated the preparation of a list of about 100 core indicators that could be utilised to monitor the impacts of the five-year and annual plans, the NGPES, the MDGs and the Brussels Programme of Action for Least Developed Countries (2001-2010). Many of these indicators are incorporated in the LaoInfo 4.1, which has been launched in December 2005. A list of key indicators and targets to assess progress on the outcomes and impacts of the Sixth Plan (2006-2010) has been provided in Annex 1 of the Plan document. They include the indicators and targets in the MDGs and the Brussels Programme of Action for Least Developed Countries. The NSC is receiving continued support from UNDP, UNFPA and UNICEF on the LaoInfo and from other partners on strengthening the statistical databases.

- NGPES Project - Phase I

The UNDP has provided support for implementation and monitoring of the NGPES in the 47 poorest districts (ten pilot districts in 2004) identified in the NGPES as the focus for targeted poverty reduction efforts, under the National Growth and Poverty Eradication Strategy Project (Project No. 00032536). Specifically, the project was to assist the Government of the Lao PDR in achieving three outcomes by the end of 2004: (i) capacity building and dialogues for NGPES implementation strengthened; (ii) effective monitoring of NGPES implementation enabled; and, (iii) longer-term assistance developed for systematic NGPES monitoring and implementation.

Implementation of the project encountered delays, largely due to capacity limitations. Also, as project implementation progressed, other priority activities such as the estimation of the costs of priority programmes and projects in the four key sectors – Agriculture  and Forestry, Education, Health and Infrastructure – that are critical for poverty reduction was initiated. By the end of March 2006, the project had facilitated the estimation of the costs of priority programmes in the four sectors; and preparation of focal area (kum ban) development plans for poverty reduction in 21 areas in 21 of the 47 poorest districts, through a highly participatory process with the full involvement of the communities and their leaders and local officials. The plans contain priority projects to support both production and employment (mainly self-employment) and expanding access to economic and social services. The villages in the focal development area or kum bans have established village development funds, which are supported by the Government with contributions from the villagers. The village development funds are being included in the respective district, provincial and sector plans. The process of preparation of the focal area development plans built significant local capacity (including training of trainers and training of local officials) for participatory planning with the involvement of communities and other stakeholders. Preparation of similar development plans and programmes for other focal development areas (kum bans)  in the 47 poorest districts and eventually the 25 other poor districts will be undertaken and implemented during the next four years, primarily through the integration of the activities in the Annual Plans of the respective districts, provinces and sectors. Also, the Project has facilitated the production and wider dissemination of the NGPES document in the Lao and English Languages.

The Government Ministries and Agencies and the Provinces saw the NGPES as a new (additional) programme that is outside the ambit of the Fifth five-year National Socio-Economic Development Plan (2001-2005) and the constituent Annual Plans. The formulation of an “additional 3-year programme of support for NGPES implementation and monitoring” mentioned in the Project document never materialized. Except for the modest technical assistance from the UNDP and the World Bank, there were little earmarked resources either from the Government or the partners in development for the programmes identified in the NGPES. As a result, the overall implementation of NGPES suffered.

# Part 2. Strategy

To remedy the situation, it was felt desirable to integrate the NGPES and the MDGs with the regular five-year plans of the country as poverty reduction and the MDGs are seen to be integral parts of overall development. Accordingly, with encouragement from the partners in development, the Government has integrated the NGPES and the MDGs in the Sixth five-year National Socio-Economic Development Plan (2006-2010). The Plan draws together the various strands of poverty reduction in the NGPES into a coherent strategy, and integrates as appropriate the various poverty reduction interventions including the targeted ones and the MDGs into the respective sector development and regional development chapters of the Plan. It  pod scarcity;             ise ed in throm the UNDP and the World bankADB staff, several countries budget.ning programmesOFfocuses on the eradication of poverty and promotion of equity among different groups of the Lao multi-ethnic population within a rapid and sustainable economic growth framework.

The poverty reduction strategy in the Sixth Plan comprises actions by the Government and other stakeholders under four broad categories: (i) creating an enabling environment to generate and expand opportunities for the economic participation of the poor and improving their productivity and incomes; (ii) providing and encouraging others to provide basic social services to the poor at affordable terms; (iii) helping to ensure the security of the people against natural disasters, unforeseen shocks and food scarcity; and (iv) promoting the participation of the poor and other vulnerable groups in deciding upon and managing development in their villages, focal development areas (kum bans), districts and provinces and empowering them.

Thus, the NGPES and the MDGs have been substantially integrated in the Sixth five-year Plan (2006-2010). The poverty eradication strategy including the MDGs will be implemented primarily through the regular development programmes of the sectors, provinces and districts using their Annual Plans and Budgets as the main vehicles; whilst the targeted programmes too will be implemented largely through the existing systems. In other words, poverty reduction and the MDGs are being mainstreamed in the Plans, budgets and activities of the Ministries, Agencies, provinces, districts and villages. The process will require the assimilation of the poverty eradication strategy and the MDGs in the Sixth five-year Plan in the Annual Plans, budgets and activities of the Ministries, Agencies, provinces and districts. This would require considerable capacity strengthening at all levels given the modest capacities of the public administration overall and the people at the grass roots. This is necessary to ensure the sustainability of implementation of the strategy during the Plan period and beyond.

The present project will assist the Government in the implementation of the Sixth Plan (2006-2010) including the constituent poverty reduction strategy and the MDGs; and in monitoring and evaluating the results. Specifically, the project will help the Government of the Lao PDR in achieving three outcomes: (i) strengthened capacity of selected Ministries and three pilot provinces in incorporating the poverty reduction and MDG priorities and programmes in the Sixth Plan (2006-2010) in their respective annual plans and budgets and in implementing them; (ii) enhanced capacities of CPI, selected Ministries and three pilot provinces for improved implementation monitoring, evaluation and reporting; and (iii) strengthened capacity of the National Economic Research Institute (NERI) and selected Ministries and Agencies to undertake policy research to support planning, monitoring and evaluation. The Department of General Planning in CPI will be the implementing partner for the project.

# Part 3. Justification of UNDP support

The present project directly supports the implementation and monitoring and evaluation of the Sixth five-year Plan (2006-2010) including the poverty reduction strategy and the MDG targets therein. The UNDP Country Office has been working closely with the World Bank and other partners in development to provide considerable support to the Government for the formulation of the Plan including the costing of priority programmes in the four key sectors (catalytic for achieving the MDGs) and the poorest districts, and integration of the NGPES in the Plan. As co-chair of the Round Table Meetings, UNDP is in a unique position to undertake further cooperation in this area, specifically, working with the Committee for Planning and Investment (CPI) to ensure the implementation and monitoring and evaluation of the Sixth Plan including the poverty reduction strategy overall and in the 47 poorest and 25 poor districts.

The project is closely linked to the core elements of the UNDP mandate in the Lao PDR such as poverty reduction, achieving the MDGs and capacity strengthening. It builds on previous UNDP supported initiatives including the National Growth and Poverty Eradication Strategy Project and aims to mainstream poverty reduction and the MDGs in the annual plans and budgets of the Ministries and Agencies at the centre and at the local level in the provinces and districts. The Common Country Assessment (CCA, December, 2005) identified five overarching development themes: (i) poverty, food security and growth; (ii) governance, (iii) education, (iv) health, and (v) HIV/AIDS; and the draft UNDAF (March 2006) adopted enhanced ownership and capacity for pro-poor national and decentralized planning and its implementation as one of the outputs of the first outcome on enhancing by 2011, the livelihoods of poor, vulnerable and food insecure populations through sustainable development (within the MDG framework).  The project contributes to these themes as follows:

- The project will encourage an integrated and coordinated approach to mainstream  poverty eradication and achievement of the MDGs by providing support for piloting capacity strengthening for planning at the central (National) and local (provinces and  districts) levels.

- The project aims to reinforce the “downstream” participatory planning, budgeting, implementation and monitoring and evaluation capacities by piloting and institutionalizing the requisite approaches within provincial and district governments.

- The project aims to “improve” the implementation monitoring and evaluation of the Sixth Plan to promote the utilization of the information for more effective future implementation, policy and strategy formulation and planning.

- The project aims to initiate and nurture a research network in the country (involving NERI and selected Ministries and Agencies) for undertaking policy research as an important input to planning, implementation, monitoring and evaluation.

# Part 4. Management Arrangements

The Department of General Planning in the Committee for Planning and Investment (CPI) is the implementing partner of the Support for Implementation of the Sixth Five – Year Plan (2006-2010) project. The project provides support to strengthen the existing coordination, implementation and monitoring roles of the Department of General Planning in CPI to facilitate cooperation with other relevant Government agencies and Committees, including the Prime Minister’s Office (responsible for implementation of the decentralization strategy), the Ministry of Foreign Affairs (responsible for coordination of ODA) and the Ministry of Finance.

The project is supervised by the Project Board which has the following three roles: (i) an Executive to chair the group, who is the Director General of the Department of General Planning, CPI;  (ii) a Senior Beneficiary to ensure the realization of project benefits from the perspective of project beneficiaries, which is the Government’s Steering Committee on the Round Table Process, MDGs and Planning and the relevant working groups as well as the appropriate authorities at the sub-national levels; (iii) a Senior Supplier, who are the UNDP Assistant Resident Representative (Unit Chief) of Poverty and Economic Unit and a Representative of donors from whom resources are mobilized.  The Project Board is responsible for making executive management decisions on the project when guidance is sought by the Project Manager, including approval of project revisions.

The project Manager will be appointed by the Department of General Planning. The Project Manager is responsible for day-to-day management and decision-making for the project. She/he is responsible for successfully running the project. The Project Assurance role (to be played by UNDP Programme Analyst) supports the Project Board by carrying out objective and independent project oversight and monitoring functions.  Please see Annex 1 for an organizational arrangements chart of the project.

The “Project support team” will consist of staff appointed by CPI to manage the project.  The Project staff will be based at CPI and they will be directly linked to the Department of General Planning and other Departments participating in the project.

Other national institutions and local and international consultants will be contracted as required to assist with implementation of specific components of the project.

The project will ensure that there is regular consultation among key government and international stakeholders to facilitate coordination, encourage national ownership and continuing international interest.

The project will be implemented over a period of four years (October 2006 to September 2010) covering the final four years of the Sixth five-year Plan. In collaboration with UNDP, the project management will review the substantive progress of the project, provide advisory support to guide the implementation process and facilitate coordination at senior levels of the Government. In addition, the CPI will facilitate the harmonization of the project activities with the national policies and other initiatives, including the support by other partners for implementation of the Sixth Plan, the Gender Empowerment for Poverty Reduction Project, the Support to Round Table Process Project and the GPAR programme supported by UNDP, and other poverty related programmes supported by other donors such as UNCDF, the World Bank, IFAD and ADB.

Part 5. Monitoring and Evaluation

The project will be closely monitored by UNDP. A set of performance indicators have been included in the results frame work. Monthly meetings will be held with the project management team with the involvement of technical consultants and UNDP.

The project management team will prepare and submit annual work plans and periodic progress reports. A Project Annual Review meeting will be convened each year by the Project Board to discuss the progress made and review the work plan for the following year. An evaluation will be undertaken at the conclusion of the project.

# Part 6. Legal Context

The project document shall be the instrument referred to as such in Article 1 of the standard Basis Assistance Agreement between the Government of Lao PDR and the United Nations Development Programme, signed by the parties on 10 October 1988. The host country-implementing agency shall, for the purpose of the Standard Basis Assistance Agreement, refer to the Government co-operating agency described in that Agreement.

The following types of revisions may be made to this project document with the agreement and signature of UNDP Resident Representative only, provided he or she is assured that the other signatories of the project document have no objections to the proposed changes.

- Revisions in or addition of any of the annexes of the project document.

- Revisions which do not involve significant changes in the objectives, outputs or activities of the project, but are caused by arrangement of inputs agreed to or by cost increases due to inflation;  and

Mandatory annual revisions, which rephase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility.

Section II. Results and Resources Framework

UNDAF outcome: Improved capacity within government to assess the macroeconomic policies on human and income poverty

| Outputs | Indicative Activities | Performance Indicators | Inputs | Indicative timeframe (Year quarter) |
| --- | --- | --- | --- | --- |
| Outcome 1. Incorporation of poverty reduction and MDG priorities and programmes in the Sixth Plan (2006-2010) in annual plans and budgets |
| 1.1 Translate and disseminate widely the Sixth five-year Plan | Translate the Sixth Plan into Lao Language and disseminate widely including among ministries and agencies at the Centre, and to provinces and districts. | Distribution of Sixth Plan in Lao Language to all ministries and agencies and all provinces and districts Dissemination through workshops and the media | Translator Printing and distribution Dissemination workshops Media pamphlets | III-IV 2006 and I-II 2007 |
| 1.2 Approaches to incorporation of poverty reduction including MDGs in the Sixth Plan in the annual plans and budgets of selected ministries and three provinces evolved and adopted. | Assist the CPI and four key sectors in finalizing the costing and prioritization of priority programmes in the Sixth Plan in cooperation with MoF Assist CPI, selected ministries and agencies and three provinces in evolving and adopting approaches and mechanisms for integrating the poverty reduction and MDG priorities in the Sixth Plan in their annual plans and budgets. Revise planning and budget guidelines/manuals incorporating the successful approaches (above) and disseminate to other ministries and agencies and provinces | Costing and prioritization of priority programmes in four sectors completed Annual plans and budgets of selected ministries and agencies and three provinces reflect the poverty reduction and MDG priorities in the Sixth Plan. Revised planning and budget guidelines used through out the Government | Short-term foreign expert(s) Interpreter/translator National workshop Long-term foreign expert (also supports Outcome 2 below) Long-term local consultant (also supports Outcome 2 below) Interpreter/translator National/Sectoral/ regional workshops and training sessions Support to planning departments of selected ministries and agencies and three provinces to test and adopt approaches Long-term foreign and local experts Interpreter/translator National/Sectoral/ regional workshops and training sessions | III-IV 2006 2007 to 2010 2008 to 2010 |
| 1.3 Preparation of focal area development plans in remaining poorest districts and 25 poor districts completed. | Organise refresher course(s) on participatory planning for local officials and leaders in the 47 poorest and 25 poor districts Revise the manual on participatory planning and disseminate to all CPI together with stakeholders complete preparation of focal area development plans in remaining poorest districts and 25 poor districts through participatory processes involving the local communities | Refresher courses organized Manual revised through harmonization of participatory planning methodologies used by different projects in the country and gender mainstreamed throughout the manual and disseminated Focal area development plans in remaining poorest districts and 25 poor districts completed | Training sessions Exposure and study visits Foreign and local experts Training sessions Exposure and study visits Support to district staffs trained to continue the PRA for the rest of Kum Bans in the poorest and poor districts | IV 2006 & I 2007 I & II 2007 2007 to 2010 |
| 1.4 Resource mobilization for implementation of Sixth Plan | In coordination with MOFA and MOF, CPI to undertake informal consultations with each partner in development on PIP and areas of potential support by the partners In coordination with other ministries and agencies and provinces, CPI to undertake consultations with the domestic and foreign private investors on Sixth Plan investment requirements and opportunities for private investments | Informal consultations completed and results compiled for presentation possibly at the 9th Round Table Meeting (which could include a pledging session) Consultations completed and results compiled for presentation possibly at the 9th Round Table Meeting | - RTP Senior Advisor - Informal meetings Short-term consultant Consultation meetings | III-IV 2006 III-IV 2006 |
| 1.5 Implement the Sixth Plan including the poverty reduction and MDG programmes and targeted interventions in the annual plans and budgets of selected ministries and agencies and three provinces | Implementation advisory support to selected ministries and agencies and three provinces Establishment and operationalisation of village and kum ban development funds in remaining poorest and poor districts Establishment and operationalisation of fiscal oversight mechanism for village, kum ban and district development funds | Improved implementation (see monitoring below) Village and kum ban development funds established and operationalised Fiscal oversight mechanism established and operational | Short-term foreign expert(s) Interpreter/translator Seed funds for a few village/kum ban development funds in three provinces Exposure and study visits Short-term foreign and local experts Interpreter/translator Training and equipment Other initial operational support | IV 2006 to IV 2010 2008-2010 2007-2010 |
| Outcome 2. Enhanced capacities of CPI, selected Ministries and three provinces for improved implementation monitoring, evaluation and reporting |
| 2.1 Strengthened capacity of CPI in monitoring the implementation of the Sixth Plan and the annual plans, evaluation and reporting | Review and upgrade the current implementation monitoring formats and forms in consultation with ministries, agencies and provinces, drawing upon the activities and targets in the annual plans Introduce the revised formats and forms in selected ministries and agencies and three provinces Upgrade the monitoring information compilation in CPI including training of personnel, computer software and hardware, communications equipment (including links with selected ministries and agencies and three provinces) and other support facilities Update the implementation evaluation and reporting system in CPI drawing upon quantitative and qualitative targets and bench marks in annual plans and monitoring information | Plan implementation monitoring formats and forms revised to capture both quantitative and qualitative dimensions Revised formats and forms introduced in selected ministries and agencies and three provinces Improved monitoring information system in CPI Results of implementation monitoring and evaluation used in formulation of future plans | Long term foreign consultant (also supports Outcome 1 above) and short term local consultant Consultation workshops Training sessions Interpreter/translator Computer and communications equipment and supplies Furniture, support facilities and supplies Training sessions Interpreter/translator Training sessions Interpreter/translator | IV 2006 – 2007 IV 2007 – 2010 IV 2007 – 2010 2008 - 2010 |
| 2.2 Strengthened capacity of selected ministries and agencies in monitoring the implementation of the Sixth Plan and the annual plans, evaluation and reporting | Upgrade the monitoring information compilation in ministries and agencies including training of personnel, computer software and hardware, communications equipment (including links with provinces) and other support facilities Update the implementation evaluation and reporting system in ministries and agencies drawing upon quantitative and qualitative targets and bench marks in their annual plans and the monitoring information | Improved monitoring information systems in selected ministries and agencies Results of implementation monitoring used in decisions on future implementation of ministries and agencies Results of implementation monitoring and evaluation used in formulation of future plans of ministries and agencies | Training sessions Interpreter/translator Computer and communications equipment and supplies Furniture, support facilities and supplies Training sessions Interpreter/translator Training sessions Interpreter/translator | IV 2007 – 2010 2008 – 2010 2008 – 2010 |
| 2.3 Strengthened capacity of three provinces in monitoring the implementation of the Sixth Plan and the annual plans, evaluation and reporting | Upgrade the monitoring information compilation in province including training of personnel, computer software and hardware, communications equipment (including links with CPI and other central ministries and agencies) and other support facilities Update the implementation evaluation and reporting system in provinces drawing upon quantitative and qualitative targets and bench marks in their annual plans and the monitoring information | Improved monitoring information systems in three provinces Results of implementation monitoring used in decisions on future implementation Results of implementation monitoring and evaluation used in formulation of future plans of provinces | Training sessions Interpreter/translator Computer and communications equipment and supplies Furniture, support facilities and supplies Training sessions Interpreter/translator Training sessions Interpreter/translator | IV 2007 – 2010 2008 – 2010 2008 – 2010 |
| 2.4 Strengthened capacity to monitor implementation of the focal area development plans in the poorest and poor districts, evaluation and reporting | Upgrade the monitoring information compilation in poorest and poor districts including training of personnel, computer software and hardware, communications equipment (including links with provinces and CPI) and other support facilities Update the implementation evaluation and reporting system in poorest and poor districts drawing upon quantitative and qualitative targets and bench marks in their focal area development and/or annual plans and the monitoring information | Improved monitoring information systems in the poorest and poor districts, including through the use of participatory monitoring techniques. Results of implementation monitoring used in decisions on future implementation in the focal areas and districts Results of implementation monitoring and evaluation used in formulation of future focal area and districts development plans | Training sessions Interpreter/translator Computer and communications equipment and supplies Furniture, support facilities and supplies Training sessions Interpreter/translator Training sessions Interpreter/translator | IV 2007 – 2010 2008 – 2010 2008 – 2010 |
| 2.5 Results of annual implementation monitoring and evaluation fed into and incorporated in the impact monitoring system (including the LaoInfo system) maintained by NSC | Assist CPI, ministries and agencies and provinces to feed the results of the annual implementation monitoring and evaluation to NSC | - NSC incorporating the results of the annual implementation monitoring and evaluation in the impact monitoring system (including the LaoInfo system) - CPI, ministries and agencies and provinces integrating the results of impact monitoring and evaluation in formulation of future development plans | Workshops Training Communication links between NSC and CPI, ministries and agencies and provinces Training sessions Interpreter/translator | 2008 – 2010 2008 – 2010 |
| Outcome 3. Establishment of a National Research Network [comprising the National Economic Research Institute (NERI) and selected Ministries and Agencies] to undertake policy research to support planning, monitoring and evaluation |
| 3.1. National Research Network established in Lao PDR | Identification of Government agencies to participate in research network and its establishment Establishment of advisory committee of research network Establishment of a secretariat for the research network at NERI | Nomination of high-ranking officers and senior researchers from NERI, research institutes and identified Ministries Organization of a workshop to identify the research agenda for the network over the next 2-3 years | Support to Workshop Support to establish secretariat in NERI (a room with air conditioner, computers and other necessary equipment, furniture, stationary and supplies) and operating costs for two years Support periodic meetings of the research network and the research advisory committee | 2006 2006 2006-2008 |

Section III. The total work plan and budget

Total Work Plan and Budget (01 October 2006 to 30 September 2010)

UNDAF objective: Improved Capacity within Government to assess the Macro-Economic Policies on Human and Income Poverty

| Project Expected Output | Key Activities | Donor | Resp. | Budget | Budget Description | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Agency | code |  | Amount |
| Outcome 1. Incorporation of poverty reduction and MDG priorities and programmes in the 6th NSEDP (2006-2010) | ($) |
| 1 .1 Translate and disseminate widely the | Assist CPI to translate the Sixth Plan language and | UNDP | NEX | 71300 | Support staff/translator | 6,000 |
| Sixth Five-Year Plan | disseminate widely including among ministries and |  |  | 74200 | Printing | 32,000 |
|  | agencies at the Centre, and to provinces and districts |  |  | 74500 | Dissemination Workshops | 9,000 |
|  |  |  |  | 73100 | Rental & Maintenance equipment | 1,500 |
|  |  |  |  | 71600 | Travel (DSA) | 1,500 |
|  |  |  |  |  |  | 50,000 |
|  | Sub total |  |  |  |  | 50,000 |
| 1.2 Approaches to incorporation of poverty | Assist CPI and four key sectors in finalising the costing | UNDP | NEX | 71200 | International Consultant | 10,000 |
| Reduction including MDGs in the Sixth | and prioritisation of priority programmes in the Sixth Plan |  |  | 74100 | Workshop | 2,300 |
| Plan in the annual plans and budgets of | in cooperation with MoF |  |  | 72500 | Supplies | 1,000 |
| Selected ministries and three provinces. |  |  |  | 71300 | Support Staff | 1,000 |
| Evolved and adopted |  |  |  | 73500 | ISS | 700 |
|  |  |  |  |  |  | 15,000 |
|  | Assist CPI, selected ministries and agencies and three | UNDP | NEX | 71200 | International Consultant | 80,000 |
|  | provinces in evolving and adopting approaches and |  |  | 71300 | Local Consultants | 40,000 |
|  | mechanisms for integrating the poverty reduction and MDG |  |  | 74100 | Workshops | 30,000 |
|  | priorities in the Sixth Plan in their annual Plans and budgets |  |  | 74500 | Trainings | 48,000 |
|  |  |  |  | 71600 | Exposure visits | 28,400 |
|  |  |  |  | 71600 | Travel (DSA) | 18,000 |
|  |  |  |  | 73500 | ISS | 5,600 |
|  |  |  |  |  |  | 250,000 |
|  | Revise planning and budget guidelines and | UNDP | NEX | 71200 | International Consultant | 10,000 |
|  | manuals incorporating the successful |  |  | 71300 | Local Consultants | 5,000 |
|  | approaches (above) and disseminate |  |  | 74500 | Dissemination workshops | 10,000 |
|  | to other ministries, agencies and |  |  | 71600 | Travel (DSA) | 2,500 |
|  | provinces |  |  | 74200 | Printing | 6,800 |
|  |  |  |  | 73500 | ISS | 700 |
|  |  |  |  |  |  | 35,000 |
|  | Sub total |  |  |  |  | 300,000 |
| 1.3 Preparation of focal area development | Organise refresher courses on | UNDP | NEX | 71300 | Local Consultants | 5,000 |
| plans in 47 poorest districts and 25 | participatory planning for community |  |  | 74500 | Training workshops | 7,500 |
| poor districts completed | leaders and local officials |  |  | 71600 | Travel (DSA) | 2,500 |
|  |  |  |  |  |  | 15,000 |
|  | Revise the manual on participatory | UNDP | NEX | 71200 | Local Consultants | 7,500 |
|  | planning and disseminate to all |  |  | 71300 | Support staff/translator | 2,500 |
|  |  |  |  | 74200 | Printing | 30,000 |
|  |  |  |  | 74500 | Dissemination workshops | 7,500 |
|  |  |  |  | 71600 | Travel (DSA) | 2,500 |
|  |  |  |  |  |  | 50,000 |
|  | CPI together with stakeholders | UNDP | NEX | 71300 | Local Consultants | 100,000 |
|  | complete preparation of the focal |  |  | 72400 | Tools / Equipments | 40,000 |
|  | areas development plans in 47 poorest |  |  | 74800 | one 4-wheel drive vehicle | 32,500 |
|  | districts and 25 poor districts |  |  | 73300 | Vehicle Maintenance | 12,000 |
|  | through participatory processes |  |  | 74500 | Workshops | 60,000 |
|  | involving the local communities |  |  | 73300 | Fuel and lubricants | 40,000 |
|  |  |  |  | 71600 | Other Transportation | 24,000 |
|  |  |  |  | 71600 | Travel (DSA) | 24,225 |
|  |  |  |  | 73500 | ISS | 2,275 |
|  |  |  |  |  |  | 335,000 |
|  | Sub total |  |  |  |  | 400,000 |
| 1.4 Resource mobilization for | In coordination with MoFA and MoF, | UNDP | NEX | 71200 | International Consultant |  |
| implementation of Sixth Plan | CPI to undertake informal |  |  | 74500 | Informal meetings | 1,000 |
|  | consultations with each partner in |  |  | 72500 | Logistics | 3,000 |
|  | development on PIP and areas |  |  | 72500 | Communications | 1,000 |
|  | of potential support by the partners |  |  |  |  | 5,000 |
|  | In coordination with other ministries | UNDP | NEX | 74500 | Workshops | 2,500 |
|  | and agencies, CPI to undertake |  |  | 72500 | Logistics | 500 |
|  | consultations with the domestic and |  |  |  |  |  |
|  | foreign private investors on Sixth |  |  |  |  |  |
|  | Plan investment requirements |  |  |  |  |  |
|  |  |  |  |  |  | 3,000 |
|  | Sub total |  |  |  |  | 8,000 |
| 1.5 Implement the Sixth Plan including | In coordination with other ministries |  |  | 74500 | National Workshops | 60,000 |
| the poverty reduction and MDG programmes | and agencies, CPI to undertake |  |  | 72500 | Logistics | 12,000 |
| and targeted interventions in the annual | annual consultations with ministries |  |  | 72500 | Communications | 8,000 |
| Plans and budgets of selected ministries | and provinces on PIP, Annual Plans |  |  | 72500 | Consultations in provinces/regions | 40,000 |
| and agencies and three provinces | and annual budgets |  |  | 71600 | Travel (incl. DSA) | 20,000 |
|  |  |  |  |  |  | 140,000 |
|  | In consultation with MOF and other | UNDP | NEX | 74500 | Workshops | 10,000 |
|  | stakeholders, CPI to organise annual consultations with domestic and foreign private investors |  |  | 72500 | Logistics | 2,000 |
|  |  |  |  |  |  | 12,000 |
|  | Implementation advisory support to selected | UNDP | NEX | 71300 | Local Consultants | 16,000 |
|  | ministries and agencies and three provinces |  |  | 73300 | Training equipment | 2,000 |
|  |  |  |  | 73400 | Training workshops | 16,000 |
|  |  |  |  | 72800 | Computers | 4,000 |
|  |  |  |  | 71600 | Travel (DSA) | 10,000 |
|  |  |  |  | 72500 | Supplies | 2,000 |
|  |  |  |  |  |  | 50,000 |
|  | Establish and operationalise village development funds in poorest and poor districts | Other (TBD) | NEX |  | Seed Fund | 250,000 |
|  | Establish and operationalise a fiscal oversight | SNV | DEX |  | SNV ($300,000) | 300,000 |
|  | mechanism for village development funds | UNDP | NEX |  |  | 20,000 |
|  |  |  |  |  |  | 570,000 |
|  | Sub total |  |  |  |  | 772,000 |
| Outcome 2. Enhanced capacities of CPI, selected Ministries and three provinces for improved implementation monitoring, evaluation and reporting |
| 2.1 Strengthened capacity of CPI in | Review and upgrade the current | UNDP |  | 71200 | International Consultant | 50,000 |
| monitoring the implementation of the | implementation monitoring formats |  |  | 71300 | Local Consultants | 10,000 |
| Sixth Plan and the annual plans, | and forms in consultation with |  |  | 71600 | Travel (DSA) | 7,800 |
| evaluation and reporting | ministries, agencies and provinces, |  |  | 71400 | Support staff/interpreter | 2,000 |
|  | drawing upon the activities and |  |  | 72500 | Supplies | 1,000 |
|  | targets in the annual plans |  |  | 73500 | ISS | 4,200 |
|  |  |  |  |  |  | 75,000 |
|  | Introduce the revised formats and | UNDP | NEX | 71300 | Local Consultants | 10,000 |
|  | forms in selected ministries, agencies |  |  | 74200 | Printing | 5,000 |
|  | and three provinces |  |  | 74500 | Workshops | 6,000 |
|  |  |  |  | 71600 | Travel (DSA) | 3,000 |
|  |  |  |  | 71400 | Support staff | 1,000 |
|  |  |  |  |  |  | 25,000 |
|  | Upgrade the compilation of information | UNDP | NEX | 71200 | International Consultant | 15,000 |
|  | on implementation monitoring in CPI |  |  | 71300 | Local Consultants | 15,000 |
|  | including training of personnel, |  |  | 74500 | Training workshops | 12,000 |
|  | and provision of computer software and |  |  | 72200 | Computer software and hardware | 35,000 |
|  | hardware, communications equipment |  |  | 72200 | Communications equipment | 5,000 |
|  | (including links with selected ministries |  |  | 72500 | Office equipments | 3,000 |
|  | and three provinces ) and other support |  |  | 73100 | Rental & Maintenance equipment | 3,000 |
|  | facilities |  |  | 71600 | Travel (DSA) | 5,000 |
|  |  |  |  | 71400 | Support staff/interpreter | 2,000 |
|  |  |  |  | 72500 | Office supplies | 800 |
|  |  |  |  | 71600 | Study tours | 28,000 |
|  |  |  |  | 73500 | ISS | 6,200 |
|  |  |  |  |  |  | 130,000 |
|  | Update the implementation evaluation | UNDP | NEX | 71200 | International Consultant | 10,000 |
|  | and reporting system in CPI drawing |  |  | 71300 | Local Consultants | 10,000 |
|  | upon quantitative and qualitative targets |  |  |  | Computer software and hardware | 20,000 |
|  | and bench marks in annual plans and |  |  | 73100 | Rental & Maintenance equipment | 9,000 |
|  | monitoring information |  |  | 72500 | Office supplies | 2,250 |
|  |  |  |  | 73500 | ISS | 1,750 |
|  |  |  |  |  |  | 53,000 |
|  | Sub total |  |  |  |  | 283,000 |
| 2.2 Strengthened capacity of selected | Upgrade the compilation of information | UNDP | NEX | 71200 | International Consultant | 15,000 |
| Ministries and agencies in monitoring | on implementation monitoring in selected |  |  | 71300 | Local Consultants | 15,000 |
| the implementation of the Sixth Plan and | ministries including training of personnel, |  |  | 72200 | Computer software and hardware | 58,000 |
| the annual plans, evaluation and reporting | and provision of computer software and |  |  | 72200 | Communications equipment | 5,000 |
|  | hardware, communications equipment |  |  | 72500 | Office supplies | 2,450 |
|  | (including links with provinces ) and other |  |  | 73500 | ISS | 4,550 |
|  | support facilities |  |  |  |  |  |
|  |  |  |  |  |  | 100,000 |
|  | Upgrade the implementation evaluation | UNDP | NEX | 71200 | International Consultant |  |
|  | and reporting system in ministries and |  |  | 71300 | Local Consultants | 10,000 |
|  | agencies drawing upon quantitative and |  |  | 71300 | Support staff/translator | 2,000 |
|  | qualitative targets and bench marks in their annual plans and the monitoring information |  |  | 72500 | Office supplies |  |
|  |  |  |  |  |  | 20,000 |
|  | Sub total |  |  |  |  | 120,000 |
| 2.3 Strengthened capacity of three | Upgrade the compilation of information | UNDP | NEX | 71200 | International Consultant | 20,000 |
| provinces in monitoring the | on implementation monitoring in three |  |  | 71300 | Local Consultants | 15,000 |
| implementation of the Sixth Plan | provinces including training of personnel, |  |  | 74500 | Training workshops | 10,000 |
| and the annual plans, evaluation | and provision of computer software and |  |  | 72200 | Computer software and hardware | 30,000 |
| and reporting | hardware, communications equipment |  |  | 72200 | Communications equipment | 12,000 |
|  | (including links with ministries and CPI) |  |  | 71300 | Support staff/translator | 2,000 |
|  | and other support facilities |  |  | 71600 | Travel (DSA) | 10,000 |
|  |  |  |  | 72500 | Office supplies | 3,000 |
|  |  |  |  |  | ISS | 1,400 |
|  |  |  |  |  |  | 103,400 |
|  | Upgrade the monitoring evaluation and | UNDP | NEX | 71200 | International Consultant | 35,000 |
|  | reporting system in three provinces drawing |  |  | 71300 | Local Consultants | 15,000 |
|  | upon quantitative and qualitative targets |  |  | 71300 | Support staff/translator | 2,000 |
|  | and bench marks in their annual plans |  |  | 72500 | Office supplies | 2,050 |
|  | and the monitoring information |  |  | 71600 | Travel (DSA) | 6,500 |
|  |  |  |  | 73500 | ISS | 2,450 |
|  |  |  |  |  |  | 63,000 |
|  | Sub total |  |  |  |  | 166,400 |
| 2.4 Strengthened capacity to | Upgrade the compilation of information | UNDP | NEX | 71300 | Local Consultants | 25,000 |
| monitor implementation of the | on implementation monitoring in poorest |  |  | 74500 | Training workshops | 24,000 |
| focal area development plans in | and poor districts including training of |  |  | 72200 | Communications equipment | 10,000 |
| the poorest and evaluation and | personnel, and provision of communications |  |  | 72500 | Office equipment | 30,000 |
| reporting | equipment (including links with provinces, |  |  | 71600 | Travel (DSA) | 9,000 |
|  | ministries and CPI) and other support |  |  | 72500 | Office supplies | 6,000 |
|  | facilities |  |  |  |  | 104,000 |
|  | Upgrade the monitoring evaluation and | UNDP | NEX | 71300 | Local Consultants | 20,000 |
|  | reporting system in poorest and poor |  |  | 74500 | Training workshops | 16,000 |
|  | districts drawing upon quantitative and |  |  | 71600 | Travel (DSA) | 6,000 |
|  | qualitative targets and bench marks in their |  |  | 72500 | Office supplies | 4,000 |
|  | focal development areas and/or annual |  |  |  |  |  |
|  | plans and the monitoring information |  |  |  |  | 46,000 |
|  | Sub total |  |  |  |  | 150,000 |
| 2.5 Results of annual | Assist CPI, Ministries, Agencies and | UNDP | NEX | 71300 | Local Consultants | 15,000 |
| implementation monitoring and | provinces to feed the results of the |  |  | 74500 | Workshops | 9,000 |
| evaluation fed into and | annual implementation monitoring and |  |  | 71600 | Travel & DSA | 4,500 |
| incorporated in the impact | evaluation to NSC |  |  | 72500 | Office supplies | 1,500 |
| monitoring system (including the |  |  |  |  |  | 30,000 |
| LaoInfo system) maintained by |  |  |  |  |  |  |
| NSC | Help NSC incorporate the results in | UNDP | NEX |  |  |  |
|  | the National Database on impact |  |  |  |  |  |
|  | monitoring including the LaoInfo |  |  |  |  |  |
|  |  |  |  |  |  | 25,000 |
|  | Sub total |  |  |  |  | 55,000 |
| 2.6 Project management secretariat support | Help CPI manage the project implementation | UNDP | NEX |  | Account Assistant | 19,200 |
|  | with secretariat support |  |  |  | Project Assistant | 19,200 |
|  |  |  |  |  | Secretary | 16,800 |
|  |  |  |  |  | Driver | 16,800 |
|  |  |  |  |  | Cleaner | 1,700 |
|  |  |  |  | 72500 | Office equipment | 5,000 |
|  |  |  |  | 72200 | Communications incl. internet | 10,000 |
|  |  |  |  | 72500 | Office supplies | 6,000 |
|  |  |  |  | 71600 | Transport | 5,000 |
|  |  |  |  |  | Other misc. running costs | 400 |
|  |  |  |  |  |  | 100,100 |
|  | Sub total |  |  |  |  | 100,100 |
| Output 3. National Research Network to undertake policy research to support planning, monitoring and evaluation established |
| 3.1. National Research Network | National Research Network | UNDP | NEX | 71200 | International Consultant | 17,000 |
| established in Lao PDR | comprising the National Economic |  |  | 74500 | Workshop | 5,000 |
|  | Research Institute (NERI) and |  |  |  | Periodic Meetings | 6,000 |
|  | selected Ministries and Agencies |  |  |  | Computers | 9,000 |
|  | established, with a Research Advisory |  |  |  | Communications equipment | 3,000 |
|  | Board and a secretariat |  |  |  | Other equipment incl. a/c | 2,000 |
|  |  |  |  |  | Secretariat operation cost | 5,970 |
|  |  |  |  | 73500 | ISS | 2,030 |
|  |  |  |  |  |  | 50,000 |
|  | Sub total |  |  |  |  | 50,000 |
|  | TOTAL |  |  |  |  | 2,454,500 |

Section IV. The annual work plan

Annual Work Plan and Budget (01 October 2006 to 30 September 2007)

UNDAF outcome: Improved Capacity within Government to assess the Macro-Economic Policies on Human and Income Poverty

| Expected | Key Activities | Donor | Resp. | Code | Budget Description | Total | YR 1 | YR 2 | YR 3 | YR4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output |  |  | Agency |  |  | Amount |  |  |  |  |
| Outcome 1. Incorporation of poverty reduction and MDG priorities and programmes in the 6th NSEDP (2006-2010) |
| 1 .1 Translate | Assist CPI to translate the | UNDP | NEX | 71300 | Support staff/translator | 6,000 | 6,000 |  |  |  |
| and disseminate | Sixth Plan and disseminate |  |  | 74200 | Printing | 32,000 | 32,000 |  |  |  |
| widely the Sixth | widely including among |  |  | 74500 | Dissemination Workshops | 9,000 | 9,000 |  |  |  |
| Five-Year Plan | ministries and agencies at the Centre, and to provinces and |  |  | 73100 | Rental & Maintenance of equipment | 1,500 | 1,500 |  |  |  |
|  | districts |  |  | 71600 | Travel (DSA) | 1,500 | 1,500 |  |  |  |
|  |  |  |  |  |  | 50,000 | 50,000 |  |  |  |
|  | Sub-total |  |  |  |  | 50,000 | 50,000 |  |  |  |
| 1.2 Approaches | Assist CPI and four key | UNDP | NEX | 71200 | International Consultant | 10,000 | 10,000 |  |  |  |
| to incorporation | sectors in finalising the |  |  | 74100 | Workshop | 2,300 | 2,300 |  |  |  |
| of poverty | costing and prioritisation of |  |  | 72500 | Supplies | 1,000 | 1,000 |  |  |  |
| reduction | priority programmes in the |  |  | 71300 | Support Staff | 1,000 | 1,000 |  |  |  |
| including MDGs in the | Sixth Plan in cooperation |  |  | 73500 | ISS | 700 | 700 |  |  |  |
| Sixth Plan in the annual plans and budgets of selected ministries and three provinces evolved and adopted | with MoF |  |  |  |  | 15,000 | 15,000 |  |  |  |
|  | Assist CPI, selected | UNDP | NEX | 71200 | International Consultant | 80,000 | 50,000 | 10,000 | 10,000 | 10,000 |
|  | ministries and agencies and |  |  | 71300 | Local Consultants | 40,000 | 10,000 | 10,000 | 10,000 | 10,000 |
|  | three provinces in evolving |  |  | 74100 | Workshops | 30,000 | 12,000 | 6,000 | 6,000 | 6,000 |
|  | and adopting approaches and |  |  | 74500 | Trainings | 48,000 | 12,000 | 12,000 | 12,000 | 12,000 |
|  | mechanisms for integrating |  |  | 71600 | Exposure visits | 28,400 | 8,000 | 6,800 | 6,800 | 6,800 |
|  | the poverty reduction and |  |  | 71600 | Travel (DSA) | 18,000 | 4,500 | 4,500 | 4,500 | 4,500 |
|  | MDG priorities in the Sixth s |  |  | 73500 | ISS | 5,600 | 3,500 | 700 | 700 | 700 |
|  | Plan in their annual Plans and budget |  |  |  |  | 250,000 | 100,000 | 50,000 | 50,000 | 50,000 |
|  | Revise planning and budget | UNDP | NEX | 71200 | International Consultant | 10,000 |  | 10,000 |  |  |
|  | guidelines and manuals |  |  | 71300 | Local Consultants | 5,000 |  | 5,000 |  |  |
|  | incorporating the successful |  |  | 74500 | Dissemination workshops | 10,000 |  | 10,000 |  |  |
|  | approaches (above) and |  |  | 71600 | Travel (DSA) | 2,500 |  | 2,500 |  |  |
|  | disseminate to other |  |  | 74200 | Printing | 6,800 |  | 6,800 |  |  |
|  | ministries, agencies and |  |  | 73500 | ISS | 700 |  | 700 |  |  |
|  | provinces |  |  |  |  | 35,000 |  | 35,000 |  |  |
|  | Sub-total |  |  |  |  | 300,000 | 115,000 | 85,000 | 50,000 | 50,000 |
| 1.3 Preparation | Organise refresher courses | UNDP | NEX | 71300 | Local Consultants | 5,000 | 5,000 |  |  |  |
| of focal area | on participatory planning for |  |  | 74500 | Training workshops | 7,500 | 7,500 |  |  |  |
| development | community leaders and local |  |  | 71600 | Travel (DSA) | 2,500 | 2,500 |  |  |  |
| plans in 47 | officials |  |  |  |  | 15,000 | 15,000 |  |  |  |
| poorest districts |  |  |  |  |  |  |  |  |  |  |
| and 25 poor | Revise the manual on | UNDP | NEX | 71200 | Local Consultants | 7,500 | 5,000 | 2,500 |  |  |
| districts | participatory planning and |  |  | 71300 | Support staff/translator | 2,500 | 2,500 |  |  |  |
| completed | disseminate to all |  |  | 74200 | Printing | 30,000 | 30,000 |  |  |  |
|  |  |  |  | 74500 | Dissemination workshops | 7,500 |  | 7,500 |  |  |
|  |  |  |  | 71600 | Travel (DSA) | 2,500 |  | 2,500 |  |  |
|  |  |  |  |  |  | 50,000 | 37,500 | 12,500 |  |  |
|  | CPI together with | UNDP | NEX | 71300 | Local Consultants | 100,000 | 25,000 | 25,000 | 25,000 | 25,000 |
|  | stakeholders complete |  |  | 72400 | Tools / Equipments | 40,000 | 10,000 | 10,000 | 10,000 | 10,000 |
|  | preparation of the focal areas |  |  | 74800 | one 4-wheel drive vehicle | 32,500 | 32,500 |  |  |  |
|  | development plans in 47 |  |  | 73300 | Vehicle Maintenance | 12,000 | 3,000 | 3,000 | 3,000 | 3,000 |
|  | poorest districts and 25 poor |  |  | 74500 | Workshops | 60,000 | 15,000 | 15,000 | 15,000 | 15,000 |
|  | districts through |  |  | 73300 | Fuel and lubricants | 40,000 | 10,000 | 10,000 | 10,000 | 10,000 |
|  | participatory processes |  |  | 71600 | Other Transportation | 24,000 | 6,000 | 6,000 | 6,000 | 6,000 |
|  | involving the local |  |  | 71600 | Travel (DSA) | 24,225 | 6,225 | 6,000 | 6,000 | 6,000 |
|  | communities |  |  | 73500 | ISS | 2,275 | 2,275 |  |  |  |
|  |  |  |  |  |  | 335,000 | 110,000 | 75,000 | 75,000 | 75,000 |
|  | Sub-total |  |  |  |  | 400,000 | 162,500 | 87,500 | 75,000 | 75,000 |
| 1.4 Resource | In coordination with MoFA | UNDP | NEX | 71200 | International Consultant |  |  |  |  |  |
| mobilization for | and MoF, CPI to undertake |  |  | 74500 | Informal meetings | 1,000 | 1,000 |  |  |  |
| implementation | informal consultations with |  |  | 72500 | Logistics | 3,000 | 3,000 |  |  |  |
| of the Sixth Plan | each partner in development |  |  | 72500 | Communications | 1,000 | 1,000 |  |  |  |
|  | on PIP and areas of potential support by the partners |  |  |  |  | 5,000 | 5,000 |  |  |  |
|  | In coordination with other | UNDP | NEX | 74500 | Workshops | 2,500 | 2,500 |  |  |  |
|  | ministries and agencies, CPI |  |  | 72500 | Logistics | 500 | 500 |  |  |  |
|  | to undertake consultations with the domestic and foreign private investors on Sixth Plan investment requirements |  |  |  |  | 3,000 | 3,000 |  |  |  |
|  | Sub-total |  |  |  |  | 8,000 | 8,000 |  |  |  |
| 1.5 Implement | In coordination with other | UNDP | NEX | 74500 | National Workshops | 60,000 | 15,000 | 15,000 | 15,000 | 15,000 |
| the Sixth Plan | ministries and agencies, CPI |  |  | 72500 | Logistics | 12,000 | 3,000 | 3,000 | 3,000 | 3,000 |
| including the | to undertake annual |  |  | 72500 | Communications | 8,000 | 2,000 | 2,000 | 2,000 | 2,000 |
| poverty reduction and | consultations with ministries and provinces on PIP, |  |  | 72500 | Consultations in provinces/regions | 40,000 | 10,000 | 10,000 | 10,000 | 10,000 |
| MDG | Annual Plans and annual |  |  | 71600 | Travel (incl. DSA) | 20,000 | 5,000 | 5,000 | 5,000 | 5,000 |
| programmes and | budgets |  |  |  |  | 140,000 | 35,000 | 35,000 | 35,000 | 35,000 |
| targeted |  |  |  |  |  |  |  |  |  |  |
| interventions in | In consultation with MOF | UNDP | NEX | 74500 | Workshops | 10,000 | 2,500 | 2,500 | 2,500 | 2,500 |
| the annual Plans | and other stakeholders, CPI |  |  | 72500 | Logistics | 2,000 | 500 | 500 | 500 | 500 |
| and budgets of selected ministries and agencies and three provinces | to organise annual consultations with domestic and foreign private investors |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 12,000 | 3,000 | 3,000 | 3,000 | 3,000 |
|  | Implementation advisory | UNDP | NEX | 71300 | Local Consultants | 16,000 | 5,000 | 5,000 | 3,000 | 3,000 |
|  | support to selected ministries |  |  | 73300 | Training equipment | 2,000 | 1,000 | 1,000 |  |  |
|  | and agencies and three |  |  | 73400 | Training workshops | 16,000 | 4,000 | 4,000 | 4,000 | 4,000 |
|  | provinces |  |  | 72800 | Computers | 4,000 | 2,000 | 2,000 |  |  |
|  |  |  |  | 71600 | Travel (DSA) | 10,000 | 2,500 | 2,500 | 2,500 | 2,500 |
|  |  |  |  | 72500 | Supplies | 2,000 | 500 | 500 | 500 | 500 |
|  |  |  |  |  |  | 50,000 | 15,000 | 15,000 | 10,000 | 10,000 |
|  | Establish and operationalise | Other (TBD) | NEX |  | Seed Fund | 250,000 |  | 250,000 |  |  |
|  | village development funds |  |  |  |  |  |  |  |  |  |
|  | in poorest and poor districts |  |  |  |  |  |  |  |  |  |
|  | Establish and operationalise a fiscal oversight mechanism | SNV | DEX |  | SNV? ($300,000) | 300,000 | 250,000 | 50,000 |  |  |
|  | for village development funds | UNDP | NEX |  |  | 20,000 | 10,000 | 10,000 |  |  |
|  |  |  |  |  |  | 570,000 | 260,000 | 310,000 |  |  |
|  | Sub-total |  |  |  |  | 772,000 | 313,000 | 363,000 | 48,000 | 48,000 |
| Outcome 2. Enhanced capacities of CPI, selected Ministries and three provinces for improved implementation monitoring, evaluation and reporting |
| 2.1 Strengthened | Review and upgrade the | UNDP |  | 71200 | International Consultant | 50,000 | 50,000 |  |  |  |
| capacity of CPI in | current implementation |  |  | 71300 | Local Consultants | 10,000 | 10,000 |  |  |  |
| monitoring the | monitoring formats and |  |  | 71600 | Travel (DSA) | 7,800 | 7,800 |  |  |  |
| implementation of | forms in consultation with |  |  | 71400 | Support staff/interpreter | 2,000 | 2,000 |  |  |  |
| the Sixth Plan and | ministries, agencies and |  |  | 72500 | Supplies | 1,000 | 1,000 |  |  |  |
| the annual plans, | provinces, drawing upon |  |  | 73500 | ISS | 4,200 | 4,200 |  |  |  |
| evaluation and | the activities and targets in |  |  |  |  | 75,000 | 75,000 |  |  |  |
| reporting | the annual plans |  |  |  |  |  |  |  |  |  |
|  | Introduce the revised | UNDP | NEX | 71300 | Local Consultants | 10,000 | 10,000 |  |  |  |
|  | formats and forms in |  |  | 74200 | Printing | 5,000 | 5,000 |  |  |  |
|  | selected ministries, |  |  | 74500 | Workshops | 6,000 | 6,000 |  |  |  |
|  | agencies and three |  |  | 71600 | Travel (DSA) | 3,000 | 3,000 |  |  |  |
|  | provinces |  |  | 71400 | Support staff | 1,000 | 1,000 |  |  |  |
|  |  |  |  |  |  | 25,000 | 25,000 |  |  |  |
|  | Upgrade the compilation of | UNDP | NEX | 71200 | International Consultant | 15,000 | 15,000 |  |  |  |
|  | information on |  |  | 71300 | Local Consultants | 15,000 | 10,000 | 5,000 |  |  |
|  | implementation monitoring |  |  | 74500 | Training workshops | 12,000 | 6,000 | 6,000 |  |  |
|  | in CPI including training of personnel, and provision |  |  | 72200 | Computer software and hardware | 35,000 | 30,000 | 5,000 |  |  |
|  | of computer software and |  |  | 72200 | Communications equipment | 5,000 | 5,000 |  |  |  |
|  | hardware, communications |  |  | 72500 | Office equipments | 3,000 | 3,000 |  |  |  |
|  | equipment (including links with selected ministries |  |  | 73100 | Rental & Maintenance equipment | 3,000 | 1,500 | 1,500 |  |  |
|  | and three provinces ) and |  |  | 71600 | Travel (DSA) | 5,000 | 3,000 | 2,000 |  |  |
|  | other support facilities |  |  | 71400 | Support staff/interpreter | 2,000 | 2,000 |  |  |  |
|  |  |  |  | 72500 | Office supplies | 800 | 300 | 500 |  |  |
|  |  |  |  |  | Study Tours | 28,000 | 14,000 |  | 14,000 |  |
|  |  |  |  | 73500 | ISS | 6,200 | 5,200 |  | 1,000 |  |
|  |  |  |  |  |  | 130,000 | 95,000 | 20,000 | 15,000 |  |
|  | Update the implementation | UNDP | NEX | 71200 | International Consultant | 10,000 |  | 10,000 |  |  |
|  | evaluation and reporting |  |  | 71300 | Local Consultants | 10,000 |  | 5,000 | 5,000 |  |
|  | system in CPI drawing upon quantitative and |  |  |  | Computer software and hardware | 20,000 |  | 15,000 | 5,000 |  |
|  | qualitative targets and bench marks in annual |  |  | 73100 | Rental & Maintenance equipment | 9,000 |  | 3,000 | 3,000 | 3,000 |
|  | plans and monitoring |  |  | 72500 | Office supplies | 2,250 |  | 750 | 750 | 750 |
|  | information |  |  | 73500 | ISS | 1,750 |  | 1,750 |  |  |
|  |  |  |  |  |  | 53,000 |  | 35,500 | 13,750 | 3,750 |
|  | Sub-total |  |  |  |  | 283,000 | 195,000 | 55,500 | 28,750 | 3,750 |
| 2.2 Strengthened | Upgrade the compilation of | UNDP | NEX | 71200 | International Consultant | 15,000 |  | 15,000 |  |  |
| capacity of | information on |  |  | 71300 | Local Consultants | 15,000 |  | 5,000 | 5,000 | 5,000 |
| selected ministries | implementation monitoring in selected ministries |  |  | 72200 | Computer software and hardware | 58,000 |  | 50,000 | 4,000 | 4,000 |
| and agencies in | including training of |  |  | 72200 | Communications equipment | 5,000 |  | 5,000 |  |  |
| monitoring the | personnel, and provision of |  |  | 72500 | Office supplies | 2,450 |  | 450 | 1,000 | 1,000 |
| implementation of | computer software and |  |  | 73500 | ISS | 4,550 |  | 4,550 |  |  |
| the Sixth Plan and the annual plans, evaluation and reporting | hardware, communications equipment (including links with provinces ) and other support facilities |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 100,000 |  | 80,000 | 10,000 | 10,000 |
|  | Upgrade the | UNDP | NEX | 71200 | International Consultant |  |  |  |  |  |
|  | implementation evaluation |  |  | 71300 | Local Consultants | 18,000 |  | 6,000 | 6,000 | 6,000 |
|  | and reporting system in |  |  | 71300 | Support staff/translator | 1,000 |  | 1,000 |  |  |
|  | ministries and agencies |  |  | 72500 | Office supplies | 1,000 |  | 400 | 300 | 300 |
|  | drawing upon quantitative and qualitative targets and bench marks in their annual plans and the monitoring information |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 20,000 |  | 7,400 | 6,300 | 6,300 |
|  | Sub-total |  |  |  |  | 120,000 |  | 87,400 | 16,300 | 16,300 |
| 2.3 Strengthened | Upgrade the compilation of | UNDP | NEX | 71200 | International Consultant | 20,000 |  | 10,000 | 10,000 |  |
| capacity of three | information on |  |  | 71300 | Local Consultants | 15,000 |  | 5,000 | 5,000 | 5,000 |
| provinces in | implementation monitoring |  |  | 74500 | Training workshops | 10,000 |  | 3,000 | 6,000 | 1,000 |
| monitoring the implementation | in three provinces including training of |  |  | 72200 | Computer software and hardware | 30,000 |  | 10,000 | 20,000 |  |
| of the Sixth Plan | personnel, and provision of |  |  | 72200 | Communications equipment | 12,000 |  | 4,000 | 8,000 |  |
| and the annual | computer software and |  |  | 71300 | Support staff/translator | 2,000 |  | 1,000 | 1,000 |  |
| plans, evaluation | hardware, communications |  |  | 71600 | Travel (DSA) | 10,000 |  | 2,500 | 5,000 | 2,500 |
| and reporting | equipment (including links |  |  | 72500 | Office supplies | 3,000 |  | 500 | 1,000 | 1,500 |
|  | with ministries and CPI) |  |  | 73500 | ISS | 1,400 |  | 700 | 700 |  |
|  | and other support facilities |  |  |  |  | 103,400 |  | 36,700 | 56,700 | 10,000 |
|  | Upgrade the monitoring | UNDP | NEX | 71200 | International Consultant | 35,000 |  | 10,000 | 25,000 |  |
|  | evaluation and reporting |  |  | 71300 | Local Consultants | 15,000 |  | 5,000 | 5,000 | 5,000 |
|  | system in three provinces |  |  | 71300 | Support staff/translator | 2,000 |  | 1,000 | 1,000 |  |
|  | drawing upon quantitative |  |  | 72500 | Office supplies | 2,050 |  | 300 | 1,250 | 500 |
|  | and qualitative targets |  |  | 71600 | Travel (DSA) | 6,500 |  | 2,000 | 3,000 | 1,500 |
|  | and bench marks in their |  |  | 73500 | ISS | 2,450 |  | 700 | 1,750 |  |
|  | annual plans and the |  |  |  |  | 63,000 |  | 19,000 | 37,000 | 7,000 |
|  | monitoring information |  |  |  |  |  |  |  |  |  |
|  | Sub-total |  |  |  |  | 166,400 |  | 55,700 | 93,700 | 17,000 |
| 2.4 Strengthened | Upgrade the compilation of | UNDP | NEX | 71300 | Local Consultants | 25,000 |  | 10,000 | 10,000 | 5,000 |
| capacity to | information on |  |  | 74500 | Training workshops | 24,000 |  | 8,000 | 8,000 | 8,000 |
| monitor | implementation monitoring |  |  | 72200 | Communications equipment | 10,000 |  | 10,000 |  |  |
| implementation of | in poorest and poor districts |  |  | 72500 | Office equipment | 30,000 |  | 10,000 | 10,000 | 10,000 |
| the focal area | including training of |  |  | 71600 | Travel (DSA) | 9,000 |  | 3,000 | 3,000 | 3,000 |
| development | personnel, and provision of |  |  | 72500 | Office supplies | 6,000 |  | 2,000 | 2,000 | 2,000 |
| plans in the poorest and evaluation and reporting | communications equipment (including links with provinces, ministries and CPI) and other support facilities |  |  |  |  | 104,000 |  | 43,000 | 33,000 | 28,000 |
|  | Upgrade the monitoring | UNDP | NEX | 71300 | Local Consultants | 20,000 |  |  | 10,000 | 10,000 |
|  | evaluation and reporting |  |  | 74500 | Training workshops | 16,000 |  |  | 8,000 | 8,000 |
|  | system in poorest and poor |  |  | 71600 | Travel (DSA) | 6,000 |  |  | 3,000 | 3,000 |
|  | districts drawing upon |  |  | 72500 | Office supplies | 4,000 |  |  | 2,000 | 2,000 |
|  | quantitative and qualitative targets and bench marks in their focal development areas and/or annual plans and the monitoring information |  |  |  |  | 46,000 |  |  | 23,000 | 23,000 |
|  | Sub-total |  |  |  |  | 150,000 | 0 | 43,000 | 56,000 | 51,000 |
| 2.5 Results of | Assist CPI, Ministries, | UNDP | NEX | 71300 | Local Consultants | 15,000 |  | 5,000 | 5,000 | 5,000 |
| annual | Agencies and provinces to |  |  | 74500 | Workshops | 9,000 |  | 3,000 | 3,000 | 3,000 |
| implementation | feed the results of the |  |  | 71600 | Travel & DSA | 4,500 |  | 1,500 | 1,500 | 1,500 |
| monitoring and | annual implementation |  |  | 72500 | Office supplies | 1,500 |  | 500 | 500 | 500 |
| evaluation fed into and | monitoring and evaluation to NSC |  |  |  |  | 30,000 |  | 10,000 | 10,000 | 10,000 |
| incorporated in |  |  |  |  |  |  |  |  |  |  |
| the impact | Help NSC incorporate the | UNDP | NEX |  |  |  |  |  |  |  |
| monitoring system (including the LaoInfo system) maintained by NSC | results in the National Database on impact monitoring including the LaoInfo |  |  |  |  | 25,000 |  | 10,000 | 10,000 | 5,000 |
|  | Sub-total |  |  |  |  | 55,000 |  | 20,000 | 20,000 | 15,000 |
| 2.6 Project | Help CPI manage the | UNDP | NEX |  | Account Assistant | 19,200 | 4,800 | 4,800 | 4,800 | 4,800 |
| management | project implementation |  |  |  | Project Assistant | 19,200 | 4,800 | 4,800 | 4,800 | 4,800 |
| secretariat support | with secretariat support |  |  |  | Secretary | 16,800 | 4,200 | 4,200 | 4,200 | 4,200 |
|  |  |  |  |  | Driver | 16,800 | 4,200 | 4,200 | 4,200 | 4,200 |
|  |  |  |  |  | Cleaner | 1,700 | 420 | 420 | 420 | 440 |
|  |  |  |  | 72500 | Office equipment | 5,000 | 3,000 | 1,000 | 500 | 500 |
|  |  |  |  | 72200 | Communications incl. internet | 10,000 | 2,500 | 2,500 | 2,500 | 2,500 |
|  |  |  |  | 72500 | Office supplies | 6,000 | 1,500 | 1,500 | 1,500 | 1,500 |
|  |  |  |  | 71600 | Transport | 5,000 | 1,250 | 1,250 | 1,250 | 1,250 |
|  |  |  |  |  | Other misc. running costs | 400 | 100 | 100 | 100 | 100 |
|  |  |  |  |  |  | 100,100 | 26,770 | 24,770 | 24,270 | 24,290 |
|  | Sub total |  |  |  |  | 100,100 | 26,770 | 24,770 | 24,270 | 24,290 |
| Output 3. National Research Network to undertake policy research to support planning, monitoring and evaluation established |
| 3.1. National | National Research Network | UNDP | NEX | 71200 | International Consultant | 17,000 | 17,000 |  |  |  |
| Research Network | comprising the National |  |  | 74500 | Workshop | 5,000 | 5,000 |  |  |  |
| established in Lao | Economic Research |  |  | 74500 | Periodic Meetings | 6,000 | 3,000 | 3,000 |  |  |
| PDR | Institute (NERI) and |  |  | 72500 | Computers | 9,000 | 9,000 |  |  |  |
|  | selected Ministries and |  |  | 72500 | Communications equipment | 3,000 | 3,000 |  |  |  |
|  | Agencies established, with |  |  | 72200 | Other equipment incl. a/c | 2,000 | 2,000 |  |  |  |
|  | a Research Advisory Board |  |  |  | Secretariat operation cost | 5,970 | 3,250 | 2,720 |  |  |
|  | and a secretariat |  |  | 73500 | ISS | 2,030 | 2,030 |  |  |  |
|  |  |  |  |  |  | 50,000 | 44,280 | 5,720 |  |  |
|  | Sub-total |  |  |  |  | 50,000 | 44,280 | 5,720 |  |  |
|  | TOTAL |  |  |  |  | 2,454,500 | 914,550 | 827,590 | 412,020 | 300,340 |

|  | SIGNATURE PAGE |  |
| --- | --- | --- |
| Government of Lao People’s Democratic Republic |
| UNITED NATIONS DEVELOPMENT PROGRAMME LAO PDR |

| UNDAF Outcome(s)/Indicator(s): | Outcome 1: By 2011, the livelihoods of poor, vulnerable, and food insecure populations are enhanced through sustainable development (within MDG framework). |
| --- | --- |
| Expected Outcome(s)/Indicators(s): | CP Outcome 1.4: Enhanced ownership and capacity for pro-poor planning and implementation, harmonized aid coordination and disaster management. |
| Expected Output(s)/Indicator(s): | Increased capacity at the central and local levels for MDG based development strategies, policies and planning that combine a pro-poor and equitable approach to development processes; and effective implementation of public investment programmes in poor areas. |
| Implementing Partner: | Department of General Planning, Committee for Planning and Investment |
| Other Partners: | Selected ministries and agencies and three provinces |

| Programme Period: | 1 October 2006- 30 September 2010 |
| --- | --- |
| Programme Component: | MYFF Goal 1: Service Line 1.2- Pro-poor policy reform to achieve MDG targets |
| Project Title: | Support for Implementation of the Sixth Five-Year Plan (2006-2010) |
| Project Short Title: | Sixth Five-Year Plan |
| Project Code: |  |
| Project Duration: | 4 years |

| Total Budget: | USD 2,454,500 |
| --- | --- |
| Allocated Resources: |  |
| Government |  |
| Regular (TRAC Funds) | USD 800,000 |
| Other (including in-kind contributions) |  |
| DGTTF |  |
| Donor (SNV) |  |
| Donor (others TBD) |  |
| Unfunded Budget: | USD 1,654,500 |

| Agreed by: |  | Signature |  | Date |  | Name/Title |
| --- | --- | --- | --- | --- | --- | --- |
| CPI |  |  |  |  |  | HE Mr. Thongmy Phomvixay Vice-President of CPI |
| UNDP |  |  |  |  |  | Ms. Setsuko Yamazaki Resident Representative a.i. |

Annex 1

Project Management Structure

|  | Project Assurance |  | Project Board |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Supports Project Board and Outcome Board |  | Senior Supplier | Executive | Senior Beneficiary |  |  |  |  |
|  | UNDP Programme Analyst |  | UNDP ARR/Head of PE unit | DG, Department of General Planning, CPI | Steering Committee on RTM/NSEDP |  |  |  |  |
|  |  | Deputy Project Manager |  | Project Manager |  | Project Support |  |
|  |  |  |  | DDG, Department of General Planning, CPI |  | Advisors Project staff Administrative Staff UNDP PA |  |
|  |  | DDG, Department of General Planning, CPI |  |  |  |  |  |
|  |  |  | Outcome 1 & 2 |  | Outcome 3 |  |  |  |
|  |  |  | DOP With: NSC, MAF, MOH, MOE, MCTPC, MOF, MOFA, selected provinces, Long-Term and Short-term Foreign Experts, National consultants |  | NERI With Selected Ministries and agencies |  |  |  |

# Footnotes

Lao PDR Committee for Planning and Investment, National Statistics Centre and World Bank, Lao PDR Poverty Trends, 1992/3 – 2002/3, Draft Report, prepared by Kaspar Richter, Roy van der Weide and Phonesaly Souksavth, March 2005.

The Prime Minister’s Decree 01 proposes to strengthen the Provinces as the strategic units, the districts as the budget/planning units and the villages as the implementing units.

The LaoInfo v.4.1 is a common indicator database system providing access to national data across sectors for monitoring progress on the indicators and targets of the MDGs, the NGPES, and the five-year and annual plans. It includes data from national census, surveys, and the Government reporting systems by Ministries and Agencies. The LaoInfo v.4.1 has been adapted from DevInfo (see http://www.devinfo.org for more information) technology to the specific requirements of the Lao PDR by the NSC, with the assistance of UNDP, UNICEF and UNFPA.

A district may have as many as eight focal development areas or kum bans with each kum ban comprising a group of villages.

This is also the direction in which the international community, including the Bretton Woods institutions, the regional development banks and the UNDP, has begun to move by encouraging countries to integrate the PRSPs in their national development plans. It was also the consensus of the Forum on National Development Plans as PRSPs in East Asia organized in Vientiane during 4-6 April 2006.

The Ministries are to be selected based on their direct relevance to poverty reduction and achieving the MDGs. Potential ministries include Agriculture and Forestry, Education, Health, Infrastructure, Industry and Commerce and Energy and Mining, and the Tourism Authority. The selection will be made in consultation with the Ministries.

One province from each of the three (Northern, Central and Southern) regions will be selected. The selection criteria will include the number of poor districts, number of other donor-supported projects, capacity of Provincial Planning Department, and access to the Province. The selection will be made in consultation with the provinces.

The National Research Network [comprising NERI and selected Ministries and Agencies] to be set up under this component would facilitate the preparation of a package of policy research proposals (focusing on, among others, pro-poor policies) to support planning, monitoring and evaluation. It will establish/strengthen links with regional and global policy research networks including the Global Development Network.

In addition to mainstreaming gender, the project will incorporate the relevant indicators on gender dimensions in the monitoring and evaluation component, in collaboration with the Gender Empowerment for Poverty Reduction Project.

The project will link with the GPAR Central and Provincial projects (in Luang Prabang, Saravane and Xiengkhouang) in harmonizing the participatory planning methodologies/guidelines; and participatory monitoring and evaluation.

# Text boxes

Audit