ADDENDUM

SUPPORT TO ANGIE BROOKS INTERNATIONAL CENTER

2015 JOINT WORK-PLAN ON Gender and HIV & AIDS

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME 2015 | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  | List activity results and associated actions | Aug | Sept | Oct | Nov |  | Funding Source | Budget Description | Amount in USD |
| Angie Brooks International Center (ABIC) |
| Output 1: Empowered female motorcyclists through livelihood provision and protection. Indicators: Baseline: Targets: | Action 1.1: procurement of 11 motorbikes and accessories (including boots, protective jackets, paper spray, communication cards and insurance of motorbikes) for 10 female motorcyclists and one supervisor |  | X | X | X | ABIC UNDP |  |  | 19,345 |
|  | Action 1.2: Hold a 2-day training workshops for female motorcyclists and female taxi drivers as well as other representatives on safety and defensive driving. |  | X | X | X | ABIC UNDP |  | 75700 Workshop and Training | 6,845 |
| Sub-total | 26,190 |
| Output 2: Enhanced participation of rural women in decision making processes through provision of adult literary education Indicators: Baseline: Targets: | Action 2.1: Training of 30 rural women in adult literacy program for a period of three months (4 times a week) and procurement of training materials |  | X | X | X | ABIC |  | 75700 | 5,220 |
|  | Action 2.2: Stationery supplies, printing of t-shirts, certificates, phone cards and payment of facilitation fees for facilitators |  | X | X | X | ABIC UNDP |  | 72500 | 1,735 |
| Sub-total | 6,955 |

| Output 3: Increased awareness on maintenance of peace through awareness workshops prior to 2017 General and Presidential Elections. Indicators: Baseline: Targets: | Action 3.1: Hold 1 day advocacy and awareness workshop for not less than 115 participants on peace and conflict management |  | X | X | X | ABIC UNDP |  | 75700 | 3,050 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Action 3.2: Provision of logistics, phone cards, banners, fuel, vehicle rental, stationery supplies |  | X | X | X | ABIC UNDP |  | 72100 | 1,430 |
| Sub-total | 4,480 |
| Compensation fees | Compensation fees for 3 months for two ABIC staff (Coordinator @ US$800/month and Assistant @ US$500/month for three months each |  | X | X | X | UNDP |  | 71800 | 3,900 |
|  | Misc. |  | X | X | X | UNDP | 04000 (UNDP) | 74500 | 1,000 |
| Grand Total | 42,525 |