Early recovery and Livelihoods cluster – UNDP

Ebola Crisis Response and Resilience Program in Liberia (ECRRP-L)

Social Safety Net Cash Transfers and Resilience Strengthening

Project Financing Summary Total Project Budget: US$ 12,903,436 Available Resources To Date: US$ 2,000,000 Balance of Funding Sought: US$ 10,903,436

Executive Summary

In early 2014, Liberia seemed to be well on its way to re-building physically, economically, and socio-emotionally from a long period of devastating civil war.  The Ebola virus not only stalled the country’s progress toward peace, stability and economic development, but risked creating setbacks.  Since the onset of the Ebola Crisis in Liberia, there have been 9,718 cases of the virus recorded by the Ministry of Health (MOH) through its Incident Management System. 4,304 persons have died from the disease.  With every passing day, hopes increase that the country will pass the 42-day threshold for declaring Liberia Ebola-free. That, however, cannot and should not be taken for granted.

In addition to the suffering and death experienced by those households directly touched by the disease, many more experienced social and economic interruptions and hardship.  Economic growth has slowed markedly and tax revenues have fallen, placing in jeopardy the government’s capacity to provide basic services.  Jobs have been lost since the initial outbreak while prices for basic foods have risen compounding the hardship for households with reduced income.

Those households living below the poverty line (over 47% over the population) have been severely affected.   With livelihoods impaired or lost, food insecurity has worsened, and because of lost livelihoods the poorest households have resorted to more negative coping mechanisms.  The longer the crisis lasts, the more impaired will be the resilience of the poorest segments of society against future shocks.  Any erosion or impairment of social cohesion resulting from the Ebola Virus Disease (EVD) shock would represent a devastating setback for a society emerging from decades of civil strife.

Overcoming endemic lack of confidence in government institutions on the part of large segments of the population, especially those poor and extremely poor who risk a worsening sense of disenfranchisement should their situation remain dire or even deteriorate, proved to be a challenge for implementing an effective response to EVD.  Studies are showing that robust link exists between trust in government and compliance with imposed or recommended EVD response measures.  Individuals who are more trusting of government are more likely to support control policies and more likely to adopt preventative measures.

This project seeks to provide a safety net for those households which have had a member succumb to the disease and on which quarantine has been imposed.  It will extend a similar safety net to extremely poor and labor-impaired households which have been most vulnerable to the shocks that EVD has caused.  Support will take the form of monthly cash distributions to qualifying households, which they will use to take care of their basic requirements for sustenance.

20,000 households in three targeted counties – Bong, Lofa, and River Cess – will receive cash transfers of up to LD 4,500 (USD 50) for a period of 9 months, in accordance with government cash transfer guidelines.  At the same time, the project will offer beneficiaries an opportunity to receive literacy (including numeracy) and enterprise skills training during the period of the project.  Members of Village Savings and Loan Associations (VSLA), and households who decide to become members, will be able to accelerate their accumulation of savings shares by way of a 5-to-1 “savings accelerator” matching grant (up to an maximum of LD 7,650 (USD 90).

In accordance with the Government of Liberia’s (GoL) Social Protection Policy, the Ministry of Gender, Children, and Social Protection (MGCSP) will lead the implemention of the social safety net cash transfers element, and will coordinate with key ministries and stakeholders which are able and willing to contribute complimentary support to beneficiaries in order to strengthen sustainable livelihoods and resilience against future shocks.  In this regard, the Ministry of Education (MoE) will participate to organize adult education and business skills training.  The National VSLA Apex (VSLA NAPEX) will be an operational partner through which cash will be channeled to beneficiaries by way of their network of VSLAs in communities throughout the three counties, and through which beneficiaries will be able to build savings so as to obtain credit for productive investments.

This project is a cornerstone of the Liberian National Social Protection System as a nationally owned and implemented service which delivers coordinated and targeted protection programs to vulnerable segments of the population when and where they are required.  An efficient, responsive, effective and accountable safety net system in Liberia will support Liberia’s social contract with its citizens and contribute significantly to generating trust in Government to govern with the interest of its citizenry, particularly the most vulnerable, in mind.

In addition, safety net cash transfers will represent a direct infusion of liquidity into local economies which has stagnated in the face of EVD.  The cash placed in the hands of extremely poor and poor households will immediate percolate up through local economies. It will, to its own degree, contribute to a rejuvenation of the nation’s fiscal stream.

The project requires USD 12,903,436 of which USD 10,299,960 is earmarked for cash transfers to beneficiaries.

Context

Since early 2014, the Ebola Virus has spread in West Africa and has most severely hit Liberia, Sierra Leone and Guinea. It has also touched Mali, Nigeria, and Senegal, as well as Spain and the United States of America on a much smaller scale.

As of 17 March 2015, Liberian Ministry of Health reports a total number of 9,718 cases (suspected, probable and confirmed), and 4,304 deaths nationwide.  However, statistics involving the number of cases of the illness and resulting mortality, only describes a portion of the negative impact that the disease has inflicted on the country.  More widely, economic development has been interrupted, livelihoods have been lost, resilience among the poorest has been severely impaired, tax revenues have fallen, and social cohesion could be threatened in Liberia.

Growth in nation’s anticipated 2014 output, measured as Gross Domestic Product (GDP), has been reduced by 5.5 percentage points, from 5.9% to 0.4.% as a result of the crisis. Projections for a drop in 2015 GDP range from USD 114 million drop (5.8 pp) under a low Ebola scenario to USD 234 million (12 pp) in a high Ebola scenario.

On a micro level, a survey by the World Bank revealed that 46% of those working at the start of the Ebola Crisis were no longer working in early November.  Self-employed and wage workers have been the hardest hit, while those in agriculture were starting to return to work as the harvest approached.  Food insecurity is worsening due to rising rice prices and falling incomes.  While the price of rice historically tends to reach its highest levels around October (7% above its January base in 2013), the October/November 2014 price of rice was over 40% higher.

By December 2014, the deterioration in key business/employment indicators seems to have slowed slightly.  While promising, the data came only from formal sector S/M sized businesses (not the overwhelming informal sector), and could not rule out seasonal influences (holiday demands).  Even with that glimmer of hope, the road to economic recovery and re-activation of livelihoods will be long.

The prospects for the national economy continue bleak.  Economic growth in 2015, which was projected to be 6.8%, has been revised downward further to no growth due to further contraction in activities in the key sectors of the economy—mining, agriculture and services.  Further reductions in growth projections, and even negative growth in all sectors of the economy, bode poorly for employment prospects, as well as levels of revenue for the self-employed and those in the informal sector.

The very rapid spread of the disease led the Liberian government, at one point, to declare a State of Emergency and special measures to control the outbreak including the closure of borders, schools and suspension of some major food markets in the most affected areas. From a FAO fact finding mission (September 2014) and the FAO/WF/Ministry of Agriculture Ebola Food Security Impact Assessment (October/November 2014), the main impacts assessed were the reduction in agricultural production, the increase in food prices and the depletion of household/women associations’ savings.   The depletion of household assets (material as well as financial) bodes poorly for the capacity of households, particularly those in the lowest economic quintile of society, to weather future shocks when they might occur. Households are also likely to be engaging in other negative coping mechanisms, such as decreased food consumption and the substitution of highly nutritious foods for cheaper but less nutritious commodities, or failure to send children to school, once they restart, to save school fees and related expenses. Such money-saving/resource-stretching actions would negatively affect the development of human capital and future productivity.   In desperate cases, members of households in need could resort to unlawful activities (i.e. thievery or prostitution).  This would have a wide negative affect on governance and the security of society.

One must keep in mind that main rainy season planting begins now in March, 2015.  Depending on whether adequate inputs and credit could be motivated on time, farmers may confront a challenging planting season.  In the event of shortfalls this agricultural cycle, the traditional hungry/lean season for the poor/extremely poor could be harder and longer.  In that case, the role of safety net assistance will be even more important.

THE OVERALL STRATEGY

The project will address the effects of the EVD and structural poverty on three dimensions:

Household welfare

- It will provide temporary financial assistance to the most affected communities and households so that Ebola-affected and extremely poor/labor constrained families can provide for their minimal sustenance (food and non-food) without having to utilize negative coping mechanisms;

Household productive capacity, human capital and resilience

- Set in motion a reactivation and strengthening of household productive capacities and  development of human capital, essential for build resilience to shocks  by:

- Re-building  household savings, and the access to credit through Village Savings and Loan Associations (VSLA); and

- Increasing literacy (including financial) and enterprise skills as contributing elements for economic and social advancement.

- Provide a temporary supplemental income to teachers and qualified unemployed young adults whose jobs have been suspended by school or business closures through Cash For Work (CFW) for their collaboration in conducting adult literacy and business skills training.

Institutional Strengthening

- Contribute to strengthening the institutional capacity of the Ministry of Gender and Social Protection (MGSP) to provide effectively and efficiently social safety net assistance to persons/households suffering from abject poverty or the sudden shock of natural or man-made disaster, of which the current EVD presents particular organizational and operational challenges and complexities.

LINKS TO GOVERNMENT PLANS FOR IMMEDIATE STABILISATION AND RECOVERY

The Government of Liberia is finalizing an official publication of an Economic Stabilization and Recovery Plan in response to the Ebola crisis and its immediate aftermath. The plan calls for Social Protection, and specifically Social Safety Net Cash Transfers to play a key role in recovery and building resilience in the face of future shock, which, if left un-attended, could put at risk social cohesion and security.

This project builds on the lessons from the recently concluded Pilot Social Cash Transfer (SCT) project, supported by UNICEF and implemented by the MGCSP.  It is in line with Liberia’s Social Protection Policy.  This project has been designed and will be implemented to support the MGCSP in achieving the four policy objectives of the Social Protection Policy in a number of ways:

- The project will be invested in providing the MGCSP with resources to continue building out a robust M&E system (PO 1).

- Funding for cash transfers will be channeled to beneficiaries through a variety of innovative delivery systems (through VSLAs, by way of Mobile Money, and through off-site banking payments), according to requirements in different locations and feasibility (PO 1).

- Implementation will be inclusive, involving local authorities and concerned stakeholders at the country, district and community level.  The project will ensure that they have support to do the job. Promotional and technical assistance will be provided in regional and county offices of the MGCSP and county social protection sub-committees to strengthen their capacities to plan, mobilize, coordinate and implement actions not only associated with this intervention, but also for continued social protection, inclusive governance and development (PO 1).

- The MGCSP and UNDP, in concert with all partners, will implement the cash transfers, mindful of how they can be employed as part of a lean season safety net.  By partnering with VSLAs, the project will contribute to promoting entrance of cash transfer recipients into community savings and credit mechanisms, whether in the form of VSLAs or traditional “Susus”. (PO 3).

- Within the scope of the project, the MGCSP will coordinate with and strengthen linkages to policies and programs of other sectors to ensure that the poorest and most vulnerable households have opportunities to engage in economic activities to enhance acquisition of assets and capital.  With the Ministry of Education, the incorporation of literacy and vocational skills training into assistance to cash transfer recipients will represent greater access to an essential package of education.  The VSLAs will provide a linkage to financial services and savings schemes that could help beneficiaries to access micro-finance. (PO 4).

Overall, the project falls completely within the scope of actions of the Social Protection Sector in Liberia’s Agenda for Transformation, to “Improve protection of the poorest and most vulnerable households and groups from poverty, deprivation and hunger and enhance their resilience to risks and shocks”.

PROGRAMME GOAL

Extend a social safety net, as part of the social contract between the Government of Liberia and its citizens, to stabilize the economic welfare and livelihoods of, as well as initiate a path of recovery for, households which have been directly affected by the Ebola virus and those which have suffered the social and economic shocks generated by the disease.

PROGRAMME OBJECTIVE(S)/RESULTS

- Beneficiary households provide for their sustenance for the duration of the Ebola crisis without further recourse to negative coping mechanisms, such as depleting financial savings, liquidating material assets, incurring debt, reducing food consumption in quantity and quality, hindering economic opportunities, etc.

- Members of approximately 300 Village Savings and Loan Associations (existing and new members) begin to rebuild their savings in VSLAs.

- Using share savings as collateral, VSLA members regain access to credit for income-generating investments, with improved prospects of being able to repay their loans.

- CT recipients who elect to participate improve their level of literacy, numeracy and small business skills as a tool for improving their livelihoods.  At the same time educators and other qualified persons (i.e. unemployed youth) who have lost income during the EVD crisis due to school and job suspensions recuperate some of their losses through obtaining supplemental income (cash-for-work) as adult literacy trainers.

PROGRAMME OUTPUTS

  - 20,000 women receive, on behalf of their families, a “semi-conditional” cash transfer of up to US$50 per month for a period of twelve months.

  - In acknowledgement of the assistance provided, beneficiaries of cash assistance will be strongly encouraged to spread the information/knowledge they receive from sensitization sessions by actively promoting actions/practices of Ebola prevention in their respective communities.

2.1 Up to 9,000 active members of VSLAs (including up to 1,875 new members) receive a supplemental grant of up to US$90 during the life of the project, in the form of monthly matching “savings accelerator” cash transfers, which will be utilized to purchase share savings in their VSLAs.

3.1 Up to 3,500 VSLA members will be granted small loans from their VSLAs for IGAs on the basis of their share savings on deposit.

4.1 Adult literacy, numeracy and business skills training classes are organize and conducted in up to 200 communities in accordance with national curricula and training plans established by the Ministry of Education.  Classes will be open to all members of targeted communities, regardless of whether or not they receive cash transfers.  Up to 5,000 trainees and 500 trainers could participate in adult literacy training.

5.1 The MGCSP will add a third regional office in Gbarnga, Bong County to serve the northern part of the county, as well as roll out its safety net cash transfer programme in three counties as part of its goal of national coverage.

PROGRAMME IMPLEMENTATION

Coordination and Operational Partnerships

The intent of the project is to bring together a range of national (public and private) and international actors, under the coordination of the MGCSP, to address the immediate household needs for cash on the part of EVD-affected, as well as poor/extremely poor households for their sustenance in the wake of the EVD. Through focused and multifaceted collaboration, the project will provide affected households with means by which they may recover and improve their livelihoods so as to strengthen their resilience to future shocks.

This project’s actions and investments will be overseen, alongside other related interventions, by the National Social Protection Steering Committee, with a secretariat set up under the Department of Regional and Sectoral Planning.  It will be in that forum that this project’s approaches can be harmonized and specific actions coordinated with similar interventions so as to form a coherent and comprehensive social protection programme which meets the needs of the most vulnerable segments of the population.

The project will also be implemented in partnership with the Ministry of Education (MoE), which will coordinate literacy and vocational skills training activities in association with cash transfers in the targeted communities.  In addition, the National Apex of Village Savings and Loans Association, will partner in coordinating the participation of VSLAs in targeted communities to provide the conduit for transferring and distributing cash to approved beneficiaries.

In the counties, planning and execution will be coordinated with the Social Protection Sub-committees of the County Development Committees, chaired by Development Superintendents.

UNDP will support the MGCSP to establish its third planned regional office in Gbarnga, Bong County and to roll out safety net cash transfer operations in three new counties (Bong, Lofa, and River Cess). The project will provide MGCSP with a budget to establish its operational capacity in the region and counties.

The project will supplement that capacity with the presence of two international (UNV)  field officers  and three national monitoring officers (assigned to cover each of the three counties).  Those UNDP staff will support MGCSP field personnel with sensitization of county and district authorities/stakeholders, and subsequent planning and executing screening/validating of beneficiaries in close concert with community cash transfer coordinating committees, which will be organized in each targeted community.  They will also support the Ministry’s monitoring of the distribution of cash assistance to designated beneficiaries, and the management of information as it is generated.

Operations will utilize the MGCSP’s existing systems and procedures.  The project will also take advantage of contributions by community-based social workers to be dispatched by the Department of Social Welfare.  The MGCSP and UNDP will assess the existing regional management structure, systems/procedures/tools, and infrastructure and, based upon the results, UNDP will allocate programme resources to make the necessary strengthening investments to ensure effective and efficient implementation.

The MoE, with UNDP support, will implement activities of adult literacy enterprise skills development in the counties and districts served by this project.  The intention will be to utilize the services of teachers and other qualified persons to collaborate in their communities in conducting adult literacy classes and business skills to cash transfer recipients.  The project will be based on existing curriculum, lesson plans and materials sanctioned by the Ministry.   This project will support the Ministry in having adequate quantity and type of training materials in place in the districts/communities where training will take place.  If required, the Ministry will, with programme support, organize training-of-trainers for those trainers with regard to scope, sequence and methods of teaching adult literacy and numeracy.

It is hoped that this initial intervention will be recognized in the communities and throughout the counties served for its important contribution to building essential human capital by the poorest, most vulnerable segments of the population, and that it will be expanded in scale and scope in the form of longer-term development investments to ensure increasing access to an essential package of education to adult learners (two of the three counties report the highest incidences of adult illiteracy among  in the country).

The VSLA NAPEX will participate as an operational partner with UNDP and the MGCSP for actually carrying out cash distribution by way of its network of established community associations.  Those associations, comprising 25-30 members each, are positioned to provide front-line contributions in terms of:   management of the cash transfer process in communities (facilitation of local banking, cash handling, and distribution to designated beneficiaries); and carrying out of first-level local accounting and ensuring that appropriately detailed support documentation on cash distributed and cash received is obtained and submitted).

VSLAs can serve as gateways into communities and households. They are voluntary associations that are set up to attract savings and grant loans to its members.  As they are voluntary and self-governing, members can be from different socio-economic strata.  However, as the poorest households have great difficulty accessing the formal banking sector (difficult access to banks located only in county capitals, prohibitively high fees for very small account holders, and an unwillingness of banks to lend to poor persons with little or no collateral).  By giving more than poor/extremely poor (50% of the population) an entry point to the formal components of the economy of the country, the become true stakeholders in the peace and stability of the nation, required to build and grow an economy that addresses the needs of all.

As a conduit for cash transfers to poor households, VSLAs will offer several advantages within the scope of this project:

- Members of VSLAs are already organized and committed to the improving their lives and livelihoods;

- Most members are women (approximately 60% of VSLAs are formed as women’s groups, the rest of the groups are mixed), who have been among the most affected by the EVD, and actively manage the well-being and needs of their  families;

- VSLA members are committed to savings as a key element in building resilience; and through their savings gain access to credit for IGAs;

- VSLAs constitute an extensive network, present in all counties of the country; and

- VSLAs already possess bank accounts, and their members are versed in handling and accounting for funds entrusted to them.

As the next agricultural cycle starts (approximately March 2015),   safety net assistance should pave the way for further interventions/investments to ensure that farming households plant to full capacity and improve their production/productivity. Through collaborative planning and coordination of interventions with FAO, it is hoped that complimentary assistance (material and technical) can be targeted toward communities and beneficiaries in support of the next planting season. Household livelihoods and resilience strengthening will also be supported through more active and stronger VSLAs which can effectively assist members accumulate savings and access credit for small-scale productive enterprises either from the VSLA or other sources of financing.

The project will invest in strengthening the architecture of social protection in Liberia, starting with a sustainable safety net system that enables the most vulnerable segments of society to ride out the social and economic shocks that might affect the country.

Coordinating Cash Transfer Assistance and Avoiding Duplication

The project will coordinate with similar programmes under development by the World Bank and FAO, both bilaterally, as well as within the National Social Protection Steering Committee.  It will focus particularly on ensuring that the investments made by the three organizations are mutually supportive to meet the immediate and short-term recovery needs of targeted communities.

Within the scope of its mandate as coordinating agency for implementation of the social protection, the MGCSP will coordinate the efforts of numerous aid organizations which are implementing or planning to implement cash transfer assistance in support of a variety programmes.  As Chair of the  Technical Working Group for Cash Transfers (within the Early Recovery Cluster) the Ministry will seek to harmonize and coordinate the efforts of  like-minded aid organizations in terms of approaches, systems and targeting for optimal efficiency and effectiveness.

The ultimate objective will be to create, with the cooperation of all concerned actors implementing cash transfer assistance (unconditional and conditional), a comprehensive “3W” (Who is Doing What Where) data base of interventions in all counties that will be a resource for all in identifying needs and gaps, as well as opportunities for partnerships in extending safety nets to as many households which require them as possible.

Such coordination will extend to county administrations through their Development Committees and Sub-Committees for Social Protection.  The project, through Ministry and UNDP field personnel and targeted material/financial support, will provide county authorities with the backstopping they require to carry out effectively coordination, mobilization and engagement of stakeholders, and assistance tracking to avoid duplication and to optimize limited resources within their jurisdictions.

Targeting

The effects of Ebola are not limited to the families who have unfortunately had members succumb to the disease or even those who have been obliged to be quarantined as a result of contact with sick persons.  The economic effects caused  by border and road closures, restrictions on market activities, job layoffs and reductions in earnings of the self-employed have occurred throughout the country, not just in counties with the highest incidence of the disease. Safety net assistance can be provided in any county where the poorest households have had their livelihoods affected by the economic shock that the disease has brought about (See Annex 1).

Mindful that a number of aid organizations will be providing social safety net and early recovery assistance in Liberia, this UNDP-supported project should be implemented in a way that identifies gaps and fills them.  In this regard, the Cash Transfer Working Group of the Early Recovery Cluster will serve as the forum for collecting, tabulating and diffusing information on “who is doing what where” (3W), ideally resulting in members collectively targeting their interventions in a coordinated manner to ensure that coverage is as wide as possible to meet all identified needs, while avoiding overlap/duplication.  Likewise, the cluster can be used to harmonize the amount and duration of cash assistance provided, as well as implementation  modalities (i.e. eligibility criteria; identification, screening and selection procedures) among concerned actors, so that best practices are widely employed throughout the country.

County Targeting

That said, however, this project will roll out in three counties that have been assessed on the basis of available data in terms of the following metrics (see Annex 2):  1) level of Ebola infection, 2) percentage of the population living in food insecurity, 3) incidence of global acute malnutrition among children under 5, and 4) the presence of other aid organizations with livelihoods or social protection programmes.  The degree to which Ebola has affected each country and the level of known programming coverage we accorded higher weightings.  Having weighted each county against those criteria, and taking into account the MGCSP’s expansion plan for cash transfer assistance, the counties chosen for roll-out are:

- Bong

- Lofa

- River Cess

Bong will the site of a new MGCSP regional office. Targeting Bong County will result in project funds being used to building their operational capacity in the northern part of the country.  Lofa Country will fall under the responsibility of the Bong Regional Office. While Lofa may have been ranked in the mid-tier of counties, it is found to be among the counties that has been most affected by Ebola. It has an extensive border with Guinea, thus of strategic importance in terms of having a safety net capacity in the unfortunate event of a renewed cross-border outbreak.

District Targeting Within Counties

In partnership with the MGCSP and in close concert with each county’s Development Committee and informed stakeholders (i.e  NGOs, religious leaders, CBOs, among others) the most affected districts will be identified and prioritized.  A first criteria for targeting should rightfully be those districts where there have been/are confirmed cases of Ebola and quarantines.  Districts with high incidences of extreme poverty, food insecurity, and child malnutrition along with those which are under-served in terms of social assistance and development projects will be accorded targeting priority.

Ideally, once districts are identified for targeting, every possible effort will be made to conduct cash transfers in all communities/villages of those districts.  This should be undertaken to minimize misunderstanding and social tensions among communities within the same district, so that the project does not adversely affect social cohesion and local governance.

Household Targeting Within Districts/Communities

The MGCSP has developed rigorous procedures and tools for surveying, registering and screening potential beneficiaries of safety net assistance.  Those systems will be employed in the implementation of this project, though the ministry and UNDP will collaborate in assessing them to make them as stream lined and effective as possible.  The criteria/indicators used to select ultimate beneficiaries will be objectively verifiable so as to be the least subjective as possible, as well as clearly and easily understood to community members and their leadership.  Eligibility criteria in order of priority/importance will be:

- Households with documented Ebola patients (present or past; deceased or recovered)

- Households on which quarantine has been imposed

- Households headed by a single female,  an elderly (>60),  handicapped, or young member  (<18)

- Households with children <5 being treated for MAM/SAM

- Households with a dependency ration of 3 or greater

- Members in good standing in a VSLA

- Dry meat (bush meat) sellers and hunters who need to develop alternative livelihoods

Meeting any one of the above criteria would make a household eligible for assistance.  Within the scope of the project’s objective to reactivate and strengthen structures which support household saving, access to credit and productive enterprises, members in good standing of VSLAs will be target within the scope of early recovery from the EVD crisis.  An allowance will be made to register new households (not initially meeting under any of the above criteria) which may fall into categories A & B after the initial screening. Before being used in first level community assessments, the criteria will be analyzed and validated with MGCSP staff and a representative sampling of informed local stakeholders in each county.

Care will be taken to liaise with organizations which already may be providing assistance in one form or another to households with Ebola patients (i.e. in the form of food aid to quarantined households, solidarity kits to survivors, death benefits, etc.) so as to avoid redundancy and to ensure that those not receiving assistance do so in the form of cash. Similar coordination will be undertaken with organizations providing various forms of cash assistance in each jurisdiction.

The beneficiary selection process will be inclusive.  In each community, the project will bring community leaders and respected community stakeholders (including the chairperson of VSLAs) together as a cash transfer coordinating committee which will:

- Work with MGCSP and UNDP field staff to inform community members of the project, raising awareness of its nature, purpose, methods, timeframe, and expectations of beneficiaries.

- Identify an initial list of community households which, to their knowledge, meet the objective eligibility criteria established by the MGCSP.  That list will be subjected to screening by MGCSP staff.

- Participate in a final beneficiary validation process in which the results of the MGCSP’s screening will be put forward for public scrutiny to identify any selection errors/omissions.

- Assist the MGCSP and UNDP in making arrangements for orderly registration of beneficiaries and distributions (convoking chosen beneficiaries, arranging any required security measures on registration/distribution days, and helping organize associated awareness-building and training events).

- Serving as a first channel of reception of complaints for the attention of the MGCSP and, if warranted, UNDP.

One or more pre-implementation meetings will be carried out to orient and train community cash transfer coordination committees and VSLA committee members who will be carrying out cash distributions prior to commencing the process of beneficiary identification, screening, selection and registration.

Initial beneficiary lists provided by coordination committees will be screened and vetted by way of direct visitation to households by MGCSP social workers and targeting assistants, aided by UNDP field staff, utilizing standardized assessment tools.  Duly screened/vetted community lists of beneficiaries who meet eligibility criteria will be submitted to a MGCSP/UNDP project management steering committee for final approval prior to formal registration.

Community VSLAs will be operating partners for actual cash distribution activities.  Community coordination committees will convoke approved beneficiaries for registration to be carried out by MGCSP and UNDP field staff (or a cooperating NGO partner, when pertinent).  ID cards will be issued to a designated adult female family member, unless compelling considerations warrant that a male member receive the transfer, in representation of the household. The beneficiary card will have a date of expiry and will contain the designated recipient’s important information (i.e. national identification number, address/location,  a photo, number of eligible family members, etc.).

At that time, key information will be gathered on beneficiary households to serve as a baseline for assessing the results/impact of the project on household welfare and livelihoods.  In parallel, information will be collected from a sampling of other community households to establish a control group against which to measure and assess results accruing to cash transfer beneficiaries. Such baseline information will include, among others:  household demographics, food consumption levels and food diversity (by way of quick recall), off-farm sources of revenue (formal and informal) and income generated, agricultural production (acreage planted, last harvest amounts), household debt levels and sources.

After six monthly cash distributions, beneficiaries and non-beneficiaries will be re-surveyed to monitor changes in their status/conditions.  Between the full surveys, monitors will randomly visit beneficiary households within the scope of a Post Distribution Monitoring (PDM) plan to check on how households utilize their cash assistance and the impact it has on their lives. Base line data will be collected on community economies. The same indicators will be monitored through PDM and analyzed to identify any “multiplier” or “ripple” effects of the cash transfers. Monitors will also seek out unforeseen difficulties or problems that will be addressed during the course of implementation.

On registration day, beneficiaries will be provided a standard orientation on the nature/purpose of the assistance, the terms and conditions associated with the assistance, the timing and procedures for the payment of transfers, how recipients will acknowledge receipt of payment, and mechanisms/channels that will be in place for beneficiary to make complaints about improper treatment by staff (particularly harassment and solicitation of kick-backs) or quality of service.  The number of disbursements and the anticipated end date of assistance will be very explicitly and clearly conveyed to beneficiaries and reiterated throughout the life of the project.

Cash Transmittals and Distribution

Safety net cash assistance will be provided to qualifying households on the basis of a family size in accordance with a scale adopted by the MGCSP for social safety net cash transfers.  Those rates will be:

- 1 person household LD 1,700 (USD 20.00)

- 2 person household LD 2,550 (USD 30.00)

- 3 person household LD 3,400 (USD 40.00)

- 4+ person household LD 4,250 (USD50)

The rates have been established in consideration of the acute shock to households resulting from the EVD crisis.  At the same time they are set at levels that avoid creating a disincentive to a household pursuing all available avenues for generating income to meet its needs. Likewise, the amounts should not dis-incentivize recipients from participating in livelihoods development initiatives.  In the future, however, the government could elect to adjust lower safety net assistance levels to address household needs resulting from non-acute (structural/chronic) vulnerabilities/shocks.

As an added element, beneficiaries who are currently active and members in good standing of VSLAs will receive a supplemental “savings accelerator” grant of up to a total of LD 7,650 (US$90) during the life of the distribution period.  This temporary grant will help members rebuild their share savings in VSLAs, which, in turn, will re-capitalize the associations, allowing them to make more loans to members sooner.  Beneficiaries who eventually become new members in existing or new VSLAs and who will be in good standing will also be eligible for the supplemental grant.

The supplemental grant will be conditioned on beneficiaries renewing and maintaining their monthly savings as prior to the EVD crisis.  Respecting the fact that VSLAs are locally managed, operate according to their own by-laws, and that individual savings rates are voluntary according to the means of each member, the project wishes to motivate members to return to their prior habits.  To be eligible for the “savings accelerator” grant, members will have to demonstrate that they have made three consecutive months of savings shares purchases of at least LD 340(USD 2) each time, in accordance to their means.  Upon the third share savings purchase, a qualifying household will receive a supplemental grant of five times (5-to-1) the value of that month’s savings, up to a maximum of LD 2,550 (USD 30) per month.  Each member will be allocated a maximum of LD 7,650 (USD 90) over the life of the distribution period.  The use of proportional match conditionality is to motivate effort and commitment.

VSLA members who have outstanding VSLA loans, may elect to use part or all of their ”savings accelerator” to pay down/cancel their debt, thus making them eligible for new credit.  VSLAs currently grant credit to members on a 5-to-1 ratio to their savings account value.  For the most part, members take out loans for productive investments for micro-enterprises or agriculture, though they are also known to use credit to cover school and medical expenses, which represent valid investments in human capital.

To guard against “household padding”, the project will take care to ensure that “households” adhere to strict definitions of being a grouping of persons who live under the same roof on a full-time basis, share all meals together, and depend on a common budget for meeting their living needs.

The programme will utilize the existing bank accounts, cash handling, and cash accounting capacities of participating VSLAs.  On the basis of approved lists, UNDP will deposit the allotted funding in the designated VSLA bank accounts.  Prior to the first disbursal, the VSLA NAPEX and VSLAs will sign operating agreements with UNDP which will govern receipt, distribution and accounting for funds from this programme.  Prior to beneficiary registration and orientation, UNDP and the MGSP will organize a series of regional and sub-regional orientation workshops for VSLA leaders (executive committee members, especially treasurers) which will provide them with all they will need to know about the systems and procedures that will be implemented in the course of making cash transfers.  Special attention will be paid to how “quasi-conditionality” will be carried out.

UNDP will make bank transfers into the designated bank accounts of participating VSLAs according to a pre-agreed beneficiary lists and calendar of distributions.  Deposit confirmation documentation will be sent to participating VSLAs by way of the MGCSP field staff or designated NGO partner.  VSLAs will be provided with standardized forms for documenting beneficiary receipt of allotted cash, which will be designed by UNDP and MGCSP, in concert with the VSLA NAPEX and cooperating NGO partners.

VSLAs will make payments from the funds deposited into their accounts to designated beneficiaries on dates and times to be officially established by UNDP and the MGCSP.  VSLAs may recommend making cash distributions on multiple days if they believe that handling less cash is preferable to ensure security.  With the assistance of the MGCSP or a cooperating partner NGO, and in concert with the concerned community cash transfer steering committee, each VSLA will be responsible for establishing appropriate security measures at an official distribution site. The MGCSP and UNDP will establish guidelines on distribution site security and provide VSLAs with the necessary training and guidance. Those VSLA members who withdraw and handle funds from association accounts will do so according to the rules and regulations stipulated in their by-laws and duly vetted by UNDP/MGCSP.  Duplicate copies of signed cash receipt forms will be drawn up by VSLAs, one copy of which will be sent to the MGSP for inspection, certification and dispatch to UNDP for approval and accounting.  Each beneficiary ID card will contain space to record and acknowledge each cash receipt.

During planning at the county level, an assessment will be carried out of conditions that might indicate the feasibility of the use of Mobile Money as a means of transferring cash (signal coverage, a critical mass of mobile phone users, adequate Mobile Money distribution capacity of the service provider – especially agents - and adequate liquidity).  When conditions are deemed right, one or more pilot groups will be organized to test the efficiency and efficacy of that means of cash transfer.  The pilot groups will be subject to particular monitoring within the scope of PDM.

Awareness, Training and Conditionality

The relatively short duration and the urgent nature of the programme, and the limitations facing some households that are labor-constrained do not justify that strict conditionality be set for receipt of safety net cash transfers.  However, assistance will be framed as “semi-conditional”.  The semi-conditional element of the cash transfers refers to UNDP’s principle to support unconditional cash that encourages individual beneficiaries to make productive investments in time and effort toward their advancement. Lessons learned from UNICEF’s unconditional cash transfer programmes over a number of years have illustrated a strong relationship between unconditional cash programmes and significant improvement in social indicators. This has informed UNDP’s approach to encourage beneficiary participation in training rather than establish it as a condition.  Local communities and individuals identify their own priorities, can make their own choices, and experience has shown that households improve health practices and invest in educational when they get cash transfers.

Beneficiaries will be actively encouraged to participate in at least one of two opportunities that will contribute to increasing their human or financial capital:

- Take part in literacy, numeracy and business skills training offered by the MoE and/or other institutions;

- Join a VSLA, adhere to its rules and conditions, and regularly make share savings deposits (relevant for those who are not currently members of a VSLA).

It should be noted that only beneficiaries who opt to join and actively participate in a VSLA will be eligible to receive a “savings accelerator” grants described above.

Within the scope of the National Social Protection Strategy and Policy, as it relates to promoting “productive social protection” for those able to participated in such actions, UNDP and the MGCSP will consult extensively with county, district and community authorities and stakeholders on what types of productive investments are of importance to their development plans. If and when viable options arise and appropriate for recipient households, non-conditional transfers could be modified to take the form of conditional transfers (cash for work or cash for training) during the course of implementation.  Such would be contingent on adequate technical and operational planning, and the availability of the necessary accompanying technical and financial resources.

All beneficiaries will receive Ebola awareness and prevention training in conjunction with monthly cash distributions.   Education sessions will be conducted before each distribution.  The programme will coordinate with the Ministry of Health and/or designated organizations in the country/district to obtain lesson plans and materials, as well as schedule event trainers.  As part of post-distribution monitoring, follow-up will be conducted with households to document how beneficiaries practice the lessons they received and whether they were passing on or modelling those lessons to others in the community.

Adult Literacy, Numeracy, and Enterprise Skills Training

Schools have been closed in Liberia in an attempt to reduce the potential for communal gatherings in public places and avoid close contact between people.  They will finally open in February. The loss of income by some teachers and other professionals, will have left them in a financial hole which will take months to remedy.  Some will welcome an opportunity to teach evening or weekend training sessions to earn some additional income.  Unemployed youth may also be tapped to serve as literacy trainers.  In such case, they will be provided the necessary training on didactic methods and the curricula for literacy and numeracy training.

The coverage of existing adult literacy programs is insufficient to address the needs of the large segments of the population who remain illiterate.  The momentum established within the scope of this programme will provide a spring board for putting in place longer-term literacy programming, in scope and scale, to address the full extent of the problem in the three counties.

Existing or enhanced curricula and lesson plans developed by the Ministry of Education (MoE) will be used.  UNDP and the MGCSP will coordinate with MoE their participation in/support for the program in the form of oversight of the training activities for the purposes of quality control.  If necessary, the programme will support rapid teacher training in adult education methods.  The program will offer a stipend of LD 4,250 (US$50)per month to motivate trainers to provide their services at night and/or on weekends.  In any case, care will be taken to avoid providing an unintended motivation to teachers to neglect or abandon their duties as full-time instructors in formal educational facilities.

Besides existing teachers working in the education sector, literacy/numeracy/business skills trainers will be sought from among interested, available and qualified persons who are unemployed, have experienced job suspensions or income reductions. For the purpose of the first levels of literacy training, even unemployed youth who have completed high school could be recruited to conduct sessions, while benefiting from the opportunity to earn some short-term income in the form of CFW. After the project, those trainers could form a ready cadre of adult educators who might be integrated and utilized within the scope of longer-term, more extensive programs of adult education.

Business skills training will be another contributor to building/strengthening of human capital, which will have direct influence on the building of financial capital.  Skills training provided to beneficiaries will contribute to strengthening the growth and development of the VSLAs and participants in other micro/small enterprises.  VSLA leadership has cited such training as a key necessity among their members.  The project will seek out and utilize skills training curriculum, lesson plans and methods utilized by other organizations, such as those which have been implemented by CARE in the county of Bong in support of over 100 VSLAs.

At this time, it is assumed that approximately 33% of beneficiaries (approximately 5,000) will elect to participate in adult literacy and skills training.  In addition, it is anticipated that all VSLA members (over 9,300 existing and new members) will take advantage to participate in enterprise skills/business development training.  It is safe to assume that the training described above would meet a need of not only beneficiaries of cash transfers, but many, if not all, members of the targeting communities.  So as not to deny such an important opportunity to only select groups within communities, training will be open to all persons interested in participating.  In fact, overwhelming demand will signal a need to the concerned authorities and to partners such as UNDP and others, that expanded, longer-term programmes should be developed to address fully the manifested need.

As currently designed and resourced, the project will invest in building/strengthening the human capital of over 13,000 persons, and the households they represent.

VSLA  Membership

Membership in a VSLA offers several benefits to women and men who represent their households.  While there apparently is an extensive network of VSLAs throughout the country, still many households have yet to take advantage and join one.   Participating members of existing VSLAs will be strongly encouraged to promote the values and benefits of a VSLA, seeking out potential new members from among others in their communities.

To become a VSLA member, candidates will have to meet existing admission conditions and be formally approved according to VSLA procedures.

Improving the livelihoods of existing and new members should contribute to longer-term growth and development of the associations.  Their ability to sustain their operational capacity will assure more and better service in support of their membership, with beneficial effects to their respective communities at large.

The National VSLA Apex has registered to date 59 VSLA in Bong and Lofa Counties (Lofa-31;  Bong-28).

Roll-out Strategy

Recognizing the imperative to begin introducing liquidity into the households and communities of targeted counties/districts as soon as possible, the project will commence roll-out in one county, Bong, utilizing approximately USD 2 million of UNDP internal funds.  This tight focus is done to responsibly ensure that the Bong Regional Office of the Ministry can be set up (including required supplemental staff can be recruited by UNDP and the MGCSP); effective targeting is carried out; systems, procedures and tools for efficient cash distribution and accountability are designed, validated and put in place; appropriate and effective associated training is designed, planned and implemented;  and effective monitoring systems and tools are designed and implemented with the limited initial funds available.

The county of Bong will be the “beta” for UNDP’s full-scale implementation.  Cash distribution will occur in 2,900 households in a yet undetermined number of communities (to be determined by targeting exercises at the county and district levels).  The MGCSP and UNDP will closely monitor distributions systems, procedures and tools for effectiveness and efficiency, with changes made as warranted.  The methods employed for community sensitization, local cash distribution steering committee formation, reliability of beneficiary identification, screening, selection and registration will be assessed and honed as required.

Roll-out in the other two targeted counties will occur when available resources are secured.  As additional funding is secured, the second county designated for implementation will be Lofa.

Linkage to Longer-Term Recovery

The various elements of the programme contribute to early recovery as well as establish a foundation for longer-term recovery and development interventions.

- The basic cash transfers to households will inject vital liquidity that will not only be used for current household consumption, but could also provide the means for them to repay debt they may have incurred to make up for lost income, thus improving their eligibility for new agricultural credit as the next planting season approaches (March-May) or for reactivating/expanding non-farm enterprises.  Households will also be in a better position to cover school fees/expenses or medical expenses, both important investments in human capital.

- Where and when feasible, conversion of assistance to “productive cash transfers” (CFW) will contribute further to developing household livelihoods capacity through investing physical and human capital for increased production/productivity.

- Literacy and business skills training represent tools that beneficiaries will use to improve their production/productivity, resulting in increased income.  In addition, higher rates of literacy are known to translate into improved nutritional status of family members, higher levels of educational attainment by children of the household, among other indicators of human development.

- Households which receive “savings accelerator” assistance to re-activate and accelerate their regular savings or pay down debts incurred in the wake of the EVD will become eligible to apply for new credits at larger rates for productive investments.  That will allow them to enhance their revenue streams going forward, which should translate into sustainable improvements in household livelihood.

- Finally, the temporary cash transfers to households will translate into liquidity streams into the community economy as a whole (markets and service providers), thus contributing to a quicker overall recovery.

One should not overlook the fact that the economic stabilization and recovery of extremely poor and poor households filters throughout their communities’ local economies.  Stable economies contribute to a strong sense of social cohesion.  The inclusive nature of social protection, and safety nets in particular, represents one pillar upon which inclusive governance is built. When the social pact of the government with its most vulnerable segments of society (in this case over 50% of the population) is formed, maintained, and recognized/respected, the ability of government at all levels to govern effectively is greatly reinforced.

Project Risk Factors

| FINANCIAL | A low level of funding will force significant trade-offs between the scale of assistance that can be offered as cash transfers (which will affect geographic coverage even within a county) while still ensuring that adequate financing for UNDP and Partner programme operations (certain elements of fixed costs apply) and ancillary investments can be allocated. Risk Level: High |
| --- | --- |
| OPERATIONAL | In the face of an imperative to commence implementation quickly, key staff will not be recruited, logistical support put in place, and systems and procedures can be designed, produced and ready for execution on time. Risk Level: High VSLAs, under the supervision of UNDP/MGCSP field staff, will be unable to carry out effectively cash distributions to beneficiaries in a secure and accountable manner. Risk Level: Medium |
| ORGANIZATIONAL | Primary partners (MGCSP and the MoE) and implementing partner (VSLA NAPEX) will not have the necessary organizational elements in place to carry out effectively their roles within the scope of the programme. Risk Level: Medium UNDP and its partners (MGCSP, VSLA NAPEX, and MoE) will not establish an effective modus operandi toward which UNDP programme staff can provide effective management support and capacity building to them. Risk Level: Medium |
| POLITICAL | The MGCSP and MoE fail to sign on to the programme, demonstrate full buy-in to it’s the strategy, and commit to carrying out their respective roles. Risk Level: Low County and district authorities do not fully/actively buy in to the strategy and the plan, forge an inclusive engagement with concerned stakeholders, and cooperate fully in sensitizing/mobilizing communities and identifying households that truly meet eligibility criteria. Risk Level: Low |
| STRATEGIC | Government implementing partners do not buy in to the programme’s dual focuses of immediate relief and early recovery, consequently providing political leadership to produce desired results. Risk Level: Low The MoE does not buy in and actively participate/contribute to the literacy/skills training component of the project, both in its short-term plan and using the project as a starting point for longer term strategic planning/investment. Risk Level: Low |
| SECURITY | Public unrest occurs if Ebola response workers are not paid on time and/or the economy recovers too slowly. Risk Level: Low Adequate security measures cannot be arranged to ensure the safe delivery and distribution of cash transfers to beneficiaries in all localities. Risk Level: Medium |
| X_OTHER | The number of cases of Ebola spikes to the degree that extreme measures are taken to restrict movement, commerce/business, and social intercourse. Risk Level: Low |

# Results and Resources Framework

| INTENDED OUTPUTS | YEARLY OUTPUT TARGETS | INDICATIVE ACTIVITIES | RESPONSIBLE PARTIES | UNDP INPUTS |
| --- | --- | --- | --- | --- |
| 1.1 Baseline: The MGCSP currently provides cash transfer assistance in two counties to 4,400 households and individuals. Indicators: Number of households which receive regular monthly cash transfers | Target: 2015 20,000 households in three counties. | Activity 1: Sensitization, mobilization and planning with county social protection sub-committees, as well as community authorities and stakeholders. | MGCSP | Field technical support MGCSP Operational financing |
|  |  | Activity 2: Identification, screening, and selection of most-vulnerable households adversely affected by the EVD crisis. | MGCSP | Technical support to MGCSP for design and planning. MGCSP Operational financing |
|  |  | Activity 3: Delivery of cash transfers to approved/registered households via bank off-site distributions, through VSLA and/or mobile money. | MGCSP VSLAs | Cash Transfers MGCSP Operational financing VSLA Operational financing |
|  |  | Activity 4: Conduct random Post. Distribution Monitoring of beneficiaries | MGCSP UNDP | TA for design of PDM inquiry. MGCSP PDM costs VSLA PDM costs |
| 1.2 Baseline: There are a multitude of community awareness-building/training programs being conducted to promote appropriate health/hygiene practices designed to prohibit the spread of Ebola. Key for sustainable practices is to base promotion on active local modeling, in place of external promoters. Indicators: The number of households which demonstrate that they model appropriate practices in their lives and urge friends/neighbors to do the same. | Target: 2015 At least 10,000 households are found to actively practice appropriate health/hygiene practices in their homes and communities. | Activity 1: Coordinate with on-going Ebola prevention promotion programmes in targeted communities to extend their promotion/training activities to project beneficiaries. | MGCSP . | Field technical support for planning MGCSP Operational financing |
|  |  | Activity 2: Conduct sensitization/training activities in conjunction with cash transfers | MOH Aid Organizations operating in each district/ community |  |
|  |  | Activity 3: Conduct select Post Distribution Monitoring of CT beneficiaries to verify the extent to which practices are being adopted and modeled. | MGCSP UNDP | TA for design of PDM inquiry. MGCSP PDM Costs |
| 2.1 Baseline: To be determined through a baseline survey of participating VSLAs. It is widely assumed that most members have drawn down/ liquidated their savings during the crisis. Indicator: The number of VSLA members who have reactivated their monthly savings and the amount they accumulate over the life of the project. | Target: 2015 7,500 existing and 1,875 new VSLA members buy savings shares monthly, accumulating at least USD 90 during the life of the project. | Activity 1: Carry out a rapid assessment of savings levels before and during the EVD crisis. | VSLA NAPEX UNDP | TA for design and monitoring. Financing for NAPEX implementation |
|  |  | Activity 2: Carry out savings sensitization and outline the type of assistance and conditionality attached that the project will provide to members if they reactivate and maintain a pattern of savings. | VSLA NAPEX | NAPEX field operations |
|  |  | Activity 3: Distribute through bank transfers “savings accelerator” disbursements to VSLA members who meet savings conditionality. | UNDP VSLA NAPEX | TA for design and review of CT accounting documents VSLA CT planning & execution |
|  |  | Activity 4: Carry out monitoring of VSLA savings data and conduct select PDM of members to determine the impact that savings has made on their livelihoods and lives. | UNDP VSLA NAPEX | TA for design of PDM TA for field implementation. Financing of NAPEX field operations. |
| 3.1 Baseline To be determined It is widely assumed that VSLAs have been unable to grant loans to members, as share savings has ceased among many members. Indicators Number of VSLA members who apply and are approved for productive loans. The average value of loans granted The productive uses for which loans are utilized. | Target: 2015 Up to 3,500 VSLA members are granted loans on the basis of their savings shares on deposit. | Activity 1: Processing and approval of loan applications, and disbursement of approved loans. | VSLAs VSLA NAPEX | Financing of NAPEX field operations. |
|  |  | Activity 2: Loan monitoring and assessment of the impact the loans have achieved. | VSLA NAPEX UNDP | TA for design of PDM TA for field implementation. Financing of NAPEX field operations. |
| 4.1 Baseline: To be determined Indicator: Number of CT recipients to elect to participate in adult literacy/skills training Number of participants who attend classes regularly and complete the 12-month course of study. Participants pass tests of knowledge retention. | Target: 2015 5,000 CT recipients from up to 200 communities elect to participate in training At least 75% maintain a 90% attendance rate at classes. At least 65% of trainees pass knowledge retention tests. | Activity 1: Carry out a rapid assessment of literacy and essential skills levels of adult members of households selected for CT assistance. | MGCSP MOE | TA to MOE and MGCSP for design and planning Monitoring of literacy training. MGCSP operating costs MOE implementation |
|  |  | Activity 2: Assemble curriculum, lesson plans and teaching materials, recruit trainers, identify training sites, plan schedules and oversee training quality. | MOE | Financing for production of training materials. |
|  |  | Activity 3: Make CT payments to trainers. | UNDP | Cash transfers to trainers |
|  |  | Activity 4: Conduct knowledge retention testing of trainees after each training module and at the end of the project. | MOE UNDP | Post-training monitoring |
| 5.1 Baseline: The MGCSP currently has two Regional Offices for the South and West of Liberia. Indicator: The MGCSP establishes a fully functional third Regional Office in Gbarnga, Bong County to serve the northern counties. | Target: 2015 A Regional Office is set up and functional by 1 June 2015. | Activity 1: Adequate office space is secured from county authorities, cost-sharing of any common services is negotiated, and necessary physical upgrading carried out. | Bong Country authorities. MGCSP | MGCSP Operational financing |
|  |  | Activity 2: The MGCSP and UNDP recruit and hire staff to fill posts within the regional management structure. | MGCSP UNDP | Budgets for Human Resources |
|  |  | Activity 3: Procurement of furnishings, equipment, vehicles and supplies is carried out. | UNDP | Budgets for Procurement |
| 5.2 Baseline: The MGCSP currently has a rigorous targeting methodology from its 5-year pilot project. It is, however extensive and time-consuming. Indicator: Enhanced methods and tools for geographic and household targeting as well as post-distribution monitoring (PDM) that is harmonized across the UNDP and WB projects. | Target: 2015 The MGCSP adopts a stream-lined, but still rigorous and inclusive target methodology and tools | Activity 1: Assess the existing targeting system and tools for cost-effectiveness and inclusiveness, adapting/modifying it as warranted and in harmony with the system/tools to be used by the WB project. | UNDP MGCSP World Bank County stakeholders | TA for assessment MGCSP Operational financing |
|  |  | Activity 2: Carry out a rapid field-testing/ validation of the enhanced system before employment | MGCSP Country Stakeholders UNDP World Bank | TA for testing and validation MGCSP Operational financing |
| 5.3 Baseline: The MGCSP operates an IMS from the pilot phase. It may not be as robust as necessary to form a platform for a scalable comprehensive system and may not adequately protect data or its access. Indicator: A robust and reliable Information Management System (IMS) is put in place to manage a scalable “payroll” of cash recipients | Target: 2015 A robust and reliable IMS platform is identified and put in place, along with a system to manage data on a day-to-day basis that is robust enough for ready access under conditions that may render data inaccessible. | Activity 1: Carry out a technical assessment of the current IMS platform of data storage and processes for managing data on a data on a day-to-day basis. | MGCSP UNDP | TA for IMS technical assessment |
|  |  | Activity 2: Identify, procure, and adapt a cost-effective data platform that addresses the MGCSP’s need | UNDP MGCSP | TA for technical specs Procurement Process |
|  |  | Activity 3: Identify a service provider for managing and servicing a cloud-based data management system. | UNDP | TA for technical specs Procurement Process Orienting and training MGCSP IM staff MGCSP Operational financing |

BUDGET

| Description | Cost Basis | Amount (USD) |
| --- | --- | --- |
| Cash Transfers |
| Basic Safety Net | 20,000 recipients @ USD 50/month for 9 months | 9,000,000 |
| Supplemental VSLA Savings Grants | 9,700 recipients @ USD 90 | 873,000 |
| CFW payments to trainers | 500 trainers @ USD 50/month for 9 months | 225,000 |
| Transaction Charges on Cash Transfers | 4.0% | 403,290 |
| Sub-total: Cash Transfers | 10,501,290 |
| Partner Programme Management |
| MGCSP Human Resources | Regional Office staff: 1 Regional Coordinator; Finance, MIS and M&E Assistants; 3 Targeting Assistants; 2 Social Workers and 1 Driver | 72,300 |
| MGCSP Operating Costs | Fuel; transport; communications; Coordination, Mobilization and Training Events; Public Information & Branding | 131,000 |
| MGCSP Procurement of Goods and Services | 1 Vehicle & Insurance; 3 motorcycles; 3 Generators; ICT Equipment; Furniture; Minor Office Equipment/Supplies; Publications & Advertising | 100,400 |
| MGCSP IMS | Platform and Cloud-based Data Management Service | 450,000 |
| Sub-total: MGCSP | 753,700 |
| MoE Headquarters Operations | Project staff, office expenses, logistics and communications | 35,000 |
| MoE Field Operations | Staff, office expenses, logistics and communications in 3 Counties | 65,000 |
| Sub-total: MoE | 100,000 |
| VSLA NAPEX/County Operations | Project staff, office expenses, logistics and communications | 75,000 |
| Sub-total: VSLA NAPEX | 75,000 |
| Total Partner Programme Management Costs | 928,700 |
| UNDP Programme Management |
| International Staffing | 1 UNV Project Manager and 2 UNV Field Officers | 165,600 |
| National Staffing | 3 Field Monitors and 1 Data Analyst | 59,800 |
| Staff Travel | Field missions allowances (6 staff) | 30,240 |
| Vehicles Purchase and Operations | 1 Landcruiser, 5 motorcycles, fuel, maintenance and repairs | 78,500 |
| Equipment, Communications and Supplies | Computers, office furniture/equipment, supplies and communications | 13,496 |
| Consultancies | Technical Assistance, M&E and Audit | 165,000 |
| Public Information & Branding | Publications, T Shirts/Vests, Etc. | 5,000 |
| Sub-total: UNDP Programme Management | 517,636 |
| Total Project Direct Costs | 11,947,626 |
| UNDP Indirect Support Cost (8%) | 955,810 |
| Total Project Cost | 12,903,436 |

ANNEX 1

Most Vulnerable Households by Counties and Incidences of Ebola

| MOST AFFECTED COUNTIES |
| --- |
| County | Population-2008 | # Persons in Lowest | # Households |
|  | Census | Quintile | (@ 5 per HH) |
| Bomi | 84,119 | 23,385 (28%) | 4,677 |
| Bong | 333,481 | 113,717 (34%) | 22,743 |
| Lofa | 276,863 | 92,195 (33%) | 18,439 |
| Margibi | 209,923 | 28,550 (14%) | 5,710 |
| Nimba | 462,026 | 66,994 (15%) | 13,399 |
| Sub-total | 1,366,412 | 324,841 | 64,968 |
| MODERATELY AFFECTED COUNTIES |
| County | Population-2008 | # Persons in Lowest | # Households |
|  | Census | Quintile | (@ 5 per HH) |
| Montserrado | 1,118,241 | 20,128 (2%) | 4,026 |
| Gran Bassa | 221,693 | 95,328 (43%) | 19,066 |
| Grand Cape Mount | 127,076 | 35,708 (28%) | 7,142 |
| Sub-total | 1,467,010 | 151,164 | 30,233 |
| LESS AFFECTED COUNTIES |
| County | Population-2008 | # Persons in Lowest | # Households |
|  | Census | Quintile | (@ 5 per HH) |
| Gbarpolu | 125,258 | 51,481 (41%) | 10,296 |
| Grand Gedeh | 125,258 | 44,717 (36%) | 8,943 |
| Grand Kru | 57,913 | 30,868 (53%) | 6,174 |
| Maryland | 135,938 | 29,363 (22%) | 5,873 |
| River Gee | 66,789 | 26,248 (39%) | 5,250 |
| River Cess | 71,509 | 50,986 (71%) | 10,197 |
| Sinoe | 102,391 | 42,287 (41%) | 8,457 |
| Sub-total | 685,056 | 275,950 | 55,190 |
| Total potentai beneficiaries | 787,447 | 751,955 | 150,391 |

| ANNEX 2 WEIGHTED RANKING OF COUNTIES BY CERTAIN VULNERABILITY CRITERIA |
| --- |
| County | Ebola Affected | Food Insecurity | GAM Incidence | Service Coverage | Weighted Score | Rank |
| Bomi | 4 | 3 | 3 | 3 | 13 | 1 |
| Bong | 4 | 2 | 3 | 1 | 10 | 4 |
| Gbarpolu | 1 | 1 | 3 | 4 | 9 | 11 |
| Grand Bassa | 3 | 1 | 3 | 3 | 10 | 5 |
| Grand Cape Mount | 3 | 2 | 2 | 4 | 11 | 2 |
| Grand Gedeh | 1 | 2 | 2 | 4 | 9 | 12 |
| Grand Kru | 1 | 3 | 1 | 4 | 9 | 13 |
| Lofa | 4 | 1 | 1 | 3 | 9 | 9 |
| Margibi | 4 | 1 | 2 | 1 | 8 | 14 |
| Maryland | 1 | 3 | 3 | 3 | 10 | 8 |
| Nimba | 4 | 1 | 1 | 1 | 7 | 15 |
| River Gee | 1 | 3 | 1 | 4 | 9 | 10 |
| River Cess | 1 | 2 | 3 | 4 | 10 | 6 |
| Rural Montserrado | 3 | 3 | 3 | 2 | 11 | 3 |
| Sinoe | 1 | 2 | 3 | 4 | 10 | 7 |

| Ebola Effected Couties |  | Most affected |  | Food Insecurity |  | >60% food insecure |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Moderately affected |  |  | 40-60% food insecure |
|  |  | Less affected |  |  |  | 20-40% food insecure |
| Acute Malnutrition |  | > 3% incidence |  |  |  |  |  |
| (GAM) |  | 2-3% incidence |  |  |  |  |  |
|  |  | < 2% incidence |  |  |  |  |  |
| Note: | in each ranking category, the "tie-breaker" went to the county with |  |  |
|  | the county more affected by Ebola |  |  |  |  |

# Footnotes

MOH daily situation report through 17 March 2015.  Refers to suspected, probable and confirmed cases.

MIT Governance Lab.  Patterns of Cooperation in the Fight against Ebola: Results from a Population-Based Survey of Monrovia, Liberia. March, 2015

The World Bank.  Economic Impact of the 2014 Ebola Epidemic:  Short and Medium Term Estimates for West Africa.  October 7, 2014

The World Bank, op.cit.

The World Bank.  The Socio Economic Impacts of Ebola in Liberia:  Results From A High Frequency Cell Phone Survey.  November 19, 2014

Building Markets.  The Impact of Ebola on Liberian Businesses:  Results of a Telephone Survey.  March, 2015.

Republic of Liberia, Ministry of Finance and Development Planning.  Liberia Economic Stabilization and Recovery Plan.  October, 2014