## Sheet1
UNDP LIBYA:Strengthening Local Capacities for Resilience and Recovery Project Multi Year AWP 2017-2020
Project ID: 104158 Output ID:105858
EXPECTED OUTPUTS | ACTIVITIES AND ACTIONS | 2017 |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | III | IV | I | II | III | IV | I | II | III | IV | I | II | Account Description | Total in USD | 2017 (Q3/4) | 2018 (Q1/Q2) | Total Year 1 | 2018 (Q3/ Q4) | 2019 Q1/Q2 | Year 2 | 2019 Q3/Q4 | 2020 Q1/Q2 | Year 3 | Total 2017 | Total 2018 | Total 2019 | Total 2020
Output 1: Local capacities for service delivery Better provision of basic services at local level and increase access for most vulnerable groups from host communities - including Internally Displaced Populations (IDPs) and returnees - as well as migrants and refugees is ensured | 1.1 Support municipalities in identifying, planning, leading and coordinating efforts to achieve resilience in local service delivery and socio-economic recovery
| 1.1.1. Establish and train 6 Municipal Facilitation Teams to facilitate needs analysis and planning/implementation of the activities – Linked to Activity 1.1.3. | [12 empty] | Grants; travel, accomodation, workshop, miscellaneous; consultants | 140000 | 70000 | 70000 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 70000 | 0 | 0 | bar: 2017 III to 2018 I
| 1.1.2. Identify urgent priority projects in the 6 locations to support resilience in access to services through participatory process, based on fast-track diagnostics + feasibility studies (BoQs and Tech. Specs.) | [12 empty] | Grants, workshop, accomodation, travel | 300000 | 100000 | 200000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 200000 | 0 | 0 | bar: 2017 III to 2018 I
| 1.1.3. Establish and run municipal development working groups/desks with a special focus on migration, IDPs, returnees, refugees and migrants (i.e. Human mobility desk) | [12 empty] | workshop, travel, accomodation, consultants, grants | 360000 | 40000 | 80000 | 120000 | 60000 | 60000 | 120000 | 100000 | 20000 | 120000 | 40000 | 140000 | 160000 | 20000 | bar: 2018 I to 2020 I
| 1.1.4. Conduct conflict-analysis in each of the targeted municipalities to inform the EU-funded activities (Only 6 municipalities) | [12 empty] | grants | 240000 | 60000 | 180000 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 180000 | 0 | 0 | bar: 2017 III to 2017 IV
| 1.2. Support selected rehabilitation needs on critical health, education and public facilities | [12 empty] | contractors, consultans, miscellaneous | 10220000 | 0 | 3066000 | 3066000 | 2500000 | 1400000 | 3900000 | 2900000 | 354000 | 3254000 | 0 | 5566000 | 4300000 | 354000 | bar: 2018 I to 2020 I
| Subtotal Output 1 | [13 empty] | 11260000 | 270000 |  | 3866000 |  |  | 4020000 |  | 374000 | 3374000 | 270000 | 6156000 | 4460000 | 374000 | 11260000