Country: Sri Lanka

Project Document

| Project Title | Disaster Risk Management Through Partnerships (DRM-P) in Sri Lanka |
| --- | --- |
| UNDAF Outcome(s): | Economic growth and social services are pro-poor, equitable, inclusive and sustainable in fulfilment of the MDGs and MDG plus, and focus in particular on the rural areas. |
| Expected CP Outcome(s): | Service providers ensure equitable access to improved quality services and economic infrastructure to vulnerable populations in disadvantaged areas |
| Expected Output(s): | Capacity and systems for effective preparedness, mitigation and response to natural and man-made disaster developed at national and sub-national levels |
| Implementing Partner: | Ministry of Disaster Management and Human Rights |
| Responsible Parties: | Disaster Management Centre |

# Annual Work Plan

| Agreed by Implementing Partner | Title and Signature: | Date: |
| --- | --- | --- |
| Agreed by UNDP: | Title and Signature: | Date: |

Year: 2009

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated acstions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| CPAP Output 7: Capacity and systems for effective preparedness, mitigation and response to natural and man-made disaster developed at national and sub-national levels 7.a Baseline: District level preparedness and early warning systems are beginning to be developed 7.a Indicator: # of districts with preparedness and early warning systems developed 7.a Target: 2 2009 7.b Baseline: Village level disaster management communities are being formed and disaster risks to be identified and mitigation plans to be developed 7.b Indicator: # of communities engaged in disaster risk reduction activities 7.b Target: 3 2009 7.c. Baseline: 0 7.c. Indicator: Presence of coordination mechanisms at sub-national levels for preparedness and response to disaster 7.c. Target: coordination mechanisms established at the sub-national levels for preparedness and response to disasters Related CP outcome: Service providers ensure equitable access to improved quality services and economic infrastructure to vulnerable populations in disadvantaged areas | Key Activity Result 1. Key Stakeholders actively participate in national and provincial disaster risk reduction forums |
|  | 1.1. Private Sector, Media and Research Institutes sensitised on the role and importance of participation in NDMCC |
|  | Conduct an assessment to identify Key Private Sector Institutions, Media outlets and research institutions to be targeted in Sensitisation campaign | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74100-Professional services | 5,452 USD |
|  | Promote the values and objectives of the NDMCC among the identified private companies, media and research institutes through discussions and workshops | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500 – Misc. | 10,912 USD |
|  | 1. 2. Annual Work Plan for the NDMCC based on the Hyogo Framework of Action and the Road Map for safer Sri Lanka drafted |
|  | Hire a consultant to identify the gaps in implementation of the ‘Road Map for Safer Sri Lanka’ at national and district level | X | X |  |  | DMC, UNDP | UNISDR-IOC | 71400- Contractual services-Indiv. | 27,273 USD |
|  | District and national level discussions and workshops to identify the gaps in implementation of the ‘Road Map for Safer Sri Lanka’ | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500 – Misc. | 2,046 USD |
|  | Prepare action plans at two selected districts and at the national level to address the gaps identified in Road map implementation | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 71400- Contractual services-Indiv. | 3,410 USD |
|  | Present the Action Plans to key stakeholders for validation and approval | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500 – Misc. | 1,362 USD |
|  | 1. 3. Develop new features and improve the user friendliness of DMC website |
|  | Develop web pages in the DMC web site | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 3,000 USD |
|  | Update and maintaining the relevant web pages | X | X |  |  | DMC, UNDP | UNISDR-IOC | 74200- Audio visual prod. charges | 3,000 USD |
|  | 1. 4. Grant scheme established to implement DRR activities in vulnerable communities |
|  | Identify suitable DRR initiatives to be assisted | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500-Miscellaneous | 2,000 USD |
|  | Implement the activities within vulnerable communities with the supervision of District Disaster Management | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 72600-Grants | 27,273 USD |
|  | 1. 5. Establish a research grant scheme for scientists to conduct DRR related research |
|  | Support 15 final year under graduate research students to conduct DRR related research | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 72600-Grants | 6,818 USD |
|  | 1.6 Provide scientific equipment and grants to research institutes to conduct research on DRR |
|  | a. Needs assessment of the DRR related research institutes | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500-Miscellaneous | 2,000 USD |
|  | Purchase of the equipments and distribution of the equipment | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 72200-Equipments | 20,000 USD |
|  | Support scientists to conduct DRR related research | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 72600-Grants | 48,000 USD |
|  | Conduct a national symposium on DRR related research | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC |  | 6,818 USD |
|  | 1.7. Assist the Training and Education Unit of the DMC to develop knowledge products on land use planning best practices and building guidelines for tsunami affected areas |
|  | Best practices on land use planning and construction for tsunami affected areas collected | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 71400- Contractual services-Indiv. | 6,818 USD |
|  | Best practices on land use planning and construction printed | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 29,091 USD |
|  | Best practices on land use planning and construction shared with the Local Government Authorities | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 8,182 USD |
|  | Conduct 4 training programmes for officials of the Local Government Authorities on incorporating best practices of land use planning and construction | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500 – Misc. | 21,818 USD |
|  | Provide equipment necessary for Local Government Authorities to incorporate best practices of land use planning and construction into their development plans | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 72200- Equipment and furniture | 15,000 USD |
|  | 1. 8. Assist the Training and Education Unit of the DMC to develop knowledge products required for a public awareness raising campaign on disaster- development linkages and multiple tsunami early warning dissemination methodologies |
|  | Develop Information, Education and Communication materials (2 booklets and 3 posters) | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 2,727 USD |
|  | Publish the Information, Education and Communication materials (2 booklets and 3 posters) | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 43,182 USD |
|  | Develop a booklet on the responsibilities of stakeholders targeting school children, general public and media institutions during a tsunami alert | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 7,272 USD |
|  | Document and share the successes, failures and challenges of community based DRR programme | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 1,818 USD |
|  | 1.9 Standard Operating Procedures drafted for areas not currently covered by existing DRR SOPs |
|  | Hiring a consultant to identify the gaps in existing SOPs and develop SOPs for identified gaps | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 71400- Contractual services-Indiv. | 16,364 USD |
|  | Draft SOPs as required | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 71400- Contractual services-Indiv. | 5,682 USD |
|  | Conduct a SOP validation workshop | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC |  | 3,000 USD |
|  | Share the validated SOPs amongst the stakeholders | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74200- Audio visual prod. charges | 3,000 USD |
|  | 1. 10 Conduct (2) rehearsals using draft SOPs with all key stakeholders involved in tsunami early warning generation and dissemination |
|  | Provide logistic facilities to conduct two rehearsals on tsunami early warning generation and dissemination | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-IOC | 74500 – Misc. | 9,090 USD |
|  | Key Activity Result 2. The most vulnerable Community Centres, Health Centres and Schools in Uva and Eastern Provinces are supported to draft Infrastructure development plans with disaster risk reduction mainstreamed |
|  | 2.1 A list of the most vulnerable educational and health facilities in Uva and Eastern provinces is made available |
|  | Collect information and develop a data base of all health and educational infrastructure facilities | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 74100-Professional services | 1,887 USD |
|  | Agree on most vulnerable and critical educational and health facilities of the selected provinces through meetings and discussions | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 74500 – Misc. | 2,000 USD |
|  | 2.2 Disaster risk reduction Infrastructure development plans drafted |
|  | a. Survey and ground verifications | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 72100-Contractual services -companies | 2,000 USD |
|  | b. A team of consultants hired to formulate plans for 40 schools and 10 hospitals | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 72100-Contractual services -companies | 79,717 USD |
|  | Key Activity Result 3. Disaster Management Centre provided with materials for community level training and advocacy activities |
|  | 3.1 A mobile training and awareness generation unit provided to Disaster Management Centre |
|  | Purchasing a caravan to be modified as a mobile Training and Awareness Generation unit | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 72215-Transportation equipment | 55,000 USD |
|  | Modify the caravan according to the requirements of the DMC | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 72100-Contractual services -companies | 5,000 USD |
|  | 3.2 Information, education and communication materials on DRR made available in local languages |
|  | Compile, translate and dissemination of posters, booklets, game boards and leaflets | X | X |  |  | DMC, UNDP, NDMCC members | UNISDR-EU | 74200- Audio visual prod. charges | 33,458 USD |
|  | Key Activity Result 4. Cost effective delivery and management of project |
|  | a. Contractual services-IOC | X | X |  |  | UNDP, DMC | UNISDR-IOC | 71400- Contractual services-Indiv. | 63,543 USD |
|  | b. Contractual services-AIDCO | X | X |  |  | UNDP, DMC | UNISDR-EU | 71400- Contractual services-Indiv. | 3,962 USD |
|  | c. Printing and communication | X | X |  |  | UNDP, DMC | UNISDR-IOC | 74200- Audio visual prod. charges | 2,728 USD |
|  | d. Transport-IOC | X | X |  |  | UNDP, DMC | UNISDR-IOC | 71600-Travel | 36,095 USD |
|  | e. Transport-AIDCO | X | X |  |  | UNDP, DMC | UNISDR-EU | 71600-Travel | 1,415 USD |
|  | f. Stationeries | X | X |  |  | UNDP, DMC | UNISDR-IOC | 72505-Stationery and office supplies | 1,456 USD |
|  | g. Miscellaneous-IOC | X | X |  |  | UNDP, DMC | UNISDR-IOC | 74500-Miscellaneous | 20,976 USD |
|  | h. Miscellaneous-AIDCO | X | X |  |  | UNDP, DMC | UNISDR-EU | 74500-Miscellaneous | 1,658 USD |
|  | i. Facilities and administration-IOC | X | X |  |  | UNDP, DMC | UNISDR-IOC | 75105-Facilities and Administration | 32,704 USD |
|  | j. Facilities and administration-AIDCO | X | X |  |  | UNDP, DMC | UNISDR-EU | 75105-Facilities and Administration | 13,027 USD |
| TOTAL |  |  |  |  |  |  |  |  | 699,035 |

# Project Management Arrangements:

The project will be implemented through National Implementation Modality [NIM]

The project organizational structure will be as follows:

The Project Board will have overall responsibility for project implementation, oversight & quality assurance.  The PB will provide policy guidance and monitor the performance of the project, review progress on a periodic basis, approve progress reports and end of project report as well as manage risks and issues.  It will approve the appointment and responsibilities of the Project Manager (PM) and will define the latter’s responsibilities.  It will provide consensus based management decisions, when guidance is required by the PM.  The extent to which the UNDP Programme Officer will be delegated quality assurance responsibilities will be determined during the first Project Board meeting, based on the frequency with which the Project Board meets and its ability to provide substantive quality control and monitoring of project planning, implementation and reporting processes.   In addition, it will ensure that required resources are committed and arbitrate any conflicts within the project as well as negotiate a solution to any problems between the project and external bodies.  The Project Board will review and make recommendations for UNDP/Implementing Partner approval as well as authorize any major deviations in project work plans. It will also be responsible for assessing and deciding on substantive project changes through revisions.

The representatives from the Government and Beneficiary groups will be invited to participate in the Project Board meetings.  They will include: Ministry of Disaster Management and Human Rights, External Resources Department, Department of Treasury Operations, Disaster Management Centre, Ministry of Local Government, Ministry of Education, Ministry of Health, University Grants Commission and Chamber of Commerce.  The Project Board should meet regularly, at least every three months, and extraordinarily whenever circumstances require. The proceedings of meetings are recorded. The project manager should act as secretariat of the Project Board with the responsibility to call meetings, distribute information and follow up on their recommendations.

The Secretary to the Ministry of Disaster Management and Human Rights will serve as the Senior Executive and will have ultimate responsibility for the project, supported by the Senior Beneficiary and Senior Supplier. As part of the responsibilities of the Project Board, the Senior Executive will ensure that the project is focused, throughout the project cycle, on achieving outputs that will contribute to higher level outcomes. Additional responsibilities include monitoring and controlling the progress of the project at a strategic level [i.e. contribution to national priorities], ensuring that risks are being tracked and mitigated as effectively as possible and organizing, chairing and ensuring that the Project Board meet in a timely manner, as stipulated in the project document. The Senior Executive will be responsible for approving and signing the Annual Work Plan (AWP) for the following year on behalf of the Implementing Partner, approving and signing the Combined Delivery Report (CDR) at the end of the year. The Senior Executive will be responsible for delegating authority to a Responsible Officer within the Ministry for signature of the Funding Authorization and Certificate of Expenditures (FACE) form.

The Assistant Resident Representative – Energy, Environment and Disaster Risk Management of UNDP will represents the interests of those designing and developing the project deliverables and providing project resources.  The primary function of the Senior Supplier will be to provide guidance regarding the technical feasibility of the project. The Senior Supplier will have authority to commit or acquire supplier resources as required.  As part of the responsibilities of the Project Board, Senior Supplier will advise on the selection of the strategy, design and methods to carry out project activities.  Quality assurance and oversight roles include ensuring that standards defined for the project are met and used to good effect, monitoring potential changes and their impact on the quality of deliverables and monitoring any risks in project implementation.  Within the context of the Project Board, the Senior Supplier will also be responsible for ensuring that progress towards outputs remains consistent, contributing the supplier’s perspective & opinions on implementing any proposed changes and arbitrating on and ensuring resolution of input/resource related priorities or conflicts.

The Director General of Disaster Management Centre will serve as the Senior Beneficiary with the primary function of ensuring the realization of project results from the perspective of project beneficiaries. As part of the responsibilities for the Project Board, the Senior Beneficiary will be responsible for ensuring that specification of the Beneficiary’s needs are accurate, complete and unambiguous, implementation of activities at all stages is monitored to ensure that they will meet the beneficiary’s needs and are progressing towards identified targets, impact of potential changes is evaluated from the beneficiary point of view, risks to the beneficiaries are frequently monitored, providing the opinion of beneficiaries of implementation of any proposed changes, and helping to resolve priority conflicts.

The Project Manager (PM), as appointed by the Implementing Partner, will have the authority to run the project on a day-to-day basis on behalf of and within the constraints outlined by the Project Board. The Project Manager is responsible for project implementation, financial management, administration, monitoring and reporting.  This Includes providing direction and guidance to the project team and responsible party (ies) and liaising with the Project Board & UNDP Programme Officer to monitor the direction and integrity of the project. Under the guidance of the Executive of the Project Board, the PM shall ensure efficient coordination efforts between the project, UNDP, and other concerned agencies. The project manager should act as secretariat of the Project Board with the responsibility to call meetings, distribute information and follow up on their recommendations. The PM will be responsible for managing the realization of project outputs through activities as specified in a jointly (UNDP-Disaster Management Centre) agreed annual work plan and within specified constraints of time and cost.  This includes: planning activities, preparing annual work plans & monitoring progress against quality criteria; monitoring events and updating the Monitoring & Communication Plan; liaising with any suppliers to mobilize goods and services to initiative activities; monitoring financial resources & accounting to ensure accuracy & reliability of financial reports; managing requests for the provision of financial resources using advance of funds, direct payments, or reimbursement using the FACE (Fund Authorization and Certificate of Expenditures); managing, monitoring and updating the project risks as initially identified and submitting new risks to the Project Board for consideration and decision on possible actions; managing issues & requests for change by maintaining an Issues Log;  preparing the Project Quarterly Progress, Annual and Final Reports and submitting reports to the Project Board and UNDP Programme Officer and managing and facilitating transfer of project deliverables, documents, files, equipment and materials to national beneficiaries at project closure.

As required additional staff will be added for the purposes of providing project administration, knowledge management and network development support to the Project Manager.

As delegated by the Project Board, the designated UNDP Programme Officer, supported by the UNDP Programme Associate will serve as Project Assurance.  In undertaking this role, the UNDP Programme Officer will take action to address as well as alert the Project Board of issues with regard to project quality assurance such as alignment with the overall Country Programme, availability of funds, observation of UNDP rules and regulations and adherence to Project Board decisions.  The UNDP Programme Officer will assist the Project Board by performing some oversight activities, such as periodic monitoring visits and “spot checks,” ensuring that revisions are managed in line with the required procedures, RMG monitoring and reporting requirements and standards are maintained, Project output(s) & activities, including description and quality criteria, risks and issues are properly recorded and are regularly updated in Atlas. The UNDP Programme Officer will also assist the Project Board in ensuring that the project follows the approved plans, meets planned targets as well as project Quarterly Progress Reports are prepared and submitted on time, and according to standards.  During project closure, the UNDP Programme Officer will work to ensure that the project is operationally closed in Atlas, financial transactions are in Atlas based on final accounting of expenditures and project accounts are closed and status set in Atlas accordingly.

Financial Procedures

Funding for this project is funded by ISDR- Indian Ocean Consortium and ISDR- European Union resources.

Under the Harmonized Cash Transfer system (HACT) to be introduced by the UN EXCOM Agencies (UNDP, UNICEF, WFP and UNFPA) as part of the UN reform commitment to reduce transaction costs on implementing partners, four modalities of payments are foreseen for nationally implemented projects. They include: 1) Prior to the start of activities against agreed work plan cash transferred (direct cash transfer) to the Treasury, Ministry of Finance and Planning, for forwarding to the Implementing Partner; 2) Reimbursements after completion of eligible activities by the Implementing Partner; 3) Direct payment to vendors or third parties for obligations incurred by the Implementing Partners on the basis of requests signed by the designated official of the Implementing Partner; 4) Direct payments to vendors or third parties for obligations incurred by UN agencies in support of activities agreed with Implementing Partners.

As per requirements under the Harmonized Cash Transfer (HACT) system, direct payments will be the preferred modality applied to the project until completion of a satisfactory assessment of the financial management systems and internal control frameworks of the Commission as the project Implementing Partner.

It will be the responsibility of the PM to liaise with the UNDP Programme Associate to prepare a consolidated financial report, in the required format, and provide it to UNDP at regular and necessary intervals.

Under the project’s national implementation arrangement (NIM) Government guidelines for competitive procurement of goods and services (advertising, tender bidding, evaluation, and approval) in line with international standards will apply for all project-related activities.

Upon specific request of the implementing partner UNDP can in line with UNDP procurement policy provide procurement and recruitment services to the implementing partner including:

a). Identification and recruitment of project and programme personnel

b). Identification and facilitation of training activities

c). Procurement of goods and services

As per the letter of agreement between the Government of Sri Lanka and UNDP for the provision of support services signed on 5th July 2002, UNDP shall recover the cost of providing the support services outlined above. The rate of the cost recovery is up to 3% on the value of the amount of the contracts of the services to be procured or obtained through UNDP [See Annex: 2]

In accordance with the decisions and directives of UNDP's Executive Board, the total contribution shall be charged a fee equal to 7% to cover the cost of general management support (GMS) services provided by UNDP headquarters and country offices;

The project will be audited periodically as per the annual audit plan prepared by the government coordinating authority in consultation with the UNDP Sri Lanka. The Disaster Management Centre will be responsible for ensuring that all audit requirements are met.

III. Monitoring & Evaluation

The project will be monitored against the annexed M & E Framework, which builds on the CPAP M & E Framework. Progress against each of the indicators will be reviewed at least annually, and the tracking table updated accordingly.

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Project M & E Framework.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted (see annex 1), a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, Quarterly Progress Reports (QPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard UNDP report format.  The signed QPR for the previous quarter shall be submitted with the Quarterly Work Plan and FACE by each NIM project to the concerned programme units for the release of quarter advance.

- A project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project

- A Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

Annually

- Field visits will take place as required, but at minimum, once a quarter.

- Annual Review Report. An Annual Review Report shall be prepared by the Project Manager and shared with the Project Board and the Outcome Board. As minimum requirement, the Annual Review Report shall consist of the Atlas standard format for the QPR covering the whole year with updated information for each above element of the QPR as well as a summary of results achieved against pre-defined annual targets at the output level. The M & E Framework and updated Tracking Tool will be annexed to the Annual Review Report.

- Annual Project Review. Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes. If necessary, following the Annual Project Review, the Annual Review Report should be revised and finalized.

Quality Management for Project Activity Results

| OUTPUT: Capacity and systems for effective preparedness, mitigation and response to natural and man-made disaster developed at national and sub-national levels |
| --- |
| Activity Result 1 (Atlas Activity ID) | Key Stakeholders participate in national and provincial disaster risk reduction forums strengthened | Start Date: 1st January 2009 End Date: 30th April 2009 |
| Purpose | To strengthen partnerships and support the active participation of Private Sector, Media and Research Institutes in NDMCC activities |
| Description | 1.1 Private Sector, Media and Research Institutes sensitised on the role and importance of participation in NDMCC 1.2 Annual Work Plan for the NDMCC based on the Hyogo Framework of Action and the Road Map for safer Sri Lanka drafted 1.3 Develop existing web site of the DMC to include new features and improve the user friendliness 1.4 Grant scheme established to implement DRR activities in vulnerable communities 1.5 A Establish a research grant scheme for scientists to conduct DRR related action researches 1.6 Provide scientific equipment and grants to the research institutes to conduct research on DRR 1.7 Assist the Training and Education Unit of the DMC to develop knowledge products on land use planning best practices and building guidelines for tsunami affected areas 1.8 Assist the Training and Education Unit of the DMC to develop knowledge products required for a public awareness raising campaign on disaster- development linkages and multiple tsunami early warning dissemination methodologies 1.9 Standard Operating Procedures drafted for areas not currently covered by existing DRR SOPs 1.10 Conduct (2) rehearsals using draft SOPs with all key stakeholders involved in tsunami early warning generation and dissemination |
| Quality Criteria | Quality Method | Date of Assessment |
| 1.1 20% increase in NDMCC membership by end of the project. | Progress reports | 15 April 2009 |
| 1.1 Minimum of 15 key private sector institutions, media outlets and research institutions participate in NDMCC meetings | Attendance records of the NDMCC | 15 April 2009 |
| 1.1 Minimum of 50 organizations at national and district level contribute to the Work Planning process of NDMCC | Workshop / discussion reports | 15 January 2009 |
| 1.2 Minimum of 10 stakeholders pledge support to implement activities identified in the NDMCC action plan | Action plan validation workshop reports | 15 February 2009 |
| 1.3 Minimum of two DMC web pages developed on community based DRR initiatives and funding opportunities available for CBDRM work | Web pages | 15 April 2009 |
| 1.3 Minimum of 15 organizations provide information to be listed in the web pages within the first three months of operation | Information reports submitted by different organizations | 15 April 2009 |
| 1.4 Minimum of 3 CBDRR initiatives identified for providing financial assistance | CBDRR proposals evaluated and accepted for funding | 01 Jan 2009 |
| 1.5 Minimum of 15 undergraduate research projects on DRR financially supported | Research reports | 15 March 2009 |
| 1.6 Research equipment needs of minimum of 10 research institutes working on disaster management related subjects identified | Proposals submitted by the research institutes | 01 February 2009 |
| 1.6 Minimum of 50 papers related to DRR related researches presented in the symposium | Proceedings of the symposium | 15 February 2008 |
| 1.7 Best practices of land use planning and building guidelines available in Sinhala and Tamil languages and shared with minimum of 50 LGAs | Published booklets on good practices of land use planning and building guidelines in Sinhala and Tamil languages, Workshop reports, distribution lists | 15 April 2009 |
| 1.7 Minimum of 50 officials from LGAs trained on good practices of land use planning and building guidelines | Training curriculum, Reports on the training programmes conducted | 15 April 2009 |
| 1.8 Minimum of 2 booklets and 3 posters on DRR developed with input from relevant technical agencies and translated into Sinhala and Tamil | Published posters and booklets | 15 April 2009 |
| 1.8 Minimum of two organizations working on CBDR activities accept the publication as a resource material for their CBDRR related training programmes | Correspondence related to the acceptance of the publication as a resource material | 15 April 2009 |
| 1.9 Minimum of 3 sets of SOPs available on selected three areas where SOPs are not available currently / need exist to clarify the roles further | Draft SOPs | 20th Feb 2009 |
| 1.9 Hazard specific awareness materials addressing 3 SOPs developed and publicized | Progress reports | 15 April, 2009 |
| 1.9 3 SOPs developed by key hazard specific technical agencies to issue early warnings. | Progress reports | 15, April 2009 |
| 1.9 Validated SOPs shared with minimum of 50 institutions relevant to the implementation of SOPs | Distribution lists | 30th Mar 2009 |
| 1.10 Minimum of 2 rehearsals conducted with all key stakeholders on tsunami early warning message generation and dissemination involving key stakeholders | Rehearsal assessment reports | 31st March 2009 |

| Activity Result 2 (Atlas Activity ID) | The most vulnerable Community Centres, Health Centres and Schools in Uva and Eastern Provinces are supported to draft Infrastructure development plans with disaster risk reduction mainstreamed | Start Date: 01st January End Date: 31st March |
| --- | --- | --- |
| Purpose | To facilitate the risk reduction processes of identified health and educational infrastructure facilities in Uva and Eastern provinces as well as to reduce the vulnerability of the users of health and educational infrastructure facilities to the risks posed by socio natural disasters |
| Description | 2.1 A list of the most vulnerable educational and health facilities in Uva and Eastern provinces is available 2.2 Disaster risk reduction Infrastructure development plans drafted |
| Quality Criteria | Quality Method | Date of Assessment |
| 2.1 A list detailing vulnerable health and educational infrastructure facilities at District level available | Progress reports | 15 February 2009 |
| 2.1 Minimum of 50 most vulnerable facilities identified for infrastructure plans formulation | List of criteria developed to prioritise the facilities based on their importance and vulnerability | 15 February 2009 |
| 2.2 Minimum of 30 infrastructure development plans selected for implementation by the relevant authorities | Correspondence between the relevant authorities and the Project | 30 March 2009 |
| 2.2 40 schools and 10 hospitals with Infrastructure development plans that mainstream DRR in the development planning | Progress Reports | 15 April 2009 |

| Activity Result 3 (Atlas Activity ID) | Disaster Management Centre provided with materials for community level training and advocacy activities | Start Date: 01st Jan End Date: 30th April |
| --- | --- | --- |
| Purpose | To improve the outreach capacity of the DMC to remote areas of the country and most vulnerable communities living under resource poor environments To facilitate the Training and Public Awareness Division of the DMC to improve the awareness programmes to suit different target groups of the society |
| Description | 3.1 A mobile training and awareness generation unit provided to Disaster Management Centre 3.2 Information, education and communication materials on DRR made available in local languages |
| Quality Criteria | Quality Method | Date of Assessment |
| 3.1 Availability of a caravan that is modified to suit the conditions required by DMC to improve their outreach capacity | Specifications established by DMC, Copy of the registration of the vehicle, Photographs, | 30 March 2009 |
| 3.1 Number of training curricula developed by the DMC | Curricular | 30 March 2009 |
| 3.2 2 training modules developed by the DMC | Progress reports | 15 April, 2009 |
| 3.2 At least 3 of communities served through the mobile training and awareness generation unit | Field visits & progress reports | 15 April 2009 |

| Activity Result 4 (Atlas Activity ID) | Cost effective delivery and management of project | Start Date: 01st Jan End Date: 30th April |
| --- | --- | --- |
| Purpose | Assist the Implementing partner to deliver the project deliverables within the given resource limitations of the project |
| Description | 4.1 Project oversight mechanisms are established and maintained |
| Quality Criteria | Quality Method | Date of Assessment |
| 4.1 At minimum 80% of project deliverables are fully achieved, within the time constraints and given resource limitations of the project | Project Progress Reports | 30th April 2009 |

IV. Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA [or other appropriate governing agreement] and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document”.

Annex 1: Risks Log

| # | Description | Type | Impact & Probability | Countermeasures / Mngt response | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Changes in operational context | Environmental | Potential changes have been anticipated and reflect in project design. Activities are mainly concentrated in areas characterised by stability in terms of its operational environment. P = 2 I =4 | The project will adopt a flexible approach to implementation. Activities are highly transferable and are not limited to any one specific geographical context. | Programme officer-UNDP |

# Text boxes

2009 AWP budget:	            699,035 USD

Total resources required:           699,035 USD

Total allocated resources:	699,035 USD

- Regular

- Other:

  - ISDR-IOM	499,909

  - ISDR-EU		199,126

Unfunded budget:		0

In-kind Contributions		0

Programme Period:	2008-2012

Key Result Area (Strategic Plan):	Energy 						& Environment

Atlas Award ID			50992

Project ID:			63269

Start date:		     	Jan     01, 2009

End Date				April   30, 2009

PAC Meeting Date			28 Oct. 2009

Management Arrangements		NIM

Brief Description

With the established disaster management framework and the institutional structures in Sri Lanka this project’s primary aim is to develop partnerships and collaborative programmes with other agencies engaged in socio economic development activities. This can be achieved through providing tools and approaches for mainstreaming disaster risk reduction into development planning and creating awareness among the general public on affordable and sustainable risk reduction technologies. Strengthening national and sub national level platforms for collaborative risk reduction initiatives and promoting partnerships towards creating safer schools and hospitals will contribute towards the vision of ‘Safer Sri Lanka’. Engagement of the public, private and nongovernmental sector stakeholders in mainstreaming will strengthen the outreach capacity of the key government institutions involved in promoting risk reduction concepts and will contribute to create a culture of collaborative actions for risk reduction.

Project Manager

Programme Coordinator

Project Board

Senior Beneficiary

Director General -DMC

Executive

Secretary-

Ministry of DM & HR

Senior Supplier

Deputy / Assistant Resident Representative- UNDP

Project Assurance

UNDP Programme Officer

Project Support

Project Organisation Structure