Agreed by UNDP Resident Representative / UNDP Director:

| (Enter Name, Position) | Signature | Date: (Month, day, year) |
| --- | --- | --- |

INITIATION   PLAN

for a GEF Project Preparation Grant (PPG) or
Programme Coordination Budget (PCB)

Section I. Brief Description of Initiation Plan

The Project Preparation Grant phase will initially embark on an extensive gathering of sources of information related to three Rio Conventions and others including the formats the data being stored, frequency of collection, quality of data and ownership of the information. This process will also identify gaps in the data to design an effective information system that help the envisaged post-conflict rapid development. Second phase of the PPG will devise a strategy and an action plan in consultation with stakeholder agencies on the system to be developed in the project implementation phase including the responsibilities of agencies and infrastructure gaps. PPG will provide a log frame matrix with project goal and objectives, with detailed activities related to each outcome/output identified and the preliminary cost of implementation of each activity along with timelines and indicators. Based on the initial discussions with the key project partners, namely, the Information Communication Technology Agency (ICTA) in charge of the e-governance programme (www.icta.lk) and government “cloud”; Ministry of Environment and Renewable Energy (http://www.environmentmin.gov.lk/web/index.php?lang=en) ; and Ministry of Finance and Planning (http://www.treasury.gov.lk/) the need of the services of two local consultants to facilitate and compile the PPG and international support during the process and in reviewing the final PPG Document has been confirmed. ICTA and Ministries will appoint focal points to the PPG. Due to the short-duration UNDP Sri Lanka plans to implement the PPG phase in close consultations with the above three organizations and other key stakeholders from Govt., NGO and Private Sector.

GEF PPG/PCB approved grant document and TBWP

Project PREPARATION GRANT (ppg)

Project Type:

type of Trust Fund:

Submission date:  01/22/2013

GEF Project ID: 5130

GEF Agency  Project ID: 4940

Country(ies): Sri Lanka

Project Title: Ensuring Global Environmental Concerns And Best Practices Mainstreamed In The Post-Conflict Rapid Development Process Of Sri Lanka Through Improved Information Management

GEF Agency(ies): , ,

GEF Focal Area(s):

a.   Project preparation Timeframe

| Start date of PPG | 02/01/2013 |
| --- | --- |
| Completion date of PPG | 08/01/2013 |

B.  proposed project preparation activities ($)

| Describe the PPG activities and justifications: The PPG consists of two components. The first will undertake the detailed background analysis and prepare the detailed technical strategies for each component of the project. The second component will use outputs from the first component to prepare detailed project design and GEF submission documents. Stakeholder validation, completing the financial package, and securing partnerships will be part of this second component. COMPONENT 1 – Background analysis This will build on the significant information available from the NCSA process. 1.1 Develop project strategy to prepare an improved national system to manage (i.e. collect, store and access) data and information - that supports monitoring and implementations of the Rio Conventions: • Analyze current and planned system to manage related data and information; • Assess stakeholders involved; • Analyse baseline investments from government, UNDP and others; • Define objectives of GEF support, with indicators; • Prepare project strategy consisting of: strategic entry points; priority objectives of the GEF project; the most effective activities to be supported by GEF; Outputs to be achieved by GEF; Costs, risks and partners. 1.2 Develop the project strategy to ensure planners, policy-makers and decision-makers are effectively addressing national and global environmental issues: • Define and assess stakeholders; • Collect data from previous capacity assessments and awareness assessments and analyse the baseline capacity situation; • Define objectives of GEF support, with indicators; • Prepare project strategy consisting of: strategic entry points; priority objectives of the GEF project; the most effective activities to be supported by GEF; Outputs to be achieved by GEF; Costs, risks and partners. COMPONENT 2 – Prepare Project Design Documents 2.1 Secure government commitment to project strategy: Negotiate with government representatives to ensure agreement on the project objectives, outcomes, outputs, and activities, including partnerships for support and government co-financing. Agree on mechanisms and measures to ensure accountability of project partners. Undertake an analysis of the financial implications of the project strategy and activities to construct a budget, and consult with key government representatives to identify sources of funds from among potential donors. 2.2 Secure government commitment to project implementation arrangements: Undertake consultations with government representatives to secure agreement to the arrangements to execute project activities, including the roles, responsibilities, and accountabilities of lead and partner agencies, and the policy guidance to be provided by the Project Steering Committee. Agree on implementation arrangements, following UNDP implementation guidelines. 2.3 Secure bilateral and multilateral financing opportunities: Develop partnerships and co-financing opportunities with bilateral and multilateral donor agencies and organizations, including networking among other potential regional and international development organizations. Negotiated partnerships with on-going projects to re-align their activities to meet project objectives will be considered as co-financing. 2. 4 Definition of a Monitoring and Evaluation (M&E) Plan: A detailed M&E work plan will be defined, including clear identification of responsibilities and accountabilities, as well as an appropriate budget allocation (based on best practices and UNDP guidelines). The Plan will reflect the requirements of the GEF M&E Policy and Capacity Building M&E framework. The Plan will also include provisions for an independent evaluation and provision to ensure the learning of lessons from implementation at both the mid-point and termination of the project. 2.5 Capacity Development Scorecard (GEF Tracking Tool): The CD scorecard uses indicators and their corresponding ratings in order to quantify the qualitative process of capacity change, and will be applied as a three-point time series programme evaluation of how the project contributes to CD outcomes. CD ratings for all 15 indicators will be assessed by stakeholder participants during the inception workshop, and by the independent evaluation consultant(s) as part of the mid-term and final evaluation. 2.6 Sustainability Plan: Building on the M&E plan, the Sustainability Plan will outline an exit strategy that ensures that those project activities necessary to sustain outcomes will continue without the need of long-term international financing. This plan will also outline an approach of adaptive collaborative management to facilitate the necessary management changes agreed by representatives of key stakeholder groups. 2.7 Medium-Size Project Guidelines: Review guidelines for the preparation of a Medium-Size Project based on GEF and UNDP requirements, as well as best practices for the holistic design of a resilient project that takes an adaptive collaborative management approach. Standard UNDP reporting, monitoring and evaluation procedures will apply to this project and will be elaborated in the project document. 2.8 Final stakeholder validation workshop: The workshop will gather representatives from all relevant stakeholders to present and discuss the draft MSP. The workshop will further legitimize the project strategy and activities, and maintain the full engagement of stakeholders throughout the project development process. 2. 9 Obtain official letters of endorsement and donor financing commitment. Technical assistance will be required by national and international consultants who are experienced in: a) GEF project formulation; b) UNDP project implementation requirements; c) Rio Convention interventions; d) institutional strengthening; e) data and information management systems. PPG OUTPUTS • A work plan with detailed roles and responsibilities for project implementation; • An analysis of the baseline covering (i) data and information management systems (ii) development planning/decision-making and the global environment; • Papers outlining strategies to meet MSP objectives; • Building on the above, an updated report on the partnership and co-financing opportunities for the proposed project; • Specification of all capacity building activities to be financed under the project and the rationale of their additionality to meeting Rio Convention objectives; • A deconstruction of the project strategy using the Logical Framework Approach (log frame), that clearly defines the project goal, immediate objectives, strategies, expected outcomes and outputs, as well as measurable performance and outcome indicators with means of verification and assumptions; • A monitoring and evaluation plan for the project that builds upon the log frame; • A stakeholder participation and sensitization plan for the project, with particular reference to the broader involvement by civil society; • Identification of the targeted groups and their representatives through an open consultative process; • Endorsement letters from the government and letters confirming co-financing commitments; • Medium-Size Project document per GEF and UNDP formatting and submission requirements, and; • Terms of Reference for all project staff and consultants to be recruited under the project, including the design and structure of the Project Steering Committee. |
| --- |
| List of Proposed Project Preparation Activities | Output of the PPG Activities | Trust Fund | Grant Amount (a) | Co-financing (b) | Total c = a + b |
| Background analysis of data and info management | A targeted analysis and outline strategy. |  | 3,000 | 1,000 | 4,000 |
| Background analysis of planning, policy making and decision-making | A targeted analysis and outline strategy |  | 3,000 | 1,000 | 4,000 |
| Project strategy, detailed budget, workplan, and logical framework: costs will be basically one inter national expert for five weeks (2.1 - 2.9) | Project document, work plan, log frame, monitoring and evaluation framework and replication strategy |  | 4,000 | 2,000 | 6,000 |
| PPG Management : costs will be basically one national expert for four months, plus one validation workshop, plus communications, printing (all activities). | PPG Coordination |  | 13,000 | 11,000 | 24,000 |
| Total Project Preparation Financing |  | 23,000 | 15,000 | 38,000 |

C.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| Grant Amount | 23,000 | 2,185 |
| Co-financing | 15,000 |  |
| Total | 38,000 | 2,185 |

D.  PPG  Amount requested by agency(ies), focal area(s) and country(ies) 1

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | SriLanka | 23,000 | 2,185 | 25,185 |
| Total PPG Amount | 23,000 | 2,185 | 25,185 |

1 No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.   PPG Budget

| Cost Items | Total Estimated Person Weeks for Grant (PW) | Grant Amount ($) | Co-financing ($) | Total($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 28.00 | 14,000 | 6,000 | 20,000 |
| International consultants* | 2 | 4,000 | 2,000 | 6,000 |
| Travel |  |  |  | 0 |
| Workshops |  | 3,000 | 5,000 | 8,000 |
| Other |  | 2,000 | 2,000 | 4,000 |
|  |  |  |  | 0 |
| Total PPG Budget |  | 23,000 | 15,000 | 38,000 |

* Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

F.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF LDCF/SCCF/NPIF Trust Fund criteria for project identification and preparation.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec, Executive Coordinator UNDP/GEF |  | January, 22, 2013 | Tom Twining-Ward, UNDP (Green-LECDRS) | +421 2 59337 386 | tom.twining-ward@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Type of Consultant | Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be Performed |
| --- | --- | --- | --- | --- |
|  | Data And Information Management Expert | 500 | 6.00 | 1. Analyze current and planned system to manage related data and information; 2. Assess stakeholders involved; 3. Analyze baseline investments from government, UNDP and others; 4. Define objectives of GEF support, with indicators; 5. Prepare project strategy consisting of: strategic entry points; priority objectives of the GEF project; the most effective activities to be supported by GEF; Outputs to be achieved by GEF; Costs, risks and partners. 6. Facilitate consultation and finalization of report. |
|  | Planning, Policy Making And Decision-Making Expert | 500 | 6.00 | 1. Define and assess project stakeholders in terms of planners, policy-makers and decision-makers; 2. Collect data from previous capacity assessments and awareness assessments and analyse the baseline capacity situation; 3. Define objectives of GEF support, with indicators; 4. Prepare project strategy consisting of: strategic entry points; priority objectives of the GEF project; the most effective activities to be supported by GEF; Outputs to be achieved by GEF; Costs, risks and partners; 5. Facilitate consultation and finalization of report. |
|  | Project Coordinator | 500 | 16.00 | - Coordinate with the international consultant (IC), UNDP and national counterparts on setting PPG implementation strategy. - Facilitate necessary project stakeholder workshops and meetings. - Assist the IC in communication with local authorities and decision-makers and support the IC in the process of disseminating results; - Assume main responsibility for discussions with potential partners and co-financers, and for obtaining co-financing and endorsement letters; - Secure government commitment to project strategy - Secure government commitment to project implementation arrangements; - Take the lead in preparing the project Sustainability Plan;. - Assume main responsibility for finalizing the project document, with significant input from the international consultant. |
|  | Expert On Capacity Development And Global Environmen | 2000 | 2.00 | - Work together with the local consultants (LC), UNDP and national counterparts on setting PPG implementation strategy; - Finalize PPG work plan, TOR for LCs, and design consultation and validation workshops. - Support LC as they undertake background studies, providing guidance and support; - Oversee completion of background studies, ensuring they are appropriate in scope and provide required analysis; - Conduct meetings with national decision-makers to identify priorities and approaches; - Facilitate and guide consultations to determine project strategy, priorities, key partners, and key barriers to success; - Provide technical and professional support to the LC and national stakeholders. - Develop the project strategy; detailed budget, work plan and logical framework, develop a replication strategy. - Support the LC in finalizing the project document. |

1 Provide dollar amount per person week.

2   Provide person weeks  needed to carry out the task

Total Budget and Work Plan

| Award ID: | 00072460 |
| --- | --- |
| Award Title: | PMIS 4940-Global Environment in Post Conflict Rapid Dev. |
| Business Unit: | LKA10 |
| Project Title: | Ensuring Global Environmental Concerns and Best Practices mainstreamed in the post-conflict rapid development process of Sri Lanka through improved information management |
| Project ID: | 00085538 |
| PIMS No. | 4940 |
| Implementing Partner (Executing Agency) | UNDP |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Development of medium size project document | UNDP | 62000 | GEF | 71300 | Local consultants * | 14,000 |
|  |  |  |  | 71200 | International consultants* | 4,000 |
|  |  |  |  | 75700 | Training, Workshop and Conferences | 3,000 |
|  |  |  |  | 74500 | Miscellaneous Expenses | 2,000 |
|  |  |  |  |  | Total Outcome 1 | 23,000 |
|  |  |  |  | TOTAL | 23,000 |

| Summary of Funds: |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | GEF | 23,000 |  | $ |
|  |  | Government - in kind | 15,000 |  | $ |
|  |  | TOTAL | 38,000 |  | $ |

# Footnotes

Summary table should include all financing of all kinds: GEF financing, co-financing, cash, in-kind, etc.  etc

# Text boxes

Programme Period: 2013-2017

Programme Component: Environment Sustainability and Disaster Resilience (ESDR)

PPG Title: Ensuring Global Environmental Concerns and Best Practices mainstreamed in the post-conflict rapid development process of Sri Lanka through improved information management

ATLAS Award ID: 	00072460

ATLAS Project ID: 	00085538

PIMS Project ID:  	4940

Duration: 	Feb. 01, 2013 to Dec. 31, 2013

Management Arrangement: DIM

Total budget:		USD 38,000

Allocated resources:	USD 38,000

- Govt. 	       	USD 2,000

- Regular

- Other:

  - GEF	USD  23,000

- In kind contributions  	USD 13,000

Country:  Sri Lanka

UNDAF Outcome: Policies, programmes and capacities to ensure environmental sustainability, address climate change, mitigation and adaptation and reduce disaster risks in place at national, sub national and community levels

UNDAF Indicator: Number of national and sectorial policies approved by the Government in the areas of environment sustainability, climate change and disaster resilience

CP/CPAP Outcome: Policies, programmes and capacities to ensure environmental sustainability, address climate change, mitigation and adaptation and reduce disaster risks in place at national, sub national and community levels (same as the UNDAF outcome)

CP/CPAP indicator: Number of policies, and strategies contributing towards sustainable and resilient development updated or developed

Relevant UNDP Strategic Plan 2013-2017 Key Result Area: Environment Sustainability and Disaster Resilience

Expected Project Outcome (s) and Indicator (s):  In addition to CPAP outcomes

Project Output(s) and Indicator(s):