Strengthening Enforcement of Law, Access to Justice and Social Integration Programme

Progress and Results Update (January- 	31 March 2015) for March 2015 Programme Board Meeting

| UNDAF Outcome 3: Communities empowered and institutions strengthened to support local governance, access to justice, social integration, gender equality, and monitoring, promotion and protection of human rights in alignment with international treaties and obligations and in alignment to the constitution of Sri Lanka. |
| --- |
| Implementing Partner: Ministry of Justice and Labour Relations |
| Output and Indicators | Activities in the 2014 Annual Work Plan | Progress /Results |
| Output 1 Coordination, co-operation and systems between justice, police and prisons enhanced in three “area models” for an effective, efficient and equitable legal system and administration of justice 1 District Case-flow Management Committees (CFM) established and in operation 1.2 Intra prison network electronic database established and operational in three area models. Case-flow management systems operational in 3 area models. No of priority cases identified to be addressed in three area models( courts, prosecution) % of backlog cases reduced in three area model courts. 1.6 Trilingual policy introduced for police and Justice Sector | Criminal Justice Case Flow Management Committee established in one area model. | The Ministry of Justice submitted letters to the Judicial Services Commission (in September, November, December 2014 and January 2015) seeking its approval to nominate the Magistrate as the Chair of the CFM committees in the area models. The Ministry received a response from the JSC (in January 2015) rejecting the request. Given that the Court is a key actor within the Penal Chain, the efforts to strength CFM must involve the Court. The Ministry is submitting a fresh letter of request elaborating on the proposed plan to strengthen CFM within the area models to the JSC in order to secure the approval necessary to move forward with the activity; failing which the Ministry proposes establishing the Committees with the support of the Police, State Counsel, JMO and Prisons within the area models. |
|  | Establishment of the Case Flow Management Committee at the National Level | During the 1st quarter of 2015, following a series of discussions, the Ministry decided to secure the services of the organizations/individuals tasked with developing the research tool for the Baseline Study on the challenges within the penal chain in order to carry out the aforementioned institutional assessment. The reason being that the Baseline Study envisaged conducting one-to-one interviews with the stakeholder institutions within the penal chain in order to ascertain the bottlenecks. Since the institutional assessment would involve the same actors, the Ministry envisages conducting the assessment with the support of the research organization/individuals that developed the study tool for the Baseline Assessment. The institutional assessment will be conducted during the months of April/May 2015. |
|  | Analysis on the bottlenecks/needs of the Justice Sector Baseline Assessment on the bottlenecks in the Penal Chain. Conduct an area model capacity needs assessment including a gender analysis to enhance women’s equality and participation in the Justice Sector. | Following a number of technical discussions, Verite Research, Center for Study of Human Rights (CSHR) and Mr Harshana Nanayakkara in consultation with the Ministry of Justice developed the proposed Research Tool. CSHR selected the legal researchers (attorneys-at-law with 5 years of experience) that would conduct the field study. A comprehensive training workshop was held for the researchers with the technical expertise of Mr Harshana Nanayakkara, Verite Research and the Ministry of Justice/UNDP technical coordinator on 19th December 2014. While the research team was to visit the field from the 22nd – 30th December, the activity could not be conducted as the Ministry of Justice had not yet received a response from JSC to its letters of request (submitted in October, November, and December 2014). In light of this and given the heavy rains/flooding in Anuradhapura during this period, the study was postponed. However, on 10th January 2015, the Ministry received a response from the JSC rejecting approval to conduct the study. The Ministry submitted another letter of request (to the JSC) on 6th February 2015 detailing the proposed plan seeking the JSC’s guidance on how best to revisit the study strategy. Following discussions yet another letter was submitted along with the proposed research tool and the profiles of the organizations/individuals tasked with carrying out the study. The Ministry is now exploring the possibility of conducting the study (as an internal/confidential study) with the support of the Sri Lanka Judges Institute utilizing the research tool developed by Verite Research, Mr Harshana Nanayakkara, CSHR, the Ministry of Justice/UNDP technical coordinator. |
|  | Assist Judicial and Prosecution services to identify and process priority cases to clear case backlog. | Following renewed discussions with the AG’s Department in February 2015, the Ministry has pledged its support to clear the backlog of 1191 narcotics cases within the Criminal Division of the AG’s Department. Towards this end, the Ministry will be supporting the Department to secure the services of 6 fiat officers who will be specifically tasked with reviewing and finalizing the selected narcotics cases within a period of one year. Support will also be extended to the Department to conduct a one-day Workshop/Forum on the identification of priority cases within the Department during the month of April 2015. |
|  | Development of an Integrated Electronic Information flow system across the Penal Chain | A series of discussions were held with the Government Analysts’ Department and the Attorney General’s Department after which it was proposed that the initial linkages (via the Database) should be established between the AG’s Department, the Government Analyst’s Department, the Judicial Medical Officer and the Courts (Magistrate’s Courts). Following a number of meetings, it was decided that a Consultant (Individual) be contracted to develop the specific criteria (call for proposals) from reputed IT companies in order to work extensively in close cooperation with the selected institutions in order gauge their needs (vis-à-vis case tracking) and develop a proposal that will subsequently be tabled at the Sub Committee. The Ministry is currently in the process of identifying the individual consultant for this purpose. |
|  | Conduct a study on the Community Based Corrections Mechanism in the Ratnapura District. | The study has been completed and the findings submitted by the Consultants to the MRPR and the final reports and the recommendations are under review. The overall objective of this study was to assess the implementation of the provisions in the Community Based Corrections Act No. 46 of 1999 and to identify successes, failures, necessary changes and other improvements that may be required to increase the effectiveness and efficiency of the Community Based Corrections Department in carrying out the Community Based Correction Orders. |
| Implementing Partner: Ministry of Justice and Labour Relations |
| Output and Indicators | Activities in the 2014 Annual Work Plan | Progress /Results |
| Output 2 Improved access to justice for vulnerable and marginalized populations through systematized legal aid service provision and dispute resolution mechanisms accessible to all 2.1 Coordination mechanism for legal aid providers established 2.2 System for needs-based legal aid service delivery in prisons established 2.3 % reduction in pre-trial detainees who are in the prisons for more than 2 years in target prisons 2.4 No. of vulnerable (Criteria for identifying vulnerable persons in need of legal aid will be identified in 2014.) persons provided with legal aid 2.5 No of land cases handled by dispute resolution mechanisms | Establish a coordination mechanism of legal aid service providers (National Committee) to provide a coordinated engagement to the formulation and implementation of a National Policy and strategy on legal aid. Amendments to the legal aid law to be initiated through the Committee. | The Ministry held three meetings with the Chairman of the LAC, and Consultant, Dr Ramani Jayasundara following which the members of the Legal Aid Committee that would guide the development of the National Policy were identified. The Consultant also developed and submitted the concept document as well as the Terms of Reference of the proposed Committee. The Ministry is currently in the process of scheduling the first meeting of the Committee to be Chaired by the Chairman, LAC. |
|  | Support the Bar Association of Sri Lanka (BASL) in increasing the involvement of its junior members in pro-bono work /legal aid as well as public interest litigation. | A specific database of junior lawyers willing to undertake legal aid cases is in the process of being established following the Forum discussions held during the last quarter of 2014. A specific link to the LAC will subsequently be created. |
|  | Awareness raising for public officials (court staff) on human rights, women and children’s rights, criminal procedure etc. | The Ministry supported the LAC to conduct a one-day Training Forum for over seventy five (75) police officers within the Colombo and Kalutara districts on the recently enacted victim and witness protection Bill, challenges in expediting criminal cases, and on forensic psychiatry with the technical expertise of Mr Palitha Fernando, former Attorney General, Deputy Solicitor General, and a Forensic psychiatrist. |
|  | Provision for development of a legal aid strategy at the Department of Prisons to provide free legal aid for the pre-trial detainees. | Discussions were held with the Legal Aid Commission on the existing legal aid support extended to the prisons through the SELAJSI (Access to Justice component) during the year 2014. Following discussions, it was decided that support will be extended to the pre-trial detainees within the area models and Welikada Prison during the year 2015. The LAC conducted a brief assessment of the legal needs of the prisoners in Anuradhapura in order to scope out the type of support needed as well as the number of persons seeking legal aid support. Discussions are held with the Department of Prisons and the Legal Aid Commission on providing legal aid support for the pretrial detainees. The legal aid support shall be provided in the three area models and in Welikada Prison in the year 2015. |
| Implementing Partner :Ministry of Women’s Affairs |
| Output and Indicators | Activities in the 2014 Annual Work Plan | Progress /Results |
| Output 3 Capacities of state and non-state actors strengthened for a comprehensive and coordinated response to address sexual and gender based violence (SGBV) 3.1 Inter-agency coordination mechanism established among service providers for oversight and coordination to address SGBV 3.2 No of coordination meetings (to strengthen referral network) held at Women and Children Units /police desk or any other location at Divisional level 3.3 No of workshops held to strengthen the capacities (sensitization and technical knowledge on SGBV) of Police Women and Children Desks and MWA Child and Women Development Units at Divisional level 3.4 Training modules finalized ( endorsed by MWA/Police) for Police women and children’s desks, relevant staff of the Women and Children Units on CEDAW, National legislation and judicial services 3.5 No of SGBV products/ materials developed for awareness on SGBV conducted through print , radio, TV and social media 3.6 National Action Plan on SGBV formulated 3.7 Percentage change in the number of SGBV including domestic violence complaints recorded/referred by police to penal chain. 3.8 Increased capacities of Child and Women Development Units, Police Women and Children Desks at DS level. 3.9 Referral system of SGBV cases to penal chain operational | Strengthen the capacity of MWA to lead the development of a National Action Plan on eliminating SGBV. | - National Framework and National Action Plan on GBV: Two national Consultants with international experience (Dr. Lakshman Senanayake and Ms. Sriyani Perera) were recruited by the Ministry (initially for a 6 month period) to commence work on the national policy framework and National Action Plan (NAP) on GBV. The Consultants have developed the concept note and have finalized the sectors which will include Prevention and Response to GBV through Education, Health Response to GBV, Economic advancement and prevention /response to GBV, Protection and Law enforcement, Justice and Law Reform, Media and GBV and Disaster management and prevention/response to GBV. The Ministry will be writing to the lead Ministries to appoint the technical leads as well as representatives that will attend the Steering Committee. Relevant government ministries, UN agencies that are engaged in the above sectors as well as leading civil society organizations (NGOs/ INGOs) will be invited to be part of the technical teams as relevant. An attempt will be made to keep each technical team to about 8 representatives who will be formulating the sector specific policy and plan. |
|  | Advocate for implementation, review, amendment and introduction of legislation/ policies to combat violence against women. | - Advocating on laws and polices: The National Committee on Women (NCW) takes the lead in the Ministry to advocate for the implementation, review and amendment of laws and policies that affect women, and policies that combat violence against women. The participation of the Chairperson, NCW at the CSW59 and Beijing +20 in New York was essential for further interventions with the MWA. Hence to facilitate participation at this very important fora where gender equality/ HR policies as well as the post 2015 SDG would be discussed, partial support towards the participation of Mrs. Swarna Sumanasekara, Chairperson NCW was provided on the request of the Ministry. Ministry wide briefing sessions on the outcomes following CSW 59/ Beijing +20 will be held in order to identify further where the MWA is able to affect change to enhance equality of women and combat VAW as a human rights violation. Advocating on laws: Support was also extended to a legal clinic held in Anuradhapura on 7th April in commemoration of International Women’s Day. Many women sought legal advice related to GBV at these sessions. This strengthened the MWA role in advocating for legal redress in situations of VAW. |
|  | Develop (Audio visual / print) & disseminate materials related to combat violence against women (on implementation of laws, review/ ammendment of legislation and new laws - on Rape/ DV/ incest, shelter, CEDAW, UNSCR 1325 etc.) (linked to activity 3.1.5 ) | A resource note book containing information on laws, policies, CEDAW, helpline numbers which was designed and printed as a joint initiative of the Forum against GBV, is being distributed at present to all officers of the Ministry Women and Child Units and the Police- Women and Child Desks (W&C Desks) at divisional level. A TV production on the need for positive action within the family to overcome GBV and other related issues was developed by the National Committee on Women, MWA and produced by the Rupavahini Corporation under UNDP-SELAJSI support. Rupavahini. Corporation broadcast this docu-drama on 8th March 2015 – International Women’s Day. A brochure with the contact numbers of the police, W&C Units and hospital desks which was printed in Sinhala, has been translated into Tamil and will be printed in Tamil shortly. This initiative supports materials related to combat VAW and will strengthen initiative to strengthen the referral system as well. |
|  | Strengthen the referral system of SGBV cases to the penal chain (away from mediation boards) in 3 area models - through MWA’s Women and Child Development Units. | -- Strengthening the referral system “response and prevention of SGBV”: District level multi-sectoral referral symposiums on GBV will be held in Anuradhapura and Ratnapura end April/ May 2015. The referral symposium will bring together participants from the Police W&C Desks, MWA’s Women and Child Development Units, GBV Hospital Desks, Mediation Boards, Judicial Medical Officer, Civil society groups, police training school officials, shelter staff, district committee representatives among others. The referral model developed by the Ministry and UNDP will be shared at this meeting as well as initial divisional level referral mapping in relation SGBV will be undertaken. The Ministry is checking that all equipment given to Women and Child Development Units at divisional level in the 3 area models have been received by them. Field monitoring visits by the MWA & UNDP SELAJSI will commence after this is complete. In 2014 UNDP SELAJSI strengthened by way of providing basic equipment / furniture support to 21 out of 23 units in Anuradhapura, 15 out of 18 units in Ratnapura and all 15 units in Batticaloa. The other units that were not strengthened through UNDP support had already received support earlier from the Ministry. This provision of equipment / furniture needs to be understood in light of overall strengthening of the referral system as well as being a the foundation for the collection of gender disaggregated data on GBV. |
|  | Support collection of gender disaggregated data on crime and identify measures to address priority issues on violence against women | Support collection of gender disaggregated data on crime/VAW: Printing support was provided to a publication on gender disaggregated data titled “Sri Lanka Women in Progress” which contained data on different aspects of violence against women. The initiative was undertaken by the Department of Census and Statistics on the request of the MWA. The first publication of this nature was undertaken about 5 years ago. The MWA initiated a process to collect data on widows as well as Female Headed Households (FHH) in Sri Lanka, given their vulnerability to GBV as well as other situations. At present the MWA has 30,000 filled data forms on widows and FHH with the MWA data entry unit (that is those which have been received from DS level) to be entered to the e-women database. Support is extended for a period of 5 months towards the data entry function of the 30,000 forms received on FHH, being a group vulnerable to VAW. The estimated number of forms which are yet to be received from the divisions amount to over 700,000 forms island-wide, which too will also have to be entered into the e-women database. |
|  | Support and strengthen the MWA’s institutional reporting functions – including reporting under the Convention to Eliminate All Forms of Discrimination Against Women (CEDAW). | CEDAW Reporting: -The work undertaken by the Technical Team (consisting of 12 experts) and one lead technical expert with reference to the 8th Periodic State party CEDAW report is complete and is at present undergoing the final review by the MWA and Ministry of External Affairs. MWA hopes to submit the report in April 2015 to the CEDAW Committee. |
|  | Undertake a capacity assessment of Women Development Officers (WDOs) and other staff working in all Women and Child Development Units of the MWA at divisional level (in the 3 area models). | - The Capacity Assessment of MWA’s Women and Child Development Units was completed in the three area models of Anuradhapura, Ratnapura and Batticaloa last year. The assessment was undertaken by the Ministry together with the SELAJSI-Technical Coordinator. The data is being analyzed and collated and the report is being prepared. |
|  | Support the mapping and development, if required, of curriculum, training modules and training techniques on SGBV for all justice sector institutions and actors (law enforcement officers, medico-legal, judicial and other relevant officials) | Training on SGBV - The projects hopes to roll-out the training manual developed by the Sri Lanka Police in collaboration with UN Resident Coordinator’s Office. The manual is to be handed over to the IGP shortly. The manual is already being rolled out in the Police College in Kalutara for new recruits. SELAJSI will focus on strengthening the capacity of in-service officers attached to the police Women and Children’s desks in the 3 area models in 2015. |
|  | Refurbish the Police Women and Children's Desks (W&C Desks) in the 3 area models ensuring availability of female offices, with trilingual language abilities, adequate legal representation/ legal aid services, and confidential counselling services and provide necessary equipment. | -Strengthening Women and Children Police desks: Basic equipment/ furniture for the 3 Police W & C Coordinating desks at district level in the 3 area models and 47 police women and children’s desks were provided in Q4 2014 (that is a total of 50 police women and children desks in the 3 area models). Equipment required for all W&C Desks in Anuradhapura, Ratnapura and Batticaloa were purchased in 2014, and have been dispatched. At present the Ministry is checking that all equipment/ furniture given to Police women and children desks at divisional level in the three area models were received by the respective desks. Field monitoring visits will commence after this is complete. Ministry will also setup a meeting with the IGP to brief him on progress made. - Gender/ GBV sensitization of police officers attached to the women and child police desks: Individual Agreements signed with the 6 police officers from Batticaloa who are following a course on counselling conducted by the National Institute of Social Development (NISD) through its Batticaloa centre. Another 34 police officers are enrolled at the Anurdhapura and Colombo centres. The duration of the course is 21 months. The total number of police officers following the course is 40. The gender breakdown of officers as per the area models is as follows: In Batticaloa 5 female and 1 male officer, in Ratnapura 7 officers are female no male officers, in Anurdhapura 7 female officers and 5 male officers, and from Colombo (include HQ of the Bureau in Pagoda) 12 female officers and 3 male officers. |
| Implementing Partner: Ministry of Justice and Ministry of Rehabilitation and Prison Reforms |
| Output and Indicators | Activities in the 2014 Annual Work Plan | Progress /Results |
| Output 4 Institutional capacities strengthened for improved administration of justice, strategic planning and policy development for a longer-term sector wide approach to justice, police and prisons 4.1 No of Law reform committees established and operational. 4.2 No. of policy advocacy events from experience generated in area models as well as from other ongoing initiatives 4.3 Research and Policy Unit established for the Justice sector 4.4 A sector- wide road map for Justice, police and prisons developed. 4.5 Sector wide National coordination mechanism operational (identified through the national sector wide Steering Committee) | Strengthen the Ministry of Justice Translation Unit to undertake interventions relating to the Language within the Justice sector: Provide support to the Court of Appeal Special Translations Unit to undertake priority translations. | Activity completed. A total of 122 cases (case briefs in the Tamil language) were pending to be brought before the Court of Appeal due to the lack of availability of the brief in the English language, when the Translation Unit was established in mid-2013 was 122. While the Programme initially undertook to support the translation of 30 briefs as a pilot initiative in the last quarter of 2013, further support was extended in 2014 to clear the backlog of translations of the above mentioned case briefs and an additional two (2) briefs listed for 2014. The Unit translated a total of 98 case briefs. The President of the Court of Appeal speaking at the event to mark the completion of the translation recognized and commended the work of the Translation Unit for its efficiency and also made a special note of the high standard/quality of the translations. Moreover, he also conveyed that these sentiments were shared by most of the Judges of the Court of Appeal before whom the translated briefs were presented. A letter outlining the success of the project and the need to sustain it in order to prevent the build-up of a fresh backlog was submitted to the President of the Court of Appeal for consideration. |
|  | Support the consolidation and translation of the five key pieces of legislation in both official languages. | The Project recruited seven consultants (senior officers who were attached to the Legal Draftsman’s Department) to consolidate and review the Penal Code and the Code of Criminal Procedure Act in Sinhala, Tamil and English. By 31st December 2014, the consultants finalized the first typed draft of the relevant consolidated legislations. At a meeting held on the 29th of January 2015, the consultants requested the Ministry of Justice to extend the time allowed to hand in the final copy till March 2015, as the Sinhala and Tamil versions require a second round of checking in order to bring them in line with the English consolidations. The Ministry is presently in the process of receiving the finalized versions of the consolidations from the Consultants. The Project has also been communicating with the Government Printer in order to get the estimated costs for the printing of 2000 copies of each Code in the respective medium. The Ministry is expecting to receive written communication from the Government Printer by the 31st March. |
|  | Support law enforcement (Police etc.) on criminal profiling. | Following a series of discussions, the training initiative has been scheduled for 2015 in light of the need to develop specific training modules in order to introduce the subject into the criminal justice sector in Sri Lanka. |
|  | Support the Bar Association of Sri Lanka in creating awareness (especially among young lawyers) of the latest international developments in criminal justice and public law (constitutional and Administrative). | The Programme supported the BASL to incorporate specific sessions on criminal justice and at its Junior National Law Conference held from 31stOctober – 1st November 2014. A specific session on “sentencing” was also held (following a criminal trial enactment) and a report containing recommendations on sentencing was shared by BASL with MoJ. This will subsequently be presented to the Thematic Committee that will be set up under the National Steering Committee on Justice tasked with developing a National Sentencing Policy. The importance of victim and witness protection within the criminal justice system was also discussed. Given that the Conference secured the participation of lawyers (in practice for 1-10years) from across the island, a survey questionnaire on specific challenges relating to case-flow management was also shared and a report of the survey findings was presented to the Ministry of Justice and will be tabled at the Sub Committee meeting on CFM. |
|  | Establish a National Steering Committee on Justice. | A National Steering Committee on Justice (NSCJ) was established and launched on 16th July 2014. The NSCJ is Chaired by the Hon. Minister of Justice and consists of senior representatives of all institutions relating to the Justice Sector. Under the aegis of this Committee, Sub Committees were established on Sentencing, Case Flow Management and Electronic Case Tracking Mechanism. Additional thematic Committees will be established in 2015 on Judicial Mediation, and Criminal Profiling. |
|  | Regional best practices forum to be held in Sri Lanka. | Following a series of technical and budgetary discussions during the months of January and February 2015, it was decided that the Forum to be held will be a National Forum and not a Regional Forum. While the overall technical structure of the Programme will remain the same, the Ministry in consultation with Additional Solicitor General Mr Yasantha Kodagoda decided that a few key experts (international) in the field of sentencing will be invited to support the Government in its endeavor to develop the national sentencing policy. The Forum will serve as a foundational platform at which the key sentencing guidelines that would be incorporated within the Policy will be developed. |
|  | Establish a thematic Sub-Committee on Sentencing | The first meeting of the thematic subcommittee on Sentencing Policy was held on 20th November 2014 under the Chairmanship of Secretary/MoJ, at the Ministry of Justice. The Committee includes the representation of the Attorney General’s Department, the BASL, DIG of Police/Legal, the Ministry of Rehabilitation and Prison Reforms. The representative from the Judicial Services Commission is yet to be nominated and is expected to attend the next sitting of the Committee. The Committee having finalized its TOR, decided on the following: Develop a paper based on the existing judicial decisions Discuss the criteria for granting suspended sentences Examine the existing practices in relation to sentencing and make judges aware of these practices/judgments. Existing training modules of the Judges Training Institute to include of the existing practices identified above |
|  | Strengthen the capacity of the legal draftsman’s department on drafting of criminal justice legislation in keeping with international standards | The Training programme was launched in December 2014 and is currently being conducted by the British Council Colombo. The preliminary coursework is being conducted after which the Legal Draftsman’s Department will commence its intermediate programme. |
|  | Training of Superintendent of Prisons and Assistant Superintendent of Prison of Administration of Prisons in keeping with international standards and human rights standards in collaboration with the Malaysian Prison Academy. | Completed: The three day workshop on enhancing Counselling skills, interpersonal skills and attitudes towards rehabilitation was held at Centre for Research and Training in Corrections and in Open Prison Camp in Pallekalle from 1st-5th July 2014. 4 Assistant Superintendent of Prisons, 15 Class I Jailors and 5 Class I Rehabilitation Officers participated in the workshop. A trainer from the Malaysian Prison Academy served as a resource person in the trainings. The Theories of Counselling, Approaches of Counselling in Malaysian Prisons, Techniques of Communication, Techniques of Reflection, Problem Solving and Mentoring were also included in the workshop. |
|  | Develop an Intra Prison electronic database for an effective and efficient administration of the Prisons. | The inception report has been submitted by the software developer and the agreement for developing the database has been signed between the Ministry of Rehabilitation and Prisons Reforms (MRPR) and the software developer. The Contingency and Disaster Recovery Management Plan, Change Management Plan, Responsibility Matrix Plan, Information Security Plan, Risk Management Plan, Data Classification Systems, System Requirements, Information Flow Management and Data Migration plans are developed in order to support the designing of the Database by the software developer. The software development process is expected to be completed by the end June 2015. |
|  | Conduct a Capacity Needs Assessment/Training Needs Assessment for the Prisons Officers of the Department of Prisons. | The assessment has been completed and the final report submitted to the MRPR. The assessment aims to review information relating to trainings undertaken in the past and identify whether the ongoing and past trainings are adequate for the Department of Prisons to effectively and efficiently achieve its goals in relation to relation to rehabilitation of prisoners through effective prison management. The findings of the assessment shall be used by the Centre for Research and Training in Corrections to design a comprehensive training plan, training curricula and training modules for the Prison Officials targeting the different levels of officers and focusing on providing trainings at regular periods in their career. |
|  | Conduct a study on the overcrowding of Remand Prisons and the Rehabilitation of Prisoners in the Welikada and Batticaloa Prisons. | The final report of this study has been submitted and it is being reviewed by the Department of Prisons and the UNDP. |
| Implementing Partner: Ministry of National Languages and Social Integration |
| Output and Indicators | Activities in the 2014 Annual Work Plan | Progress /Results |
| Output 5 National institutions and actors (state and civic) have stronger capacities for policy-making and policy actions aimed at promoting dialogue, social integration and reconciliation No. of policy actions on social integration and reconciliation adopted No of policy actions on social integration and reconciliation implemented. No of people benefitting from mobile documentation clinics (MDCs) (gender and age disaggregated) | Conduct legal documentation mobile clinics in the in 2014 based on the findings of the Documentation Needs Assessment undertaken in 2013. Support an assessment of language gaps in selected geographic multi-ethnic hotspots and in key service delivery sectors Establish a systematic postal mail delivery system in the estate-sector in collaboration with the Postal Department and other respective local government authorities and civil organizations | Ministry of Public Administration, Provincial Councils, Local Government and Democratic Governance conducted Two (02) legal documentation final mobile clinics in Hanguranketha and Walapone DS Divisions on the 7th & 8th of March 2015 respectively. This was conducted with the financial assistance of UNHCR as part of their assistance to conduct legal documentation mobile clinics in the estate sector. Mobile clinic in Hanguranketha DS Division Mobile was conducted by the Ministry with the support of DS office. Social integration officers attached to District Secretariat provided support to the programme. Hanguranketha Clinic was conducted in Hanguranketh DS Division and the clinic was able to cover Fifteen (15) Grama Niladhari Divisions whilst it served to people from Seven (07) estates located therein. Services rendered at the clinic were issuance of probability birth certificates, birth certificates (replacements for lost & unclear certificates), new birth certificates, elder identity card, identity cards, justice of peace certificates and police reports. In addition to said services, indigenous medical clinic was conducted very successfully and were attended by hundred and fifty (150) persons. Number of attendees to the legal documentation mobile clinic were one hundred and forty two (142) females and one hundred (100) male citizens. 110 birth certificates (replacement for lost & unclear birth certificates ), 02 new birth certificates, 04 probability birth certificates, 08 police reports, 84 elder identity cards, 30 justice of peace certificates were issued and 28 applications received to process the issuance of NICs issued at the mobile clinic. Assistant Additional Registrar General requested to have another clinic in “Castle Ree” since it covers most of the estates in Nuwera Eliya and also no clinics had been conducted for last 7 -8 years in that area. Walapone clinic was conducted in High Forest Tamil Vidyalaya located in High Forest estate in Walapone DS Division. The clinic was able to cover four (04) estates in five (05) Grama Niladhari Divisions in Walapone DS Division. Services rendered at the clinic were issuance of probability birth certificates, birth certificates (replacements for lost & unclear certificates), identity cards, justice of peace certificates and police reports. In addition to said services, indigenous medical clinic was conducted very successfully and Two Hundred and Sixty Eight (268) attended. Number of female attendees were Two Hundred and Twenty Five (225) and Two Hundred Fourteen (214) male citizens were attended to obtain services. In addition to the above some were attended to make inquiries with regard to the services such as Samurdhi provided by the DS offices. The clinic was located inside a estate (High Forest Estate) and it was recognized as a good central point where people can reach easily. Therefore considerable number of people attended to the clinic. 02 birth certificate (replacement lost & unclear birth certificates ), 06 probability birth certificates issued , 75 elder identity cards, 20 justice of peace certificates, 10 police reports were issued and 79 applications received to process the issuance of NIC , 512 applications received to process the issuance of birth certificates . In addition to the above, Five (05) pre-mobiles were conducted in Ayagama DS on 19th 20th 24th 26th & 27th March . Detailed information is yet to receive from DS divisions. Final mobile in Ayagama DS Division is already organized to conduct on the 4th of April. Language gap assessment Information gathering/desk review and planning of this activity is being processed. The Project was able to liaise with Social Integration (SI) officer based in Ratnapura District Secretariat in order to collect information on existing postal delivery system. A Questionnaire was prepared and shared with SI officer to place gathered information accordingly. |
|  | Provide translation support for the Department of Registration of Persons. | Activity Completed. The urgent need to continue providing this support was identified and accordingly SELAJSI supported the Department of Registration of Persons to place translators at the Department to facilitate the process of translating documentation/National Identity Cards until end September 2014. Accordingly 91,875 documents including National Identity Cards have been translated from the Sinhala to Tamil language by seven Translators. |
|  | Provide equipment for the Legal Aid Commission (LAC) centers and support the initial stages of development of a database in Batticaloa office in order to provide an effective legal aid service. | Activity Completed. A Memorandum of Understanding (MoU) was signed between the Ministry and the Legal Aid Commission (LAC) to provide support to enhance the institutional capacities of the LAC offices in the districts of Mullaithivuu, Vavuniya, Killinochchi and Batticaloa. Further under the same MoU it was agreed to undertake a "village profiling" exercise on legal requirements among families at the village level. A total of 190 families were covered through this assessment. The villages covered are Maruthodai (30 families) Pattikudiyiruppu (30 families) Pavatkulam (34 families) Kukulai East (24 families) Puliyamunai (13 families) Kukulai South (26 families) Kokuthodovai South (33 families) in the Districts of Mullaithivu, Killinochchi and Vavuniya. - After having further discussions with the LAC it was understood that development of data base is a time taking process and therefore it was decided to not to frame under this MOU due to time lines as stipulated by the donor. |
|  | Provide support to extend legal aid service delivery in the Northern Districts with emphasis upon Vavuniya, Killinochchi and Mullaithivu. | The Provincial Centre of the Ministry of National Languages and Social Integration (MNLSI) was established on 15th of July 2014. Through this activity all required equipment and furniture was provided for this office. Through the establishment of this office it is expected that the Ministry would be able to extend its services to the people further and enable more active engagement with the communities in the Northern Province, including coordination of legal aid and legal documentation service delivery with respective stake holders in the Province. |
|  | Support the Ministry Women’s Affairs (MWA) to (re) print the Law Directory (with laws relating to Sexual and Gender Based Violence-SGBV) in the Sinhala, Tamil and English languages. | Activity Completed: The critical need having been identified and the request being made by another SELAJSI Implementing Partner- the Ministry of Child Development and Women's Affairs (MWA) support was provided to print the law Directory in the Sinhala, Tamil and English languages for urgent dissemination. MNLSI entered in to a MoU with MWA to enable undertaking this activity. 10,000 – Sinhala: 5,000, Tamil: 4,000 -English copies are being printed. |
|  | Support MWA to carry out the Diploma in women and political Empowerment for women from the North and East of Sri Lanka. National policy on schools twinning developed and piloted as a concrete policy action for social integration and reconciliation | Activity Completed: The request being made by another SELAJSI Implementing Partner- the MWA the Programme provided financial assistance to conduct, a training for women community leaders in the North on empowerment, SGBV and laws, women’s rights, leadership etc. (undertaken in the form of a Diploma) under the aegis of the National Committee on Women under Ministry of Child Development and Women’s Empowerment. The trainings were conducted by the NISD (National Institute of Social Development). 75 women were trained from the North including the districts of Killinochchi, Mullaithivu, Vavuniya and also from Batticaloa. Initial discussions with the Ministry of Education(MOE) & UNDP policy unit was conducted. Objective of the meeting was to understand the existing Twinning School Prgrmme (TSP) structure of the MOE , to share findings of UNDP evaluation on TSP conducted from 2006 – 2013 and also to discus way forward. |
| Output and Indicators | Activities in the 2014 Annual Work Plan | Progress /Results |
| Output 6 A better aware public, especially youth and women, engaged in social integration and reconciliation actions No of events conducted to sensitize public on social integration (disaggregated by gender and age) No. of persons reached through social integration and reconciliation activities (disaggregated by gender and age) Percentage of persons targeted reporting increased understanding of social integration and reconciliation after being outreached through social integration and reconciliation awareness activities (disaggregated by gender and age) Percentage of persons targeted reporting changes in attitudes after being outreached through social integration and reconciliation awareness activities (disaggregated by gender and age) Percentage of persons targeted reporting getting involved in social integration and reconciliation actions after being outreached | Facilitate and support a more expanded public discourse across the media landscape, including through the use of social and community media Promote social integration through direct engagement with the media during Social Integration Week July 2014 Develop a TV drama series on issues relating to social integration. Monitoring and Evaluation of the pilot initiative to raise awareness on the communities which are small in number through the production and distribution of a calendar in the districts of Puttalam, Vavuniya and Badulla. | Activity completed: In order to support the widest possible outreach for the National Kite Festival during Social Integration Week utilizing the media, through SELAJSI the Ministry secured the services of Capital Maharajah (MTV). Accordingly a media campaign was conducted from 30th June to 15th July 2014, drawing attention to the National Kite Festival (NKF), providing media coverage for the social integration workshops conducted in collaboration with United Nations Volunteers (UNV) in the lead up to and during Social Integration Week and also media interviews for the Ministry to present its work in relation to the Week. This coverage was provided across MTV's three media outlets which are in the Sinhala, Tamil and English languages. Additionally, MTV came onboard as a partner for the National Kite Festival and provided live coverage of the Kite Festival from 5 of the 7 locations at which it was held. A documentary on the kite festival is developed and is in the final stages of editing. The documentary will be telecasted by the said TV station as agreed in the MOU in early 2015. -Unintended Results: For the first time the Ministry was provided the opportunity to have constructive media engagement on the topic of social integration. The print media also caught on to the NKF and Social Integration Week 2014. |
|  |  | The script developed for the TV drama series in the fourth quarter of 2013 has been reviewed by a Committee of Technical experts (comprising of social integration experts, Ministry Officials and experts on TV series development) and has been finalized. The procurement process for the selection of a Producer is currently in progress. Discussions with the Ministry of Mass Media and Communications have been initiated in order to identify the arrangements for production in 2014 and airing of the TV series in 2015. Unintended Results: This activity provided the entry point for the Ministry to be able to the first time establish a partnership with the Ministry of Mass Media and Communication (MMMC) to work on language issues and social integration. Accordingly a Technical Working Committee has been set up to start addressing language issues relating to media. The foundation for longer term engagement with the media on social integration has been laid as a result of this activity. The MMMC has proposed to conduct trainings to sensitive the media on social integration in collaboration with MNLSI. Due to the new institutional changes of the government after the presidential election 2015, it was not possible to SLRC and the Ministry to enter into a Memorandum of Understanding as previously agreed. SLRC new heads of relevant departments require to review the script and also considering their busy schedules due to forthcoming general election it will take six months to complete the production. Therefore the request for the second extension to retain funds for the said production was submitted for necessary actions. Evaluation of the Impact of the Calendar on Numerically Small Ethnic Groups The evaluation survey/assessment of the impact of the calendar used to raise awareness on numerically small communities/ethnic groups is underway and the final report will be submitted by the end of December 2015. The evaluation is undertaken by the Department of Sociology of University of Colombo. A half-day training session was conducted by the University to train the relevant Social Integration Officers (SIOs) on the how to undertake the evaluation prior to the roll out of the Questionnaire, which was developed by the Project. The survey was conducted in 40 schools by the SIOs in the target districts, with a sample size of the sample was 1000, including school teachers, Principals and students. The Pilot study was conducted in Puttalam and data collection has been completed and the data analysis is currently in progress. Preliminary analysis indicates that the calendar disseminated information which was new and was highly appreciated by the teachers and Principals. Extremely useful/creative/effective suggestions were highlighted through the pilot study. MNLSI aims to take on board the recommendations of the evaluation report through the Task Force to be appointed under the National Action Plan for Social Integration with a view to upscale raising awareness on the numerically small ethnic communities. Final draft of the report was completed and was submitted for Ministry’s comments and the suggestions are being in cooperated by the University of Colombo. |
|  | Outreach through the Convention on National Unity to promote one Sri Lankan identity and unity in diversity among school children through literature and art (integrating volunteerism). | Activity Completed. -In April 2014 the National Convention on Unity was held and the Government officially launched the Charter on National Unity. As part of this event SELAJSI supported the conduct of an art and essay competition and an exhibition. Additionally as part of promoting wider outreach on social integration and on the Charter on National Unity, SELAJSI also linked to Activity 6.1.1 (a) supported the conduct of 14 district level work-shops on social integration and also the conduct of the National Kite Festival. Both these initiatives were conducted as part of Social Integration Week 2014. All these initiatives were also designed to promote volunteerism and therefore the Ministry partnered with the United Nations Volunteers, to design, and implement these activities and also ensure the concept of volunteerism was re-introduced to the communities through the social integration workshops. - Project monitoring indicated that 52% of participants from the 14 districts had not heard of MNLSI prior to the district level social integration workshops. Unintended Results: The NKF provided an invaluable opportunity for the Ministry staff based in the districts to enhance their skills as trainers, by serving for the first time as resource persons for the district level Social Integration workshops. Use of innovative tools to promote social integration and strengthen outreach on the role of the Ministry. |
|  | Complete implementation of the Women's Empowerment for Social Integration in the Killinochchi and Moneragala districts (scale-up initiative). Promote Social Integration through Volunteerism Youth as change agents for social integration | -This initiative was completed in 2014 and enabled the participants to improve their language skills, provided an opportunity for the participants to gain exposure to different locations in the country and experience different cultures, meet with members from different communities, create and then strengthen relationships/friendships and establish networks/linkages to relevant local and national level government officials. The participants’ skills and knowledge with regards to designing, planning and implementing community level initiative, and accordingly manage resources required for these initiatives have been developed. Unintended Results: -Provided an opportunity for the women leaders to link up with the Women’s Caucus of the Parliament of Sri Lanka which is headed by the Hon. Minister of Parliamentary Affairs representing the Moneragala District. -The selected participants to be considered to be Mediators under the Ministry of Justice after a comprehensive training. -The initiative provided an opportunity for the PIU staff to strengthen their interactive presentation skills. -The participants from the Killinochchi district have initiated discussions at the community level to explore the options available to form a Women’s Organization in the future. The SI unity has now initiated discussions with the Ministry of Women Affairs to explore the possibility of linking trained women officers with women societies (Kantha Karaka Sabha). Ministry has made an official request this from MWA and the following up is being processed. The Project has requested a meeting from National Volunteerism Secretariat (NVS) to understand their functions in volunteering. The programme strategy is developed and will be discussed with the Secretary for his advice and approval. |
|  | Establishment of a Project Implementation Unit (PIU) | Officials from the Ministry have been identified to serve dedicatedly in the PIU and the required equipment and furniture for the PIU have been procured. |