## AWP 2016
Addressing Climate Change Impacts on Marginalized Agricultural Communities Living in the Mahaweli River Basin of Sri Lanka Project Annual Work Plan - Year 2017 Implementing Partner - Ministry of Mahaweli Development and Environment
Key Activity Results | Indicative Activities/Actions | Donor | Fund |  | Responsible party | A/C ID | Total Estimated Cost (USD)
Q4
1.0 Develop household food security and build resilient livelihoods for rain-fed farming households | 1.1 Stocking fingerlings for 20 minor irrigation tanks
| Contractual Services Companies | WFP |  | X | 8021 | 72100 | 18039
| Local Consultants | WFP |  | X | 8021 | 71300 | 10458
| Travel | WFP |  | X | 8021 | 71600 | 2750
| Sub total 1.1 | [5 empty] | 31247
Sub total 1 | [6 empty] | 31247
Key Activity Results | Indicative Activities/Actions | Donor | Fund |  | Responsible party | A/C ID | Total Estimated Cost (USD)
Q4
2.Build institutional capacity in village, local, regional service delivery to reduce risks associated with climate induced rainfall variability | 2.1 Conduct climate vulnerability assessments and produce climatic vulnerability maps for three divisions
| Local consultants | WFP |  | X | 8021 | 71300 | 19608
| Contractual Services Individual | WFP |  | X | 8021 | 71400 | 1961
| Sub total 2.1 | [5 empty] | 21569
Key Activity Results | Indicative Activities/Actions | Donor | Fund |  | Responsible party | A/C ID | Total Estimated Cost (USD)
Q4
2.Build institutional capacity in village, local, regional service delivery to reduce risks associated with climate induced rainfall variability | 2.2Develop climate resilient divisional development plans for three divisions
| Contractual Services Individual | WFP |  | X | 8021 | 71400 | 13333
| Travel | WFP |  | X | 8021 | 71600 | 1307
| Subtotal 2.2 | [5 empty] | 14640
Key Activity Results | Indicative Activities/Actions | Donor | Fund |  | Responsible party | A/C ID | Total Estimated Cost (USD)
Q4
2.Build institutional capacity in village, local, regional service delivery to reduce risks associated with climate induced rainfall variability | 2.3 Training farmers organization on 5 areas viz (a) construction supervision, (b) organizational development, leadership and financial management © risk assessments, tank ecosystem development and climate change adaptation, (d) water management and tank based livelihood development - resilient agriculture, aquaculture and animal husbandry, (e) operation and maintenance of minor tanks.
| Local consultants | WFP |  | X | 8021 | 71300 | 23922
| Sub total 2.3 | [5 empty] | 23922
Key Activity Results | Indicative Activities/Actions | Donor | Fund |  | Responsible party | A/C ID | Total Estimated Cost (USD)
Q4
2.Build institutional capacity in village, local, regional service delivery to reduce risks associated with climate induced rainfall variability | 2.4 Upgrade THE manual on CCA in agriculture and water resource management will be produced
| Local consultants | WFP |  | X | 8021 | 71300 | 13072
| Sub total 2.4 | [5 empty] | 13072
Sub total 2 (2.1+2.2+2.3+2.4) | [6 empty] | 73203
Total (sub total 1+ sub total 2) | [6 empty] | 104450
Management cost (9.5%) | [6 empty] | 9922.75
Grand Total | [6 empty] | 114372.75