## Delivery Monitoring
2016 Monthly Project Delivery Monitoring Calendar
Completed
On track
Delayed
Cancelled
Contracts already in system
Contracts/MCGs to be prepared
Project No. and Name | Key Activity Results (Annual Output) | Planned Activities (Above $5,000) | Key Milestones | QUARTER/MONTH OF COMPLETION (Please tick the box) | [7 empty] | Activity Status Scorecard | AWP Budget (USD) | Revised AWP Budget (if any) - provide explanation in column BD | Procurement of Goods and Services and Other agreements with Responsible Parties (indicate amount and colour code as per status) |  |  |  | Quarter 1 |  | Quarter 2 |  | Quarter 3 | [7 empty] | Quarter 4 | [7 empty] | Implementation Issues/Remarks/Progress towards meeting AWP Key Activity Results
|  |  |  | Q1 | Q2 | JUL | AUG | SEP | OCT | NOV | DEC |  |  |  | Procur. | HR | MCGAs & LoAs | Others | Q1 Target | Q1 Exp. | Q2 Target | Q2 Exp. | Jul Target | Jul Exp | Aug Target | Aug Exp | Sept Target | Sept Exp. | Q3 Target | Q3 Exp. | Oct Target | Oct Exp. | Nov Target | Nov Exp | Dec Target | Dec Exp | Q4 Target | Q4 Exp.
Strategic support to operationalize the Sri Lanka Comprehensive Disaster Management Programme (SS2CDMP) Atlas Project ID: 00078432 Atlas Output ID: 00090538 | 1.0 Technical Assistance on policy advocacy, agency coordination, knowledge management and monitoring for SLCDMP ensured | 1.1 Provision of Technical assistance (Technical Advisor) | [10 empty] | 0 | [25 empty] | As there is limited budget for the project, the salary of the technical advisor and the project is cost shared between SCCF and data projects.
|  | 1.2 Provide technical assistance to develop DRR incorporated sectoral proposals | 1. Stakeholder meetings conducted 2. Project proposals identified 3. Consultants for project proposal development identified (where required) 4. 12 Draft proposals developed 5. Comments provided and 12 finalized proposals submitted | [9 empty] | 18050 | [5 empty] | 5000 | 5321
| 2.0 Enabling environment for risk based disaster management decision making and implementation established | 2.1 Review legal and institutional framework for DRR | 1. Technical Steering Committee appointed 2. ToR and RFP documents prepared 3. Consultants selected and study conducted | [9 empty] | 20000
|  | 2.2 Strengthen the legal framework for disaster risk reduction in selected local authorities | 1. Standard By Law developed and approved 2. NCDM informed about the By Law 3. Support 10 Urban Local Authorities to develop By Law | [9 empty] | 15000 | [5 empty] | 15000 | 15000
|  | 2.3 Finalizing of the regulations for the implementation of National Housing Policy available and finalization of Housing Training | 1. Technical working group established 2. Training manual finalized and a training programme conducted 3. Regulations prepared | [9 empty] | 4700
|  | 2.4 Assist the University of Colombo to develop the Masters programme in Disaster Risk Reduction | 1. Draft course content available 2. Technical committee appointed to develop the course materials 3. Course materials developed | [9 empty] | 0
|  | 2.5 Establish a mechanism to streamline research studies in DRR with Universities | 1. Technical working Group established 2. discussions with UGC and university administrations taken 3. Mechanism agreed | [9 empty] | 0
|  | 2.6 Develop a Public Awareness Campaign for Disaster Management | 1. Technical committee established 2. Consultations conducted with district officials and media 3. Public awareness strategy developed | [9 empty] | 0
|  | 2.7 Conduct a regional (SAARC) PDNA workshop | 1. participants identified 2. Logistics arranged 3. Programme conducted | [9 empty] | 0
|  | 2.8 Carry out a study on making value chains of SME sector resilient to DRR and climate change | 1. Consultant hired 2. Consultation meetings with regional Chambers conducted 3. Vulnerable sectors identified 4. Sector value chain assessments conducted | [9 empty] | 0
|  | 2.9 Develop a DRR incorporated development plan for Badulla | 1. Technical working group conducted 2. Hazard mapping conducted 3. Exposure maps developed 4. district consultation conducted 5. Sector development strategies identified 6. Investment proposals developed | [9 empty] | 0
|  | 2.10 Finalize the M&E system for SLCDMP and conduct training programmes for respective agencies | 1. Data from development projects incorporated 2. Training programmes conducted | [9 empty] | 11125
|  | 2.11 Develop a landslide sensor to detect landslides in advance | 1. Tenders called and supplier selected 2. Specifications for the sensor developed 3. Sensor developed and tested | [9 empty] | 0
|  | 2.12 Develop national action plan for the implementation of the Sendai Framework for Disaster Risk Reduction | 1. Consultation meetings conducted 2. National Action Plan drafted 3. Action plan finalized and share with UNISDR
|  | 2.13 Donor Forum with the External Resources Department | 1. ERD informed and approval obtained 2. promotional materials developed 3. agencies identified and logistics arranged 4. forum conducted | [9 empty] | 5000
Admin/ Security Costs | [12 empty] | 1125
Total Budget for 2015 | [12 empty] | 75000 | [5 empty] | 20000 | 20321

## Indicator Tracking
PROJECT NAME, PROJECT DURATION, ATLAS NO,
Project No. and Name | Indicator | Baseline (year,month) | PLANNED TARGETS | [5 empty] | ACHIEVMENT TOWRADS RESULTS | [12 empty] | Un intended results/Changes achieved | DISAGREGATION OF DATA
|  |  | End of the project | Annual |  |  |  |  | Quartely progress for Year 1 |  |  |  | Year 1 |  |  | year 2 |  |  | year 3 |  |  |  | Year 1 | [5 empty] | Year 2 | [5 empty] | Year 3
|  |  |  | year 1 | year 2 | Year 3 | Year 4 | year 5 | Q1 | Q2 | Q3 | Q4 | Actual results year 1 | Variance | Remarks | Actual results year 2 | Variance | Remarks | Actual results year 3 | Variance | Remarks |  | M | F | FHH | Differently abled | Youth | District | M | F | FHH | Differently abled | Youth | District | M | F | FHH | Differently abled | Youth | District
SS2CDMP | Demonstrated impact of the Strategic Support to Sri Lanka CDMP programme on minimum of 15 policies, legislations, strategies and guidelines are made available | 0 | 15 | Annual year 1: 0; Annual year 2: 5; Annual Year 3: 5; Annual Year 4: 5
| Number of officers trained on integrating DRR, climate change gender sensitivity and other related areas | 0 | 250 | Annual year 1: 50; Annual year 2: 50; Annual Year 3: 50; Annual Year 4: 100; Quartely progress for Year 1 Q1: 30
| Comprehensive M&E system in place |  | System in place
| At least 10 public – private partnerships operating in the country to promote responses( first-aid, , search and rescue ) | 0 | 10 | Annual year 1: 0; Annual year 2: 2; Annual Year 3: 2; Annual Year 4: 6
| Minimum of 10 risk profiles developed for Sri Lanka | 0 | 10 | Annual year 1: 2; Annual year 2: 5; Annual Year 3: 3
| Number of urban development plans incorporates DRR based on results of risk profiles | 4 | 10 | Annual year 1: 0; Annual year 2: 5; Annual Year 3: 5
| Results of Integrated Strategic environment assessment incorporated into National physical planning policy | 0 | Results of ISEA integrated into NPP&P | bar: Annual year 2
| Number of knowledge management products developed and disseminated | 0 | 4 | Annual year 1: 1; Annual year 2: 1; Annual Year 3: 2
| National emergency operations plan is in operation |  | Plan in Operation | bar: Annual year 1

## Field Visits Monitoring
Field Visits Monitoring
Project No. and Name
| No. | VISIT PLANNED DATE | FIELD VISIT |  |  | FIELD REPORT | Follow up Actions | Remarks
|  |  | PURPOSE OF THE VISIT | Field Visit members | STATUS OF THE VISIT | Status
| 1 |  | Study the suitability of drones for mapping purposes | Project Coordinator, University of Moratuwa
| 2 |  | Workshop on finalization of the DRR incopotared plan for Badulla | Technical advisor, DMC and NBRO teams
|  | Visit Status |  |  | Report Status
|  |  | Completed |  |  | Shared with Prog. Cluster and Senior Management, saved in shared drive
|  |  | Delayed |  |  | Not completed
Cancelled

## Risk Log
RISK LOG MONITORING
Project No. and Name | No. | Descripiton | Date identified | Type | Impact & Probability | Countermeasures/Mgmt Response | Owner | Submitted by | Q1 Update | Q2 Update | Q3 Update | Q4 Update | Status
Strategic Support to Comprehensive Disaster Management Programme | 1 | The budject allocation for year 2016 is 75,00 USD . This allocation is insufficient to contenu the agreed support to the Ministry of Disaster Managemnet. | Jan. 2016 | Management | High | Explore possibilities for resource mobilization | UNDP | project team
| 2 | As there are no dedicated staff for the porject, the situtaion may affect the overall effectiveness of the project. | Jan. 2016 | Management | High | Explore possibilities for resource mobilization | UNDP | project team

## Contract Management
Contract Management Tool
Procurement Contracts (CWCs, ICs)
Project No. and Name | End Date of proejct | New Extension date | PO # | Vendor Name | Type of Contract | NIM/DIM | Duration of Contract | Contract Amount | Milestone Payments (Y/N) | Milestone Dates
Strategic support to operationalize the Sri Lanka Comprehensive Disaster Management Programme (SS2CDMP) Atlas Project ID: 00078432 Atlas Output ID: 00090538
Programmatic contracts (MCGA & LOAs)
Project No. and Name | End Date of proejct | New Extension date |  | Vendor Name | Type of Contract |  |  | Contract Amount | Milestone Payments (Y/N) | Milestone Dates