# 2018 Annual Work Plan: Award ID: 00096045

Project ID and Title: 00096045 Programme on Reform of Governance, Rights and Empowerment for Sustained Stability (PROGRESS)

| Expected Outputs | Planned Activities | Resources | TIMEFRAME | Implementing Partner | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source/Donor | Budget Description | Total Amount (USD) | TRAC | Donor |
| UNDAF Outcome: National and local governance structures deliver quality and accessible services to all citizens respecting the protection of human rights & access to justice, and peaceful resolutions of conflict |
| ACTIVITY 1: Support the execution of a credible, participatory and inclusive reform agenda in Lesotho through provision of process, technical and advisory support |
| Baseline: 1. Commonwealth Report on the Study Tour to New Zealand 2014, Coalition Government Agreement 2015, SADC Commission of Inquiry Report 2016, 2. Commonwealth Report on the Study Tour to New Zealand 2014; CSOs 2017 proposal on the reform programme | Support to national dialogue on Reforms and ‘The Lesotho we want” 1.. Strategy meetings with stakeholders(CCL, Heads of Churches, civil society, GoL and political parties). 2. Technical support to CCL and Head of Churches on National Dialogue Reforms Process | IRRF # 5.6.1 CPD Outcome 35 | x | x | x | x | CCL, GoL and Political Parties. CCL | TRAC TRAC NUL | 1. Catering; venue; stationery-$ 2000 2.Catering; accommodation; DSA; stationery; venue; $1,000 | 20500 (5000 TRAC) |  |  |
| Indicators: Mechanisms for constructive engagement and dialogue for successful reform agenda in place. | 3. Technical support to the Lesotho Foresight and Scenarios Project (LFSP)e 1. National Dialogue Process Preparatory Meeting with LCN and affiliated members. 2. Provide technical, financial and advisory support specific to women participation, engagement, and participation in the National Reforms process | IRRF # 5.6.1 CPD Outcome 35 | x | x | x | x | NUL TRAC |  | 3.Catering; venue; stationery; DSA; accommodation $15000 With NUL 1.Catering; venue; stationery-$1000 2.Catering, venue, accommodation; stationery $1000 | 2000 |  |  |
| SUB TOTAL: $20,000.00 |

| Activity 2. Deepen a culture of good governance and human rights protection through strengthening the capacity of key institutions of governance (Parliament, IEC, DCEO and the Human Rights Unit of the Ministry of Law and Constitutional Affairs) |
| --- |
| Result: Capacity of key institutions of governance strengthened |
| Baseline: Voter awareness in electoral matters; Results of the 2015 electoral process No minimum standards/benchmarks established for MP roles and responsibilities (2012); Lack of Parliamentary Service Commission National Human Rights Commission legislated 137 accepted UPR recommendations 8 state party reports overdue National Anti-Corruption Strategy and Action Plan (NACSAP) developed and launched (2015) |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicators: 1.Proportion of eligible voters who are registered to vote, disaggregated by sex, age, and excluded groups (IRRF 2.1.3) 2.Proportion of women (to men) participating as candidates in local and national elections 3.No. of bills that apply the public participatory process 4.Extent to which the parliament engages SDGs in debates 5.# of UPR recommendations implemented; 6. # of treaty body reports submitted and laws reviewed | Support to IEC Cond 1. Conduct Civic and Voter Education Assessment 2. Civic and Voter Education and validation workshop on the curriculum 3. Train IEC staff and develop a training manual for Election Dispute Resolution and establish a Conflict Resolution mechanism and have a repository of trained conflict managers |  |  | X X | X | X | IEC, UNDP | TRAC | 1. Consultancy fee- -$2,924 Consultancy,–$1,400.00*5=$7,000.00Venue and catering (30*109*2=$6,540.00) 2., Venue and catering 20ppl *5 Days*$109.00=$5,900.00 3. Facilitation Fee $763.60*10=$7,636.00 | 30,000 |  |  |
| 7.Number of proposals adopted to mitigate sector specific corruption risk 8 Number of mechanisms to address awareness, prevention and enforcement in place | Support to Parliament National Assembly 1. Training of MPs particularly in oversight committees - on Lesotho’s Budget Cycle to enhance their role and to improve their understanding on Public Financial Management System. 2. Training for the National Assembly SDG committee members 3. Establishment of Women’s Caucus (“WC”) and conducting Training for Women MPs on global practice/trends and gender-sensitive budgeting 4.Participation of one female MP to attend the Commission on status of Women (CSW) in New York |  |  | x | x | x | UNDP and National Assembly | TRAC TRAC | 1.Venue, Consultancy fee, - $ 5,000 2.Venue, Consultancy fee, - $ 4,330 3.Venue and stationary x 20 - $ 5,740 4.Return ticket and DSA $ 15, 730 | 30,000 |  |  |
|  | Support to Senate Senate Conduct training for Committee chairpersons and Clerks on their role, practice and procedures of committees. Attachment of five (5) Committee Clerks to the Zimbabwean Parliament Budget Office. Conduct the People’s Assembly Support to Human Rights Support to Human Rights 1. Advocacy and Community Outreach for National Human Rights Commission in 3 selected districts – Mokhotlong, Qacha’s Nek & Thaba-Tseka (emphasized and strategic advocacy and outreach to women in select districts for reporting on gender based violence) |  |  |  | x | x | Ministry of Law and Constitutional Affairs and UNDP | TRAC | 1.Venue and catering 2 days for 25 pple. – 1,450 2. Air tickets x 5 - $ 6,363, Accommodation x 5- $ 2,586 and DSA x 5- $ 1,818,. – $ 10, 567 3. Tents and chairs hire, tea\water/lunch x 2 days for 25 pple. – $ 5,883 Printing/translation of Communication Material- $ 1,200; Accommodation for 4 officials @ $ 109.00*4*3-$1,308.00 per night by 3 districts; Dinner for 4 officials @ $ 25 pp by 3 districts - $ 305*4*3-$3,660.00; Lunch for 4 officers pp by 3 districts- and allowances – $ 600 Total: $1,768.002 | 30,000 35,000 ($ 30,200 TRAC) |  |  |
|  | 2. Dissemination of recommendations of the mission of the Special Rapporteur on Poverty & Human Rights 3. Integration of Human Rights in High School Curriculum through the Establishment of Human Rights Clubs (1 per 1 district=10 clubs) Development of School Training Materials Training 4 Trainers for Teachers Human Rights Essay Competition for Students |  |  | x | x x | x x |  | TRAC TRAC | Venue per day, Water x 40 people x2 days - $ 335; Tea X 40 X 2 days - $ 350; Catering for lunch p/p for by 40 officials - $ 1,018 Total: $ 1,703.00 Printing = $1,500; Training Workshops 4 Officers (2 human rights Unit staff; 1 UNDP Staff; Driver) 10 Teachers 3 students per school by 10 schools = 30 Total number of people = 44 Venue and catering = $1,200 Competition Prizes: = $ 455; Prize Presentation: Catering for 30 officials (including judges and teachers); 5 finalists (students) = $ 1,018 Total: $4,173.00 |  |  |  |
|  | 4. HIV and the Law National Action Plan 2018 (implementing the HIV/AIDS Legal Environment Assessment (2016)) Development of National Action Plan Validation of the National Action Plan 5. Drafting of the State Party Report to the International Covenant on Economic, Social and Cultural Rights (ICESCR) and the Convention on the Rights of Persons with Disabilities (CRPD) 6. Commemoration of the 2018 International Human Rights Day (10 December) |  | x x | x x |  | x |  | UBRAF and SIDA TRAC TRAC | 1- Day Multi-Stakeholder Consultation Workshop : $1,800 2-Day National Action Plan Drafting Retreat : $1,000 National Action Plan Validation Workshop: $2,000 Total: $4,800 2-Day ICESCR Drafting Retreat: $9,500 ICESCR Report Validation Workshop: $1,500 CRPD Training/Drafting Retreat: $4,000 CRPD Report Validation Workshop: $1,500 Total: $16,500 Banner: $ 300 Venue: $ 150 Catering 80ppl: $ 2,000 Printing Communication Material: $ 1,500 Total: $3,950.00 |  |  |  |
|  | Support to DCEO 1. Implementation of NACSAP framework through sectorial workshops for the 1.Legislature,2.Public Sector, 3.Judiciary 4.Private sector, 5.CSOs and establishment of the National Coalition Against Corruption (NCAC) 2. Effective implementation of Asset Declaration system 3. Commemoration of International Anti-Corruption Day, 9 December 2018 through awareness campaigns and anti-corruption symposium. | IRRF # 2.3.1.A.1.1 Outcome 35 |  | x x | x | x | DCEO and UNDP | TRAC | Venue and catering: 1. $5,000, 2. - $ 4,000, 3.$ 3,00 3,. 4. - $ 3,000, 5. $ 3,000 and 6. $ 2,00=$ 20,000 2. workshop and catering - $ 3,000; sampling techniques 4. Venue and catering - $ 7,000, Anti-Corruption Symposium | 30,000 |  |  |
| Sub Total: $155,000.00 |
| Activity 3. Support the development of sustainable mechanism for peace infrastructures and enhancing gender and youth empowerment |
| Result: A functional peace infrastructure in place, enhanced advocacy for youth empowerment and gender equality |
|  | 1. Review and translation of Training Manual in conflict prevention and management. 2. Engagement of trauma counsellors and psychosocial experts to train Ribaneng community leadership on counselling and trauma | IRRF # 5.6.1 CPD Outcome 35 |  |  |  |  | CCL/CCJP GOL AND UNDP CCL, GOL AND UNDP | TRAC TRAC | Consultancy and printing $10000, 2. Service fee Transport, accommodation; training material 5,000 | 15,000 |  |  |
|  | Support to Youth 1. Mapping Exercise Programme for Gender (Women)/Youth-led Organisations • Development of Training Manual/Guide • Training 4 Trainers (District Officers/ Community Councilors) on Community Outreach/Data Collection & Analysis/Report Drafting • Mapping Exercise (March-April) for 10 Districts (3-4days in 1 District) • Report Drafting (Consultant Hire) • Report Translation, Printing and Dissemination 2. Capacity Building Workshop for Selected Youth/Gender Organisations (selected from the Mapping Exercise Report) • Training on basic organisation management (report writing, minute keeping, grant-writing, book keeping, logistics, finance management etc) • Networking Events with sponsors in Lesotho (i.e, USAIDS, RISE, Peace Corps etc) 3. Translation, Printing and Dissemination of the National Youth Policy (simplified Sesotho version) |  |  | x | x | x |  | TRAC | Capacity-Building Workshop (x3/ per thematic area) : $4,000 Total: $ 4,000 Capacity-Building Workshop (x3/ per thematic area) : $6,000 Total: $ 6,000 | 15,000 |  |  |
|  | 3. Translation, Printing and Dissemination of the National Youth Policy (simplified Sesotho version) |  |  |  | x |  |  | TRAC | Translator: $1,500 Printing: $2,000 Youth Policy Validation Workshop: $1,500 Total: 5,000 |  |  |  |
| Sub Total: $ 30,000.00 |

| Activity 6 Programme Management |
| --- |
| Programme Manager costs x 12 months, Governance PA, Governance Assistant Salary x 12 months Learning and capacity building Direct Project Cost GMS (5%) Steering Committee Meetings GPU Administrative costs |  |  |  |  |  |  |  |  |  | 89700 4600 76000 19 000 500 300 |  |  |
|  | Sub- total | 190700 |  |  |
|  | Grand total = $380,000.00 |  |  |  |