## Romanian
Proiectul Comun | [15 empty] | FINAL 11/EN
"Îmbunătăţirea disponibilităţii, calităţii şi utilizării datelor statistice dezagregate"
ANNUAL WORK PLAN BUDGET SHEET
Rezultatul 1 al UNDAF | Către anul 2011, instituţiile publice, cu sprijinul organizaţiilor societăţii civile (OSC) vor dispune de capacităţi mai bune de asigurare a bunei guvernări, supremaţiei legii şi accesului egal la justiţie şi promovării drepturilor omului
Indicatorul rezultatului UNDAF
Rezultatul PŢ 1.1 | Sunt formulate, implementate şi monitorizate, în mod transparent şi participativ, politici în favoarea săracilor ce abordează probleme de populaţie şi dezvoltare
Produsul UNDAF PŢ 1.1.9 | Disponibilitatea, calitatea şi utilizarea datelor statistice dezagregate sunt îmbunătăţite (accentul se va pune pe dezagregarea pe localizarea geografică, vârstă şi gen)
Rezultate scontate |  | Activităţi | Activităţi semnificative | Partners | Termenul de realizare |  |  |  | Bugetul indicativ | [5 empty] | Sursa de finantare |  |  |  |  | Amount
[5 empty] | 2007 | 2008 | 2009 | 2010 | Line | 2007 | 2008 | 2009 | 2010 | Total |  |  |  | Unit cost | Unit | 2007 | 2008 | 2009 | 2010 | Total
1. Capacitate îmbunătăţită a Biroului Naţional de Statistică şi a altor ministere de linie implicate în producerea informaţiei prin intermediul sistemului administrativ de raportare, chestionarelor şi recensămintelor (Ministerul Sănătăţii , Ministerul Educaţiei şi Tineretului, Ministerul Protecţiei Sociale, Familiei si Copilului etc.) pentru a produce oportun date de o calitate corespunzătoare, fiind dezagregate pe sex, vârstă şi localizare geografică. |  |  | 1.1. Revizuirea infrastructurii statistice in scopul harmonizarii cerinţelor de raportare, inclusiv: |  | X | X | X
| În baza analizei sutuatiei curente sunt elaborate recomandările pentru imbunătăţirea sistemului naţional de statistica (20087) | Activity 1 | 1.1.1. Revizuirea indicatorilor disponibili pentru monitorizarea ODM , Programelor Nationale de Dezvolatre (SCERS si PND) precum si Indicatorilor Europene de Incluziunea Sociala (European Social Inclusion Indicators); identificarea necesitatilor si elaborarea recomandărilor pentru îmbunătăţirea sistemului statistic (perfectionarea instrumentarului statistic, optimizarea fluxurilor informationale etc.) | BNS, MEC, Ministerile de Ramura | X | X | X |  | National consultant | 1500 | 19500 | 18000 | 0 | 39000 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth | 2 | 26 | 24 |  | 52
[9 empty] | Miscellaneous Expenses | 11.25 | 146.25 | 135 | 0 | 292.5 | UNDP | TRAC | UNDP TRAC
|  | Review the statistical infrastructure | • inclusiv, analiza situatiei, elaborarea recomandarilor pentru îmbunatatirea dezagregarii datelor statistice dupa gen, vîrsta; şi aspectul geografic |  | X | X | X |  | National consultant | 5000 | 9700 | 9000 | 0 | 23700 | UNIFEM | parallel | UNIFEM parallel | 750 | p/mnth | 2 | 16 | 12 |  | 30
[9 empty] | Miscellaneous Expenses | 37.5 | 72.75 | 67.5 | 0 | 177.75 | UNIFEM | parallel | UNIFEM parallel
| Recomandarile sunt implementate in practica prin imbunatatirea instrumentarului statistic, fluxurilor informationale si procesului de coordonare activitatilor Biroului National de Statistica si mnisterelor de resort (2009) |  | 1.1.2. Revizuirea instrumentarului statistic (rapoarte statistice) si fluxurilor informationale utilizate pentru monitorizarea ODM, Programelor Nationale de Dezvolatre (SCERS si PND) si Indicatorilor Europene de Incluziunea Sociala (European Social Inclusion Indicators) | BNS, Ministerile de Ramura |  |  |  |  | International consultant | 0 | 32000 | 20000 | 0 | 52000 | UNDP | TRAC | UNDP TRAC | 800 | p/day |  | 40 | 25 |  | 65
[9 empty] | Miscellaneous Expenses | 0 | 240 | 150 | 0 | 390 | UNDP | TRAC | UNDP TRAC
[9 empty] | International consultant | 0 | 13600 | 8800 | 0 | 22400 | UNIFEM | pooled | UNIFEM pooled | 800 | p/day | 5 | 12 | 11 |  | 28
[9 empty] | Miscellaneous Expenses | 0 | 102 | 66 | 0 | 168 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 959.14 | 620.62 | 0 | 1579.76 | UNIFEM | pooled | UNIFEM pooled
| Metadatele sunt elaborate in scopul unificarii metodologiei de calculare si evitarii divergentelor existente |  | 1.2. Elaborarea metadatelor şi ajustarea definiţiilor pentru indicatorii de monitorizare a ODM, Programelor Nationale de Dezvolatre (SCERS si PND) si IndicatoriEuropene de Incluziunea Sociala (European Social Inclusion Indicators) | NBS | X | X |  |  | National consultant | 1200 | 12000 | 3600 | 0 | 16800 | UNDP | TRAC | UNDP TRAC | 600 | p/mnth | 2 | 20 | 6 |  | 28
[9 empty] | Miscellaneous Expenses | 9 | 90 | 27 | 0 | 126 | UNDP | TRAC | UNDP TRAC
[9 empty] | National consultant | 0 | 20000 | 16000 | 0 | 36000 | UNIFEM | pooled | UNIFEM pooled | 750 | p/mnth |  | 40 | 8 |  | 46
[9 empty] | Miscellaneous Expenses | 0 | 150 | 120 | 0 | 270 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 1410.5 | 1128.4 | 0 | 2538.9 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | Translation | 500 | 4500 | 2500 | 0 | 7500 | UNDP | TRAC | UNDP TRAC | 5 | per page | 100 | 900 | 500 |  | 1500
[9 empty] | Miscellaneous Expenses | 3.75 | 33.75 | 18.75 | 0 | 56.25 | UNDP | TRAC | UNDP TRAC
|  |  | ACTIVITY1 -TRAC | [5 empty] | UNDP TRAC | 3224 | 68510 | 44430.75 | 0 | 116164.75
|  |  | ACTIVITY1 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY1 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY1 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 36221.64 | 26735.02 | 0 | 62956.66
|  |  | ACTIVITY1 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 5037.5 | 9772.75 | 9067.5 | 0 | 23877.75
|  |  | ACTIVITY1 -Unfunded | [5 empty] | Unfunded | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL ACTIVITY1 | [6 empty] | 8261.5 | 114504.39 | 80233.27 | 0 | 202999.16
| Datele statistice sunt disponibile si corespunde standardelor/recomandărilor internationale si cerintelor nationale | Activity 2 | 2.1 Statistica sociala: Imbunatatirea elaborarii datelor statistice dezagregate in urmatoarele domenii: | NBS, MET
Improve statistics tools
Statistica nivelului de trai:
|  |  | • build capacities for calculation and analysis of poverty and social exclusion indicators |  | X | X | X |  | Training | 0 | 900 | 0 | 0 | 900 | UNDP | TTF | UNDP TTF | 1000 | per annum |  | 1 |  |  | 1
[9 empty] | International consultant | 0 | 23850 | 0 | 0 | 23850 | UNDP | TTF | UNDP TTF | 800 | p/day |  | 30 |  |  | 30
[9 empty] | Miscellaneous Expenses | 0 | 250 | 0 | 0 | 250 | UNDP | TTF | UNDP TTF
[9 empty] | Training | 0 | 0 | 1000 | 1000 | 2000 | UNDP | TRAC | UNDP TRAC | 1000 | per annum |  |  | 1 | 1 | 2
[9 empty] | International consultant | 0 | 0 | 20000 | 0 | 20000 | UNDP | TRAC | UNDP TRAC | 800 | p/day |  |  | 25 |  | 25
[9 empty] | Miscellaneous Expenses | 0 | 0 | 157.5 | 7.5 | 165 | UNDP | TRAC | UNDP TRAC
|  |  | • Pregătirea şi efectuarea studiului privind excluderea socială | [5 empty] | Research | 0 | 19800 | 0 | 0 | 19800 | UNDP | TTF | UNDP TTF | 20000 | per research |  | 1 |  |  | 1
[9 empty] | Miscellaneous Expenses | 0 | 200 | 0 | 0 | 200 | UNDP | TTF | UNDP TTF
| Informatia cu privire la fenomenele si problemele social-economice este disponibila si diseminata factorilor de decizie |  | 2.2 Statistica forţei de muncă Organizarea şi lansarea cercetărilor statistice tematice (modulele): | NBS
|  |  | 2.2.1 Migraţia de muncă | NBS | X | X | X |  | Ad-hoc module LFS | 5000 | 20000 | 0 | 0 | 25000 | Unfunded |  | Unfunded | 25000 | per module | 0.2 | 0.8 |  |  | 1
|  |  | 2.2.2 Employment of persons with health problems (disabled) -- to be confirmed; | NBS, MSPFC |  |  | X | X | Ad-hoc module LFS | 0 | 0 | 10000 | 20000 | 30000 | Unfunded |  | Unfunded | 30000 | per module |  |  | 0.33333 | 0.66667 | 1
|  |  | 2.2.3 Ocuparea persoanelor cu dizabilităţi mentale; -- TBC | NBS |  | X |  |  | Ad-hoc module LFS | 0 | 12000 | 3000 | 0 | 15000 | Unfunded |  | Unfunded | 15000 | per module |  | 0.8 | 0.2 |  | 1
|  |  | 2.2.4 Munca copiilor | NBS |  |  | X |  | Ad-hoc module LFS | 0 | 0 | 24000 | 6000 | 30000 | Unfunded |  | Unfunded | 30000 | per module |  |  | 0.8 | 0.2 | 1
| Studiului de Utilizare a Timpului este pregătit pentru implementarea, inclusiv metodologia elaborată, chestionarile pregătite, planul de activităţi elaborat, costurile de implenmentare sunt identificate (2008) |  | 2.3. Pregătirea şi efectuarea Studiului de Utilizare a Timpului pentru a produce datele necesare pentru cercetările şi elaborarea politicilor de gen; întru îmbunătăţirea datelor statistice privind ocuparea în sectoarele pieţei muncii care sunt dificile de măsurat din punct de vedere statistic, etc. | NBS, MSPFC | X | X | X | X | National consultant | 0 | 11250 | 9000 | 2250 | 22500 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth |  | 15 | 12 | 3 | 30
[9 empty] | Miscellaneous Expenses | 0 | 84.375 | 67.5 | 16.875 | 168.75 | UNDP | TRAC | UNDP TRAC
| Studiului de Utilizare a Timpului este implementat, datele sunt procesate si distribuite (2009, TBC) | [7 empty] | International consultant | 0 | 28000 | 24000 | 0 | 52000 | UNIFEM | pooled | UNIFEM pooled | 800 | p/day | 0 | 25 | 30 |  | 55
[9 empty] | Miscellaneous Expenses | 0 | 210 | 180 | 0 | 390 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 1974.7 | 1692.6 | 0 | 3667.3 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | International consultant | 0 | 24000 | 0 | 0 | 24000 | Unfunded |  | Unfunded | 800 | p/day |  | 30 |  |  | 30
[9 empty] | Training | 0 | 5000 | 5000 | 0 | 10000 | UNDP | TRAC | UNDP TRAC | 5000 | per annum |  | 1 | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 0 | 50 | 50 | 0 | 100 | UNDP | TRAC | UNDP TRAC
[9 empty] | implementation (2009, TBC) | 0 | 0 | 0 | 30000 | 30000 | Unfunded |  | Unfunded | 30000 | one off |  |  |  | 1 | 1
|  |  | 2.4. Statistica demografică | NBS
| Datele demografice dezagregate dupa gen, virsta etc.(inclusiv si prognozele populatiei) sunt disponibile si diseminate la timp |  | 2.4.1. Procurarea echipamentului pentru procesare a datelor privind mişcarea naturală a populaţiei | NBS | X |  |  |  | Equipment | 15000 | 0 | 0 | 0 | 15000 | UNFPA | parallel | UNFPA parallel | 15000 | one off | 1 |  |  |  | 1
|  |  | 2.4.2. Elaborarea unui noi Soft de procesare a datelor privind mişcarea naturală a populaţiei | NBS |  | X | X |  | National consultant | 0 | 10000 | 10000 | 0 | 20000 | UNFPA | parallel | UNFPA parallel | 20000 | one off |  | 0.5 | 0.5 |  | 1
|  |  | 2.4.3. Instruirea specialiştilor BNS în utilizarea acestui SOFT | NBS |  | X | X |  | Training | 0 | 3000 | 3000 | 0 | 6000 | UNFPA | parallel | UNFPA parallel | 6000 | one off |  | 0.5 | 0.5 |  | 1
|  |  | 2.4.4. Elaborarea/procurarea complexului automatizat privind calculele demografice de analiza si prognozare a numarului populatiei Republicii Moldova ". | NBS |  | X | X |  | Companie/Consultant internaţional | 0 | 150000 | 50000 | 0 | 200000 | Unfunded |  | Unfunded | 200000 | one off |  | 0.75 | 0.25 |  | 1
|  |  | ACTIVITY2 - TRAC | [5 empty] | UNDP TRAC | 0 | 16384.375 | 35275 | 3274.375 | 54933.75
|  |  | ACTIVITY2 -TTF | [5 empty] | UNDP TTF | 0 | 45000 | 0 | 0 | 45000
|  |  | ACTIVITY2 -UNFPA | [5 empty] | UNFPA parallel | 15000 | 13000 | 13000 | 0 | 41000
|  |  | ACTIVITY2 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 30184.7 | 25872.6 | 0 | 56057.3
|  |  | ACTIVITY2 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY2 -Unfunded | [5 empty] | Unfunded | 5000 | 206000 | 87000 | 56000 | 354000
|  |  | TOTAL ACTIVITY2 | [6 empty] | 20000 | 310569.075 | 161147.6 | 59274.375 | 550991.05
|  | Activity 3 | 3.1. Îmbunătăţirea capacităţilor efectuării cercetărilor prin sondaj | NBS
| Posibilităţile sporite de BNS pentru organizarea instruirii continuă pentru colaboratorii sistemului statistic pe domenii de activitate | Capacity building | 3.1.1 Organizarea instruirii continuă pentru colaboratorii oficiului BNS si a sectiilor raionale de statistica pe domenii de activitate -- elaborarea planurilor si programelor de instruire -- elaborarea si tiparirea materialelor | NBS | X | X | X | X | National consultant | 750 | 8250 | 0 | 0 | 9000 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth | 1 | 11 |  |  | 12
[9 empty] | International consultant | 0 | 16000 | 0 | 0 | 16000 | UNDP | TRAC | UNDP TRAC | 800 | p/day |  | 20 |  |  | 20
[9 empty] | Printing of materials | 0 | 5000 | 0 | 0 | 5000 | UNDP | TRAC | UNDP TRAC | 2500 | per annum |  | 2 |  |  | 2
[9 empty] | Training | 0 | 2500 | 2500 | 2500 | 7500 | UNDP | TRAC | UNDP TRAC | 2500 | per annum |  | 1 | 1 | 1 | 3
[9 empty] | Miscellaneous Expenses | 5.625 | 238.125 | 18.75 | 18.75 | 281.25 | UNDP | TRAC | UNDP TRAC
| Personalul BNS de a testa Practiclele statistice mai avansate in colectarea datelor |  | 3.1.2 Trecerea la metode moderne de colectare a informatiei statistice (interviuri de tip CAPI) - pilot in Chisinau si Balti | NBS |  | X | X |  | Procurement of equipment | 0 | 25000 | 0 | 0 | 25000 | Unfunded |  | Unfunded | 1000 | per set of equipment |  | 25 |  |  | 25
[9 empty] | Adjustment of data entry software | 0 | 10000 | 0 | 0 | 10000 | Unfunded |  | Unfunded | 10000 | one off |  | 1 |  |  | 1
| Personalul BNS are o posibilitate de a beneficia de schimb in experienta in Practiclele statistice mai avansate |  | 3.1.3. Organize professional events for sharing experience in statistical areas (gender statistics, etc) and participate in statistical events and conferences. | NBS | X | X | X | X | Logistics for events | 500 | 2500 | 2000 | 2000 | 7000 | UNDP | TRAC | UNDP TRAC | 1000 | per event | 0.5 | 2.5 | 2 | 2 | 7
[9 empty] | Miscellaneous Expenses | 3.75 | 18.75 | 15 | 15 | 52.5 | UNDP | TRAC | UNDP TRAC
|  |  | * Organize topical conferences and seminars with the participation of international experts: UNECE, ILO, Eurostat; users etc. in order to inform on and promote statistical research | NBS |  |  |  |  | Logistics for events | 5000 | 3000 | 1500 | 0 | 9500 | UNIFEM | parallel | UNIFEM parallel | 1000 | per event | 1 | 7 | 1.5 |  | 9.5
[9 empty] | Miscellaneous Expenses | 37.5 | 22.5 | 11.25 | 0 | 71.25 | UNIFEM | parallel | UNIFEM parallel
[9 empty] | In-country traveling | 1500 | 4500 | 4500 | 4500 | 15000 | UNDP | TRAC | UNDP TRAC | 300 | persons/day of travel | 5 | 15 | 15 | 15 | 50
|  |  | * participation of NBS specialists in international conferences and seminars (Migration Statistics, 2007; Crime Statistics, 2007, International Conference of Labour Statisticians, 2008; IARIW Conference 2008, Seminar on Employment Quality, 2009, etc) | NBS |  |  |  |  | Travelling | 4800 | 20000 | 20000 | 10000 | 54800 | UNDP | TRAC | UNDP TRAC | 400 | persons/day of travel | 12 | 50 | 50 | 25 | 137
[9 empty] | Miscellaneous Expenses | 47.25 | 183.75 | 183.75 | 108.75 | 523.5 | UNDP | TRAC | UNDP TRAC
[9 empty] | Travelling | 10000 | 5000 | 5000 | 0 | 20000 | UNIFEM | parallel | UNIFEM parallel | 400 | persons/day of travel | 25 | 50 | 25 |  | 100
[9 empty] | Miscellaneous Expenses | 75 | 37.5 | 37.5 | 0 | 150 | UNIFEM | parallel | UNIFEM parallel
| Imbunatatirea calitatii cercetarilor efectuate de catre cercetatori independente, fortificarea capacitatilor BNS ca un organ responsabil pentru coordonarea activitatii statistice in tara |  | 3.2. Consolidarea capacităţilor al BNS pentru evaluarea calităţii şi instrumentelor a cercetărilor independente, şi, în caz de necesitate, îndrumare metodologică | NBS | X | X | X |  | International consultant | 0 | 9000 | 9000 | 0 | 18000 | UNDP | TRAC | UNDP TRAC | 600 | p/mnth |  | 15 | 15
[9 empty] | National consultant | 0 | 9000 | 9000 | 0 | 18000 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth |  | 12 | 12 |  | 24
[9 empty] | Travelling | 0 | 4000 | 4000 | 0 | 8000 | UNDP | TRAC | UNDP TRAC | 400 | persons/day of travel |  | 10 | 10 |  | 20
[9 empty] | Miscellaneous Expenses | 0 | 165 | 165 | 0 | 330 | UNDP | TRAC | UNDP TRAC
|  |  | ACTIVITY3 - TRAC | [5 empty] | UNDP TRAC | 7606.625 | 81355.625 | 51382.5 | 19142.5 | 159487.25
|  |  | ACTIVITY3 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY3 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY3 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY3 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 15112.5 | 8060 | 6548.75 | 0 | 29721.25
|  |  | ACTIVITY3 -Unfunded | [5 empty] | Unfunded | 0 | 35000 | 0 | 0 | 35000
|  |  | TOTAL ACTIVITY3 | [6 empty] | 22719.125 | 124415.625 | 57931.25 | 19142.5 | 224208.5
2. Accesul universal la date statistice prin îmbunătăţirea sistemelor, practicilor şi instrumentelor de diseminare (publicaţii, pagina web a BNS, baza de date DevInfo ) in scopul satisfacerii cerinţelor utilizatorilor ; |  | Activity 4 | 4.1. Revizuirea formatului publicaţiilor şi elaborărea unor materiale tematice "easy-to-use" pentru diseminarea datelor de ODM, Programele Nationale de Dezvolatre si Indicatoarele Europene de Inclusiunea Sociala (European Social Inclusion Indicators) | NBS
| Culegerii statistice „Femei şi Bărbaţi în Moldova 2007, 2009” sunt pregatite in format revizuit, tiparite, si diseminate de catre utilizatori de date. | Diseminarea datelor | - editarea culegerii statistice „Femei şi Bărbaţi în Moldova 2007, 2009” | NBS | X |  | X |  | Printing costs | 3000 | 0 | 3000 | 0 | 6000 | UNIFEM | parallel | UNIFEM parallel | 3000 | one off | 1 |  | 1 |  | 2
|  |  | * revizuirea formatului publicarii | NBS |  |  |  |  | International consultant | 3000 | 0 | 1500 | 0 | 4500 | UNIFEM | parallel | UNIFEM parallel | 750 | p/mnth | 2 |  | 2 |  | 4
[9 empty] | Miscellaneous Expenses | 100 | 0 | 100 | 0 | 200
|  |  | * publicarea culegerii in numarul mai mare de examplari si in formatul noi--pe mini-CD-uri | NBS |  |  |  |  | Printing costs | 500 | 0 | 500 | 0 | 1000 | UNDP | TRAC | UNDP TRAC | 500 | one off | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 25 | 0 | 25 |  | 50
[9 empty] | Logistics for events | 2000 | 0 | 2000 | 0 | 4000 | UNIFEM | pooled | UNIFEM pooled | 2000 | one off | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 50 | 0 | 50 | 0 | 100 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 143.5 | 0 | 143.5 | 0 | 287 | UNIFEM | pooled | UNIFEM pooled
|  |  | * organizarea prezentarii culegerii si altor evenimentilor de distribuire | NBS |  |  |  |  | Logistics for events | 1000 | 0 | 1000 | 0 | 2000 | UNDP | TRAC | UNDP TRAC | 1000 | per event | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 50 | 0 | 50 | 0 | 100 | UNDP | TRAC | UNDP TRAC
[9 empty] | Logistics for events | 0 | 1000 | 1000 | 0 | 2000 | UNIFEM | pooled | UNIFEM pooled | 1000 | per event | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 0 | 50 | 50 | 0 | 100 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 73.5 | 73.5 | 0 | 147 | UNIFEM | pooled | UNIFEM pooled
| Culegerea statistica „Criminalitatea in Moldova” este elaborata si diseminata organelor de resort, organizatiilor internationale si publicului larg |  | - editarea culegerii statistice „Criminalitatea în RM, 2009" | NBS |  |  | X |  | Printing costs | 0 | 0 | 5000 | 0 | 5000 | UNIFEM | parallel | UNIFEM parallel | 5000 | one off |  |  | 1
|  |  | • studierea si perfectionarea indicatorilor din domeniu, racordarea acestora la standardele internaţionale (perfecţionarea fişei de evidenţă a inculpatului, elaborarea softului de procesare a datelor, etc.) | NBS |  |  |  |  | International consultant | 0 | 1600 | 1600 | 0 | 3200 | UNIFEM | parallel | UNIFEM parallel | 800 | p/day |  | 2 | 2 |  | 4
[9 empty] | Miscellaneous Expenses | 0 | 50 | 100 | 0 | 150 | UNIFEM | parallel | UNIFEM parallel
[9 empty] | National consultant | 1500 | 3750 | 3750 | 0 | 9000 | Unfunded |  | Unfunded | 750 | p/mnth | 2 | 5 | 5 |  | 12
| Gradul de satisfacere a utilizatorilor de date este măsurat in mod regulat si utilizat pentru imbunatatirea practicilor de diseminare. |  | 4.2. Efectuarea sondajului de opinie privind nivelul satisfacerii utilizatorilor de informaţie statistică | NBS | X |  | X |  | Oppinion poll | 0 | 5000 | 5000 | 0 | 10000 | UNDP | TRAC | UNDP TRAC | 5000 | one off |  | 1 | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 0 | 50 | 50 | 0 | 100 | UNDP | TRAC | UNDP TRAC
| Utilizatori de date cunosc mai bine sursele de date si graficul de publicare a lor; si utilizeaza datele mai eficient |  | 4.3. Informarea utilizatorilor despre materialele disponibile şi graficul de publicare a datelor prin intermediul evenimentelor speciale, seminarelor, campaniilor şi altor activităţi, în baza informaţiilor disponibile, rezultatelor studiilor şi evaluărilor; evaluarea necesitatilor utilizatorilor in datele statistice | NBS | X | X | X | X | Miscellaneous | 750 | 750 | 750 | 750 | 3000 | UNDP | TRAC | UNDP TRAC | 750 | per annum | 1 | 1 | 1 | 1 | 4
[9 empty] | Miscellaneous | 0 | 1500 | 1000 | 0 | 2500 | UNIFEM | parallel | UNIFEM parallel | 500 | per annum | 1 | 2 | 2 |  | 5
| Paginea reproiectata a BNS ofera datele necesare pentru utilizatori în mod mai uşor de utilizare Re-designed NBS page is regularly updated and supplies the users with necessary data in an “easy-to-use” manner |  | 4.4. Reproiectarea paginii WEB a BNS, cu respectarea prevederilor „cerinţelor standard faţă de paginile oficiale” şi a politicilor de diseminarea a datelor statistice, 2007 | NBS | X | X |  |  | National consultant | 1000 | 9000 | 0 | 0 | 10000 | UNDP | TRAC | UNDP TRAC | 10000 | flat rate | 0.1 | 0.9 |  |  | 1
[9 empty] | Miscellaneous | 7.5 | 67.5 | 0 | 0 | 75 | UNDP | TRAC | UNDP TRAC
|  |  | ACTIVITY4 - TRAC | [5 empty] | UNDP TRAC | 3307.5 | 14867.5 | 7350 | 750 | 26275
|  |  | ACTIVITY4 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY4 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY4 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 2193.5 | 1123.5 | 3317 | 0 | 6634
|  |  | ACTIVITY4 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 6000 | 3150 | 12200 | 0 | 21350
|  |  | ACTIVITY4 -Unfunded | [5 empty] | Unfunded | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL ACTIVITY4 | [6 empty] | 11501 | 19141 | 22867 | 750 | 54259
3. Nivel sporit de utilizare a datelor disponibile pentru procesul participativ de elaborare a politicilor prin îmbunătăţirea competenţelor utilizatorilor de date statistice, în urma majorării capacităţii în cadrul Guvernului, OSC şi altor părţi cointeresate, precum şi prin stimularea folosirii acestor date atât de analiştii politici din cadrul Guvernului cât şi de cei contractaţi din exterior. |  | Activity 5 | 5.1. Organizarea unor instruiri specifice şi orientate pentru diferite grupuri de utilizatori de date. | NBS | X | X | X | X | Logistics for events | 500 | 3500 | 1000 | 1000 | 6000 | UNDP | TRAC | UNDP TRAC | 500 | per event | 1 | 7 | 2 | 2 | 12
[9 empty] | Miscellaneous | 25 | 100 | 50 | 50 | 225 | UNDP | TRAC | UNDP TRAC
|  | Data use | [6 empty] | Logistics for events | 4000 | 5000 | 5000 | 0 | 14000 | UNIFEM | parallel | UNIFEM parallel | 1000 | per event |  | 7 | 5 |  | 12
[9 empty] | Miscellaneous | 100 | 100 | 100 | 0 | 300 | UNIFEM | parallel | UNIFEM parallel
| Sporirea gradului de utilizarea a datelor statistice in analizele in documentele de politica si rapoartele elaborate de catre organele de administratia Publica Centrala (EGPRS / NDP / strategiile sectoriale) |  | 5.2. Stimularea folosirii datelor statistice de catre Ministerile de Ramura pentru analiza politică prin susţinerea instrumentelor de monitorizare, raportare si evalure a politicilor (ODM, Programele Nationale de Dezvolatre (SCERS si PND) si Indicatoarele Europene de Inclusiunea Sociala (European Social Inclusion Indicators)) | NBS, MET, MSPFC, line ministries |  | X | X | X | Research | 0 | 10000 | 10000 | 10000 | 30000 | UNDP | TRAC | UNDP TRAC | 10000 | per year |  | 1 | 1 | 1 | 3
[9 empty] | Miscellaneous | 0 | 150 | 150 | 150 | 450 | UNDP | TRAC | UNDP TRAC
|  |  | * Stabilirea mechnismului si organizarea cercetarilor aditionale pentru analiza aprofundata a temelor speciale in rapoarte pe tematica referitor la politici sociale si grupuri vulnerabile, in special copii si femei |  |  | X | X | X | Research | 0 | 6000 | 4000 | 0 | 10000 | UNIFEM | parallel | UNIFEM parallel | 2000 | per year | 0 | 3 | 2 |  | 5
[9 empty] | Miscellaneous | 0 | 100 | 100 | 0 | 200 | UNIFEM | parallel | UNIFEM parallel
|  |  | * Analiza ex-ante a politicilor propuse de catre Ministerile / Unitatile de monitorizarea a politicilor |  |  | X | X | X | Research | 0 | 10000 | 10000 | 0 | 20000 | Unfunded |  | Unfunded | 10000 | per year |  | 1 | 1 |  | 2
| Sporirea gradului de utilizarea a datelor statistice de catrea OSC elaborarea de politici, evaluare si monitorizare |  | 5.3. Stimularea folosirii datelor statistice de catre mediul academic, OSC, etc pentru analiza politică prin susţinerea instrumentelor de monitorizare, si evalure a politicilor (ODM, Programele Nationale de Dezvolatre (SCERS si PND) si Indicatoarele Europene de Inclusiunea Sociala (European Social Inclusion Indicators) | NBS, MET, Academia, Civil society |  | X | X | X | Research | 0 | 5000 | 5000 | 5000 | 15000 | UNDP | TRAC | UNDP TRAC | 5000 | per contest |  | 1 | 1 | 1 | 3
[9 empty] | Miscellaneous | 0 | 100 | 100 | 100 | 300 | UNDP | TRAC | UNDP TRAC
|  |  | * Organizarea consursului de cercetari pe tematica incluziunii sociale |  |  | X | X | X | Research | 0 | 3000 | 3000 | 0 | 6000 | UNIFEM | parallel | UNIFEM parallel | 3000 | per research |  | 1 | 1 |  | 2
[9 empty] | Miscellaneous | 0 | 100 | 100 | 0 | 200 | UNIFEM | parallel | UNIFEM parallel
|  |  | ACTIVITY5 - TRAC | [5 empty] | UNDP TRAC | 525 | 18850 | 16300 | 16300 | 51975
|  |  | ACTIVITY5 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY5 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY5 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY5 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 4100 | 14300 | 12300 | 0 | 30700
|  |  | ACTIVITY5 -Unfunded | [5 empty] | Unfunded | 0 | 10000 | 10000 | 0 | 20000
|  |  | TOTAL ACTIVITY5 | [6 empty] | 4625 | 43150 | 38600 | 16300 | 102675
|  | Activity 6 | 6. Ensure an efficient project management |  | X | X | X | X | Project Manager | 3000 | 12000 | 12000 | 9000 | 36000 | UNDP | TRAC | UNDP TRAC | 1000 | person/months | 3 | 12 | 12 | 9 | 36
|  | Management | [6 empty] | Project Assistant | 1950 | 7800 | 7800 | 5850 | 23400 | UNDP | TRAC | UNDP TRAC | 650 | person/months | 3 | 12 | 12 | 9 | 36
[9 empty] | Supplies | 500 | 1000 | 1000 | 1000 | 3500 | UNDP | TRAC | UNDP TRAC | 1000 | per annum | 0.5 | 1 | 1 | 1 | 3.5
[9 empty] | Equipment | 5000 | 300 | 300 | 300 | 5900 | UNDP | TRAC | UNDP TRAC | 5000 | one off | 1 | 0.06 | 0.06 | 0.06 | 1.18
[9 empty] | Utilities | 400 | 1200 | 1200 | 1200 | 4000 | UNDP | TRAC | UNDP TRAC | 1200 | per annum | 0.33333 | 1 | 1 | 1 | 3.3333
[9 empty] | Communications (mail, internet) | 400 | 1200 | 1200 | 1200 | 4000 | UNDP | TRAC | UNDP TRAC | 1200 | per annum | 0.33333 | 1 | 1 | 1 | 3.3333
[9 empty] | Miscellaneous Expenses | 1000 | 500 | 500 | 500 | 2500 | UNDP | TRAC | UNDP TRAC | 500 | per annum | 2 | 1 | 1 | 1 | 5
0
|  |  | ACTIVITY6 - TRAC | [5 empty] | UNDP TRAC | 12250 | 24000 | 24000 | 19050 | 79300
|  |  | ACTIVITY6 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -Unfunded | [5 empty] | Unfunded | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL ACTIVITY6 | [6 empty] | 12250 | 24000 | 24000 | 19050 | 79300
|  |  | Total | [6 empty] | 79356.625 | 635780.09 | 384779.12 | 114516.875 | 1214432.71
including by sources of funding
|  |  | UNDP | [6 empty] | 26913.125 | 268967.5 | 178738.25 | 58516.875 | 533135.75
|  |  | TRAC | [5 empty] | UNDP TRAC | 26913.125 | 223967.5 | 178738.25 | 58516.875 | 488135.75
|  |  | Poverty TTF | [5 empty] | UNDP TTF | 0 | 45000 | 0 | 0 | 45000
|  |  | UNIFEM | [6 empty] | 32443.5 | 102812.59 | 96040.87 | 0 | 231296.96
|  |  | pooled | [5 empty] | UNIFEM pooled | 2193.5 | 67529.84 | 55924.62 | 0 | 125647.96
|  |  | parallel | [5 empty] | UNIFEM parallel | 30250 | 35282.75 | 40116.25 | 0 | 105649
|  |  | UNFPA | [5 empty] | UNFPA parallel | 15000 | 13000 | 13000 | 0 | 41000
|  |  | Financing gap | [5 empty] | Unfunded | 5000 | 251000 | 97000 | 56000 | 409000
|  |  | Total secured by UN agencies | [6 empty] | 74356.625 | 384780.09 | 287779.12 | 58516.875 | 805432.71
Inputs required
|  |  | National consultant | [5 empty] | person-months | 9.1 | 146.4 | 79.5 | 3 | 238
|  |  | National consultant | [5 empty] | average no of persons per year | 3.0333 | 12.2 | 6.625 | 0.33333 | 5.5479
|  |  | International consultant | [5 empty] | person-days | 7 | 174 | 110 | 0 | 291
Note on D26: Aceste activităţi au început deja în Republica Moldova prin abonarea la IMF GDDS şi SDDS (cu privire la indicatorii macroeconomici şi financiari) şi introducerea bazei de date DevInfo pentru monitorizarea implementării SCERS-ului şi obiectivelor ODM. Totuşi, metadatele trebuie produse pentru toţi indicatorii pentru a asigura compatibilitatea şi comparabilitatea. Should be checked if this will not be done in the framework of introduction of PC-Axis
Note on D54: ElenaVatcarau: Eurostat lanseaza aceasta cercetare in 2010, este bine sa lansam cercetarea in aceiasi perioada, dupa aceiasi metodologie
Note on D57: Standalone of module for HBS/LFS -- to be recommended during preparation stage
Note on D80: What exactly do we need to do to organize that training? Manuals? Training Costs? Something else?
Note on W94: 5 events x 2 persons x 5 days per year typically
Note on D56: ElenaVatcarau: Eurostat lanseaza aceasta cercetare in 2010, este bine sa lansam cercetarea in aceiasi perioada, dupa aceiasi metodologie

## LFA 11 EN FINAL
Joint Project | [15 empty] | FINAL 11/EN
"Improving the availability, quality and use of disaggregated statistical data"
ANNUAL WORK PLAN BUDGET SHEET
UNDAF Outcome 1 | By 2011, public institutions, with the support of civil society organizations (CSO), will have better capacities to ensure good governance, the rule of law and free access to justice and to promote human rights
UNDAF Outcome Indicator
CP Outcome 1.1 | Pro-poor policies addressing population and development issues are formulated, implemented and monitored in a transparent and participatory way
CP UNDAF Output 1.1.9 | Availability, quality and use of disaggregated statistical data are improved (with a focus on disaggregation by geographic location, age and gender)
Expected outputs |  | Activity | Significant activities | Partners | Implementing timeframe |  |  |  | Indicative budget | [5 empty] | Source of funding |  |  |  |  | Amount
[5 empty] | 2007 | 2008 | 2009 | 2010 | Line | 2007 | 2008 | 2009 | 2010 | Total |  |  |  | Unit cost | Unit | 2007 | 2008 | 2009 | 2010 | Total
1. Improved capacity of the National Bureau of Statistics and other line ministries involved in producing information through the administrative reporting system, questionnaires and census (Ministry of Health, Ministry of Education and Youth, Ministry of Social Protection, Family and Child etc.) to timely produce data of adequate quality, disaggregated by sex, age and geographic location. |  |  | 1.1. Review the statistical infrastructure to reconcile reporting requirements, including: |  | X | X | X
| Recommendations for the improvement of the national statistical system are developed on the basis of current situation analysis (2008) | Activity 1 | 1.1.1. Review the available indicators for the monitoring of MDGs, National Development Programmes (EGPRSP and NDP) as well as European Social Inclusion Indicators; identify needs and develop recommendations to improve the statistical system (improve the statistical toolkit, optimize information flows etc.) | NBS, MET, line ministries | X | X | X |  | National consultant | 1500 | 19500 | 18000 | 0 | 39000 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth | 2 | 26 | 24 |  | 52
[9 empty] | Miscellaneous Expenses | 11.25 | 146.25 | 135 | 0 | 292.5 | UNDP | TRAC | UNDP TRAC
|  | Review the statistical infrastructure | • including, situation analysis, drafting recommendations to improve disaggregation of statistical data by gender, age and geographic location |  | X | X | X |  | National consultant | 5000 | 9700 | 9000 | 0 | 23700 | UNIFEM | parallel | UNIFEM parallel | 750 | p/mnth | 2 | 16 | 12 |  | 30
[9 empty] | Miscellaneous Expenses | 37.5 | 72.75 | 67.5 | 0 | 177.75 | UNIFEM | parallel | UNIFEM parallel
| Recommendations are put into practice by improving the statistical toolkit, information flows and the coordination of activities of the National Bureau of Statistics and relevant ministries (2009) |  | 1.1.2. Review the statistical toolkit (statistical reports) and information flows used for the monitoring of MDGs, National Development Programmes (EGPRSP and NDP) and European Social Inclusion Indicators. | NBS, MET, line ministries |  |  |  |  | International consultant | 0 | 32000 | 20000 | 0 | 52000 | UNDP | TRAC | UNDP TRAC | 800 | p/day |  | 40 | 25 |  | 65
[9 empty] | Miscellaneous Expenses | 0 | 240 | 150 | 0 | 390 | UNDP | TRAC | UNDP TRAC
[9 empty] | International consultant | 0 | 13600 | 8800 | 0 | 22400 | UNIFEM | pooled | UNIFEM pooled | 800 | p/day | 5 | 12 | 11 |  | 28
[9 empty] | Miscellaneous Expenses | 0 | 102 | 66 | 0 | 168 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 959.14 | 620.62 | 0 | 1579.76 | UNIFEM | pooled | UNIFEM pooled
| Metadata are developed to consolidate the calculation methodology and avoid existing discrepancies |  | 1.2. Develop metadata and adjust definitions for the monitoring indicators of MDGs, National Development Programmes (EGPRSP and NDP) and European Social Inclusion Indicators | NBS | X | X |  |  | National consultant | 1200 | 12000 | 3600 | 0 | 16800 | UNDP | TRAC | UNDP TRAC | 600 | p/mnth | 2 | 20 | 6 |  | 28
[9 empty] | Miscellaneous Expenses | 9 | 90 | 27 | 0 | 126 | UNDP | TRAC | UNDP TRAC
[9 empty] | National consultant | 0 | 20000 | 16000 | 0 | 36000 | UNIFEM | pooled | UNIFEM pooled | 750 | p/mnth |  | 40 | 8 |  | 46
[9 empty] | Miscellaneous Expenses | 0 | 150 | 120 | 0 | 270 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 1410.5 | 1128.4 | 0 | 2538.9 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | Translation | 500 | 4500 | 2500 | 0 | 7500 | UNDP | TRAC | UNDP TRAC | 5 | per page | 100 | 900 | 500 |  | 1500
[9 empty] | Miscellaneous Expenses | 3.75 | 33.75 | 18.75 | 0 | 56.25 | UNDP | TRAC | UNDP TRAC
|  |  | ACTIVITY1 -TRAC | [5 empty] | UNDP TRAC | 3224 | 68510 | 44430.75 | 0 | 116164.75
|  |  | ACTIVITY1 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY1 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY1 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 36221.64 | 26735.02 | 0 | 62956.66
|  |  | ACTIVITY1 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 5037.5 | 9772.75 | 9067.5 | 0 | 23877.75
|  |  | ACTIVITY1 -Unfunded | [5 empty] | Unfunded | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL ACTIVITY1 | [6 empty] | 8261.5 | 114504.39 | 80233.27 | 0 | 202999.16
| Statistical data are available and comply with the international standards/recommendations and national requirements | Activity 2 | 2.1 Social statistics: Improving the development of disaggregated statistical data in the following areas: | NBS, MET
Improve statistics tools
Living standards statistics:
|  |  | • build capacities for calculation and analysis of poverty and social exclusion indicators |  | X | X | X |  | Training | 0 | 900 | 0 | 0 | 900 | UNDP | TTF | UNDP TTF | 1000 | per annum |  | 1 |  |  | 1
[9 empty] | International consultant | 0 | 23850 | 0 | 0 | 23850 | UNDP | TTF | UNDP TTF | 800 | p/day |  | 30 |  |  | 30
[9 empty] | Miscellaneous Expenses | 0 | 250 | 0 | 0 | 250 | UNDP | TTF | UNDP TTF
[9 empty] | Training | 0 | 0 | 1000 | 1000 | 2000 | UNDP | TRAC | UNDP TRAC | 1000 | per annum |  |  | 1 | 1 | 2
[9 empty] | International consultant | 0 | 0 | 20000 | 0 | 20000 | UNDP | TRAC | UNDP TRAC | 800 | p/day |  |  | 25 |  | 25
[9 empty] | Miscellaneous Expenses | 0 | 0 | 157.5 | 7.5 | 165 | UNDP | TRAC | UNDP TRAC
|  |  | • Prepare and carry out a study on social exclusion | [5 empty] | Research | 0 | 19800 | 0 | 0 | 19800 | UNDP | TTF | UNDP TTF | 20000 | per research |  | 1 |  |  | 1
[9 empty] | Miscellaneous Expenses | 0 | 200 | 0 | 0 | 200 | UNDP | TTF | UNDP TTF
| Information on social-economic phenomena and problems is available and disseminated to decision-makers |  | 2.2 Labour force statistics Organize and launch topical statistical researches (modules): | NBS
|  |  | 2.2.1 Labour migration | NBS | X | X | X |  | Ad-hoc module LFS | 5000 | 20000 | 0 | 0 | 25000 | Unfunded |  | Unfunded | 25000 | per module | 0.2 | 0.8 |  |  | 1
|  |  | 2.2.2 Employment of persons with health problems (disabled) -- to be confirmed; | NBS, MSPFC |  |  | X | X | Ad-hoc module LFS | 0 | 0 | 10000 | 20000 | 30000 | Unfunded |  | Unfunded | 30000 | per module |  |  | 0.33333 | 0.66667 | 1
|  |  | 2.2.3 Entry of the young people into the labour market | NBS |  | X |  |  | Ad-hoc module LFS | 0 | 12000 | 3000 | 0 | 15000 | Unfunded |  | Unfunded | 15000 | per module |  | 0.8 | 0.2 |  | 1
|  |  | 2.2.4 Child labour | NBS |  |  | X |  | Ad-hoc module LFS | 0 | 0 | 24000 | 6000 | 30000 | Unfunded |  | Unfunded | 30000 | per module |  |  | 0.8 | 0.2 | 1
| Study on the Use of Time is prepared for implementation: methodology is developed, questionnaires are prepared, action plan is drafted, implementation costs are identified (2008) |  | 2.3. Prepare and carry out the Study on the Use of Time to produce data required for gender researches and policy-making; in order to improve statistical data on employment in the labour market sectors which are difficult to be statistically measured, etc. | NBS, MSPFC | X | X | X | X | National consultant | 0 | 11250 | 9000 | 2250 | 22500 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth |  | 15 | 12 | 3 | 30
[9 empty] | Miscellaneous Expenses | 0 | 84.375 | 67.5 | 16.875 | 168.75 | UNDP | TRAC | UNDP TRAC
| Study on the Use of Time is implemented, data are processed and disseminated (2009, TBC) | [7 empty] | International consultant | 0 | 28000 | 24000 | 0 | 52000 | UNIFEM | pooled | UNIFEM pooled | 800 | p/day | 0 | 25 | 30 |  | 55
[9 empty] | Miscellaneous Expenses | 0 | 210 | 180 | 0 | 390 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 1974.7 | 1692.6 | 0 | 3667.3 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | International consultant | 0 | 24000 | 0 | 0 | 24000 | Unfunded |  | Unfunded | 800 | p/day |  | 30 |  |  | 30
[9 empty] | Training | 0 | 5000 | 5000 | 0 | 10000 | UNDP | TRAC | UNDP TRAC | 5000 | per annum |  | 1 | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 0 | 50 | 50 | 0 | 100 | UNDP | TRAC | UNDP TRAC
[9 empty] | implementation (2009, TBC) | 0 | 0 | 0 | 30000 | 30000 | Unfunded |  | Unfunded | 30000 | one off |  |  |  | 1 | 1
|  |  | 2.4. Demographic statistics | NBS
| Demographic data disaggregated by gender, age etc. (including population forecasts) are available and timely disseminated |  | 2.4.1. Provide equipment for the processing of data on the natural movement of population | NBS | X |  |  |  | Equipment | 15000 | 0 | 0 | 0 | 15000 | UNFPA | parallel | UNFPA parallel | 15000 | one off | 1 |  |  |  | 1
|  |  | 2.4.2. Develop a new software for the processing of data on the natural movement of population | NBS |  | X | X |  | National consultant | 0 | 10000 | 10000 | 0 | 20000 | UNFPA | parallel | UNFPA parallel | 20000 | one off |  | 0.5 | 0.5 |  | 1
|  |  | 2.4.3. Train the NBS specialists in using this SOFTWARE | NBS |  | X | X |  | Training | 0 | 3000 | 3000 | 0 | 6000 | UNFPA | parallel | UNFPA parallel | 6000 | one off |  | 0.5 | 0.5 |  | 1
|  |  | 2.4.4. Development / purchase of software package for demographic calculations and forecasts in the Republic of Moldova | NBS |  | X | X |  | Companie/Consultant internaţional | 0 | 150000 | 50000 | 0 | 200000 | Unfunded |  | Unfunded | 200000 | one off |  | 0.75 | 0.25 |  | 1
|  |  | ACTIVITY2 - TRAC | [5 empty] | UNDP TRAC | 0 | 16384.375 | 35275 | 3274.375 | 54933.75
|  |  | ACTIVITY2 -TTF | [5 empty] | UNDP TTF | 0 | 45000 | 0 | 0 | 45000
|  |  | ACTIVITY2 -UNFPA | [5 empty] | UNFPA parallel | 15000 | 13000 | 13000 | 0 | 41000
|  |  | ACTIVITY2 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 30184.7 | 25872.6 | 0 | 56057.3
|  |  | ACTIVITY2 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY2 -Unfunded | [5 empty] | Unfunded | 5000 | 206000 | 87000 | 56000 | 354000
|  |  | TOTAL ACTIVITY2 | [6 empty] | 20000 | 310569.075 | 161147.6 | 59274.375 | 550991.05
|  | Activity 3 | 3.1. Build capacities to conduct surveys | NBS
| Enhanced possibilities of the NBS to organize a continuous training for the staff of the statistical system by areas of activity | Capacity building | 3.1.1 Organize a continuous training for the NBS staff and the staff of rayon statistical sections by area of activity -- develop training plans and curricula -- develop and print training materials | NBS | X | X | X | X | National consultant | 750 | 8250 | 0 | 0 | 9000 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth | 1 | 11 |  |  | 12
[9 empty] | International consultant | 0 | 16000 | 0 | 0 | 16000 | UNDP | TRAC | UNDP TRAC | 800 | p/day |  | 20 |  |  | 20
[9 empty] | Printing of materials | 0 | 5000 | 0 | 0 | 5000 | UNDP | TRAC | UNDP TRAC | 2500 | per annum |  | 2 |  |  | 2
[9 empty] | Training | 0 | 2500 | 2500 | 2500 | 7500 | UNDP | TRAC | UNDP TRAC | 2500 | per annum |  | 1 | 1 | 1 | 3
[9 empty] | Miscellaneous Expenses | 5.625 | 238.125 | 18.75 | 18.75 | 281.25 | UNDP | TRAC | UNDP TRAC
| NBS staff to pilot advanced statistical practices in data collection |  | 3.1.2 Transition to modern statistical data collection methods (CAPI interviews) - piloting in Chisinau and Balti | NBS |  | X | X |  | Procurement of equipment | 0 | 25000 | 0 | 0 | 25000 | Unfunded |  | Unfunded | 1000 | per set of equipment |  | 25 |  |  | 25
[9 empty] | Adjustment of data entry software | 0 | 10000 | 0 | 0 | 10000 | Unfunded |  | Unfunded | 10000 | one off |  | 1 |  |  | 1
| NBS staff has an opportunity to benefit from sharing experience in more advanced statistical practices |  | 3.1.3. Organize professional events for sharing experience in statistical areas (gender statistics, etc) and participate in statistical events and conferences. | NBS | X | X | X | X | Logistics for events | 500 | 2500 | 2000 | 2000 | 7000 | UNDP | TRAC | UNDP TRAC | 1000 | per event | 0.5 | 2.5 | 2 | 2 | 7
[9 empty] | Miscellaneous Expenses | 3.75 | 18.75 | 15 | 15 | 52.5 | UNDP | TRAC | UNDP TRAC
|  |  | * Organize topical conferences and seminars with the participation of international experts: UNECE, ILO, Eurostat; users etc. in order to inform on and promote statistical research | NBS |  |  |  |  | Logistics for events | 5000 | 3000 | 1500 | 0 | 9500 | UNIFEM | parallel | UNIFEM parallel | 1000 | per event | 1 | 7 | 1.5 |  | 9.5
[9 empty] | Miscellaneous Expenses | 37.5 | 22.5 | 11.25 | 0 | 71.25 | UNIFEM | parallel | UNIFEM parallel
[9 empty] | In-country traveling | 1500 | 4500 | 4500 | 4500 | 15000 | UNDP | TRAC | UNDP TRAC | 300 | persons/day of travel | 5 | 15 | 15 | 15 | 50
|  |  | * participation of NBS specialists in international conferences and seminars (Migration Statistics, 2007; Crime Statistics, 2007, International Conference of Labour Statisticians, 2008; IARIW Conference 2008, Seminar on Employment Quality, 2009, etc) | NBS |  |  |  |  | Travelling | 4800 | 20000 | 20000 | 10000 | 54800 | UNDP | TRAC | UNDP TRAC | 400 | persons/day of travel | 12 | 50 | 50 | 25 | 137
[9 empty] | Miscellaneous Expenses | 47.25 | 183.75 | 183.75 | 108.75 | 523.5 | UNDP | TRAC | UNDP TRAC
[9 empty] | Travelling | 10000 | 5000 | 5000 | 0 | 20000 | UNIFEM | parallel | UNIFEM parallel | 400 | persons/day of travel | 25 | 50 | 25 |  | 100
[9 empty] | Miscellaneous Expenses | 75 | 37.5 | 37.5 | 0 | 150 | UNIFEM | parallel | UNIFEM parallel
| Improve the quality of surveys carried out by independent researchers, build capacities of the NBS as an authority responsible for coordination of statistical activity in the country |  | 3.2. Build capacities of the NBS to evaluate the quality and tools of independent researches (surveys), and, if required, provide methodological guidance | NBS | X | X | X |  | International consultant | 0 | 9000 | 9000 | 0 | 18000 | UNDP | TRAC | UNDP TRAC | 600 | p/mnth |  | 15 | 15
[9 empty] | National consultant | 0 | 9000 | 9000 | 0 | 18000 | UNDP | TRAC | UNDP TRAC | 750 | p/mnth |  | 12 | 12 |  | 24
[9 empty] | Travelling | 0 | 4000 | 4000 | 0 | 8000 | UNDP | TRAC | UNDP TRAC | 400 | persons/day of travel |  | 10 | 10 |  | 20
[9 empty] | Miscellaneous Expenses | 0 | 165 | 165 | 0 | 330 | UNDP | TRAC | UNDP TRAC
|  |  | ACTIVITY3 - TRAC | [5 empty] | UNDP TRAC | 7606.625 | 81355.625 | 51382.5 | 19142.5 | 159487.25
|  |  | ACTIVITY3 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY3 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY3 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY3 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 15112.5 | 8060 | 6548.75 | 0 | 29721.25
|  |  | ACTIVITY3 -Unfunded | [5 empty] | Unfunded | 0 | 35000 | 0 | 0 | 35000
|  |  | TOTAL ACTIVITY3 | [6 empty] | 22719.125 | 124415.625 | 57931.25 | 19142.5 | 224208.5
2. Universal access to statistical data through improvement of dissemination systems, practices and tools (publications, NBS web page, DevInfo database) to meet users' requirements; |  | Activity 4 | 4.1. Revision of publications’ format and elaboration of some "easy-to-use" thematic materials for data dissemination from MDG, National Development Programmes and European Social Inclusion Indicators | NBS
| The statistical compilation „Women and Men in Moldova 2007, 2009” are prepared in revised format, printed out and disseminated to data users | Data dissemination | - publishing the statistical compilation „Women and Men in Moldova 2007, 2009” | NBS | X |  | X |  | Printing costs | 3000 | 0 | 3000 | 0 | 6000 | UNIFEM | parallel | UNIFEM parallel | 3000 | one off | 1 |  | 1 |  | 2
|  |  | * revising publication format | NBS |  |  |  |  | International consultant | 3000 | 0 | 1500 | 0 | 4500 | UNIFEM | parallel | UNIFEM parallel | 750 | p/mnth | 2 |  | 2 |  | 4
[9 empty] | Miscellaneous Expenses | 100 | 0 | 100 | 0 | 200
|  |  | * publishing the compilation in a bigger number of copies and in a new format – on mini CDs | NBS |  |  |  |  | Printing costs | 500 | 0 | 500 | 0 | 1000 | UNDP | TRAC | UNDP TRAC | 500 | one off | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 25 | 0 | 25 |  | 50
[9 empty] | Logistics for events | 2000 | 0 | 2000 | 0 | 4000 | UNIFEM | pooled | UNIFEM pooled | 2000 | one off | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 50 | 0 | 50 | 0 | 100 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 143.5 | 0 | 143.5 | 0 | 287 | UNIFEM | pooled | UNIFEM pooled
|  |  | * organizing compilation presentation and follow-up events | NBS |  |  |  |  | Logistics for events | 1000 | 0 | 1000 | 0 | 2000 | UNDP | TRAC | UNDP TRAC | 1000 | per event | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 50 | 0 | 50 | 0 | 100 | UNDP | TRAC | UNDP TRAC
[9 empty] | Logistics for events | 0 | 1000 | 1000 | 0 | 2000 | UNIFEM | pooled | UNIFEM pooled | 1000 | per event | 1 |  | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 0 | 50 | 50 | 0 | 100 | UNIFEM | pooled | UNIFEM pooled
[9 empty] | GMS 7% | 0 | 73.5 | 73.5 | 0 | 147 | UNIFEM | pooled | UNIFEM pooled
| The statistical compilation „Criminality in Moldova” is developed and disseminated to interested bodies, international organizations and to the public |  | - publishing the statistical compilation „Criminality in RM, 2009" | NBS |  |  | X |  | Printing costs | 0 | 0 | 5000 | 0 | 5000 | UNIFEM | parallel | UNIFEM parallel | 5000 | one off |  |  | 1
|  |  | • review and improve area-specific indicators, adjust them to international standards (improve the offender's record card, develop data processing software, etc.) | NBS |  |  |  |  | International consultant | 0 | 1600 | 1600 | 0 | 3200 | UNIFEM | parallel | UNIFEM parallel | 800 | p/day |  | 2 | 2 |  | 4
[9 empty] | Miscellaneous Expenses | 0 | 50 | 100 | 0 | 150 | UNIFEM | parallel | UNIFEM parallel
[9 empty] | National consultant | 1500 | 3750 | 3750 | 0 | 9000 | Unfunded |  | Unfunded | 750 | p/mnth | 2 | 5 | 5 |  | 12
| Data Users Satisfaction is measured regularly and used for improvement of dissemination practices |  | 4.2. Oppinion poll of data users regarding satisfaction with statistical information available | NBS | X |  | X |  | Oppinion poll | 0 | 5000 | 5000 | 0 | 10000 | UNDP | TRAC | UNDP TRAC | 5000 | one off |  | 1 | 1 |  | 2
[9 empty] | Miscellaneous Expenses | 0 | 50 | 50 | 0 | 100 | UNDP | TRAC | UNDP TRAC
| Data users are better aware of data sources and the timetable for their publication; and use data more efficiently |  | 4.3. Informing the users about the available materials and the timetable for data publication through special events, seminars, campaigns and other activities based on available information, results of studies and assessments; evaluation of users’ needs for statistical data | NBS | X | X | X | X | Miscellaneous | 750 | 750 | 750 | 750 | 3000 | UNDP | TRAC | UNDP TRAC | 750 | per annum | 1 | 1 | 1 | 1 | 4
[9 empty] | Miscellaneous | 0 | 1500 | 1000 | 0 | 2500 | UNIFEM | parallel | UNIFEM parallel | 500 | per annum | 1 | 2 | 2 |  | 5
| Re-designed NBS page is regularly updated and supplies the users with necessary data in an “easy-to-use” manner |  | 4.4. Re-designing the NBS web page by observing the provisions of the “standard requirements for official pages” and the statistical data dissemination policies, 2007 | NBS | X | X |  |  | National consultant | 1000 | 9000 | 0 | 0 | 10000 | UNDP | TRAC | UNDP TRAC | 10000 | flat rate | 0.1 | 0.9 |  |  | 1
[9 empty] | Miscellaneous | 7.5 | 67.5 | 0 | 0 | 75 | UNDP | TRAC | UNDP TRAC
|  |  | ACTIVITY4 - TRAC | [5 empty] | UNDP TRAC | 3307.5 | 14867.5 | 7350 | 750 | 26275
|  |  | ACTIVITY4 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY4 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY4 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 2193.5 | 1123.5 | 3317 | 0 | 6634
|  |  | ACTIVITY4 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 6000 | 3150 | 12200 | 0 | 21350
|  |  | ACTIVITY4 -Unfunded | [5 empty] | Unfunded | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL ACTIVITY4 | [6 empty] | 11501 | 19141 | 22867 | 750 | 54259
3. Increased level of available data use for participatory process in policy making by improving statistical data users’ abilities as a result of capacities increase within the Government, civil society organizations and other stakeholders, as well as through fostering these data use by policy analysts from the Government and the outsourced ones. |  | Activity 5 | 5.1. Organizing some specific and well-targeted trainings for different groups of data users | NBS | X | X | X | X | Logistics for events | 500 | 3500 | 1000 | 1000 | 6000 | UNDP | TRAC | UNDP TRAC | 500 | per event | 1 | 7 | 2 | 2 | 12
[9 empty] | Miscellaneous | 25 | 100 | 50 | 50 | 225 | UNDP | TRAC | UNDP TRAC
|  | Data use | [6 empty] | Logistics for events | 4000 | 5000 | 5000 | 0 | 14000 | UNIFEM | parallel | UNIFEM parallel | 1000 | per event |  | 7 | 5 |  | 12
[9 empty] | Miscellaneous | 100 | 100 | 100 | 0 | 300 | UNIFEM | parallel | UNIFEM parallel
| Increasing the level of statistical data use in analysis, policy documents and reports drafted by the central public administration authorities (EGPRS / NDP / sector strategies) |  | 5.2. Fostering statistical data use by the line ministries for policy analysis through supporting policy monitoring, reporting and evaluation tools (MDG, National Development Programmes (EGPRSP and NDP) and European Social Inclusion Indicators) | NBS, MET, MSPFC, line ministries |  | X | X | X | Research | 0 | 10000 | 10000 | 10000 | 30000 | UNDP | TRAC | UNDP TRAC | 10000 | per year |  | 1 | 1 | 1 | 3
[9 empty] | Miscellaneous | 0 | 150 | 150 | 150 | 450 | UNDP | TRAC | UNDP TRAC
|  |  | * Establishing the mechanism and organizing additional surveys for in-depth analysis of special topic reports on social policies and vulnerable groups, especially women and children |  |  | X | X | X | Research | 0 | 6000 | 4000 | 0 | 10000 | UNIFEM | parallel | UNIFEM parallel | 2000 | per year | 0 | 3 | 2 |  | 5
[9 empty] | Miscellaneous | 0 | 100 | 100 | 0 | 200 | UNIFEM | parallel | UNIFEM parallel
|  |  | * Ex-ante analysis of proposed policies by ministries' representatives/Policy Units |  |  | X | X | X | Research | 0 | 10000 | 10000 | 0 | 20000 | Unfunded |  | Unfunded | 10000 | per year |  | 1 | 1 |  | 2
| Increasing the level of statistical data use by civil society organizations in policy making, monitoring and evaluation |  | 5.3. Fostering statistical data use by the academia, CSO, etc for policy analysis though supporting policy monitoring, reporting and evaluation tools (MDG, National Development Programmes (EGPRSP and NDP) and European Social Inclusion Indicators) | NBS, MET, Academia, Civil society |  | X | X | X | Research | 0 | 5000 | 5000 | 5000 | 15000 | UNDP | TRAC | UNDP TRAC | 5000 | per contest |  | 1 | 1 | 1 | 3
[9 empty] | Miscellaneous | 0 | 100 | 100 | 100 | 300 | UNDP | TRAC | UNDP TRAC
|  |  | * Organize a competition for researches on social inclusion |  |  | X | X | X | Research | 0 | 3000 | 3000 | 0 | 6000 | UNIFEM | parallel | UNIFEM parallel | 3000 | per research |  | 1 | 1 |  | 2
[9 empty] | Miscellaneous | 0 | 100 | 100 | 0 | 200 | UNIFEM | parallel | UNIFEM parallel
|  |  | ACTIVITY5 - TRAC | [5 empty] | UNDP TRAC | 525 | 18850 | 16300 | 16300 | 51975
|  |  | ACTIVITY5 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY5 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY5 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY5 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 4100 | 14300 | 12300 | 0 | 30700
|  |  | ACTIVITY5 -Unfunded | [5 empty] | Unfunded | 0 | 10000 | 10000 | 0 | 20000
|  |  | TOTAL ACTIVITY5 | [6 empty] | 4625 | 43150 | 38600 | 16300 | 102675
|  | Activity 6 | 6. Ensure an efficient project management |  | X | X | X | X | Project Manager | 3000 | 12000 | 12000 | 9000 | 36000 | UNDP | TRAC | UNDP TRAC | 1000 | person/months | 3 | 12 | 12 | 9 | 36
|  | Management | [6 empty] | Project Assistant | 1950 | 7800 | 7800 | 5850 | 23400 | UNDP | TRAC | UNDP TRAC | 650 | person/months | 3 | 12 | 12 | 9 | 36
[9 empty] | Supplies | 500 | 1000 | 1000 | 1000 | 3500 | UNDP | TRAC | UNDP TRAC | 1000 | per annum | 0.5 | 1 | 1 | 1 | 3.5
[9 empty] | Equipment | 5000 | 300 | 300 | 300 | 5900 | UNDP | TRAC | UNDP TRAC | 5000 | one off | 1 | 0.06 | 0.06 | 0.06 | 1.18
[9 empty] | Utilities | 400 | 1200 | 1200 | 1200 | 4000 | UNDP | TRAC | UNDP TRAC | 1200 | per annum | 0.33333 | 1 | 1 | 1 | 3.3333
[9 empty] | Communications (mail, internet) | 400 | 1200 | 1200 | 1200 | 4000 | UNDP | TRAC | UNDP TRAC | 1200 | per annum | 0.33333 | 1 | 1 | 1 | 3.3333
[9 empty] | Miscellaneous Expenses | 1000 | 500 | 500 | 500 | 2500 | UNDP | TRAC | UNDP TRAC | 500 | per annum | 2 | 1 | 1 | 1 | 5
0
|  |  | ACTIVITY6 - TRAC | [5 empty] | UNDP TRAC | 12250 | 24000 | 24000 | 19050 | 79300
|  |  | ACTIVITY6 -TTF | [5 empty] | UNDP TTF | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -UNFPA | [5 empty] | UNFPA parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -UNIFEM Pooled | [5 empty] | UNIFEM pooled | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -UNIFEM Parallel | [5 empty] | UNIFEM parallel | 0 | 0 | 0 | 0 | 0
|  |  | ACTIVITY6 -Unfunded | [5 empty] | Unfunded | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL ACTIVITY6 | [6 empty] | 12250 | 24000 | 24000 | 19050 | 79300
|  |  | Total | [6 empty] | 79356.625 | 635780.09 | 384779.12 | 114516.875 | 1214432.71
including by sources of funding
|  |  | UNDP | [6 empty] | 26913.125 | 268967.5 | 178738.25 | 58516.875 | 533135.75
|  |  | TRAC | [5 empty] | UNDP TRAC | 26913.125 | 223967.5 | 178738.25 | 58516.875 | 488135.75
|  |  | Poverty TTF | [5 empty] | UNDP TTF | 0 | 45000 | 0 | 0 | 45000
|  |  | UNIFEM | [6 empty] | 32443.5 | 102812.59 | 96040.87 | 0 | 231296.96
|  |  | pooled | [5 empty] | UNIFEM pooled | 2193.5 | 67529.84 | 55924.62 | 0 | 125647.96
|  |  | parallel | [5 empty] | UNIFEM parallel | 30250 | 35282.75 | 40116.25 | 0 | 105649
|  |  | UNFPA | [5 empty] | UNFPA parallel | 15000 | 13000 | 13000 | 0 | 41000
|  |  | Financing gap | [5 empty] | Unfunded | 5000 | 251000 | 97000 | 56000 | 409000
|  |  | Total secured by UN agencies | [6 empty] | 74356.625 | 384780.09 | 287779.12 | 58516.875 | 805432.71
Inputs required
|  |  | National consultant | [5 empty] | person-months | 9.1 | 146.4 | 79.5 | 3 | 238
|  |  | National consultant | [5 empty] | average no of persons per year | 3.0333 | 12.2 | 6.625 | 0.33333 | 5.5479
|  |  | International consultant | [5 empty] | person-days | 7 | 174 | 110 | 0 | 291
Note on D26: Aceste activităţi au început deja în Republica Moldova prin abonarea la IMF GDDS şi SDDS (cu privire la indicatorii macroeconomici şi financiari) şi introducerea bazei de date DevInfo pentru monitorizarea implementării SCERS-ului şi obiectivelor ODM. Totuşi, metadatele trebuie produse pentru toţi indicatorii pentru a asigura compatibilitatea şi comparabilitatea. Should be checked if this will not be done in the framework of introduction of PC-Axis
Note on D57: Standalone of module for HBS/LFS -- to be recommended during preparation stage
Note on D80: What exactly do we need to do to organize that training? Manuals? Training Costs? Something else?
Note on W94: 5 events x 2 persons x 5 days per year typically
Note on D54: ElenaVatcarau: Eurostat lanseaza aceasta cercetare in 2010, este bine sa lansam cercetarea in aceiasi perioada, dupa aceiasi metodologie