## Main
The Project for Developing Sustainable Agricultural Economy (PDSAE)
Applicable CPD Outcomes: | Outcome 1: Citizen expectations for voice, sustainable development, the rule of law, and accountability are met by stronger systems of democratic governance. | Outcome 1: Citizen expectations for voice, sustainable development, the rule of law, and accountability are met by stronger systems of democratic governance.
| Outcome 2: Growth and development are inclusive, sustainable, increase resilience to climate change and disasters, and contribute to enhanced food, energy and water security and natural resource management. | Outcome 2: Growth and development are inclusive, sustainable, increase resilience to climate change and disasters, and contribute to enhanced food, energy and water security and natural resource management.
Output | Linkage to global outputs | Activity | Sub-activity | Responsible Party | 2021 |  |  | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [9 empty] | Input |  | Budget 2021 | Budget 2022 | Budget 2023 | Budget 2024 | Activity Budget (US$) | Total Budget (US$)
[5 empty] | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Code | Description
Output 1: Strengthen assistance to increase local farmer expertise in agriculture | [48 empty] | 765463
Indicators | Output 3: Addressing the human rights and socio-economic impacts of COVID-19 Output 3.2: Policy and programme interventions to address the developmental impacts of COVID-19 and safeguarding progress towards the SDGs | 1.1 Mainstream & promote Good Agriculture Practices (GAP) on farms under contract with AgroNat. | 1.1.1 TOT for GAP Auditors | MoFMRA | 2022 Jan: x; 2022 Feb: x; Input Code: 71200 | International Consultants |  | 3000 |  |  | 3000 | 80250
|  |  | 1.1.2 Auditor trainings for farm inspections | MoFMRA | 2022 Feb: x; 2022 Mar: x; 2022 Apr: x; 2022 May: x; 2022 Jun: x; Input Code: 75700 | Training, Workshops and Conference |  | 10250 |  |  | 10250
|  |  | 1.1.3 GAP trainings for targeted farmers | MoFMRA | 2022 Jan: x; 2022 Jun: x; 2022 Nov: x; Input Code: 75700 | Training, Workshops and Conference |  | 2700 | 2700 | 2600 | 8000
|  |  | 1.1.4 Field analysis, sample collection and initial testing | MoFMRA | 2022 Jan: x; 2022 Jun: x; 2022 Nov: x; Input Code: 72100 | Contractual Services-Companies |  | 47000 |  |  | 47000
|  |  | 1.1.5 Random inspection trips post-certification | MoFMRA | 2023 Dec: x; 2024 Mar: x; 2024 Jun: x; Input Code: 71600 | Travel |  |  | 2333 | 4666 | 7000
|  |  | 1.1.6 Pomotion of GAP practices and certified products | MoFMRA | 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; 2024 Jan: x; 2024 Feb: x; 2024 Mar: x; 2024 Apr: x; 2024 May: x; 2024 Jun: x; 2024 Jul: x; 2024 Aug: x; Input Code: 74200 | Audio Visual & Print Prod Cost |  |  | 2500 | 2500 | 5000
| Output 3: Addressing the human rights and socio-economic impacts of COVID-19 Output 3.2: Policy and programme interventions to address the developmental impacts of COVID-19 and safeguarding progress towards the SDGs | 1.2 Establish a laboratory facility at HAC for soil testing and plant tissue culture. | 1.2.1 Develop ToR for detail drawings and BoQ | MoFMRA | [44 empty] | 146000 | bar: 2021 Dec to 2022 Jan
|  |  | 1.2.2 Design lab facility and develop BoQ | MoFMRA | 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; Input Code: 72100 | Contractual Services-Companies |  | 10000 |  |  | 10000
|  |  | 1.2.3 Construction of Lab Facility | MoFMRA | 2022 Apr: x; 2022 May: x; 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; Input Code: 72100 | Contractual Services-Companies |  |  | 136000 |  | 136000
|  | 1.3 Enhance capacity building for agricultural expertise and extension offers based in islands. | 1.3.1 Training conductions | MoFMRA | 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; 2024 Jan: x; 2024 Feb: x; 2024 Mar: x; Input Code: 75700 | Training, Workshops and Conference | 10000 |  |  | 10000 | 20000 | 20000
|  | 1.4 Establish and operate a training facility in Laamu Atoll | 1.4.1 Renovation of existing buildings | MoFMRA | 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; Input Code: 72100 | Contractual Services-Companies |  |  | 68000 |  | 68000 | 276713
|  |  | 1.4.2 Connect GAC to the main electric network of Gan island | MoFMRA | 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; 2024 Jan: x; Input Code: 72100 | Contractual Services-Companies |  |  | 150000 |  | 150000
|  |  | 1.4.3 Upgrading classroom into a conference facility | MoFMRA | [9 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [5 empty] | 72100 | Contractual Services-Companies | 25713 | 14000 | 19000 |  | 58713
|  | 1.5 Assist local farmers to adopt innovative and ‘greener’ farming practices. | 1.5.1 Adoption of vertical farming | AgroNat | 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; 2024 Jan: x; 2024 Feb: x; 2024 Mar: x; Input Code: 72100 | Contractual Services-Companies |  |  | 30000 | 37500 | 67500 | 242500
[5 empty] | 2023 Dec: x; 2024 Jan: x; 2024 Feb: x; 2024 Mar: x; 2024 Apr: x; 2024 May: x; 2024 Jun: x; 2024 Jul: x; Input Code: 71600 | Travel |  |  | 1000 | 4250 | 5250
|  |  | 1.5.2 Adopt low-irrigation and dry farming tech | AgroNat | 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; Input Code: 72100 | Contractual Services-Companies |  | 40000 | 27500 |  | 67500
[5 empty] | 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; Input Code: 71600 | Travel |  | 3000 | 2250 |  | 5250
|  |  | 1.5.3 Organic farming promotion | AgroNat | 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; Input Code: 72100 | Contractual Services-Companies |  | 25000 | 15000 |  | 40000
[9 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [10 empty] | 71600 | Travel |  | 4000 | 4000 |  | 8000
|  |  | 1.5.4 Introduction of knowledge exchange and best practices among agricultural businesses | AgroNat | 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; Input Code: 74200 | Audio Visual & Print Prod Cost |  | 5000 | 5500 |  | 10500
[5 empty] | 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; Input Code: 63500(63400) | Learning costs |  | 10000 | 10000 |  | 20000
[5 empty] | 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; Input Code: 71600 | Travel |  | 8500 | 10000 |  | 18500
Output 2: Enhance agricultural capacities and opportunities to ensure food security | [48 empty] | 170971
Indicators |  | 2.1 Scale up and mainstream the urban agricultural incubation programme for young/new generation farmers in the Greater Malé Region. | 2.1.1 Design the urban gardening facility | HDC | 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; Input Code: 72100 | Detail Design(Contractual Services-Companies) |  |  |  |  | 0 | 170971
|  |  | 2.1.2 Development a material procurement timeline and construction timeline | HDC | 2022 Apr: x; 2022 May: x; Input Code: 74100 | Project Management(Professional Services) |  |  |  |  | 0
|  |  | 2.1.3 Design of eligibility criteria for agri-business entrepreneur’s application | HDC | 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; Input Code: 74100 | TOR, Communication Plan(Professional Services) |  |  |  |  | 0
|  |  | 2.1.4 Construction of urban gardening facility (Urban Farming Project) | HDC | 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; Input Code: 72100 | Construction, Material Procurement(Contractual Services-Companies) |  | 111279.7 | 47691.3 |  | 158971
|  |  | 2.1.5 Develop application process, screen and select 36 farmers | HDC | 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; Input Code: 74100 | Announcing and Awarding(Professional Services) |  |  |  |  | 0
|  |  | 2.1.6 Provide training for selected farmers (by HDC horticulturist and greening team) | HDC | 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; Input Code: 71300 | Training, Workshops & Conference(Local Consultants) |  |  | 2000 |  | 2000
|  |  | 2.1.7 Allocate allowance for farmers for 3 months period (allowance to cover utility bills and compost for initial ground preparation) | HDC | 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; Input Code: 72600 | Farmers Stipend (Grants) |  |  | 10000 |  | 10000
|  |  | 2.1.8 Beneficiary impact monitoring | HDC | 2024 Jan: x; 2024 Feb: x; 2024 Mar: x; 2024 Apr: x; 2024 May: x; 2024 Jun: x; 2024 Jul: x; 2024 Aug: x; Input Code: 74100 | Monitoring(Professional Services) |  |  |  |  | 0
Output 3: Enhance support industries and value-added services to augment agro-businesses | [48 empty] | 1197919
Indicators | Output 3: Addressing the human rights and socio-economic impacts of COVID-19 Output 3.1: Meso-, macro- and micro-level socio-economic impact assessments | 3.1 Develop an organic market to sell local produce from the Urban Farming project. | 3.1.1 Design and construction of market place with lots | HDC | 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; 2022 Apr: x; 2022 May: x; 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; Input Code: 72100 | Construction, Material Procurement(Contractual Services-Companies) |  | 74214.7 | 31806.3 |  | 106021 | 116021
|  |  | 3.1.2 Consultancy for the Smart City goals |  | 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; 2022 Apr: x; 2022 May: x; 2022 Jun: x; Input Code: 71300 | App development consultation fee(Local Consultants)) |  | 10000 |  |  | 10000
|  |  | 3.1.3 Introduction and implementation of Smart City goals in Hulhumalé |  | 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; 2023 Dec: x; Input Code: 74100 | Management (Professional Services) |  |  |  |  | 0
|  |  | 3.1.4 Fabrication of pop-up stalls for farmers | [44 empty] | 0 | bar: 2021 Oct to Input Code
| Output 2: Inclusive and integrated multi-sectoral crisis management and response Output 2.3: Community engagement for prevention, response and social cohesion | 3.2 Develop an incubation plan for the agricultural and food and beverages sector centred on the concept of “From Farm to Plate”. | 3.2.1 Development of incubation plan | BCC | 2021 Nov: x; 2021 Dec: x; 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; 2022 Apr: x; 2022 May: x; Input Code: 71300 | Local Consultants |  | 7000 |  |  | 7000 | 156343
|  |  | 3.2.2 Creation of outlets to promote local produce |  | 2022 Apr: x; 2022 May: x; 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; Input Code: 73200 | Premise Alterations |  | 99343 |  |  | 99343
|  |  | 3.2.3 Development of SME rating system |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [11 empty] | 71300 | Local Consultants |  | 24500 | 25500 |  | 50000
|  | 3.3 Create additional support structures to enhance BCC services to the agricultural/food production sectors. | 3.3.1 Creation of CMS system | BCC |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [12 empty] | 71300 | Local Consultants |  | 39200 | 40800 |  | 80000 | 120000
|  |  | 3.3.2 Publication of first volume of SME handbook |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [10 empty] | 72500 | Supplies |  | 20000 |  |  | 20000
|  |  | 3.3.3 Procurement of marketing services for promotion of incubation programme |  | 2022 Mar: x; 2022 Apr: x; 2022 May: x; 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; Input Code: 71300 | Local Consultants |  | 20000 |  |  | 20000
|  | 3.4 Establish an effective, reliable and timely transportation mechanism for agriculture produce from farmers to markets, clients and customers. | 3.4.1 Design consultancy of boat and consultancy for the cold storage and solar power for the vessel | AgroNat |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [11 empty] | 71300 | Local Consultants |  | 10000 | 11000 |  | 21000 | 805555
[5 empty] | 2022 Jan: x; 2022 Feb: x; 2022 Mar: x; 2022 Apr: x; Input Code: 72100 | Contractual Services-Companies |  | 25000 |  |  | 25000
|  |  | 3.4.2 Vessel construction and procurement | AgroNat | 2022 May: x; 2022 Jun: x; 2022 Jul: x; 2022 Aug: x; 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; Input Code: 72100 | Contractual Services-Companies |  | 329555 | 420000 |  | 749555
[5 empty] | 2022 Sep: x; 2022 Oct: x; 2022 Nov: x; 2022 Dec: x; 2023 Jan: x; 2023 Feb: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2023 Jul: x; 2023 Aug: x; 2023 Sep: x; 2023 Oct: x; 2023 Nov: x; Input Code: 71600 | Travel |  | 5000 | 5000 |  | 10000
Project Management | [48 empty] | 386732.44
|  | M&E | M&E costs | UNDP | 2022 Mar: x; 2022 Apr: x; 2022 May: x; 2022 Jun: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2023 Jun: x; 2024 Mar: x; 2024 Apr: x; 2024 May: x; 2024 Jun: x; 2024 Sep: x; 2024 Oct: x; Input Code: 71300 | Local Consultants | 0 | 4000 | 6000 | 10000 | 20000 | 20000
|  | Travel | Travel | UNDP | 2022 May: x; 2022 Jun: x; 2023 Mar: x; 2023 Apr: x; 2024 Mar: x; 2024 Apr: x; Input Code: 71600 | Travel | 0 | 8000 | 8000 | 8000 | 24000 | 24000
|  | Staffing | Staffing | UNDP | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 71400 | Contractual Services - Individuals | 8732.44 | 100000 | 90000 | 90000 | 288732.44 | 288732.44
|  | Administrative | Audit | UNDP | 2021 Oct: x; 2021 Nov: x; 2022 Aug: x; 2022 Sep: x; 2023 Jul: x; 2023 Aug: x; 2024 Aug: x; 2024 Sep: x; 2024 Oct: x; Input Code: 73500 | Reimbursement costs | 3000 | 3000 | 6000 | 6000 | 18000 | 18000
|  |  | Trainings | UNDP | 2022 Mar: x; 2022 Apr: x; 2022 May: x; 2023 Mar: x; 2023 Apr: x; 2023 May: x; 2024 Mar: x; 2024 Apr: x; 2024 May: x; 2024 Oct: x; Input Code: 75700 | Training, Workshops and Conference | 0 | 3000 | 4000 | 4000 | 11000 | 11000
|  |  | IT equipment | UNDP | 2021 Oct: x; 2021 Nov: x; 2023 Dec: x; 2024 Jan: x; Input Code: 72800 | Information Technology Equipment | 0 | 5000 | 5000 | 0 | 10000 | 10000
|  | Communications | Communications | UNDP | 2022 Apr: x; 2022 May: x; 2023 Jan: x; 2023 Feb: x; 2023 Aug: x; 2023 Sep: x; 2024 Mar: x; 2024 Apr: x; 2024 Sep: x; 2024 Oct: x; Input Code: 72100 | Contractual Services - Companies | 0 | 500 | 3000 | 4000 | 7500 | 7500
[5 empty] | 2024 Oct: x; Input Code: 74200 | Audio Visual & Print Prod Costs | 0 | 500 | 3000 | 4000 | 7500 | 7500
[44 empty] | 47445.44 | 1081542.4 | 1204580.6 | 187516
Total Programme Budget | [48 empty] | 2521085.44
GMS (8%) | [48 empty] | 201686.8352
RC Levy (1%) | [48 empty] | 27227.7228
GRAND TOTAL | [48 empty] | 2749999.998
Note on AY20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: previous workplan 1.5 total budget is 242,500/- Reply: @Shadha Hussain but when i check AX column (AX 20 to AX 28) the total is actually 243,500. so its actually 1000 more dho? Reply: yes I also just calculated. maybe sum is removed from one of the columns so not adding up
Note on AU25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shifza Omar amended doc does not breakdown changes to these budget amounts Reply: Shadhu can you please email them on that thread and ask to clear this?
Note on E48: Fizan Ahmed: This one makes more sense to be re-allocated under act. 3.2
Note on AY49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: previous workplan 3.4 total budget is 805,555/-
Note on AU51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shifza Omar budget breakdown missing in amended doc
Note on AT56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budgets for 201-23 adjusted in this line to fit in the RCL.

## Main_AAS
The Project for Developing Sustainable Agricultural Economy (PDSAE)
Applicable CPD Outcomes: | Outcome 1: Citizen expectations for voice, sustainable development, the rule of law, and accountability are met by stronger systems of democratic governance. | Outcome 1: Citizen expectations for voice, sustainable development, the rule of law, and accountability are met by stronger systems of democratic governance.
| Outcome 2: Growth and development are inclusive, sustainable, increase resilience to climate change and disasters, and contribute to enhanced food, energy and water security and natural resource management. | Outcome 2: Growth and development are inclusive, sustainable, increase resilience to climate change and disasters, and contribute to enhanced food, energy and water security and natural resource management.
Output | Linkage to global outputs | Activity | Sub-activity | Responsible Party | 2021 | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | Input |  | Budget 2021 | Budget 2022 | Budget 2023 | Budget 2024 | Activity Budget (US$) | Total Budget (US$)
[5 empty] | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Code | Description
Output 1: Strengthen assistance to increase local farmer expertise in agriculture | [19 empty] | 0 | 182450 | 521497 | 61516 | 765463 | 765463
Indicators | Output 3: Addressing the human rights and socio-economic impacts of COVID-19 Output 3.2: Policy and programme interventions to address the developmental impacts of COVID-19 and safeguarding progress towards the SDGs | 1.1 Mainstream & promote Good Agriculture Practices (GAP) on farms under contract with AgroNat. | 1.1.1 TOT for GAP Auditors | MoFMRA | [13 empty] | 71200 | International Consultants |  | 3000 |  |  | 3000 | 80250
|  |  | 1.1.2 Auditor trainings for farm inspections | MoFMRA |  | x | x | [10 empty] | 75700 | Training, Workshops and Conference |  | 10250 |  |  | 10250
|  |  | 1.1.3 GAP trainings for targeted farmers | MoFMRA |  |  | x | [10 empty] | 75700 | Training, Workshops and Conference |  | 2700 | 2700 | 2600 | 8000
|  |  | 1.1.4 Field analysis, sample collection and initial testing | MoFMRA |  |  | x | [10 empty] | 72100 | Contractual Services-Companies |  | 47000 |  |  | 47000
|  |  | 1.1.5 Random inspection trips post-certification | MoFMRA | [8 empty] | x | x | x |  |  | 71600 | Travel |  |  | 2333 | 4666 | 7000
|  |  | 1.1.6 Pomotion of GAP practices and certified products | MoFMRA | [5 empty] | x | x | x | x | x | x | x |  | 74200 | Audio Visual & Print Prod Cost |  |  | 2500 | 2500 | 5000
| Output 3: Addressing the human rights and socio-economic impacts of COVID-19 Output 3.2: Policy and programme interventions to address the developmental impacts of COVID-19 and safeguarding progress towards the SDGs | 1.2 Establish a laboratory facility at HAC for soil testing and plant tissue culture. | 1.2.1 Develop ToR for detail drawings and BoQ | MoFMRA | x | [19 empty] | 146000
|  |  | 1.2.2 Design lab facility and develop BoQ | MoFMRA |  | x | [11 empty] | 72100 | Contractual Services-Companies |  | 10000 |  |  | 10000
|  |  | 1.2.3 Construction of Lab Facility | MoFMRA |  |  | x | x | x | x | x | x | [5 empty] | 72100 | Contractual Services-Companies |  |  | 136000 |  | 136000
|  | 1.3 Enhance capacity building for agricultural expertise and extension offers based in islands. | 1.3.1 Training conductions | MoFMRA |  |  |  | x | x |  |  |  | x | x |  |  |  | 75700 | Training, Workshops and Conference |  |  | 10000 | 10000 | 20000 | 20000
|  | 1.4 Establish and operate a training facility in Laamu Atoll | 1.4.1 Renovation of existing buildings | MoFMRA | [5 empty] | x | x | x | [5 empty] | 72100 | Contractual Services-Companies |  |  | 68000 |  | 68000 | 276713
|  |  | 1.4.2 Connect GAC to the main electric network of Gan island | MoFMRA | [5 empty] | x | x | x | x |  |  |  |  | 72100 | Contractual Services-Companies |  |  | 150000 |  | 150000
|  |  | 1.4.3 Upgrading classroom into a conference facility | MoFMRA |  |  |  | x | x | x | x | x | x | x | x |  |  | 72100 | Contractual Services-Companies |  | 14000 | 44714 |  | 58713
|  | 1.5 Assist local farmers to adopt innovative and ‘greener’ farming practices. | 1.5.1 Adoption of vertical farming | AgroNat | [7 empty] | x | x | x |  |  |  | 72100 | Contractual Services-Companies |  |  | 30000 | 37500 | 67500 | 242500
[13 empty] | x | x | x | x |  | 71600 | Travel |  |  | 1000 | 4250 | 5250
|  |  | 1.5.2 Adopt low-irrigation and dry farming tech | AgroNat |  |  | x | x | x | x | [7 empty] | 72100 | Contractual Services-Companies |  | 40000 | 27500 |  | 67500
[8 empty] | x | x | x | x | x | x |  |  |  |  | 71600 | Travel |  | 3000 | 2250 |  | 5250
|  |  | 1.5.3 Organic farming promotion | AgroNat |  |  |  | x | x | x | [7 empty] | 72100 | Contractual Services-Companies |  | 25000 | 15000 |  | 40000
[6 empty] | x | x | x | x | x | x | x | x |  |  |  |  | 71600 | Travel |  | 4000 | 4000 |  | 8000
|  |  | 1.5.4 Introduction of knowledge exchange and best practices among agricultural businesses | AgroNat |  |  |  | x | x | x | x | [6 empty] | 74200 | Audio Visual & Print Prod Cost |  | 5000 | 5500 |  | 10500
[9 empty] | x | x | x | [6 empty] | 63500(63400) | Learning costs |  | 10000 | 10000 |  | 20000
[8 empty] | x | x | x | x | x | x |  |  |  |  | 71600 | Travel |  | 8500 | 10000 |  | 18500
Output 2: Enhance agricultural capacities and opportunities to ensure food security | [19 empty] | 0 | 111279.7 | 59691.3 | 0 | 170971 | 170971
Indicators |  | 2.1 Scale up and mainstream the urban agricultural incubation programme for young/new generation farmers in the Greater Malé Region. | 2.1.1 Design the urban gardening facility | HDC |  | x | [11 empty] | 72100 | Detail Design(Contractual Services-Companies) |  |  |  |  | 0 | 170971
|  |  | 2.1.2 Development a material procurement timeline and construction timeline | HDC |  |  | x | [10 empty] | 74100 | Project Management(Professional Services) |  |  |  |  | 0
|  |  | 2.1.3 Design of eligibility criteria for agri-business entrepreneur’s application | HDC |  | x | [11 empty] | 74100 | TOR, Communication Plan(Professional Services) |  |  |  |  | 0
|  |  | 2.1.4 Construction of urban gardening facility (Urban Farming Project) | HDC |  |  | x | x | x | x | x | [6 empty] | 72100 | Construction, Material Procurement(Contractual Services-Companies) |  | 111279.7 | 47691.3 |  | 158971
|  |  | 2.1.5 Develop application process, screen and select 36 farmers | HDC |  |  |  | x | x | x | [7 empty] | 74100 | Announcing and Awarding(Professional Services) |  |  |  |  | 0
|  |  | 2.1.6 Provide training for selected farmers (by HDC horticulturist and greening team) | HDC | [7 empty] | x | [5 empty] | 71300 | Training, Workshops & Conference(Local Consultants) |  |  | 2000 |  | 2000
|  |  | 2.1.7 Allocate allowance for farmers for 3 months period (allowance to cover utility bills and compost for initial ground preparation) | HDC | [8 empty] | x |  |  |  |  | 72600 | Farmers Stipend (Grants) |  |  | 10000 |  | 10000
|  |  | 2.1.8 Beneficiary impact monitoring | HDC | [9 empty] | x | x | x |  | 74100 | Monitoring(Professional Services) |  |  |  |  | 0
Output 3: Enhance support industries and value-added services to augment agro-businesses | [19 empty] | 0 | 663812.7 | 534106.3 | 0 | 1197919 | 1197919
Indicators | Output 3: Addressing the human rights and socio-economic impacts of COVID-19 Output 3.1: Meso-, macro- and micro-level socio-economic impact assessments | 3.1 Develop an organic market to sell local produce from the Urban Farming project. | 3.1.1 Design and construction of market place with lots | HDC |  | x | x | x | x | x | x | [6 empty] | 72100 | Construction, Material Procurement(Contractual Services-Companies) |  | 74214.7 | 31806.3 |  | 106021 | 116021
|  |  | 3.1.2 Consultancy for the Smart City goals |  |  | x | x | [10 empty] | 71300 | App development consultation fee(Local Consultants)) |  | 10000 |  |  | 10000
|  |  | 3.1.3 Introduction and implementation of Smart City goals in Hulhumalé | [6 empty] | x | x | x | x |  |  |  |  | 74100 | Management (Professional Services) |  |  |  |  | 0
| Output 2: Inclusive and integrated multi-sectoral crisis management and response Output 2.3: Community engagement for prevention, response and social cohesion | 3.2 Develop an incubation plan for the agricultural and food and beverages sector centred on the concept of “From Farm to Plate”. | 3.2.1 Development of incubation plan | BCC | x | x | x | [10 empty] | 71300 | Local Consultants |  | 7000 |  |  | 7000 | 156343
|  |  | 3.2.2 Creation of outlets to promote local produce |  |  |  | x | x | x | x | x | [6 empty] | 73200 | Premise Alterations |  | 99343 |  |  | 99343
|  |  | 3.2.3 Development of SME rating system |  |  | x | x | x | x | x | x | x | x |  |  |  |  | 71300 | Local Consultants |  | 24500 | 25500 |  | 50000
|  | 3.3 Create additional support structures to enhance BCC services to the agricultural/food production sectors. | 3.3.1 Creation of CMS system | BCC | x | x | x | x | x | x | x | x | [5 empty] | 71300 | Local Consultants |  | 39200 | 40800 |  | 80000 | 120000
|  |  | 3.3.2 Publication of first volume of SME handbook |  |  | x | x | x | x | x | x | x | x |  |  |  |  | 72500 | Supplies |  | 20000 |  |  | 20000
|  |  | 3.3.3 Procurement of marketing services for promotion of incubation programme |  |  | x | x | x | x | [8 empty] | 71300 | Local Consultants |  | 20000 |  |  | 20000
|  | 3.4 Establish an effective, reliable and timely transportation mechanism for agriculture produce from farmers to markets, clients and customers. | 3.4.1 Design consultancy of boat and consultancy for the cold storage and solar power for the vessel | AgroNat | x | x | x | x | x | x | x | x | x |  |  |  |  | 71300 | Local Consultants |  | 10000 | 11000 |  | 21000 | 805555
[6 empty] | x | x | [10 empty] | 72100 | Contractual Services-Companies |  | 25000 |  |  | 25000
|  |  | 3.4.2 Vessel construction and procurement | AgroNat |  |  | x | x | x | x | x | x | x |  |  |  |  | 72100 | Contractual Services-Companies |  | 329555 | 420000 |  | 749555
[8 empty] | x | x | x | x | x | x |  |  |  |  | 71600 | Travel |  | 5000 | 5000 |  | 10000
Project Management | [19 empty] | 0 | 124000 | 136732.44 | 126000 | 386732.44 | 386732.44
|  | M&E | M&E costs | UNDP |  | x | x |  |  | x | x |  |  | x | x | x | x | 71300 | Local Consultants | 0 | 4000 | 6000 | 10000 | 20000 | 20000
|  | Travel | Travel | UNDP |  |  | x |  |  | x | x |  |  | x | x |  |  | 71600 | Travel | 0 | 8000 | 8000 | 8000 | 24000 | 24000
|  | Staffing | Staffing | UNDP | x | x | x | x | x | x | x | x | x | x | x | x | x | 71400 | Contractual Services - Individuals | 0 | 100000 | 98732.44 | 90000 | 288732.44 | 288732.44
|  | Administrative | Audit | UNDP |  |  |  | x |  |  |  | x |  |  |  | x | x | 73500 | Reimbursement costs | 0 | 3000 | 9000 | 6000 | 18000 | 18000
|  |  | Trainings | UNDP |  | x | x |  |  | x | x |  |  | x | x |  | x | 75700 | Training, Workshops and Conference | 0 | 3000 | 4000 | 4000 | 11000 | 11000
|  |  | IT equipment | UNDP | [8 empty] | x |  |  |  |  | 72800 | Information Technology Equipment | 0 | 5000 | 5000 | 0 | 10000 | 10000
|  | Communications | Communications | UNDP |  |  | x |  |  | x |  | x |  | x |  | x | x | 72100 | Contractual Services - Companies | 0 | 500 | 3000 | 4000 | 7500 | 7500
[18 empty] | 74200 | Audio Visual & Print Prod Costs | 0 | 500 | 3000 | 4000 | 7500 | 7500
Total Programme Budget | [19 empty] | 0 | 1081542.4 | 1252027.04 | 187516 | 2521085.44 | 2521085.44
GMS (8%) | [19 empty] | 0 | 86523.39 | 100162.08 | 15001.37 | 201686.84 | 201686.84
Total Atlas budget | [19 empty] | 0 | 1168065.79 | 1352189.12 | 202517.37 | 2722772.28 | 2722772.28
RC Levy (1%) | [24 empty] | 27227.7228
GRAND TOTAL | [24 empty] | 2750000.0028
Note on AA20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: previous workplan 1.5 total budget is 242,500/- Reply: @Shadha Hussain but when i check AX column (AX 20 to AX 28) the total is actually 243,500. so its actually 1000 more dho? Reply: yes I also just calculated. maybe sum is removed from one of the columns so not adding up
Note on W25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shifza Omar amended doc does not breakdown changes to these budget amounts Reply: Shadhu can you please email them on that thread and ask to clear this?
Note on E47: Fizan Ahmed: This one makes more sense to be re-allocated under act. 3.2
Note on AA48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: previous workplan 3.4 total budget is 805,555/-
Note on V55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budgets for 201-23 adjusted in this line to fit in the RCL.