United Nations Development Programme

PROJECT DOCUMENT

| Project title: Third National Communication and First Biennial Update Report to the United Nations Framework Convention on Climate Change (UNFCCC) |
| --- |
| Country: Republic of Marshall Islands (RMI) | Implementing Partner: Office of Environmental Planning & Policy Coordination (OEPPC) | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF/Country Programme Outcome: Outcome 1.1: National, local and community capacities to effectively plan and implement enhanced natural resource management, biodiversity conservation, climate change adaptation and mitigation, and disaster risk reduction are strengthened |
| UNDP Strategic Plan Output: 1.4 Scaled up action on climate change adaptation and mitigation across sectors which is funded and implemented |
| UNDP Social and Environmental Screening Category: Low | UNDP Gender Marker: GEN1 |
| Atlas Project ID/Award ID number: this should have been created at PIF stage | Atlas Output ID/Project ID number: this should be created before CEO endorsement |
| UNDP-GEF PIMS ID number: 6272 | GEF ID number: 10231 |
| Planned start date: XXXX | Planned end date: XXXX |
| LPAC date: XXXX |
| Brief project description: The enabling activity aims to assist RMI in meeting reporting requirements under the UNFCCC Convention in accordance with its commitments as a non-Annex 1 Party (as mandated by Article 4 and 12 of this Convention and COP 16 and 17 decisions), and to strengthen the technical and institutional capacity of RMI to prepare and submit its TNC and first BUR to the UNFCCC. The TNC will update the information provided regarding national circumstances, inventories of greenhouse gases, policies and measures undertaken to mitigate climate change, assessments of vulnerability to climate change and steps taken to adapt, and information on public awareness, education, training, systematic research and observation, and technology transfer. The BUR component of the project will focus on GHG inventory for 2016; mitigation actions/measures; constraints and gaps related to financial, technical and capacity and support needs and BUR support received and needed. The project will also increase the national technical and institutional capacities in preparing the NC/BUR and assisting the Government to integrate climate change issues into sectoral and national development priorities. |
| Financing Plan |
| GEF Trust Fund or LDCF or SCCF or other vertical fund | USD 852,000 |
| UNDP TRAC resources | Not applicable |
| Cash co-financing to be administered by UNDP | Not applicable |
| Total Budget administered by UNDP | USD852,000 |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |
| UNDP | Not applicable |
| Government | USD40,000 (in-kind) |
| Total co-financing | USD100,000 |
| Grand-Total Project Financing (1)+(2) | USD952,000 |
| Signatures |
| Signature: Clarence Samuel Director, GEF Operational Focal Point | Agreed by Government Implementing Partner | Date/Month/Year: |
| Signature: Mr. Bakhodir Burkhanov, Country Director, UNDP Pacific Office in Fiji | Agreed by UNDP | Date/Month/Year: |

Contents

I.	Situation analysis	4

II.	Strategy	6

III.	Project Results Framework:	16

IV.	Total budget and work plan	25

V.	Indicative Work Plan	29

VI.	Management Arrangements	33

VII.	Monitoring Framework and Evaluation	35

VIII.	Legal Context	38

IX.	Annexes	38

ANNEX I. Risks and Mitigation Measures for the TNC-BUR Project	38

ANNEX II. Terms of Reference for Key Project Personnel	39

ANNEX III. Letter of agreement between UNDP and Government of Republic of Marshall Islands (RMI) for the provision of support services	50

ANNEX IV.  Social and Environmental Screening Template	54

ANNEX V. Final Report Of RMI National Communication / Biennial Update Report Project	62

# Situation analysis

Republic of Marshall Islands (RMI) ratified the UNFCCC Convention as a non-annex I Party in 1992 and the Kyoto Protocol in 2003. In accordance with the relevant provisions of the Convention, the Government of RMI developed and submitted its First National Communication in 2000 (1NC), Second National Communication (SNC) in 2015. The Government of RMI submitted its Intended Nationally Determined Contributions (INDCs) in line with COP 19 on 21st July 2015. RMI also ratified the Paris Agreement (PA) on 22nd April 2016.

RMI’s NDC was created through a collaborative process that engaged all relevant local stakeholders, including through a National Climate Change Dialogue held in September 2014. Identified priority sectors for action included the energy (such as electricity generation), transport (land and shipping), waste, and other (cooking and lighting). Although RMI’s NDC largely identified mitigation actions, it also stressed its focus on adaptation, specifically to safeguard security and human rights while advancing its development aspirations. RMI’s NDC has an economy-wide (excluding land use, land use change, and forestry) target to reduce greenhouse gas (GHG) emissions by 32 percent below 2010 levels by 2025. The NDC also provides an indicative target to reduce GHG emissions by 45 percent below 2010 levels by 2030. The targets put the Marshall Islands on a trajectory to nearly halving the GHG emissions between 2010 and 2030, with a longer-term view to achieving net zero GHG emissions by 2050, or earlier if possible.

RMI contributes less than 0.00001 percent of the global emissions (1.94 tons per capita in 2016).  The country is heavily dependent on external support for financing, fuel, and other imported goods. The services sector dominates the Marshallese economy, contributing around 85 percent to national GDP (which includes remittances, among others), followed by industry (9.9 percent) and agriculture (4.4 percent) (2013).

The sectors that contribute the highest emissions are electricity generation (roughly 54 percent), waste (roughly 23 percent), and land and sea transport (roughly 12 percent). In the electricity generation and transport sectors, carbon dioxide emissions are a result of the combustion of imported fossil fuels, ranging from diesel for electricity generation to diesel and gasoline for transport. In addition, kerosene is used for lighting on the outer islands, and LPG, butane, and kerosene are widely used for cooking.

RMI is extremely vulnerable to the impacts of climate change given that it has no major points of elevation above two meters. As a low-lying nation, the country already experiences frequent and serious extreme weather and natural hazard events that include sea-level rise, sea surges causing inundation (king tides) floods, and droughts. These events threaten public health, water, coastal zones, and marine resources.

RMI faces several major challenges that will impede progress on climate mitigation and adaptation goals if not properly addressed. These challenges include: country’s dependence on external sources of financing and resources for most of its economic activity; constrained ability to attract external investment due to its market context (small size and relatively expensive infrastructure); dependence on imported petroleum products, which satisfy 90 percent of energy needs; weak and limited access to financial services; undeveloped infrastructure and limited capacity.

The Government charted the Vision 2018 as the first segment of the Government’s Strategic Development Plan Framework 2003-2018.  It provides a sound basis for future economic resource and self-sufficiency including sustainable growth in consistent with the Sustainable and Millennium Development Goals and now the S.A.M.O.A (Small Island Developing States Accelerated Modalities of Action) Pathway.

The Office of Environmental Planning and Policy Coordination (OEPPC) is the national operational climate change focal point for RMI.  The Ministry of Foreign Affairs as the political focal point for all climate and disaster related matters of national concern.    OEPPC acts as the chair and secretariat to the National Climate Change Committee (NCCC) established as part of rolling out activities of the 2011 National Climate Change Policy Framework.

RMI’s development targets are outlined in the National Strategic Plan (NSP), the country’s roadmap for development and progress focused on the medium term (2015-2017). The plan is designed to sync with the country’s national planning and budgeting cycle. The NSP’s objective is to improve the quality of life of the Marshallese through five priority areas of Social development; Environment, climate change, and resiliency; Infrastructure development; Sustainable economic development and Good governance.

There are several ongoing and forward-looking documents, agreements, and policies, the implementation of which will contribute to the Marshall Islands’ NDC and climate and sustainable development goals. The National Energy Policy (NEP) (2014) which aims to improve the quality of life through clean, reliable, affordable, and accessible sustainable energy services; National Climate Change Roadmap which sets out the Government of RMI’s commitments and responsibilities to address climate change;

National Climate Change Policy Framework (NCCPF) which identify priority areas for urgent response which include infrastructure to protect from sea-level rise, sea surges, typhoons and rainfall intensity; water and food security issues from changing rainfall patterns and ocean acidification; health issues from rising temperatures and prolonged drought periods; potential increasing peak wind speeds; and changes to ocean circulation patterns.

Joint National Action Plan (JNAP) for Climate Change Adaptation sets goals to establish and support an enabling environment for the improved coordination of disaster risk management and climate change adaptation; enhancing emergency preparedness and response; improving energy security and working toward a low-carbon emissions future; enhancing local livelihoods and resilience for the Marshallese people; and considering climate change and disaster risk in development planning. The Disaster Risk Management National Action Plan (DRM NAP) outlines actions to adapt to the effects of natural disasters. RMI’s broader adaptation strategy is to further enhance and develop its existing adaptation frameworks for disaster risk management strategies, considering legal and regulatory measures to support these approaches.

The 2050 Climate Strategy, Tile Til Eo (Lighting the way), published in 2018, which is RMI’s long-term low greenhouse gas emission climate-resilient development strategy under the Paris Agreement outlines a long-term pathway for RMI to achieve its objectives for net zero emissions and 100% renewable energy, as well as to facilitate adaptation and climate resilience in a way that ensures the future protection and prosperity of the country and its women, men and youth. A national NDC committee, called the Til E Til Eo Committee has also been established comprised of people across the Government and ensures that near-term action is consistent with a longer-term strategy.

RMI has also developed an Electricity Roadmap (launched during CoP 24 in Katowice, Poland) funded by New Zealand Government, that connects the country’s short-term energy sector investment plans with its high-level 2050 Strategy. The Roadmap focus on the electricity sector and potential electrification of the transport sector to map a pathway to the 2030 NDC target. The Roadmap presents well thought out, costed, technically sound pathways for the electricity sector to help achieve the Marshall Islands’ ambitious climate change targets for 2025, 2030 and to have net zero emissions by 2050 or sooner. The Roadmap also intends to provide a coordination framework for development partners to ensure their investment is effective and avoids duplication, while also developing strategies for capacity building and long-term financing for the sector. The European Union is also providing additional support regarding RMI’s energy policy.

RMI is committed to the strongest possible efforts in safeguarding security and human rights, as well as advancing development aspirations, in light of projected climate impacts and risks. RMI has no choice but to implement urgent measures to build resilience, improve disaster risk preparedness and response, and adapt to the increasingly serious adverse impacts of climate change. RMI commits to further developing and enhancing the existing adaptation framework to build upon integrated disaster risk management strategies, including through development and implement of a national adaptation plan (and further integration into strategic development planning tools), protecting traditional culture and ecosystem resources, ensuring climate-resilient public infrastructure and pursuing facilitative, stakeholder-driven methods to increase resiliency of privately-owned structures and resources. RMI seeks to consider, as appropriate, the legal and regulatory means to best support these approaches.

The Marshall Islands has established strong internal political support for its climate plans, but faces two specific key challenges. First, the Government’s human capacity and technical resources are extremely limited. The country, therefore, needs support to procure technical expertise and supplementary capacity, while taking a long-term approach to capacity building within the Marshallese Government sectors that are responsible for leading implementation on areas with more complex technical dimensions. Second, the Government will need to develop more detailed implementation plans as well as a long-term strategy for the Marshall Islands, including for adaptation.

Climate change is a cross-cutting development issue that affects every aspect of the Marshallese way of life, and it is imperative for RMI to collectively build and strengthen its drive to a low-carbon economy and resilience to climate change impacts. RMI looks to regional and global cooperation for support in pursuit of these mitigation and adaptation-related development priorities.

RMI as a party to the UNFCCC is keen to be part of the global efforts in addressing climate change and intends to fulfil reporting requirements under the convention which includes the Third National Communications (TNC) and the Biennial Update Report (BUR). RMI requests support from Global Environmental Facility (GEF) needed in order to continue with development and consolidation of technical and institutional capacities and with efforts to integrate climate change into national policies, plans and programs. RMI’s TNC and first Biennial Update Report (BUR) will provide an update of the last national communication submitted to the UNFCCC and will be based on findings and recommendations from the Second National Communication. This includes:

- Establish a system and a more detailed database to update all activity data required for the GHG inventory on an annual basis to speed up the inventory process and allow for annual monitoring of GHG emissions in the sectors.

- Reduce the amount of fossil fuel imports through the provision of affordable and environmentally sound technologies, as well as the implementation of energy efficiency and conservation measures.

- Mainstream the GHG inventory as an annual activity to allow regular monitoring of emissions and allow accurate and meaningful measurement of progress made in GHG abatement efforts.

- Focus on capacity assessment and development at the individual, organizational and societal levels before the implementation of technologies and projects.

- Strengthened Legal and Regulatory Frameworks for low carbon development sustainable energy technology.

- Difficulties retaining capacity and expertise developed during the preparation of previous National Communications are leading to draining of resources.

- a lack of mechanisms to monitor and evaluate the progress towards climate change resilience.

- a lack of human capacity as a key obstacle to RMI’s effective access and management of climate change resources.

- ensure that gender sensitivity and disability inclusiveness is addressed in its climate change programmes, projects and activities.

# Strategy

The project activity aims to assist RMI in meeting reporting requirements under the UNFCCC Convention in accordance with its commitments as a non-Annex 1 Party (as mandated by Article 4 and 12 of this Convention and COP 16 and 17 decisions), and to strengthen the technical and institutional capacity of RMI to prepare and submit its TNC and first BUR to the UNFCCC.

The project is prepared in line with GEF-7 strategic focal area on climate change mitigation, objective CCM3 on fostering enabling conditions to mainstream mitigation concerns into sustainable development strategies. In particular, Program 5 of this objective aims to mainstream the integration of climate considerations into the national planning process and to help countries mainstream mitigation action in support of the 2030 Agenda for Sustainable Development and SDGs.

The Third NC and BUR will build on the gap/constraints findings and recommendations of previous National Communications and BUR work, as well as the outcomes of the ongoing complementary projects in the country and is planned to be submitted to the UNFCCC in the last half of 2020 (BUR) and 2022 (TNC).

The main related gap/constraints, findings and recommendations are the following:

GHG Inventory

The main gaps and constraints are:

- Lack of data in most of the categories of the inventory;

- Data uncertainty and inconsistency, across all the sectors;

- Insufficient technical and human capacity for addressing the impact of climate change on different sectors,

- Insufficient financial resources.

- In order to improve uncertainty for GHG emissions, it is necessary to:

- Revise the activity data;

- Calculate national emission factors;

- Change the calculation methodology to multiple Tier, i.e. do an estimate of measurement uncertainty by also using Tier 2 methodology;

- Continue applying and working in accordance with quality assurance and quality control practices (QA/QC).

Vulnerability and Adaptation:

The main gaps and constraints:

- Lack of an adequate strategic framework, lack of expert and scientific research, lack of data;

- Lack of technical and scientific research on the vulnerability of key sectors to climate change;

- Lack of confidence in global end regional climate models;

- Insufficient technical and human capacity and financial resources.

In order to improve vulnerability assessment and the drafting of adaptation measures, it is necessary to:

- Strengthen data collection for extreme weather and hydrology events;

- Strengthen support for scientific-research work and to improve inter-institutional cooperation;

- Establish databases per sector and to secure their regular updating,

- Encourage the drafting of studies, analyses, projections of the impact of climate change on priority adaptation sectors for implementation of adaptation measures.

Mitigation:

The main gaps and constraints:

- Develop appropriate strategic framework (action plan) that will define roles, responsibilities and activities to mitigate the impact of climate change;

- Integrate mitigation measures into strategic documents;

- Define goals for the reduction of GHG emissions - overall and per sector;

- Analyse possibilities for and develop NAMA projects;

- Introduce and promote the best available techniques for mitigation measures regarding climate change, especially in the energy sector.

In order to improve the analyses of GHG abatement measures and assess their impact, it is necessary to:

- Develop plans of emission reductions per sector;

- Build institutional capacities for the application of methods and models for assessing the impacts of measures, formulating and prioritizing programs and measures and evaluating the cost of measures aimed at reducing GHG emissions.

The expected outcomes and associated key outputs and activities are:

- Review and update of the national circumstances and institutional arrangements pertinent to preparation of the national communications and biennial update reports.

- Information on national circumstances concerning the physical (geography, topography and climate) and socio-economic (economy, education, population, health, livelihoods) characteristics of the country and how these might affect the way in which RMI deals with climate change and sustainable development issues in the long term is currently being developed. The preparation of the third national communication will strengthen the linkages and facilitate better understanding of the nexus between climate change and development. This will involve analyses of policies and plans that are currently being pursued by RMI and their relevance in dealing with climate change issues and concerns.

- Coordination, cooperation and synergy between the key stakeholders in developing actions and strategies to cope with the impacts of climate change are crucial for the sustainability of project implementation. It is envisaged that the preparation of the various components of the TNC/FBUR will help strengthen and where appropriate, build synergies among and between activities. The project management team will include a strong institutional arrangement under which many of the activities/tasks will be carried out in the preparation of the third national communication.

- Gender analysis including community level stakeholder consultations (as appropriate) particularly with a gender and social inclusion element focusing on women and marginalized groups in the community.

- The guidance on gender integration through the NCs and BURs developed by the Global Support Programme through UNDP and in collaboration with UNEP and GEF, will be applied during project implementation (http://www.un-gsp.org/news/gender-responsive-national-communications-toolkit).

- The Third National Greenhouse Gases Inventory (GHGI) and the report for period 2010 to 2017 (TNC) and 2016 (FBUR).

- Collation of data for the six key thematic sectors (Energy, Industrial Processes, Solvent and other Product Use, Agriculture, Land-Use, Land-Use Change and Forestry and Waste).

- Carrying out greenhouse gas emission calculation for the six key thematic areas of emissions (Energy, Industrial Processes, Solvent and other Product Use, Agriculture, Land-Use, Land-Use Change and Forestry and Waste) for period 2010 to 2017 (TNC) and 2016 (FBUR).

- Development of the chapter on GHG Inventory as part of the TNC and 2016 as part of FBUR.

- A National Inventory Report (NIR) which includes: the procedures and arrangements undertaken to collect and achieve the data and information; anthropogenic emissions by sources (GHG Inventory); the level of uncertainty associated with inventory data, their underlying assumptions, and the methodologies used for estimating these uncertainties; summary of all activities and consultations undertaken; recommendations for integrating GHG activities with other sustainable development initiatives; recommendations for mainstreaming the GHG inventory process; and recommendations for addressing technological and capacity needs.

- Many of the problems relating to the preparation of national greenhouse gas inventory are lack of quality data and its associated problems of access, availability, management and retrieval systems; lack of expertise and capabilities to undertake inventory work and the lack of technical, financial, human and institutional capacities to carry out inventory work on a continuous basis. Therefore, a good capacity building and training of personnel and institutions is necessarily critical in order to ensure high quality inventories.

- Training and capacity building is required in data collection, analysis, archiving and management, and the use and applications of geographic information systems and remote sensing techniques as they relate to estimations of emissions and removals from land use change and forestry sector. Identification of key source categories of emissions is considered important in determining resource allocations in GHG inventories and therefore training is needed in this area as well as on the use 2006 IPCC guidelines on national greenhouse gas inventories, the IPCC good practice guidance on the National GHG inventories and Uncertainty Management and the IPCC Good Practice Guidance on Land use, land-use change and forestry.

- Completed vulnerability study including recommended adaptation measures for identified vulnerable sectors.

- Elaborating the climatic scenario for RMI including past, present and projection for the future.

- Confirmation of identified vulnerable sectors in RMI based on the latest assessment and studies.

- Description of current vulnerability and adaptation efforts; future risks including national/sectoral adaptation policies, strategies and measures.

- Identified potential adaptation actions for priority sectors including opportunities and barriers.

- Adaptation and disaster risk reduction action must be integrated into development and traditional livelihoods, rather than being seen as a stand-alone activity. Adaptation is achieved through a suite of actions that can be integrated into activities across industry sectors and implementing agencies.

- Experience shows that successful adaptation action in RMI requires collective approaches and co-implementation while also recognizing and building on existing valuable indigenous and traditional knowledge. It is essential that activities are coordinated among multiple partners. These can include national government agencies, provincial governments, traditional leaders, CSOs, private sector, development partners and academic institutions.

- Gender analysis with V & A perspective including community level stakeholder consultations (as appropriate) particularly with a gender and social inclusion element focusing on women and marginalized groups in the community.

- The guidance on gender integration through the NCs and BURs developed by the Global Support Programme through UNDP and in collaboration with UNEP and GEF, will be applied during project implementation (http://www.un-gsp.org/news/gender-responsive-national-communications-toolkit).

- Mitigation assessment of sectors, actions and projects that could be included in the national emission reduction strategy.

- Identification of all potential mitigation options for each sector listed in the GHG inventory; and prioritization of mitigation options for each sector and categorize as long, medium and short term priorities.

- Development of Mitigation Scenarios (Emission Forecast) based on the available data from the GHG inventory, as well as socio-economic information, prepares a series of mitigation scenarios to 2050. This will include a baseline scenario, whereby current trends continue, as well as at least two other scenarios showing how emissions may decrease if mitigation actions are taken.

- Preparation of brief mitigation project profiles for existing and possible future implementation. These profiles could include the following: brief overview of existing and proposed mitigation activities; estimated implementation costs; estimated mitigation potential; and arrangements for project coordination.

- Training and capacity building is required in the use of appropriate technologies, methodologies and tools for assessment of mitigations options and development of mitigation scenarios particularly in sectors with significant mitigation potential.

- Gender analysis with mitigation perspective including community level stakeholder consultations (as appropriate) particularly with a gender and social inclusion element focusing on women and marginalized groups in the community.

- The guidance on gender integration through the NCs and BURs developed by the Global Support Programme through UNDP and in collaboration with UNEP and GEF, will be applied during project implementation (http://www.un-gsp.org/news/gender-responsive-national-communications-toolkit).

- Domestic Measurement, Reporting and Verification (MRV)

- Development of Measurement, Reporting and Verification (MRV) to track the achievements resulting from the identified mitigation interventions which include baseline setting, development of monitoring Plan, identification of key Monitoring parameters and monitoring methodology and development of verification procedures

- Updated assessment of the financial and technological assistance received and capacities building needs.

- Activities related to strengthening of the capabilities and expertise of RMI to contribute to, and participate in, research and systematic observation, data collection and processing, archiving, analysis and dissemination identified and documented.

- Gender analysis with capacity building perspective including community level stakeholder consultations (as appropriate)

- Capacity-building is regarded as a key issue in all areas of work relating to the preparation of national communication. Elaboration on resources provided for capacity building including details on collaboration and synergy existing between the various Convention processes as they relate to capacity building and technology transfer.

- An assessment of training and awareness-raising activities carried out on climate change issues at the community and national level. (at least 30% of the stakeholders are women).

- Study on the needs and constraints relating to financial, technical and capacity gaps with the assistance of bilateral and multilateral organizations.

- Other information relevant for the preparation of FBUR and TNC

- Activities on Research and Systematic Observation such as improvement in data collection, analysis and management; trend analysis on temperature and rainfall data; analysis of the impact of climate change on the frequency of extreme climatic events including El Niño and analysis of rainfall under future climate change scenarios, current climate variability including tropical cyclones and ENSO.

- Information on efforts towards creating “Education, training and public awareness” on climate change through preparation and dissemination of outreach materials ((leaflets, booklets, calendars, posters, quarterly newsletters, videos etc.) through public media (TV, radio, newspapers, magazines, Internet, etc.).

- Details on “Information and Networking” activities on climate change issues including information networking with thematic groups; participation and contribution to sub-regional and regional information networks and assessment of current capacity in information communication technologies.

The project is prepared in line with GEF-7 strategic focal area on climate change mitigation, objective CCM3 on fostering enabling conditions to mainstream mitigation concerns into sustainable development strategies. To this regard, the planning process needs to begin for RMI’s Third National Communication on Climate Change, in accordance with the Convention’s directives for preparing the Parties’ national communications in non-Annex I, Decision 17/CP.8, need to report on: A national inventory of anthropogenic emissions by sources and removals by sinks of all greenhouse gases not controlled by the Montreal Protocol, to the extent its capacities permit, using comparable methods to be promoted by the Conference of the Parties. A general description of steps taken or envisaged by the non-Annex I Party to implement the Convention. Any other information the non-Annex I Party considers relevant to the achievement of the objective of the Convention and suitable for inclusion in its communication, including, if feasible, material relevant for calculation of global emission trends. The project’s long-term objective is to mainstreaming RMI’s climate change into national and sectoral sustainable development goals, giving continuity to the process of technical and institutional capacity-building, in part, initiated and sustained by the national communications process. The project’s immediate goal is to assist the country in preparing and submitting its Third National Communication and First Biennial Update Report to the Conference of the Parties to the UNFCCC, hence complying with its obligations under Decision 1/CP.16, paragraph 60 and Decision 2/CP.17, paragraph 41 and its Annex III. The expected outcomes of the project are: Review and update of the national circumstances and institutional arrangements pertinent to preparation of the national communications and biennial update reports. The Third National Greenhouse Gases Inventory and the report for the period 2010-2017 and FBUR for 2016. Completed vulnerability study including recommended adaptation measures for identified vulnerable sectors. Assessment of sectors, actions and projects that could be included in the national emission reduction strategy. Development of MRV system proposal. Updated assessment of the financial and technological assistance received and capacities building needs. FBUR and TNC completed and submitted to the UNFCCC Secretariat. The project outcomes will be achieved through a wide array of outputs and activities that include: Updated information on RMI’s geographical characteristics, population, natural resources, climate, society, and economy that could affect its ability to cope with climate change mitigation and adaptation. Updated information on the institutional arrangements pertinent to preparation of the national communications and biennial update reports. Systematic and institutional management of greenhouse gas emission data, and preparation of a national inventory for 2010-2017 and FBUR for 2016. Review of national emission factors for key source categories (methane from enteric fermentation, nitrous oxide from agricultural soils, and CO2 in the forestry sector). Support for the creation of the National Greenhouse Gas Inventory System. Development of reference mitigation, vulnerability and adaptation scenarios up to the Year 2050 for reduction of greenhouse gas emissions and to identify adaptation measures. Compilation and analysis of relevant information on mitigation actions or any set of actions being developed. Information in table form on mitigation measures, such as the name, nature of the action, coverage, quantitative objectives, progress indicators, methods and associated assumptions, implementation progress and the results obtained. Compilation of data on participation in international markets. Updated information on key sectors vulnerable to climate change. Improved technical and institutional capacities for climate change vulnerability studies. Vulnerability studies in sectors and regions including analysis of climate change impacts on these sectors and regions. Analysis of Climate change adaptation programs and projects (risk management program, environmental management systems, technology transfer projects, etc). Proposal for implementation of climate change adaptation measures including the gender perspective. Updated assessment of financing, technology, capacity-building needs and support received. Assessment of the different options and possibilities for the national MRV according to national circumstances and capacities and taking into account the different nature of the mitigation measures. Support for the development of national institutional mechanisms for internal control, reporting and verification. Results and Partnerships Expected Results: National Circumstances and Institutional Arrangements Information provided on national circumstances is critical for understanding the RMI’s vulnerability to the adverse effects of climate change, its capacity and its options for adaptation, as well as its options for addressing its GHG emissions, in particular in the energy sector, within the broader context of sustainable development. Information on national circumstances will include the analyses of national and/or regional development priorities and objectives that the RMI is pursuing and those that would serve as the basis for addressing climate change and sea-level rise issues. Information on national circumstances will be linked to information provided in other chapters of the national communication. The analyses of development priorities and objectives would be of interest to other national stakeholders investigating the benefits of specific activities and policies and the linkages between the activities and policies relating to climate change and those of other Conventions, such as the UNCBD. Information will include: Geographical characteristics, including climate, forests, land use and other environmental characteristics, Population: growth rates, distribution, density and other vital statistics; Economy, including energy, transport, industry, and tourism, agriculture, fisheries, waste, health and services sector Education, including scientific and technical research institutions, Institutional arrangements, regarding how the RMI is organized to deal with climate change challenges, as well as in the implementation of the NC and BUR reporting on continuous basis; Gender-responsive Stakeholder’s engagement, including how gender dimensions are integrated into climate change policy making and activity implementation. National GHG Inventory According to RMI’s Second National Communication (SNC), nearly 100% of GHG emissions in RMI come from four activities: energy industries (electricity production); transport (road); other (residential & commercial) and waste - solid waste disposal on land and wastewater handling. The largest contributor to GHG emissions in year 2000 was energy industries (electricity production) amounting to 51.37 % of total emissions. Total national GHG emissions excluding removals in year 2000 was 122.53 Gg CO2e; which comprises GHG emission 84.97 Gg CO2e from Energy Sector and 37.56 Gg CO2e from Waste Sector. Emissions for other GHGs like per fluorocarbons (PFCs), hydro fluorocarbons (HFCs) and sulphurs hexafluoride (SF6) were negligible in as the products containing these gases are not produced in the country. The data on Agriculture, Industrial Process and land-use change and forestry (LUCF) activities were not available, therefore emissions for these sectors were not estimated and considered for year 2000. The SNC also highlighted that “Perhaps the biggest gap in the GHG inventory is the lack of accurate and reliable data”. The following recommendations were made to strengthen RMI’s GHG inventory in coming years: Establishment of a system and a more detailed database to update all activity data required for the GHG inventory on an annual basis; Identification of options for improving the detail of activity data used for all sectoral GHG inventory and Mainstreaming the GHG inventory as an annual activity to allow regular monitoring of emissions. Currently there is no legal framework for RMI to periodically collect and compile the data and information relevant to GHG inventory development. This is expected to be initiated under the MRV component of the TNC and FBUR initiative. Appropriate training programmes to build the capacities of the stakeholders in the country is envisaged to be integrated as part of the MRV work. In order to ensure national inventories with greater transparency, coherence, comparability, exhaustiveness and accuracy, the 1994 and 2000 inventories were prepared using the method described in the Intergovernmental Panel on Climate Change (IPCC) Guidelines for National Greenhouse Gas Inventories, 1996 revised version; the IPCC Good Practice Guidance and Uncertainty Management in National Greenhouse Gas Inventories; and Good Practice Guidance for Land-use, Land-use Change and Forestry. The 1994 and 2000 inventories were also developed using emission factors and other parameters extracted from the IPCC Guidelines for National Greenhouse Gas Inventories, 1996 revised version, and the Greenhouse Gas Inventory: Reference Manual, IPCC – 1997. In the Third National Communication the biannual time-series will be completed for the period 2010-2017 and in the FBUR for 2016 including finalization of time series for the previous inventories. Special attention will be given to the key source categories and a sensitivity analysis will be undertaken to see how/whether the key sources have changed. Priority will be given to the activity data, which made constraints in the previous GHG inventory. Based on availability of data, relevant re-estimation of GHG emissions for the third GHG inventory will be made. The National GHG emission inventory will be performed according to the 2006 revised IPCC Guidelines with UNFCCC software v.1.3. The main activities that will be carried out for this component are: Compilation of data and interaction with data providers (TNC for the period 2010-2017 and FBUR for 2016). Renewal and strengthening of institutional mechanisms with other institutions and ministries for relevant sectors (energy; land-use, land-use change and forestry; agriculture; wastes; and industrial processes). Preparation of worksheets and summary tables, estimation and management of uncertainties, preparation of graphs and tables, and analysis of results. Strengthening of the existing data management systems to ensure preparation of good quality inventories over the long term. Develop quality assurance and quality control (QA/QC) procedures based on the IPCC Good Practice Guidance and Uncertainty Management in National Greenhouse Gas Inventories. Conduct training on the application of IPCC methodology/2006 guidelines including data collection, analysis and management and the use of IPCC Good Practice Guidance and Uncertainty Management in National GHG Inventories Preparation of the GHGI for 2016 under the FBUR including finalization of time series for the previous inventories Publication of the 2010-2017 inventory report (TNC) and FBUR for 2016. Preparation of summary information tables of the previous inventories, together with the 2010-2017 inventory. Vulnerability and Adaptation assessment The SNC identified 6 priority areas where appropriate interventions, consistent with the Joint National Action Plan (JNAP) for Climate Change Adaptation and Disaster Risk Management (JNAP) goals which could prove especially effective in removing obstacles and promoting DRR and CCA objectives. This include: Strengthening the capacity of the National Emergency Management and Coordination Office; Developing an information management system; Enhancing community-based awareness and education to change attitudes and behaviour toward effective risk reduction; Climate-proofing new water supply developments; Reviewing and revising draft building codes and Testing early warning response. Vulnerability and Adaptation for TNC assessment will highlight impacts of climate change on socio-economic development, natural environment and ecosystems (including forests) and human health, which have taken place over the past decade in RMI. A stocktaking exercise will be conducted to map out the most vulnerable country zones/territories to climate risks. Back to back study will complement the exercise and explore the link between Disaster Risk Reduction (DRR) and Climate Change Adaptation (CCA) for the development of response measures. The key Activities include: Set up the working group, representing local and/or international experts from key socio-economic sectors, natural environment and ecosystems, human health. Analyze air temperature and atmospheric trends and deviations over the past several decades. Update projections of key climate indicators (temperature, precipitation, sea level rise) until 2100 Perform a stocktaking exercise of vulnerability and sensitivity of the country territory to climate risks. Conduct an in-depth vulnerability assessment of key socio-economic sectors and natural environment to climate impacts. Analysis of Climate change adaptation programs and projects (risk management program, environmental management systems, technology transfer projects, etc). In line with RMI’s NDC targets develop proposal for implementation of climate change adaptation measures including the gender perspective. Assessment of vulnerability and recommendations for greater resilience of women and men to climate change as per the UNFCCC Gender Action Plan including: mainstreaming the gender perspective on climate change management, updating the risks differentiated by gender; ensure reports and economic analysis on vulnerability and adaptation highlight differentiated sectoral impacts on women and men, particularly in agriculture; monitor gender representation in training activities related to adaptation-related training. Conduct a study integrating response measures in the context of DRR and CCA. Compile and approve the section on V&A for the TNC incorporation. Climate Change Mitigation Measures: The SNC provided a narrative analysis of the strategies, national policies and best practices for addressing GHG emissions and making a practical contribution to the global mitigation efforts. It mostly reported about large emitting sectors, such as energy industries, transport and waste. A number of measures to reduce GHG emissions have been proposed and accounted the current and forecasted trends in socio-economic development, newly adopted or revised policies and programs. In the context of FBUR and TNC, mitigation measures section will analyze mitigation potential of RMI and assess its interventions towards a low-carbon future including newly adopted policies and sector-based frameworks (such as the 2050 Climate Strategy, Electricity Roadmap etc.). A list of abatement measures proposed for the mitigation for each development sector will be reviewed and updated in the light of recent developments and needs. A stakeholder consultation and research will be conducted to assess possibilities for RMI to implement its newly developed low carbon development strategy/electricity roadmap in light of a Paris Climate Agreement. The key Activities include: Enhance the capacity of OEPPC and other relevant stakeholders to coordinate the mitigation ambitions in the country. Set up the working group, representing international and/or local experts from key socio-economic sectors. Assess mitigation potential in key development sectors and propose/update a list of key abatement/reduction measures. Assess the progress of policies and actions to mitigate GHG at national, sub-national and local levels. In line with RMI’s NDC targets, conduct a study to implement the newly developed low carbon development strategy/electricity roadmap. Compile and approve the section on Climate Change Mitigation Measures for the TNC and/or FBUR incorporation. Domestic Monitoring, Reporting and Verification (MRV) There are no MRV systems in RMI that have been developed and/or implemented previously to track the progress of GHG emissions and mitigation actions. In the absence of specific guidance on MRV systems to be implemented the project will have to work with the available UNFCCC decisions to develop a credible and functional MRV system. Under the FBUR appropriate MRV system will be proposed for national mitigation actions. This includes: An assessment of options and possibilities to develop a domestic MRV system Establishment of institutional arrangements and the national MRV framework. Requirements and recommendations for development of institutional mechanisms for national MRV. Compilation and approval of the section on domestic MRV system for the FBUR incorporation. Constraints and gaps, finance, technology and capacity needs These activities as part of the TNC and FBUR will closely link the process and outcomes of the RMI’s NCs to policy formulation, planning, capacity building and decision making. Based on the assessment produced within the project outcomes on Mitigation and Policy Measures as well as V&A, a study of financial, technological and capacity needs and constraints of institutions responsible for climate change activities will be conducted through the collection, synthesis and analysis of existing information, individual interviews and stakeholder engagement meetings. As part of the exercise, the project team will also outline a list of the most effective/new technology solutions for at least two development sectors, which are the most vulnerable to climate risks. The key Activities include: Set up the working group, representing local and international experts from socio-economic sectors, finance institutions and academia. Based on the assessment produced within the outcome 4, estimate finance resources needed for implementation of the GHG emission reduction strategy. Based on the V&A assessment, perform a cost benefit analysis, estimating potential costs for a long-term adaptation and BAU. Education, training and public awareness, by preparing outreach materials (leaflets, booklets, calendars, posters, quarterly newsletters, videos etc.) and by disseminating it through public media (TV, radio, newspapers, magazines, Internet, etc.). Enhanced climate change information sharing during workshops as well as distribution of presentations and reports. The findings of the studies will be disseminated among universities, research institutions and others for further elaboration and creation of linkages with relevant thematic and specific areas. Other information Other information relevant for reporting in the frames of the TNC and FBUR will support the project outcomes with targeted studies and stocktaking analysis on gender, awareness, education and research on climate change. The project also intends to showcase best practices and lessons learned acquired within the country and region. The key Activities include: Conduct a study on gender’s role in adaptation and mitigation ambitions (please see gender approach description earlier), policy formulation and decision-making process. Perform a stocktaking exercise on best practices and lessons learned accumulated in the context of climate change in RMI and maintain the national knowledge platform to be accessed by the countries in the region. Stock-take any other relevant information, including awareness raising, education, and research. Compile and approve the section on other information, relevant for TNC and/or FBUR incorporation. Submission of FBUR and TNC, Knowledge Management, Monitoring and Evaluation Compilation and approval process of FBUR and TNC will follow a close consultation with national stakeholders. Once finalized, both documents will be edited and submitted to the UNFCCC Secretariat for posting and dissemination. The FBUR is expected to be submitted in 2020, while TNC submission deadline is tentatively set for the late 2022. The key Activities include: Compile FBUR and present it to the national stakeholders for approval. Edit and submit FBUR to the UNFCCC Secretariat. Compile TNC and present it to the national stakeholders for approval. Edit and submit TNC to the UNFCCC Secretariat. Project progress and financial reports prepared in line with the M&E plan Gender Analysis and Action Plan Stakeholder Involvement: RMI strongly believes that TNC and FBUR preparation can help in integration of climate change into existing planning processes as well as to strengthen institutional cooperation on climate change in a useful way during implementation of projects. RMI will also explore and use the existing institutional and stakeholder consultations mechanisms that have been established for initiatives such as the previous national communications and joint climate change and DRM planning processes to engage on TNC and FBUR. The implementation of TNC and FBUR project in RMI would represent a very good example on how various ministries, agencies, institutions of government and non-government organizations can work together in a collaborative manner towards developing a national plan of action. The approach used in the INC and SNC formulation is similar to what is being proposed for the TNC and FBUR preparation, whereby the immediate needs and concerns related to identification and prioritization of mitigation and adaptation options, strategies and measures are highlighted and collectively addressed by the stakeholders. The stakeholders of the project are expected to come from a wide range of backgrounds, including line departments and agencies, local communities, local authorities and NGOs, mass-media, research institutions, private sector and international organizations, with particular emphasis on related sectors. Engagement plan, roles and responsibilities of different stakeholders in the project will be mapped out in details during the Inception workshop and documented in the Inception Report. Stakeholder Role Office of Environmental Planning & Policy Coordination Implementing agency and overall coordination Ministry of Natural Resources & Commerce GHG inventory lead for Agriculture and land use, land-use change and forestry (LULUCF) Energy Planning Division GHG inventory lead for Energy Ministry of Transport Communication & Information Technology Activity Data (AD) and other information on transport, road infrastructure Ministry of Works, Infrastructure & Utilities AD and other informaiton on Waste Sector Environmental Protection Authority AD and other information on Waste Sector Ministry of Health & Human Services AD and other information on Waste Sector Public School System Work on dissemination of results College of the Marshall Islands Provide research assistance Women United Together Marshall Islands Work on dissemination of results Marshall Islands Conservation Society Work on dissemination of results The project team will create mechanisms for effective gender responsive stakeholder engagement and will ensure the meaningful participation of targeted groups. Efforts will be made to take into consideration the needs of excluded and marginalized groups, which are more affected by climate change. For this purpose, the project team will use various tools, including design thinking, behavioral science, and foresight, thus creating a collaborative space where different stakeholders will join forces to design policies and actions that will contribute to mitigation of GHG emissions and will enhance the resilience and adaptive capacities to climate change on national and local levels. Furthermore, as a party to the convention, RMI is keen to develop its TNC and FBUR and display commitment towards achieving the global goal towards abating climate change and associated impacts. The recently completed 2050 Climate Strategy, Electricity roadmap, Nationally Determined Contributions (NDC), National Climate Change Policy Framework, Joint National Action Plan (JNAP) for Climate Change Adaptation and National Gender Mainstreaming Policy of the Republic of the Marshall Islands are envisaged to contribute towards preparation of RMI’s TNC and FBUR. Risks Risks: Specify the risks that might prevent the project results from being achieved and the social and environmental risks posed by the project, as identified in the SESP included as a separate Annex. Refer to the detailed risk log included in Annex. See the 2019 Enterprise Risk Management policy for the risk categories that need to be used. Reference the Environmental and Social Management Framework (or other safeguards management plan), if required, which is also to be included as a separate Annex. If further assessment and management plan(s) are to be undertaken during project implementation, then specify which project activities cannot commence until those plans are in place. Description of a project-level Grievance Redress Mechanism, if required, should be included in the management plan (if prepared) or in an annex. Stakeholder engagement plan: A stakeholder engagement plan must be included in Annex or be included in this section. A comprehensive, gender-responsive stakeholder engagement plan is required for all projects that are considered “high risk” (as per social and environmental screening procedure). If the plan is annexed, then use this section to provide a summary on how stakeholders will be consulted and involved in project activities and monitoring, the means and timing of engagement, how information will be disseminated, and an explanation of any resource requirements throughout the project/program cycle to ensure proper and meaningful stakeholder engagement. If Free, Prior and Informed Consent (FPIC) is required for specific project activities, then ensure that this is clearly stipulated. Select what role civil society will play in the project (Consulted only; Member of Advisory Body; contractor; Co-financier; Member of project steering committee or equivalent decision-making body; Executor or co-executor; Other (Please explain)). See GEF Guidelines on the Implementation of the Policy on Stakeholder Engagement. A preliminary Stakeholder engagement plan includes the following meetings: • Inception workshop to discuss conceptual framework and design for each chapter; and to highlight any prevailing challenges to data acquisition and sharing, monitoring assessment and reporting • Validation workshops to discuss results and validate accuracy of the analyses • Individual meetings with sector representatives • Group discussions to solicit ideas, create synergies and opportunities for networking, knowledge sharing and joint actions • Final dissemination workshop to discuss findings, raise awareness and reinforce collaboration and networking Gender equality and Women’s Empowerment: The guidance on gender integration through the NCs and BURs developed by the Global Support Programme through UNDP and in collaboration with UNEP and GEF, will be applied during project implementation (http://www.un-gsp.org/news/gender-responsive-national-communications-toolkit). The project will comprehensively consider gender and equity issues in line with the GEF SEC’s policy on gender equality and Guidance to advance gender equality in GEF projects and programs. First of all, the project team will equally consider both female and male professionals and experts, dealing with climate change, economic development, natural environment, and human health. The project team will keep a track record of data disaggregation (gender, age, etc.) and use different approaches in involving female professionals to the discussions. A gender disaggregated analysis approach will be implemented and gender-sensitive stakeholders and partners involvement plan will be adopted. Understanding how the different social roles and economic status of men and women affect,and are affected differently by climate change will improve actions taken to adapt and to mitigate climate change. In this sense, the update of the national circumstances chapter will consider gender dimension in order to better understand how the different roles of men and women in social and economic circumstances may affect the country’s ability to deal with mitigating and adapting to climate change. The project is envisaged to perform a study analyzing the role of gender under all the activities including adaptation and mitigation activities, policy formulation and knowledge. The expected findings will build recommendations for most of the project outcomes (National Circumstances, V&A, Mitigation, etc.). Efforts will also be made to have acceptable gender representation (at least 30% women participation) in project management structures (committees, institutional frameworks, technical team) and capacity building actions (trainings, workshops). Institutions to be consulted on gender issues at national level will include, but not limited to: Ministries in charge of gender, the gender focal point for the convention on climate change, civil society organizations working in the fields of gender and climate change as well as research institutions and development partners working on gender issues.

Sustainability and Scaling Up

The project will continue further on the work done under the First and Second National Communication projects and will involve key national institutions/partners/stakeholders/experts responsible for specific sections/topics, in order to maintain continuity of the process.

Preparation and submission of the National Communications and Biennial Update Reports is a commitment of the Government of RMI under the UNFCCC. The process is sustained in the future through the use of results, practice, knowledge, and lessons, which have been accumulated during the project implementation. Enhanced capacity of the National Government and its principle stakeholders, who are supposed to implement the project, will undoubtedly contribute to the effective decision making and policy formulation at all stages of the climate-resilient development in the country.

The project, within the framework of its capacity building interventions, will support the development of the GHG emission data collection and MRV system. This will be done via analysing opportunities for establishment of such system, development of institutional arrangements and frameworks for MRV and GHG Inventory. To ensure sustainability of the project impact, this work will be complemented by rigorous capacity building undertaken throughout the project duration to build the critical mass of expertise among stakeholders.

## South-South and Triangular Cooperation (SSTrC)

UNDP has a strong role to play as knowledge broker, capacity development supporter and partnership facilitator when developing countries work together to find solutions to common development challenges. South-South and Triangular Cooperation (SSTrC) is a necessity to ensure an inclusive global partnership towards sustainable development. The project will support and encourage SSTrC to ensure knowledge exchanges, technology transfers, peer support, and neighborhood initiatives, as well as countries forming common development agendas and seeking collective solutions.

The project will explore possibilities for South-South cooperation within the framework of the sectoral and intergovernmental networks in which RMI participates, both related to adaptation and mitigation, and to the elaboration of National Inventories of Greenhouse Gases (GHGI). In particular, through South-South cooperation, the country will be able to optimize the development of national capacities and / or the incorporation of specific technologies that contribute to a significant improvement in the implementation of adaptation and mitigation actions. In return, RMI may support other countries in the implementation of other initiatives.

Under the guidance and exchanges facilitated via the Global Support Program for National Communication and Biennial Update Reports, RMI will participate on the South-south learning and capacity building via webinars, regional workshops and networks on NC and BUR specific topics.

# Project Results Framework:

This project will contribute to achieving the following Regional Outcome as defined in UNDAF: Regional UNDAF Focus Area: Environmental Management, Climate Change and Disaster Risk Management Regional UNDAF Outcome: 1.1: Improved resilience of PICTs, with particular focus on communities, through integrated implementation of sustainable environmental management, climate change adaptation/mitigation, and disaster risk management RMI UNDAF Country Programme Outcome: National, local and community capacities to effectively plan and implement enhanced natural resource management, biodiversity conservation, climate change adaptation and mitigation, and disaster risk reduction are strengthened

UNDAF Outcome Indicators: Outcome 1.1: Number of environmental policies/regulations successfully passed by parliament and translated into environmental protection measures for implementation by government

Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one): 1. Mainstreaming environment and energy OR 2. Catalyzing environmental finance OR 3. Promote climate change adaptation OR 4. Expanding access to environmental and energy services for the poor.

Applicable GEF Strategic Objective and Program: Objective CCM-3: Foster Enabling Conditions to Mainstream Mitigation Concerns into Sustainable Development Strategies; Program 5: Integrate findings of Convention obligations and enabling activities into national planning processes and mitigation targets

Applicable GEF Expected Outcomes: Outcome B. Policy, planning and regulatory frameworks foster accelerated low GHG development and emissions mitigation

Applicable GEF Outcome Indicators: Indicator 7. Number of countries meeting convention reporting requirements and including specific GHG reduction targets

|  | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective Support the Government of RMI to prepare its Third National Communication (TNC) and First Biennial Report under the UNFCCC (FBUR) | Preparation and submission of the TNC and FBUR | SNC completed and submitted to UNFCCC. Significant data and information gaps identified as part of earlier communications. | FBUR approved and submitted to the UNFCCC by Dec 2020 TNC approved and submitted to the UNFCCC by June 2022 | Document available online at UNFCCC website | Non- availability of data and information required for development of TNC and FBUR and poor absorptive capacity of stakeholders Inadequate consultations and coordination among the stakeholders Lack of in country expertise and capacity in developing the TNC and FBUR Political instability and lack of support |
| Outcome 1 Updated information on national circumstances concerning the physical and socio-economic characteristics of the country and how these might affect the way in which RMI deals with climate change and sustainable development issues in the long term | National circumstances and institutional arrangements pertinent to preparation of the TNC and FBUR reviewed and updated | The national circumstances in the SNC document reflects the data and information from 2014 | National Circumstance document updated to reflect most current information: Description of Geographical characteristics, including climate, forests, land use and other environmental characteristics Population: growth rates, distribution, density and other vital statistics; Economy, including energy, transport, industry, and tourism, agriculture, fisheries, waste, health and services sector; Education, including scientific and technical research institutions; Description of institutional arrangements relevant to the preparation of the national communications on a continuous basis including distribution of responsibilities within government departments, universities, research institutions, etc Gender analysis including community level stakeholder consultations (as appropriate) particularly with a gender and social inclusion element focusing on women and marginalized groups in the community. Information on involvement and participation of stakeholders with a particular focus on gender integration with appropriate gender representation (at least 30% of the stakeholders are women). | Updated national circumstances chapter for TNC and FBUR | Data/ information required to update national circumstance document is readily available |
| Outcome 2 National GHG Inventory updated for period 2010 – 2017 (TNC) and FBUR for 2016. | National GHG Inventory updated for period 2010 – 2017 (TNC) and FBUR developed for 2016. | Completed national GHG emission inventories for INC and SNC; GHG emissions details under the RMI Electricity Roadmap & 2050 Climate Strategy. | GHG inventories under the TNC and FBUR for all relevant sectors and gases as per the IPCC 2006 guidelines prepared: Collection of data for the six key thematic sectors (Energy, Industrial Processes, Solvent and other Product Use, Agriculture, Land-Use, Land-Use Change and Forestry and Waste). Carry out greenhouse gas emission calculation as per IPCC 2006 guidelines for the six key thematic areas of emissions for period 2010 – 2017 (TNC) and FBUR for 2016. Development of the chapter on GHG Inventory as part of the TNC for period 2010 – 2017 (TNC) and FBUR for 2016. An updated National Inventory Report (NIR) Training and capacity building activities on data collection, analysis, on the use of 2006 IPCC guidelines on national greenhouse gas inventories, the IPCC good practice guidance on the National GHG inventories and Uncertainty Management and the IPCC Good Practice Guidance on Land use, land-use change and forestry. Institutional strengthening and capacity building including the thematic working groups for efficient and timely development and submission of GHG inventories. Sectoral emissions determined and inventory prepared for all thematic areas 2010 – 2017 (TNC) and FBUR for 2016 prepared. | Technical reviews and reports. Spreadsheets/modules/tool support for the inventory chapter in the BUR and TNC Technical expert reviews TNC and FBUR submitted | Data available, accessible and reliable In-country capacity exists to carry out assessment exercises National expert’s capacity building through engagement of consultants as needed. |
| Outcome 3 V & A - Vulnerability study including recommended adaptation measures for identified vulnerable sectors. | Status (%) of In-depth vulnerability assessment, including recommended adaptation measures for priority sectors of socio-economic development, gender and natural environment conducted. | National adaptation policy and plans Information provided in the SNC 7 JNAP Past and on-going initiatives on climate change impacts on different sectors Available national climate scenarios | Better understanding on uncertainties of climate change scenarios Adaptation capacities to climate vulnerability and adaptation is enhanced Mainstreaming climate change vulnerability and adaptation to national sustainable development is improved. Coordination of national research and development on V&A is strengthened. Assessment and elaboration of the climatic scenario for RMI including past, present and future projection (2030). Identification of vulnerable sectors in RMI based on the latest assessment and studies Description of current vulnerability and adaptation efforts; future risks including national/sectoral adaptation policies, strategies and measures Identified potential adaptation actions for priority sectors including opportunities and barriers Assessment of vulnerability and recommendations for greater resilience of women and men to climate change as per the UNFCC Gender Action Plan. Community level stakeholder consultations (as appropriate) particularly with a gender and social inclusion element focusing on women and marginalized groups in the community. | Vulnerability assessment reports Adaptation Policy and Strategy Documents Workshops on V&A TNC submitted | lack of adequate climate relevant data, information and appropriate analytical tools in the areas of vulnerability and adaptation Tools and vulnerability studies being developed will be accepted by the stakeholders |
| Outcome 4 Climate change Mitigation measures | Mitigation actions and their effects reported and monitored, and capacity to collect and analyze this information on an ongoing basis strengthened, with a particular focus in the energy sector | The 2050 Climate Strategy, Tile Til Eo (Lighting the way) RMI Electricity Roadmap 2018 National Climate Change Policy Framework (NCCPF) | Integration of socio-economic implication into national mitigation prioritization/plans/ measures/actions National capacity enhancement for implementation of mitigation measures. Outreach on new mitigation options. A chapter on measures taken to mitigate GHG emissions: Identification of all potential mitigation options for each sector listed in the GHG inventory; and prioritization of mitigation options for each sector and categorization as long, medium- and short-term priorities. Development of Mitigation Scenarios (Emission Forecast) based on the available data from the GHG inventory, as well as socio-economic information, and preparation of a series of mitigation scenarios to 2030. Preparation of brief mitigation project profiles for existing and possible future implementation. Training and capacity building on the use of appropriate technologies, methodologies and tools for assessment of mitigations options and development of mitigation scenarios. Gender analysis with mitigation perspective including community level stakeholder consultations (as appropriate) particularly with a gender and social inclusion element focusing on women and marginalized groups in the community. | Technical reviews and reports Developed mitigation scenarios Technical expert reviews TNC submitted | Data available, accessible and reliable In-country capacity exists to carry out assessment exercises National experts capacity building through engagement of consultants as needed. |
| Outcome 5 Domestic Measurement Reporting and Verification | Domestic Measurement Reporting and Verification system supported | Approved MRV systems under the UNFCCC | Assessment of options and possibilities to develop a domestic MRV system assessed. Identification of the requirements for development of institutional arrangements and the national MRV framework. Report describing the requirements and recommendations for development of institutional mechanisms for national MRV. The development process of national institutional arrangements and framework for domestic MRV supported. Gender analysis with capacity building perspective including community level stakeholder consultations (as appropriate). | Technical expert reviews Supported MRV systems TNC submitted | In-country capacity exists to carry out assessment exercises |
| Outcome 6 Constraints and gaps identified; financial, technology, policy and capacity building needs | Constraints and gaps identified; financial, technology, policy and capacity building needs assessed and recommendation for addressing the needs provided | Information on the progress made and status of relevant components in the SNC. | Capacity-building is regarded as a key issue in all areas of work relating to the preparation of national communication. Elaboration on resources provided for capacity building including details on collaboration and synergy existing between the various Convention processes as they relate to capacity building and technology transfer A chapter on constraints and gaps related to financial, technical and capacity in addressing climate change for BUR and TNC: Based on the assessment produced within the outcome 4, finance resources needed for implementation of the GHG emission reduction strategy estimated; Based on the V&A assessment, a cost benefit analysis, estimating potential costs for a long-term adaptation priorities. | Expert review on the draft chapter | Data available, accessible and reliable |
| Outcome 7 Other information | Other information relevant for the preparation of FBUR and TNC consolidated | Information on the progress made and status of relevant components in the SNC | A chapter on other information for BUR and TNC: Update on activities related to strengthening of the capabilities and expertise of RMI to contribute to, and participate in, research and systematic observation, data collection and processing, archiving, analysis and dissemination identified and documented Elaboration on resources provided for capacity building including details on collaboration and synergy existing between the various Convention processes as they relate to capacity building and technology transfer Assessment of training and awareness-raising activities carried out on climate change issues at the community and national level. Study on the needs and constraints relating to financial, technical and capacity gaps with the assistance of bilateral and multilateral organizations | Expert review on the draft chapter | Data available, accessible and reliable |
| Outcome 8 Submission of FBUR and TNC, Monitoring and evaluation | FBUR compiled, approved by the Government of RMI and submitted to UNFCCC TNC compiled, approved by the Government of RMI and submitted to UNFCCC Project regularly monitored, financial audit conducted and lessons learned compiled | The outputs from outcome 1 to outcome 7 | TNC and FBUR submitted to the UNFCCC: FBUR compiled, approved and submitted by Dec 2020; TNC compiled, approved and submitted by Jun 2022. Project financial and progress reports prepared and submitted. End of Project report and lessons learned compiled. | Expert reviews on the BUR and TNC National Workshops on BUR and TNC | CC remains a priority on national agendas leading to fast tracking of national endorsement processes |

| This project will contribute to the following Sustainable Development Goal (s): list relevant SDG(s) |
| --- |
| This project will contribute to the following country outcome (UNDAF/CPD, RPD, GPD): copy relevant outcome here |
|  | Objective and Outcome Indicators (no more than a total of 21 indicators) | Baseline Must be determined during PPG phase | Mid-term Target Expected level of progress before MTR process starts | End of Project Target Expected level when terminal evaluation undertaken |
| Project Objective: indicators maximum | Mandatory Indicator 1: # direct project beneficiaries disaggregated by gender (individual people) (see methodology available from UNDP GEF) |  |  |  |
|  | Mandatory Indicator 2: # indirect project beneficiaries disaggregated by gender (individual people) (see methodology available from UNDP GEF) |  |  |  |
|  | Mandatory GEF Core Indicators 2 - 5: use selected GEF Core indicators (including sub-indicators, as appropriate) and other objective-level indicators here. No more than 5 objective level indicators. |  |  |  |
| Project component 1 (no indicators required) | Copy the project component from table B of the CEO endorsement request |
| Project Outcome 1 2 indicators maximum | Indicator 6: project specific |  |  |  |
|  | Indicator 7: project specific |  |  |  |
| Outputs to achieve Outcome 1 | List the outputs here. Do not add indicators for outputs. |
| Outcome 2 2 indicators maximum | Indicator 8: project specific |  |  |  |
|  | Indicator 9: project specific |  |  |  |
| Outputs to achieve Outcome 2 | List the outputs here. Do not add indicators for outputs. |
| Project component 2 (no indicators required) | Copy the project component from table B of the CEO endorsement request |
| Outcome 3 2 indicators maximum | Indicator 10: project specific |  |  |  |
|  | Indicator 11: project specific |  |  |  |
| Outputs to achieve Outcome 3 | List the outputs here. Do not add indicators for outputs. |
| Outcome 4 2 indicators maximum | Indicator 12: project specific |  |  |  |
|  | Indicator 13: project specific |  |  |  |
| Outputs to achieve Outcome 4 | List the outputs here. Do not add indicators for outputs. |
| Project component 3 (no indicators required) | Copy the project component from table B from the CEO endorsement request |
| Outcome 5 2 indicators maximum | Indicator 14: project specific |  |  |  |
|  | Indicator 15: project specific |  |  |  |
| Outputs to achieve Outcome 5 | List the outputs here. Do not add indicators for outputs. |
| Outcome 6 2 indicators maximum | Indicator 16: project specific |  |  |  |
|  | Indicator 17: project specific |  |  |  |
| Outputs to achieve Outcome 6 | List the outputs here. Do not add indicators for outputs. |
| Project component 4 (no indicators required) | Knowledge management and M&E Copy the project component from table B of the CEO endorsement request |
| Outcome 7 2 indicators maximum | Indicator 18: project specific |  |  |  |
|  | Indicator 19: project specific |  |  |  |
| Outputs to achieve Outcome 7 | List the outputs here. Do not add indicators for outputs. |
| Outcome 8 2 indicators maximum | Indicator 20: project specific |  |  |  |
|  | Indicator 21: project specific |  |  |  |
| Outputs to achieve Outcome 8 | List the outputs here. Do not add indicators for outputs. |

# Total budget and work plan

The total cost of the project is USD952,000.  This is financed through a GEF grant of USD852,000 and to be administered by UNDP and USD100,000 in parallel co-financing from Government.  UNDP, as the GEF Implementing Agency, is responsible for oversight of the GEF resources transferred to UNDP bank account only.

Confirmed Co-financing: The actual realization of project co-financing will be monitored during the implementation and will be reported to the GEF. Co-financing will be used for the following project activities/outputs:

…	…	…	…	…	…

Implementing Partner (IP) request for UNDP to provide country support services: The Implementing Partner and GEF OFP have requested UNDP to provide support services in the amount of USD$ [add total amount listed in the LOA included in Annex] for the full duration of the project. The signed letter of agreement between UNDP and the Implementing Partner detailing these support services are included in Annex. To ensure the strict independence required by the GEF and in accordance with the UNDP Internal Control Framework, these execution services should be delivered independent from the GEF-specific oversight and quality assurance services (i.e. not done by same person to avoid conflict of interest).

Budget Revision and Tolerance: As per UNDP requirements outlined in the UNDP POPP, the project board will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Board. Should the following deviations occur, the Project Manager and UNDP Country Office will seek the approval of the UNDP-GEF team to ensure accurate reporting to the GEF: a) Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more; b) Introduction of new budget items/or components that exceed 5% of original GEF allocation.

Any over expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g. UNDP TRAC or cash co-financing).

Audit: The project will be audited as per UNDP Financial Regulations and Rules and applicable audit policies. Audit cycle and process must be discussed during the Inception workshop. If the Implementing Partner is an UN Agency, the project will be audited according to that Agencies applicable audit policies.

Project Closure: Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP. On an exceptional basis only, and if there is no increase of the project budget, one extension of the operational closure date beyond the initial duration of the project may be approved by the UNDP-GEF Directorate. However, all costs incurred to close the project must be included in the project closure budget and reported as final project commitments presented to the Project Board during the final project review. The only costs a project may incur following the final project review are those included in the project closure budget.

Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed. This includes the final clearance of the Terminal Evaluation Report (that will be available in English) and the corresponding management response, and the end-of-project review Project Board meeting. Operational closure must happen with 3 months of posting the TE report to the UNDP ERC. The Implementing Partner through a Project Board decision will notify the UNDP Country Office when operational closure has been completed. At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

Transfer or disposal of assets: In consultation with the Implementing Partner and other parties of the project, UNDP is responsible for deciding on the transfer or other disposal of assets. Transfer or disposal of assets is recommended to be reviewed and endorsed by the project board following UNDP rules and regulations. Assets may be transferred to the government for project activities managed by a national institution at any time during the life of a project. In all cases of transfer, a transfer document must be prepared and kept on file . The transfer should be done before Project management Unit (team) complete their assignments.

Financial completion (closure):  The project will be financially closed when the following conditions have been met: a) the project is operationally completed or has been cancelled; b) the Implementing Partner has reported all financial transactions to UNDP; c) UNDP has closed the accounts for the project; d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

The project will be financially completed within 6 months of operational closure or after the date of cancellation. Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report. The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for confirmation before the project will be financially closed in Atlas by the UNDP Country Office.

Refund to GEF:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Directorate in New York. No action is required at CO level on the actual refund from UNDP project to the GEF Trustee.

| Award ID: | To be inserted after issuance of Delegation of Authority (DoA) | Project ID(s): | To be inserted after issuance of Delegation of Authority (DoA) |
| --- | --- | --- | --- |
| Award Title: | Republic of Marshall Islands (RMI): Third National Communication and First Biennial Update Report to the UNFCCC |
| Business Unit: | FJI10 |
| Project Title: | Republic of Marshall Islands (RMI): Third National Communication and First Biennial Update Report to the UNFCCC |
| PIMS no._______ | 6272 |
| Implementing Partner (Executing Agency) | Office of Environmental Planning & Policy Coordination (OEPPC) |

X

xx

xxx

# Indicative Work Plan

# Governance and  Management Arrangements

Roles and responsibilities of the project’s governance mechanism:

Implementing Partner: The Implementing Partner for this project is Office of Environmental Planning & Policy Coordination (OEPPC), Government of RMI.

The Implementing Partner is the entity to which the UNDP Administrator has entrusted the implementation of UNDP assistance specified in this signed project document along with the assumption of full responsibility and accountability for the effective use of UNDP resources and the delivery of outputs, as set forth in this document.

The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting.  This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Risk management as outlined in this Project Document;

- Procurement of goods and services, including human resources;

- Financial management, including overseeing financial expenditures against project budgets;

- Approving and signing the multiyear workplan;

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

Responsible Parties:  xxxx

Project stakeholders and target groups:  xxxx

UNDP: UNDP is accountable to the GEF for the implementation of this project. This includes oversight of project execution to ensure that the project is being carried out in accordance with agreed standards and provisions. UNDP is responsible for delivering GEF project cycle management services comprising project approval and start-up, project supervision and oversight, and project completion and evaluation. UNDP is responsible for the Project Assurance role of the Project Board/Steering Committee.

Project organisation structure:

Project Board:  The Project Board (also called Project Steering Committee) is responsible for taking corrective action as needed to ensure the project achieves the desired results. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.

In case consensus cannot be reached within the Board, the UNDP Resident Representative (or their designate) will mediate to find consensus and, if this cannot be found, will take the final decision to ensure project implementation is not unduly delayed.

Specific responsibilities of the Project Board include:

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the project manager;

- Provide guidance on new project risks, and agree on possible mitigation and management actions to address specific risks;

- Agree on project manager’s tolerances as required, within the parameters set by UNDP-GEF, and provide direction and advice for exceptional situations when the project manager’s tolerances are exceeded;

- Advise on major and minor amendments to the project within the parameters set by UNDP-GEF;

- Ensure coordination between various donor and government-funded projects and programmes;

- Ensure coordination with various government agencies and their participation in project activities;

- Track and monitor co-financing for this project;

- Review the project progress, assess performance, and appraise the Annual Work Plan for the following year;

- Appraise the annual project implementation report, including the quality assessment rating report;

- Ensure commitment of human resources to support project implementation, arbitrating any issues within the project;

- Review combined delivery reports prior to certification by the implementing partner;

- Provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans;

- Address project-level grievances;

- Approve the project Inception Report, Mid-term Review and Terminal Evaluation reports and corresponding management responses;

- Review the final project report package during an end-of-project review meeting to discuss lesson learned and opportunities for scaling up.

The composition of the Project Board must include the following roles:

- Project Executive: Is an individual who represents ownership of the project and chairs the Project Board. The Executive is normally the national counterpart for nationally implemented projects. The Project Executive is:  add

- Beneficiary Representative(s): Individuals or groups representing the interests of those who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. Often civil society representative(s) can fulfil this role. The Beneficiary representative (s) is/are: add

- Development Partner(s): Individuals or groups representing the interests of the parties concerned that provide funding and/or technical expertise to the project. The Development Partner(s) is/are: add

- Project Assurance: UNDP performs the quality assurance role and supports the Project Board and Project Management Unit by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. The Project Board cannot delegate any of its quality assurance responsibilities to the Project Manager. UNDP provides a three – tier oversight services involving the UNDP Country Offices and UNDP at regional and headquarters levels. Project assurance is totally independent of the Project Management function.

Project Manager: The Project Manager has the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Project Board. The Implementing Partner appoints the Project Manager, who must be different from the Implementing Partner’s representative in the Project Board.

The Project Manager’s primary responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Project Manager will inform the Project Board and the Project Assurance roles of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. The Project Manager will remain on contract until the Terminal Evaluation report and the corresponding management response have been finalized and the required tasks for operational closure and transfer of assets are fully completed.

Specific responsibilities include:

- Manage the overall conduct of the project.

- Plan the activities of the project and monitor progress against the approved workplan.

- Execute activities by managing personnel, goods and services, training and low-value grants, including drafting terms of reference and work specifications, and overseeing all contractors’ work.

- Monitor events as determined in the project monitoring plan, and update the plan as required.

- Provide support for completion of assessments required by UNDP, spot checks and audits.

- Manage requests for the provision of UNDP financial resources through funding advances, direct payments or reimbursement using the FACE form.

- Monitor financial resources and accounting to ensure the accuracy and reliability of financial reports.

- Monitor progress, watch for plan deviations and make course corrections when needed within project board-agreed tolerances to achieve results.

- Ensure that changes are controlled and problems addressed.

- Perform regular progress reporting to the project board as agreed with the board, including measures to address challenges and opportunities.

- Prepare and submit financial reports to UNDP on a quarterly basis.

- Manage and monitor the project risks – including social and environmental risks - initially identified and submit new risks to the Project Board for consideration and decision on possible actions if required; update the status of these risks by maintaining the project risks log;

- Capture lessons learned during project implementation.

- Prepare revisions to the multi-year workplan, as needed, as well as annual and quarterly plans if required.

- Prepare the inception report no later than one month after the inception workshop.

- Ensure that the indicators included in the project results framework are monitored annually in advance of the GEF PIR submission deadline so that progress can be reported in the GEF PIR.

- Prepare the GEF PIR;

- Assess major and minor amendments to the project within the parameters set by UNDP-GEF;

- Monitor implementation plans including the gender action plan, stakeholder engagement plan, and any environmental and social management plans;

- Monitor and track progress against the GEF Core indicators.

- Support the Mid-term review and Terminal Evaluation process.

# Monitoring Framework and Evaluation

The project results, corresponding indicators and mid-term and end-of-project targets in the project results framework will be monitored annually and evaluated periodically during project implementation. If baseline data for some of the results indicators is not yet available, it will be collected during the first year of project implementation. The Monitoring Plan included in Annex details the roles, responsibilities, frequency of monitoring project results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. The UNDP Country Office is responsible for ensuring full compliance with all UNDP project monitoring, quality assurance, risk management, and evaluation requirements.

Additional mandatory GEF-specific M&E requirements will be undertaken in accordance with the GEF Monitoring Policy and the GEF Evaluation Policy and other relevant GEF policies. The costed M&E plan included below, and the Monitoring plan in Annex, will guide the GEF-specific M&E activities to be undertaken by this project.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report.

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report:  A project inception workshop will be held within 60 days of project CEO endorsement, with the aim to:

- Familiarize key stakeholders with the detailed project strategy and discuss any changes that may have taken place in the overall context since the project idea was initially conceptualized that may influence its strategy and implementation.

- Discuss the roles and responsibilities of the project team, including reporting lines, stakeholder engagement strategies and conflict resolution mechanisms.

- Review the results framework and monitoring plan.

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP and other stakeholders in project-level M&E.

- Update and review responsibilities for monitoring project strategies, including the risk log; SESP report, Social and Environmental Management Framework and other safeguard requirements; project grievance mechanisms; gender strategy; knowledge management strategy, and other relevant management strategies.

- Review financial reporting procedures and budget monitoring and other mandatory requirements and agree on the arrangements for the annual audit.

- Plan and schedule Project Board meetings and finalize the first-year annual work plan.

- Formally launch the Project.

Quarterly:

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high. Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc.  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Annual progress:

- Status Survey Questionnaires to indicate progress and identify bottlences as well as technical support needs will be carried out once a year.

- Annual report on project progress will be prepared as a regular UNDP CO reporting requirement.

Periodic Monitoring:

A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for project board Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities.

Day to day monitoring of implementation progress will be the responsibility of the Project Manager based on the project's Annual Work plan and its indicators. The Project Team will inform the UNDP CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

Periodic monitoring of implementation progress will be undertaken by the UNDP CO through quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

End of Project:

During the last three months, the project team will prepare the Project Terminal Report (Annex 4). This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Knowledge management: The project team will ensure extraction and dissemination of lessons learned and good practices to enable adaptive management and upscaling or replication at local and global scales. Results will be disseminated to targeted audiences through relevant information sharing fora and networks. The project will contribute to scientific, policy-based and/or any other networks as appropriate (e.g. by providing content, and/or enabling participation of stakeholders/beneficiaries)

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  To accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

Audit clause:

Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

M& E workplan and budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | Project Manager UNDP CO, UNDP GEF | Indicative cost: 15,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | Oversight by Project Manager Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | Project manager and team UNDP CO UNDP RTA UNDP EEG | None | Not applicable |
| Periodic status/ progress reports | Project manager and team | None | Quarterly |
| Mid-term Evaluation | Project manager and team UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | None | Not applicable for EA projects |
| Final Evaluation | Project manager and team, UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | None | Not applicable for EA projects |
| Project Terminal Report | Project manager and team UNDP CO local consultant | None | At least three months before the end of the project |
| Audit | UNDP CO Project manager and team | Indicative cost per year: 8,000 | To be decided based on UNDP CO audit requirements |
| Visits to field sites | UNDP CO UNDP RCU (as appropriate) Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses | US$ 23,000 (+/- 5% of total budget) |  |

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of (country) and UNDP, signed on (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by [name of entity] (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

The designations employed and the presentation of material on this map do not imply the expression of any opinion whatsoever on the part of the Secretariat of the United Nations or UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# Risk Management

- Consistent with the Article III of the SBAA, the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

- The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

- ANNEXES

- Project Map and geospatial coordinates of the project area

- Multiyear Workplan

- Monitoring Plan

- Stakeholder Engagement Plan (as annex or in main body)

- UNDP Atlas Risk Log

- Overview of technical consultancies/subcontracts

- Terms of Reference for Technical services to be provided by UNDP, the Project Board, Project Manager, Chief Technical Advisor and other positions as appropriate

- Signed LOA between UNDP and IP requesting UNDP Support Services (if required on exceptional basis)

- Gender Analysis and Gender Action Plan

- Procurement Plan – for first year of implementation especially

- Partners Capacity Assessment Tool and HACT assessment

- Link to the UNDP Project Quality Assurance Report (to be completed in UNDP online corporate planning system)

# Annexes

ANNEX I. Risks and Mitigation Measures for the TNC-BUR Project

| Risk | Level of Risk | Mitigating Strategies and Actions |
| --- | --- | --- |
| Non- availability of data and information required for development of TNC and FBUR and poor absorptive capacity of stakeholders | High | Carry-out extensive consultations with stakeholders during the project inception phase and incorporate their feedback in the work plan for data compilation. |
| Inadequate consultations and coordination among the stakeholders | Moderaste | Involve all relevant stakeholder from the inception phase of project and maintain on-going communication and interaction throughout the project period. |
| Lack of in country expertise and capacity in developing the National Communications (TNC and FBUR) | Low | Hire consultants to assist the national team and to build capacities through training on the IPCC guidelines and procedures |
| Project Management Issues | Low | Include TNC and FBUR project management as part of the Ministry’s annual work plan and allocate appropriate resources |
| Political instability and lack of support | High | Develop business continuity plan in association with the implementing partner, project management unit, and key line agencies to ensure the means and points of coordination during disrupted periods. |

| # |  | Description | Date Identified | Risk Category | Impact & Probability | Risk Treatment / Management Measures | Risk Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | GUIDANCE: | Enter a brief description of the risk. Risk description should include future event and cause. Risks identified through HACT, SES, Private Sector Due Diligence, and other assessments should be included. (In Atlas, use the Description field. Note: This field cannot be modified after first data entry) | Enter date | Social and Environmental Financial Operational Organizational Political Regulatory Strategic Other Subcategories for each risk type should be consulted to understand each risk type (see Deliverable Description for more information) (In Atlas, select from list) | Describe the potential effect on the project if the future event were to occur. Enter probability based on 1-5 scale (1 = Not likely; 5 = Expected) Enter impact based on 1-5 scale (1 = Low; 5 = Critical) (in Atlas, use the Management Response box. This field can be modified at any time. Create separate boxes as necessary using “+”, for instance to record updates at different times. Check “critical” if P x I = 20 or above) | What actions have been taken/will be taken to manage this risk. (in Atlas, use the Management Response box) | The person or entity with the responsibility to manage the risk. (in Atlas, use the Management Response box) | Status and effectiveness of management measures. (in Atlas, use the Management Response box to describe status of management measures. Update Probability and Impact as needed) |
| 1 |  |  |  | Social and Environmental Financial Operational Organizational Political Regulatory Strategic Other | Text P = I = |  |  |  |
| 2 |  |  |  | Social and Environmental Financial Operational Organizational Political Regulatory Strategic Other | Text P = I = |  |  |  |
| 3 |  |  |  |  |  |  |  |  |

ANNEX II. Terms of Reference for Key Project Personnel

A. PROJECT MANAGEMENT

The Project Board will be responsible for the overall management of the TNC and FBUR and will be composed of the TNC Project Manager, Project Administrative Assistant and accountant (part time).

- TNC and FBUR Project Manager (PM)

- Background

RMI ratified the United Nations Framework Convention on Climate Change (UNFCCC) in 1992. The UNFCCC provides a unified means to combat the effects of climate change and recognizes that increased global temperature leads to climate change. As per the convention, all Parties must report on the steps they are taking or envisage undertaking to implement the Convention (Articles 4.1 and 12). As a Party (non- Annex 1 country) to the United Nations Framework Convention on Climate Change (UNFCCC), RMI officially submitted its Initial National Communication to the UNFCCC in 2000 and the Second National Communication (SNC) in 2015 with support from GEF funding.

The project for preparation of the Third National Communication on climate change is a logical continual step towards further implementation of the UNFCCC at national level. Its main objective is to prepare a comprehensive report on the climate change related issues. The analysis conducted within the SNC will be updated and upgraded/extended, which will result in preparation of a comprehensive national report. Furthermore, it will work towards ensuring that climate change issues are not considered as separate to national and local environmental concerns by integrating objectives into national and local strategic planning processes.

- Scope of Work

The PM will manage the project on a day-to-day basis and is accountable to the executing agency for the planning, management, quality control, timeliness and effectiveness of the activities carried out, as well as for the use of funds. The PM will ensure the regular monitoring and feedback from activities already under implementation.

The PM will work closely with the UNFCCC focal point, the Technical Working Groups on Climate Change and the Project Board (PB).

- Duties and Responsibilities

The Project Manager (PM) will have the following duties:

- Work closely with the OEPPC in implementing of the climate change enabling project as appropriate in a timely manner;

- Ensure proper and effective management of all project activities;

- Prepare a detailed work plan and budget for the project implementation;

- Organise and supervise the workshops and trainings needed for the project;

- Identify, hire and provide subcontracts in consultation with the Director, OEPPC

- Prepare and submit to UNDP and the OEPPC quarterly narrative and financial reports;

- Coordinate and oversee the preparation of the outputs of the TNC;

- Ensure effective communication and adequate information flow with the relevant authorities, institutions and government departments in close collaboration with the TWG and board;

- Liaise with relevant institutions in order to involve their staff in projects and disseminate information relevant to the project;

- Ensure appropriate stakeholder participation in the project implementation and coordinate the work of all stakeholders under the guidance of the OEPPC and in consultation with the UNDP office;

- Ensure that information is available to the Project Board about all Government, private and public sector activities, which impact on capacity development;

- Maintain and establish additional links with other related national and international programs and other Enabling Activities and other national projects;

- Prepare the Terms of Reference for consultants and experts in consultation with Director, OEPPC and ensure their timely hiring;

- Guide the work of consultants and experts and oversee compliance with agreed work plan and timely completion of tasks;

- Organize and coordinate the procurement of services and goods under the project;

- Coordinate, manage and monitor the implementation of the project activities/tasks undertaken by the various technical working groups, local experts; consultants, sub-contractors and co-operating partners;

- Assume overall responsibility for the proper handling of logistics related to all project workshops and events;

- Manage the Project finance, oversee overall resource allocation and where relevant submit proposals for budget revisions with the help of the UNDP officer;

- Undertake any other actions related to the Project as requested by the OEPPC and UNDP.

- Serve as secretary to the Project Board as it relates to climate change activities, projects and programmes;

- Prepare periodic progress reports and present to Project Board members;

- Summarise the results of the project;

- Finalise the Third National Communication and FBUR with the government personnel and national and technical experts; and

- Initiate and mobilize resources for the potential follow up activities.

- Qualifications and Skills

- Advanced University degree (Bachelors or Masters Level) in fields related to climate change, environmental sciences, natural resources or any other related disciplines.

- Minimum of 5 years of working experience in the area relevant to the project;

- Substantial involvement in the preparation of the national GHG inventory, vulnerability and adaptation assessment and the preparation of first national communication;

- Demonstrated ability in managing projects, and in liaising and cooperating with all project stakeholders including government officials, scientific institutions, NGOs and private sector;

- Familiarity with international organizations operations and structure;

- Substantial experience in Government and in interdepartmental procedures;

- Familiarity with international negotiations and processes under the UNFCCC;

- Fluent written and oral communication in Marshallese and English;

- Strong communications and interpersonal skills;

- Excellent computer knowledge (MS Office, Internet); and

- Project Administrative Assistant (PA)

- Background

The preparation of TNC will involve a multitude of tasks/activities ranging from project management, financing and administration to the implementation of day-to-day activities or tasks, which would be carried out, by numerous individuals and organizations. The PA will be located in the OEPPC who is responsible for the preparation of third national communication.

- Scope of Work

The PA will assist the PM and the project team in the coordination and management of daily activities and the organization of local travel for national/international experts. He/she will also be responsible for all administrative (contractual, organizational and logistical) and all accounting (disbursements, record-keeping, cash management) matters under the Project.

- Duties and Responsibilities

The PA will have the following duties:

- Manage the day-to-day operations of the TNC Project, particularly with respect to the provision of technical services and support;

- Ensure that necessary financial, procurement, disbursement and personnel matters are effectively addressed;

- Compile and/or prepare the documentation necessary for the procurement of services, goods and supplies under the project;

- Ensure timely disbursement of funds from the project bank account;

- Maintain the project’s files and supporting documentations;

- Maintain the project’s disbursement ledger and journal;

- Prepare internal and external correspondence for the TNC Project;

- Maintain files and assist in the preparation of documentation in advance of and following all meetings, edit reports and other documents for correctness of form and content;

- Assist the PM and project team in organizing meetings, training workshops, etc for the project personnel and the thematic working groups,

- Assist the PM and project team to organize and coordinate information exchange between participating institutions and internationally;

- Co-ordinate and assist in travel arrangements for project personnel or for representatives within the thematic working groups;

- Maintain and update the established national web site;

- Maintain and update project financial database;

- Provide oral interpretation and written translation as required;

- Assist in the preparation of documents related to project activities; and,

- Undertake other administrative/financial duties as requested by the PM or Director, OEPPC

- Qualifications and Skills

- Diploma in administration, management, accounting;

- Minimum of 3 years of working experience in the area of project administration/accounting;

- Demonstrated ability to cope with spreadsheets and book-keeping;

- Experience in Government and in interdepartmental procedures;

- Familiarity with environmental issues and UNFCCC preferred

- Fluent written and oral communication in Marshallese and English;

- Strong time-management, organizational and inter-personal skills;

- Excellent computer knowledge (Word, Excel, Power Point, etc );

- Experience with preparation of information for presentation on web site; and

- Project Board

Overall responsibilities: The Project Board is the group responsible for making by consensus management decisions for a project when guidance is required by the Project Manager, including recommendation for UNDP/Implementing Partner approval of project plans and revisions. In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance to standards that shall ensure best value to money, fairness, integrity transparency and effective international competition. In case a consensus cannot be reached, final decision shall rest with the UNDP Programme Manager. Project reviews by this group are made at designated decision points during the running of a project, or as necessary when raised by the Project Manager. This group is consulted by the Project Manager for decisions when PM tolerances (normally in terms of time and budget) have been exceeded.

Based on the approved annual work plan (AWP), the Project Board may review and approve project quarterly plans when required and authorizes any major deviation from these agreed quarterly plans.  It is the authority that signs off the completion of each quarterly plan as well as authorizes the start of the next quarterly plan. It ensures that required resources are committed and arbitrates on any conflicts within the project or negotiates a solution to any problems between the project and external bodies.  In addition, it approves the appointment and responsibilities of the Project Manager and any delegation of its Project Assurance responsibilities.

Composition and organization:  This group contains three roles, including:

- An Executive: individual representing the project ownership to chair the group.

- Senior Supplier: individual or group representing the interests of the parties concerned which provide funding and/or technical expertise to the project. The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project.

- Senior Beneficiary: individual or group of individuals representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries.

Potential members of the Project Board are reviewed and recommended for approval during the LPAC meeting. For example, the Executive role can be held by a representative from the Government Cooperating Agency or UNDP, the Senior Supplier role is held by a representative of the Implementing Partner and/or UNDP, and the Senior Beneficiary role is held by a representative of the government or civil society. Representative of other stakeholders can be included in the Board as appropriate. The proposed implementation structure has been included in Section VI (Management Arrangements).

Specific responsibilities:

Defining a project

- Review and approve the Initiation Plan (if such plan was required and submitted to the LPAC).

Initiating a project

- Agree on Project Manager’s responsibilities, as well as the responsibilities of the other members of the Project Management team;

- Delegate any Project Assurance function as appropriate;

- Review the Progress Report for the Initiation Stage (if an Initiation Plan was required);

- Review and appraise detailed Project Plan and AWP, including Atlas reports covering activity definition, quality criteria, issue log, updated risk log and the monitoring and communication plan.

Running a project

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints;

- Address project issues as raised by the Project Manager;

- Provide guidance and agree on possible countermeasures/management actions to address specific risks;

- Agree on Project Manager’s tolerances in the Annual Work Plan and quarterly plans when required;

- Conduct regular meetings to review the Project Quarterly Progress Report and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans.

- Review Combined Delivery Reports (CDR) prior to certification by the Implementing Partner;

- Appraise the Project Annual Review Report, make recommendations for the next AWP, and inform the Outcome Board about the results of the review.

- Review and approve end project report, make recommendations for follow-on actions;

- Provide ad-hoc direction and advice for exception situations when project manager’s tolerances are exceeded;

- Assess and decide on project changes through revisions;

Closing a project

- Assure that all Project deliverables have been produced satisfactorily;

- Review and approve the Final Project Review Report, including Lessons-learned;

- Make recommendations for follow-on actions to be submitted to the Outcome Board;

- Commission project evaluation (only when required by partnership agreement)

- Notify operational completion of the project to the Outcome Board.

### Executive

The Executive is ultimately responsible for the project, supported by the Senior Beneficiary and Senior Supplier. The Executive’s role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The Executive has to ensure that the project gives value for money, ensuring a cost-conscious approach to the project, balancing the demands of beneficiary and supplier.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Ensure that there is a coherent project organisation structure and logical set of plans

- Set tolerances in the AWP and other plans as required for the Project Manager

- Monitor and control the progress of the project at a strategic level

- Ensure that risks are being tracked and mitigated as effectively as possible

- Brief Outcome Board and relevant stakeholders about project progress

- Organise and chair Project Board meetings

The Executive is responsible for overall assurance of the project as described below. If the project warrants it, the Executive may delegate some responsibility for the project assurance functions.

### Senior Beneficiary

The Senior Beneficiary is responsible for validating the needs and for monitoring that the solution will meet those needs within the constraints of the project. The role represents the interests of all those who will benefit from the project, or those for whom the deliverables resulting from activities will achieve specific output targets.  The Senior Beneficiary role monitors progress against targets and quality criteria. This role may require more than one person to cover all the beneficiary interests. For the sake of effectiveness the role should not be split between too many people.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Ensure the expected output(s) and related activities of the project are well defined

- Make sure that progress towards the outputs required by the beneficiaries remains consistent from the beneficiary perspective

- Promote and maintain focus on the expected project output(s)

- Prioritise and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes

- Resolve priority conflicts

The assurance responsibilities of the Senior Beneficiary are to check that:

- Specification of the Beneficiary’s needs is accurate, complete and unambiguous

- Implementation of activities at all stages is monitored to ensure that they will meet the beneficiary’s needs and are progressing towards that target

- Impact of potential changes is evaluated from the beneficiary point of view

- Risks to the beneficiaries are frequently monitored

Where the project’s size, complexity or importance warrants it, the Senior Beneficiary may delegate the responsibility and authority for some of the assurance responsibilities (see also the section below)

### Senior Supplier

The Senior Supplier represents the interests of the parties which provide funding and/or technical expertise to the project (designing, developing, facilitating, procuring, implementing). The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project. The Senior Supplier role must have the authority to commit or acquire supplier resources required. If necessary, more than one person may be required for this role. Typically, the implementing partner, UNDP and/or donor(s) would be represented under this role.

Specific Responsibilities (as part of the above responsibilities for the Project Board)

- Make sure that progress towards the outputs remains consistent from the supplier perspective

- Promote and maintain focus on the expected project output(s) from the point of view of supplier management

- Ensure that the supplier resources required for the project are made available

- Contribute supplier opinions on Project Board decisions on whether to implement recommendations on proposed changes

- Arbitrate on, and ensure resolution of, any supplier priority or resource conflicts

The supplier assurance role responsibilities are to:

- Advise on the selection of strategy, design and methods to carry out project activities

- Ensure that any standards defined for the project are met and used to good effect

- Monitor potential changes and their impact on the quality of deliverables from a supplier perspective

- Monitor any risks in the implementation aspects of the project

TECHNICAL WORKING GROUPS

Thematic Working Group on GHG Inventory

- Scope of Work

The Technical Working Group on National GHG Inventory will be formed to carry out the inventory of GHG emissions in RMI. The group will consist of experts from relevant ministries, institutions and non-government organizations. The group will ensure that specific tasks relating to the national GHG inventory is carried out in a timely manner and will ensure efficient coordination of outputs of consultants and national institutions. The activities undertaken by the national institutions will contribute to strengthening institutional arrangements for compiling, archiving, updating and managing GHG inventories.

- Duties and Responsibilities

- Compilation of data and interaction with data providers (for the period 2010-2017 and FBUR for 2016).

- Renewal and strengthening of institutional mechanisms with other institutions and ministries for relevant sectors (energy; land-use, land-use change and forestry; agriculture; wastes; and industrial processes).

- Preparation of worksheets and summary tables, estimation and management of uncertainties, preparation of graphs and tables, and analysis of results.

- Publication of the 2010-2017 inventory report and FBUR for 2016.

- Preparation of summary information tables of the previous inventories, together with the 2010-2017 inventory.

- Qualifications and Skills

The institutions and/ or expert individuals contracted for undertaking project activities should meet the following minimum criteria:

- Sound and broadly-recognized scientific expertise on climate research in RMI;

- Prior experience in inventory preparation, through involvement in the Initial National Communication and SNC;

- Highly qualified scientists working in the fields of emission factor development or data collection methods; and

- Familiarity with the UNFCCC and IPCC technical guidelines.

- Expected output

Report on the National GHG Inventory and FBUR in accordance with the UNFCCC guidelines. The report should include information on other non- direct GHGs: HFCs, PFCs and SF6 as well as CO, NOx, SOx.

Thematic Working Group on Vulnerability Assessment and Adaptation (V&A)

- Scope of Work

The group will ensure implementation of specific activities outlined below, as well as coordination of the outputs of other consultants engaged outside the institution. The activities undertaken by the national institutions will also strengthen institutional arrangements for systematic climate observation, data management and control, processing and updating of meteorological and hydrological services data.

- Duties and Responsibilities

Particular duties may be as follows:

- Set up the working group, representing local and/or international experts from key socio-economic sectors, natural environment and ecosystems, human health.

- Analyze air temperature and atmospheric trends and deviations over the past several decades.

- Update projections of key climate indicators (temperature, precipitation, snow cover) until 2050.

- Perform a stocktaking exercise of vulnerability and sensitivity of the country territory to climate risks.

- Conduct an in-depth vulnerability assessment of key socio-economic sectors and natural environment to climate impacts.

- Conduct a study integrating response measures in the context of DRR and CCA.

- Compile and approve the section on V&A for the TNC incorporation

- Qualifications and Skills

The institutions and experts contracted for undertaking project activities should meet the following minimum criteria:

- Sound and broadly-recognized scientific expertise on climate research in RMI;

- Prior experience in vulnerability assessment and adaptation process, through involvement in the First National Communication and SNC;

- Highly qualified scientific working in the fields of climate observation and vulnerability analysis in the specific sectors; and

- Familiarity with the UNFCCC, IPCC methodology and other methods.

- Expected output

Completed report on vulnerability assessment and adaptation strategy for the following sectors: agriculture, water resources, natural ecosystems, forestry and human health.

Thematic Working Group on Mitigation

- Scope of Work

The Technical Working Group on Mitigation will be responsible for carrying out GHG mitigation analyses and identifying mitigation options for RMI. It will ensure timely and effective implementation of specific activities outlined below, as well as coordination with the outputs of other consultants engaged outside the institution.

- Duties and Responsibilities

- Enhance the capacity of OEPPC and other relevant stakeholders to coordinate the mitigation ambitions in the country.

- Set up the working group, representing international and/or local experts from key socio-economic sectors.

- Assess mitigation potential in key development sectors, and propose/update a list of key abatement/reduction measures.

- Assess the progress of policies and actions to mitigate GHG at national, sub-national and local levels.

- Conduct a study to implement the newly developed low carbon development strategy/electricity roadmap.

- Compile and approve the section on Climate Change Mitigation Measures for the TNC and/or FBUR incorporation.

- Qualifications and Skills

The institutions contracted for undertaking project activities should meet the following minimum criteria:

- Sound and broadly-recognized scientific expertise on climate research in RMI;

- Experience in preparing scenarios for GHG mitigation through involvement in the First National Communication;

- Qualified scientific working in the related areas: Energy, Agriculture, Land Use Change and Forestry, Waste; and

- Familiarity with the UNFCCC, software modeling tools such as LEAP, ENPEP, WASP, GACMO, etc.

- Expected output

A Completed GHG Mitigation report and National action plan for effective response to the GHG emissions.

The proposed activities will be undertaken in appropriate sequence so as to maximize the synergies between each component of the proposed activities, as well as the efficiency and cost-effectiveness for the implementation throughout the project cycle.

Good practices in project implementation, such as the efficient use of financial and human resources, the engagement of qualified local and regional consultants, public participation throughout the project cycle, will be adopted where appropriate. Established guidelines will be followed, while established tools and methodologies will be used.

Thematic Working Group on Research and Systematic Observation

- Scope of Work

The Technical Working Group on Research and Systematic Observation will be responsible for assessing the needs and priorities for research and systematic observation in RMI. The group will ensure timely and effective implementation of specific activities outlined below, as well as coordination with the outputs of other consultants engaged outside the institution.

- Duties and Responsibilities

- Participate in a training workshop on the use of the UNFCCC guidelines on research and systematic observation;

- Undertake an assessment of the needs and priorities for research and systematic observation in close collaboration with Pacific Islands – Global Climate Observing System initiatives;

- Prepare an analysis of the climatic conditions of various stations in RMI;

- Liaise closely and consult with the TWGs on GHG inventory, Vulnerability and Adaptation, and Mitigation on issues of relevance, especially on climate data, technologies and capacity building;

- Provide substantive input to the work of TWGs on Vulnerability and Adaptation and Mitigation;

- Organize (in cooperation with the PSC) a workshop to present the results of the research and systematic observation; and

- Prepare final report on research and systematic observation, including comments from the stakeholders.

- Qualifications and Skills

The institutions and or expert individuals contracted for undertaking project activities should meet the following minimum criteria:

Sound and broadly-recognized scientific expertise on climate research in RMI;

Experience in preparing a report on research and systematic observation through involvement in the Initial National Communication and SNC;

Qualified scientific working on issues relating to climate, weather, meteorology and hydrological services; and

- Expected output

A final report on Research and Systematic Observation including emerging needs and priorities.

Thematic Working Group on Education, Training and Public Awareness, Information and Networking and Capacity Building

- Scope of Work

The TWG will examine ways to promote climate change education, training and public awareness building. The group will ensure timely and effective implementation of specific activities outlined below, as well as coordination with the outputs of other consultants engaged outside the institution.

- Duties and Responsibilities

- An assessment of options and possibilities to develop a domestic MRV system

- Establishment of institutional arrangements and the national MRV framework.

- Requirements and recommendations for development of institutional mechanisms for national MRV.

- Compilation and approval of the section on domestic MRV system for the FBUR incorporation.

- Set up the working group, representing local and international experts from socio-economic sectors, finance institutions and academia.

- Based on the assessment produced within the outcome 4, estimate finance resources needed for implementation of the GHG emission reduction strategy.

- Based on the V&A assessment, perform a cost benefit analysis, estimating potential costs for a long-term adaptation and BAU.

- Conduct a study on gender’s role in adaptation and mitigation ambitions, policy formulation and decision-making process.

- Perform a stocktaking exercise on best practices and lessons learned accumulated in the context of climate change in RMI and maintain the national knowledge platform to be accessed by the countries in the region.

- Stock-take any other relevant information, including awareness raising, education, and research.

- Compile and approve the section on other information, relevant for TNC and/or FBUR incorporation.

Thematic Working Group on Integration of Third National Communication

- Scope of Work

This Technical Working Group will be responsible for integration of Third National Communication with input from the various thematic working groups. The group will ensure that all information pertaining to the TNC is compiled and disseminated for review and comment in a timely manner.

- Duties and Responsibilities

- Compile the TNC and FBUR in accordance with the UNFCCC guidelines based on information and or reports provided by the various TWGs;

- Liaise and consult with the various TWGS on issues relating to their respective sectors;

- Promote the integration of climate change concerns and issues into various TWG reports;

- Identify and highlight evolving needs and priorities relating to the preparation of third national communication and the implementation of the Convention;

- Prepare a final draft of the TNC and FBUR including a 10-page executive summary and technical annexes (if any);

- Conduct a national workshop in collaboration with the TWGs on the TNC and FBUR; and

- Prepare final draft of TNC and FBUR, print and submit to the UNFCCC Secretariat and disseminate through appropriate mode.

ANNEX III. Letter of agreement between UNDP and Government of Republic of Marshall Islands (RMI) for the provision of support services

Project Title “Third National Communication and First Biennial Update Report to the UNFCCC”

PIMS # 6272, Project ID:, Output ID:

Excellency,

1.	Reference is made to consultations between officials of the Government of Republic of Marshall Islands (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects. UNDP and the Government hereby agree that the UNDP country office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP country office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

- Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Standard Basic Assistance Agreement (SBAA) between the Authorities of the Government of Republic of Marshall Islands and the United Nations Development Programme (UNDP), signed by the Parties on July 18, 2008 (the "SBAA") including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter. Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

M./Ms.

Country Director

Date:

_____________________

For the Government of Republic of Marshall Islands

Minister

Ministry of ………

Date:

Attachment:  Description of UNDP Country Office Support Services

1.	Reference is made to consultations between the Office of Environmental Planning & Policy Coordination (OEPPC), the institution designated by the Government of Republic of Marshall Islands (RMI), and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed programme or project “Third National Communication and First Biennial Update Report to the UNFCCC (PIMS # 6272, Project ID:, Output ID:)

2.	In accordance with the provisions of the letter of agreement signed and the programme support document (project document), the UNDP country office shall provide support services for the Programme as described below.

3.	Support services to be provided:

| Support services | Schedule for the provision of the support services | Cost to UNDP of providing such support services (where appropriate) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- |
| 1. Support MOE in the identification and/or recruitment of project personnel * Project Manager * Finance Officer | July 2019 – September 2019 | As per the UPL: US$ 893.96 per case, including recurring cost after hire (i.e. payments) | Should be approved by the Project Board; then UNDP will directly charge the project upon receipt of request of services from the Implementing Partner/Project Board |
| 2. Procurement of goods: * Data show * PCs * Printers | July 2019 – September 2019 | As per the UPL: US$ 706.11 for each purchasing process | As above |
| 3. Procurement of Services Contractual services for companies | Ongoing throughout implementation when applicable | As per the UPL: US$ 327.53 each hiring | As above |
| 4. Payment Process | Ongoing throughout implementation when applicable | As per the UPL: US$ 30.64 for each | As above |
| 5. Staff HR & Benefits Administration & Management | Ongoing throughout implementation when applicable | N/A | N/A |
| 6. Recurrent personnel management services: Staff Payroll & Banking Administration & Management | Ongoing throughout implementation when applicable | N/A | N/A |
| 7. Ticket request (booking, purchase) | Ongoing throughout implementation when applicable | As per the UPL: US$ 28.91 for each | As above |
| 8. F10 settlement | Ongoing throughout implementation when applicable | As per the UPL: US$ 29.20 for each | As above |
| 9. Support Implementing Partner in conducting workshops and training events | Ongoing throughout implementation when applicable | As per the UPL: US$ 23.44 per day (for preparation and during workshop) | As above |
|  |  | Total: up to USD 15,000 from GEF grant |  |

4.         Description of functions and responsibilities of the parties involved:

UNDP will conduct the full process while the role of the Implementing Partner (IP) will be as follows:

- The Implementing Partner will send a timetable for services requested annually/ updated quarterly

- The Implementing Partner will send the request to UNDP for the services enclosing the specifications or Terms of Reference required

- For the hiring staff process: the IP representatives will be on the interview panel,

For Hiring CV: the IP representatives will be on the interview panel, or participate in CV review in case an interview is not scheduled

ANNEX IV.  Social and Environmental Screening Template

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document. Please refer to the Social and Environmental Screening Procedure for guidance on how to answer the 6 questions.]

Project Information

| Project Information |  |
| --- | --- |
| Project Title | Third National Communication and First Biennial Update Report to the UNFCCC |
| Project Number | XXXX |
| Location (Global/Region/Country) | Republic of Marshall Islands |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

The project supports the meaningful participation and inclusion of all stakeholders, during the design, implementation and monitoring of the project. It is anticipated that they will participate to activities supported by the project and the project will support the development of an enabling environment conducive to the participation of stakeholders in the management of natural resources. This approach is consistent with the participation and inclusion of human rights principle. The stakeholder engagement process will accommodate a wide range of stakeholders and institutions both at the national and community-based levels. The issue of mainstreaming climate change considerations into policy formulation and national development strategies is becoming more prominent. Therefore, an inter-agency coordination to meet strategic objective of sustainable development and its goals is critical. Since the process of NC/BUR preparation supports this coordination, its role can be enhanced up to a regular exchange platform for mainstreaming, policy formulation, capacity building, awareness raising and knowledge exchange. The NC/BUR process will expand its network of stakeholders and include women associations.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The project intends to empower gender by identifying appropriate female local consultants, if available. In addition, workshops will be conducted in which gender balance will be ensured. Furthermore, gender will be mainstreamed into the TNC and BUR in a way that ensures that equitable participation of women in the decision-making process of climate change adaptation and mitigation. With regard to the technical team to be hired to implement the enabling activity, gender balance will be also considered. Every effort will be made to incorporate gender issues in the implementation of this project. Roles of men and women to participate in activities of the project will be equally assigned without any discrimination. The project will take steps to ensure that women account for at least 40% of all training and capacity building in the project. Moreover, the project will strengthen data collection and monitoring programmes – gender segregation of data collection and monitoring will be introduced as a basis for ensuring long-term gender benefits. This gender inclusive project – which is part of the UNDAF 2014-2017 – will foster gender equality in environmental management and women’s empowerment and participation in environmental management. This approach will facilitate a focus on gender-based environmental issues and gender-based solutions.

Briefly describe in the space below how the Project mainstreams environmental sustainability

This project is a follow-up to the GEF-funded Second National Communication (SNC) enabling activity for RMI that was implemented over the three programme cycles of 2004-2007, 2008-2012, and 2014-2017. The project will build upon the institutional capacities that were established through the SNC project and provide continued assistance to RMI in meeting reporting requirements under the UNFCCC Convention. This is in accordance with its commitments as a non-Annex 1 Party (as mandated by Article 4 and 12 of this Convention and COP 16 and 17 decisions). The project will also strengthen the technical and institutional capacities of relevant line ministries within RMI to prepare and submit its TNC and first BUR to the UNFCCC. Through the project, relevant line ministries will be able to update the information provided regarding national circumstances, inventories of greenhouse gases, policies and measures undertaken to mitigate climate change, assessments of vulnerability to climate change and steps taken to adapt, and information on public awareness, education, training, systematic research and observation, and technology transfer. Through the BUR component of the project, relevant sectors will focus on GHG inventory for 2016 through the use of a streamlined reporting system; articulate mitigation actions/measures relevant to each sector; and identify constraints and gaps related to financial, technical and capacity and support needs and BUR support received and needed. The project will also increase the national technical and institutional capacities in preparing the NC/BUR and assisting the Government to integrate climate change issues into sectoral and national development priorities. The project is well aligned with the UNDAF 2014-2017, particularly the “environmental management, climate change and disaster risk management” programme area through strengthening the national capacity to manage environmental information. It will provide better environmental information to stakeholders to make better decisions and to better monitor the environment. Through the various components and thematic working groups, the project will contribute to strengthening the coordination between key sectors to address climate change adaptation and mitigation. There are no environmental risks involved with the implementation of this project.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |
| --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |
| Risk 1: None | I = P = | N/A | N/A | N/A |
| Risk 2 ….None | I = P = | N/A | N/A | N/A |
| Risk 3: ….None | I = P = | N/A | N/A | N/A |
| Risk 4: ….None | I = P = | N/A | N/A | N/A |
|  | QUESTION 4: What is the overall Project risk categorization? |
|  | Select one (see SESP for guidance) | Comments |
|  | Low Risk | ☐ |  |
|  | Moderate Risk | ☐ |  |
|  | High Risk | ☐ |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |
|  | Check all that apply | Comments |
|  | Principle 1: Human Rights | ☐ |  |
|  | Principle 2: Gender Equality and Women’s Empowerment | ☐ |  |
|  | 1. Biodiversity Conservation and Natural Resource Management | ☐ |  |
|  | 2. Climate Change Mitigation and Adaptation | ☐ |  |
|  | 3. Community Health, Safety and Working Conditions | ☐ |  |
|  | 4. Cultural Heritage | ☐ |  |
|  | 5. Displacement and Resettlement | ☐ |  |
|  | 6. Indigenous Peoples | ☐ |  |
|  | 7. Pollution Prevention and Resource Efficiency | ☐ |  |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | No |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | No |
| 5. Are there measures or mechanisms in place to respond to local community grievances? | No |
| 6. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | No |
| 7. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 8. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 9. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 3. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | NO |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | No |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | No |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas)? | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.4 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.5 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.6 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.7 Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | No |
| 6.8 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

ANNEX V. Final Report Of RMI National Communication / Biennial Update Report Project

Monitoring and Evaluation plans of climate change enabling activities for the preparation of National Communications on Climate Change and/or Biennial Update Reports do not require the production and publication of Terminal Evaluation Reports. Therefore, a number of intended purposes of such terminal exercises are not captured in full, including:

- The promotion of accountability and transparency, and the assessment and disclosure of the extent of the project accomplishments;

- A synthesis of lessons that can help to improve the selection, design and implementation of future GEF financed UNDP activities;

- The provision of feedback on issues that are recurrent across the portfolio, attention needed, and on improvements regarding previously identified issues; and

- The contribution to the GEF Evaluation Office databases for aggregation, analysis and reporting on effectiveness of GEF operations in achieving global environmental benefits and on the quality of monitoring and evaluation across the GEF system.

The intent of this Final Report is not to propose an abridged alternative to the Terminal Evaluation Report. Instead, its purpose is to gather some insightful details about the process of preparing the mandatory report under the UNFCCC that can be of use to both the UNDP support teams, and the current and future national project teams. Its focus is therefore on providing:

- A synthesis of lessons that can help to improve the selection, design and implementation of future GEF financed UNDP activities; and

- Feedback on issues that are recurrent across the portfolio, attention needed, and on improvements regarding previously identified issues.

National project teams in charge of the future enabling activity for the preparation of the National Communication or Biennial Update Report can therefore rely on a valuable source of information from inception to closure of the project, and UNDP support teams can further disseminate lessons across borders, fully up-taking its guiding role as implementing agency and partner within the Global Support Programme (GSP, previously known as National Communications Support Programme).

The template has been designed with the purpose of collecting relevant information, without representing a time-intensive and human resource-intensive burden to the current national project team. It is therefore divided into three core sections – project identification phase, project implementation phase and project follow-up –with for each section a limited number of open questions.

The intention is to have the team leader, project manager or equivalent figure completing the template, in close collaboration with other team members within the last two months of project implementation. It is furthermore the intention of the completion of this Final Report to trigger the discussions of the upcoming National Communication and/or Biennial Update Report, taking advantage of the momentum created by the ongoing project, the presence of the core of the current national project team, and the renewed interest of national counterparts with the perspectives of an eminent or recent submission to the UNFCCC.

The completion of this template has been made mandatory and has been budgeted for in all projects that received approval post 2014 (3 working days equivalent of project manager’s time). You are kindly invited to send the completed template to Damiano Borgogno, damiano.borgogno@undp.org and to Eva Huttova, eva.huttova@undp.org.

## Details of the project

| Project’s title |  |
| --- | --- |
| PIMS number |  |
| Overall budget including GEF grant including co-financing |  |
| Duration of implementation |  |
| Planned duration of project |  |
| Implementing partner |  |
| Team Leader’s name and contact details |  |
| Link to final report |  |

## Project identification phase

Duration of preparatory phase (expressed in months) ________________________________________

Was the project document developed by a national/international consultant? (Please, provide name if yes and expand on the satisfaction of this collaboration.)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Please, shortly describe the milestones of this initial preparatory phase (e.g. consultation workshops held, telephone interviews with key stakeholders, among others)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Where consultations made with one or more of the following stakeholder groups?

|  | Ministry of Finance (or equivalent) |  | Women’s associations |
| --- | --- | --- | --- |
|  | Other Ministries (not being the Ministry in charge of climate change) |  | Youth movements |
|  | Local Governments |  | Indigenous peoples’ representatives |
|  | National universities |  | Environment or climate related NGOs |
|  | Domestic Research Centers |  | Other NGOs/CSOs |
|  | Media |  | Others (specify) |

What were the main objectives for the project identified as a result of this preparatory phase?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What were the major challenges faced during this phase?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Looking back, what issues that were identified and/or overlooked during this preparatory phase had an impact on the successive implementation phase?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

## Project implementation phase

Technical components

- GHG inventory

Base year of the GHG inventory:

Base years used in previous GHG inventories:

| Expected outcome |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |

| Final outcome |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the GHG inventory component, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the causes (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

- Mitigation actions

| Expected outcome(s) |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |
| … |  |

| Final outcome(s) |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the vulnerability and adaptation measures and mitigation measures components, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the causes (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

________________________________________________________________________________________________________________________________________________________________________

- Vulnerability & Adaptation for NC or MRV for BUR

| Expected outcome(s) |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |
| … |  |

| Final outcome(s) |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the vulnerability and adaptation measures and mitigation measures components, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the main reasons (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

- Constraints and Gaps/Support needed

| Expected outcome |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |
| … |  |

| Final outcome |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the Constraints and gaps, and related financial, technical and capacity needs component, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the main reasons (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

Capacities and use of capacities

Do you believe the project has built - in a durable and cost-effective way - human and institutional capacities? Please, elaborate.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Please, estimate the amount of work done by national consultants versus international consultants:

______________% national consultants. ________________% international consultants and ____________% national staff.

What work was entrusted to international consultants and for what reasons?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What would you have done differently, or do you advise the next project team to consider in this context?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Additional remarks

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Institutional arrangements

Please, summarize an overview of the institutional arrangements for the project implementation.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Please, describe the composition of the project team.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Will the team remain in place, even after the project has fully closed?

____________________________________________________________________________________

Were gender considerations taken into account during the project design and implementation? If so, how?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Which were the strengths and weaknesses of the institutional arrangements used?

---------------------------------------------

What suggestions have you to make regarding the institutional arrangements for future NC/BUR work?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Additional remarks

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Technical support from GSP, CGE, or other bodies

Has the project team, or members of the project team, participated in national, regional or global training events organized by a center of excellence or above mentioned body during the course of the project? If yes, please, specify the training event(s).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What has been the contribution of this participation to the project results?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What identified knowledge gaps holding back the proper implementation of the NC project could not be addressed by any of the above mentioned bodies?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

In addition to capacity building support, what other assistance did the project team receive during project implementation? (E.g. review of draft report, technical backstopping of international expert)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Has UNDP provided timely and valuable support during project design and implementation? Please explain.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

## Next steps

How will findings of the project be further disseminated, if at all?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Are balance funds available under the NC/BUR project going to be used to identify the strategy of the next report?

____________________________________________________________________________________

____________________________________________________________________________________

At full project closure, is there a person or institute to whom one can turn in case there are follow-up questions to the NC/BUR?

____________________________________________________________________________________

____________________________________________________________________________________

Has the Government expressed interest to further work with UNDP on the next coming report? If no, please explain.

____________________________________________________________________________________

Additional information

| Date |  |
| --- | --- |
| Name and e-mail address of person who completed this template |  |
| Others involved in completion of this template (names of individuals and their institutions) |  |
| In case a terminal evaluation report has been produced, please link it here. |  |
| Other attachments |  |

# Footnotes

For UNDP supported GEF funded projects as this includes GEF-specific requirements

http://www.thegef.org/sites/default/files/council-meeting-documents/EN_GEF.C.53.04_Gender_Policy.pdf

http://www.thegef.org/sites/default/files/council-meeting-documents/EN_GEF.C.54.Inf_.05_Guidance_Gender_0.pdf

Objective (Atlas output) monitored quarterly ERBM  and annually in APR/PIR

All outcomes monitored annually in the APR/PIR.  It is highly recommended not to have more than 4 outcomes.

Baseline, mid-term and end of project target levels must be expressed in the same neutral unit of analysis as the corresponding indicator. Baseline is the current/original status or condition and need to be quantified. The baseline must be established before the project document is submitted to the GEF for final approval. The baseline values will be used to measure the success of the project through implementation monitoring and evaluation.

Target is the change in the baseline value that will be achieved by the mid-term review and then again by the terminal evaluation.

Outcomes are medium term results that the project makes a contribution towards, and that are designed to help achieve the longer-term objective.  Achievement of outcomes will be influenced both by project outputs and additional factors that may be outside the direct control of the project.

See https://www.thegef.org/gef/policies_guidelines

Source: Guidelines on UNDP Implementation of UNDAF Annual Review Process

UNDP Financial Rules and Regulations: Chapter E, Regulation 16.05: a) The administration by executing entities or, under the harmonized operational modalities, implementing partners, of resources obtained from or through UNDP shall be carried out under their respective financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP.  b) Where the financial governance of an executing entity or, under the harmonized operational modalities, implementing partner, does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, that of UNDP shall apply.

Depending on its composition, the Outcome Board can fulfill the function of the Project Appraisal Committee (LPAC)

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

# Comments

Add please Atlas IDs, project start date (month/year) and end date and LPAC date

Is 40,000 a typo, or expected co-financing has changed? Hereby, total co-financing is 100K (as reflected also in EA request). Please, make it clear and correct.

Please, adjust the cover page and parts of the project document to the newest template (from mid-July). Please, stick to the template and use the same parts/sections and titles as in the template. Current prodoc does not fit with older template. Some parts (like List of abbreviations, Results and Partnerships, annexes: Project quality assurance, IP assessment, Gender analysis and action plan) are missing.

Links to the latest prodoc template:

- Blank Project Document Template for GEF-7 Projects (July 2019)

- Annotated Project Document Template for GEF-7 Projects (July 2019)

- Total Budget and Workplan (TBWP) for GEF-7 projects (July 2019)

Please, use consistent formatting within the whole document. Do not exchange arrows with bullets in bullet lists.

Please consolidate with the text copy-pasted from the EA request below. There is a lot of duplication. Please keep ProDoc focused and avoid repetitions of information.

This is copy/past from EA proposal. The part in prodoc is entitled : Partnerships, and it includes not only stakeholders, but also other projects/initiatives/activities of partners addressing the development challenge.

Partnerships:  Describe how the project will work with partners to achieve results. Briefly map what other stakeholders and initiatives are doing to address the development challenge this project is also addressing and how their work is critical to the achievement of the results of this project (this can be presented as a table). This should include other GEF/LCDF/SCCF financed projects and other relevant projects. Elaborate on the private sector’s engagement in the project, if any.

Include this into the list of abbreviations, please.

This part is missing. Please, add.

Under new ProDoc template, there is a revised PRF template. Please transfer all information to the new format.

Guidance to project developer:  Indicators are required for the project objective and project outcomes only. As per table B in the CEO endorsement request template, each project should have no more than 4 Project Components and no more than 8 project outcomes in total (two per component). Include results that contribute to gender equality and women’s empowerment as per the findings of the gender analysis.

When choosing indicators, keep the following requirements in mind:

- Do not include more than a total of 21 indicators to keep the M&E burden manageable as these indicators must be monitored annually and will be reported to the GEF and other stakeholders through the annual PIR (see M&E section for further details).

- The GEF Core indicators relevant to this project (see Annex) must be added to the results framework at the objective level. See detailed methodologies here. Note that these indicators will be monitored annually in the GEF PIR. They must also be reported to the GEF at midterm and end of the project.

- You will need to list the source of the baseline data and targets and explain how this data was collected and how it should be collected during project implementation in the Monitoring Plan in annex. The Monitoring Plan should also outline how indicators and the corresponding targets were derived, such as what calculations or figures add up to a total value.

- The indicators must be directly connected to the objective or outcome and need to measure the change we would like to see at the objective or outcome level.

- The indicators should not be a list of outputs or activities that will be delivered under that outcome or objective. Indicators such as “number of participants to a workshop” or “report produced” for example are NOT objective or outcome level indicators and should not be included in the results framework!

- As many indicators as feasible must be gender responsive and disaggregated by gender (i.e. # male, # female, not # households).

- Include socioeconomic co-benefit indicators

- The indicators should link to data that the country already measures and collects and should link to the SDG indicators where feasible.

- Each indicator must have a baseline value and an expected value to be achieved by the mid-point (mid-term target) of implementation and an expected value to be achieved by project closure (end-of-project target).

- The indicators must be SMART: specific; measurable; attributable; relevant; time-bound, timely, trackable and targeted. See GEF Evaluation Policy for additional details.

Do not include footnotes to the framework as these will not be transferred to the project’s PIR. Any notes should be included in the Monitoring Plan in Annex.

Do not make any changes to the standard headings below (i.e. project objective, outcome 1, outcome 2 etc.). Do not embed tables within the Results Framework; use simple text-only formatting.

I entered this mandatory text from the latest template. Please, leave it here.

Atlas numbers and awarding of the proposal in Atlas should be done after the CEO approval of the EA proposal. Please, add Atlas IDs.

Could you attach the TBWP as word format table? This arrangement is difficult to read and/or add comments. You may always send it as separate excel table with the prodoc.

Total for BLs 74500 and 72500 (miscell. and supplies) is 7.34% of the whole GEF budget, while advised max. for both BLs together is 5%. Please, reduce it to max 5%.

Direct project costs cannot exceed the amount approved in the EA proposal, that is 15,000USD. Please, reduce the DPC cost.

Please, enter the budget notes in word format.

BN A: Please, use the correct terminology in budget notes. BN A concerns BL 71300, which is local consultant. Professional services is the name for different BL (74100).

BN E: The same as above. 71200 is ‘international consultant’.

BN G: please specify more details/tasks that the consultants will perform. Distinguish between local and international consultants and company services, as these three use different budget accounts. Adjust this BL and divide it according to the same BLs. Do not mix different BLs in one BN.

BN H: Letter H is not included in TBWP. Please add/correct.

BN J : Please, specify more details, spell out MCC

This will be as Annex 2: Multi-year work-plan…in the latest prodoc template. Adjust please accordingly.

The whole entered text is from the latest prodoc tamplate. Add please information where necessary (in organigram, in yellow highlighted places) and do not delete or change this text. It is mandatory.

Enter whole this section in a place as per the latest template (i.e. as section VII)

Add please info.

Add please info.

Finalize please the organisation structure where appropriate.

This part should be as part VI in the latest prodoc template.

If this is 8K per year, then the total price will be too high. 8K is quite a lot for an audit and we suppose that it will not be necessary on annual basis. Please, adjust accordingly, delete “per year”. The same price should appear in TBWP. Currently audit cost in TBWP is 10K. We consider it as exaggerated price.

I entered the text from the latest template. Please, leave it here and add information (highlighted places)

This is mandatory text from the latest prodoc template. Do not change please.

This is the list of mandatory annexes from the latest prodoc template. Please add them. If some of them are bulky, kindly send them separately or as a link to the webpage.

Annex 9 (Gender..) should be attached as well, even you only add under the title of Annex the sentence: Gender analysis and Action plan will be prepared during inception phase of the project and included into the Inception Report.

Annex 8 (LoA) – please do not have it signed until reviewed by RCU

Please, use the standard template for Risk-log (attached below and in prodoc template)

This is text from older prodoc template related to management arrangements. It does not actually belong among ToRs

Add Atlasl IDs please

Add please

Price in each cell in this column should be specified in total. It is not sufficient to reflect only the price per case/each process, but express the total price. Adding amounts in each cell should give the total 15,000USD. Try to adjust the table, so that it fits together.

Delete please, if not applicable

# Text boxes

Project Manager (Implementing Partner)

Project Board/Steering Committee

Development Partners

UNDP

Project Executive

Office of Environmental Planning & Policy Coordination (OEPPC)

Beneficiary Representatives

Directors of key Stakeholder Ministries and Departments

Project Assurance

UNDP CO and UNDP-GEF Regional Technical Advisor

Project Support (e.g. Project team)

Project Organisation Structure

Responsible Party A

Responsible Party C

Responsible Party B

Project Assurance

UNDP PaO

Project Implementation Team:

TNC/FBUR Project Manager

Admin Assistant

Accountant

Project Board

Project Organisation Structure

Thematic Working Group on GHGI & Mitigation

Thematic Working Group on RSO, Education, Training & Public Awareness

Thematic Working Group on Vulnerability & Adaptation

Project Support

Government Departments

Private Sector

NGO’s

Thematic Working Group on Mitigation

Senior Beneficiary:

Directors of key Stakeholder Ministries and Departments

Executive:

Director, OEPPC

Senior Supplier:

Country Director, UNDP PaO