# Annual Work Plan

Year 3 (January 2016 - June 2016)

| EXPECTED OUTPUTS And the basis, related indicators and annual targets | PLANNED ACTIVITIES List the outputs of activities and actions undertaken in connection with them | TIME FRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of funding | Budget description | Amount in USD |
| Output 1: Comprehensive information on citizens' satisfaction with the operation of the decentralized system and local government, obtained in a systematic way Basis: Prepared data base on the current situation including citizens’ perception analyses Indicators: www.dajpredlog.mk web portal updated and promoted | Upgrade (migration on MLSG server) and promotion of www.dajpredlog.mk web portal Analysis of the web portal operation Upgrade of the web portal based on findings and recommendations from the analyses Posting the questions from the Survey of citizens' perceptions Promotion of the upgraded web portal | X | X |  |  | UNDP/MLSG | MLSG | Costs for the translation, companies and promotional event | 2,500.00 |
| Output 2: Innovative programme for support of partnerships between municipalities and civil and business sectors for improved service delivery, put into practice Basis: Absence of programme for innovative partnership for service delivery problem solving Indicators: Established e-System for local (administrative) regulations (eRegulations system) | 2.1 Establishing e-System for local (administrative) regulations (eRegulations system) | X | X |  |  | UNDP/MLSG | MLSG | Costs for national expert | 10,000.00 |
| Output 4: Mechanisms for support and promotion of inter-municipal cooperation (IMC) improved and new IMC practices established Basis: Prepared software enables creation of an e- IMC records. IMC web page designed. Report on the status of IMC in 2014 completed. Indicators: Completed e-IMC records IMC web page updated and promoted Realized agreements for support of the three networks Established IMC for blind persons and persons with vision disabilities | 4.1 Filling the IMC electronic records with data from 2014 IMC Status Report 4.2 Upgrade (migration on the MLSG server) and promotion of www.imc.org.mk website 4.3 Operationalization of the agreements with the 3 planning centers (Vardar, Northeast and Pelagonia) that established inclusive networks 4.4 Establishing IMC for blind persons and persons with vision disabilities in Pelagonia planning region | X X | X X |  |  | UNDP/MLSG | MLSG UNDP Municipalities of Pelagonia and Northeast Planning Regions | Expenses for the Project Office and the Project employees, costs for the companies and events, and grants to the three Centres. Costs for companies and consultants regarding the implementation of the Networks Programmes in Pelagonia and Northeast Planning Regions. | 16,377.00 20,000.00* 17,000.00* |
| Output 5: Prepared analysis of the opportunities for service delivery to the private sector by the Centres for Planning Regions Development Basis: In accordance with the recommendations of the Study, units for SMEs support are established in 5 Centres for Development of Planning Regions. Indicators: Realized agreements for supporting the 5 Centers and additional support provided for implementation of the priority activities A study tour organized in the Czech Republic and three workshops in the country | 5.1 Effective implementation of the agreements on the establishment of Centres for Support of SMEs in five Centres for Planning Region Development (Skopje, Polog, East, Southwest and Southeast Regions) 5.2 Organization of a study tour to the Czech Republic and a workshop with Czech experts in the country | X | X X |  |  | UNDP/ MLSG | MLSG UNDP | Grants for the 5 Centres Costs for the study trip and for the workshops and translation Costs for the national expert | 42,000.00 40,000.00* |
| Output 6: The Local Government Sustainable Development Programme for the period 2015 - 2020 prepared in a participatory way Basis: Adopted Programme with an Action Plan Indicators: Regular on-going monitoring in accordance with the Methodology for monitoring of the implementation of the Programme with the Action Plan | 6.1 Implementation of the Methodology for monitoring of the implementation of the Programme with the Action Plan | X | X |  |  | UNDP/ MLSG | MLSG | Costs for consultants and translation | 3,000.00 |
| Output 7: Development of and support for the rural tourism for revitalization, economic development and finding new ways for development of the rural municipalities and returning the population in the villages Basis: Maps (registers) of rural tourism potentials hasn’t been prepared. The rural tourism is underdeveloped and does not contribute enough for the economic development of the villages. Still, there is process of depopulation of the villages Indicators: Mapped potentials and prepared rural tourism registers for four (4) planning regions. Partnerships established and min. one project for development of the rural tourism infrastructure prepared for the four (4) pilot municipalities (one municipality in each of the four (4) least developed planning regions). Establishment of territorial networks for development of rural tourism initiated in the each of the four (4) least developed planning regions | 7.1 Mapping of the potentials for development of forms of rural tourism and preparation of rural tourism registers in the four (4) least developed planning regions in the country (Northeast, Vardar, Southwest and Polog) in accordance with the Decision of the Government for classification of the planning regions based on the degree of development for the period 2013 – 2017 (OG 88/2013) 7.2 Establishment of partnerships between the municipalities and citizens associations in four (4) pilot municipalities (one in each of the four (4) least developed planning regions) for preparation of small infrastructure projects for rural tourism development by the communities/rural population. 7.3 Creation of a territorial network for promotion of the wealth of the rural areas through involvement of the local authorities, the local branches of the central authorities, the tourism operators, and the owners of rural tourism facilities (in the four least developed planning regions) | X | X X X |  |  | UNDP/MLSG | MLSG | Expenses for Project and Project Office employees, events, administrative costs Costs for translation, companies and consultants. | 40,000.00 |

PLANNED BUDGET (TOTAL) 113,877.00 (MLSG) + 60,000.00 (UNDP*) + 17,000.00 (Municipalities of the Northeast and Pelagonia planning Regions*) = 190,877.00 USD

*Planed finances

Approved by the Steering Committee Members:       										Skopje, 19 November 2015

Mr. Lirim Shabani,

Minister for Local Self-Government 		            			_____________________

Mr. Alessandro Fracassetti,

Deputy Resident Representative of UNDP 				_____________________

Mr. Hakif Ismaili, Bureau for Regional Development		             	_____________________