United Nations Development Programme

Country: MONTENEGRO

PROJECT DOCUMENT

| Project Title: Development of Montenegro’s Third National Communication to UNFCCC |
| --- |
| UNDAF Outcome(s): |  |
| UNDP Strategic Plan Environment and Sustainable Development Primary Outcome: Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihood for the poor and excluded. UNDP Strategic Plan Secondary Outcome: Countries are able to reduce the likelihood of conflict, and lower the risk of natural disasters, including from climate change |
| Expected CP Outcome(s): Balanced and equitable regional economic growth based on sustainable planning and use of natural resources that will provide a high quality of life and long-term economic opportunities for its inhabitants. |
| Expected CPAP Output (s): Output 3.1. Climate change adaptation and mitigation measures integrated into sector strategies and urban planning. |
| Executing Entity/Implementing Partner: UNDP |  |
| Implementing Entity/Responsible Partners: Ministry of Sustainable Development and Tourism, UNDP Montenegro |  |

Agreed by (Government):

Date/Month/Year

Agreed by (Executing Entity/Implementing Partner):

Date/Month/Year

Agreed by (UNDP):

Date/Month/Year

Contents

List of Acronyms	4

I.	Situation analysis	6

II.	Strategy	8

Project Rationale	8

Country Ownership	9

Project objective, outcomes and outputs/activities	10

Activities for project implementation	11

National Circumstances and Institutional arrangements	11

National Green House Gas Inventory	12

Vulnerability and Adaptation	13

Mitigation actions	14

Other information	15

Gender dimension	16

Sustainability and Replicability	16

III.	Project Results Framework:	18

IV.	Total budget and workplan	24

V.	Management Arrangements	29

VI.	Monitoring Framework and Evaluation	31

VII.	Legal Context	34

VIII.	annexes	34

Annex 1. Risk Analysis	35

Annex 2. Terms of Reference for key project personnel	37

Annex 3.  Social and Environmental Screening	44

SESP Attachment 1. Social and Environmental Risk Screening Checklist	48

ANNEX 4. Final Report of Montenegro National Communication’s	52

A.	Details of the project	53

B.	Project identification phase	53

C.	Project implementation phase	54

D.	Next steps	59

E.	Additional information	59

# List of Acronyms

AFOLU - Agriculture, Forestry and Other Land–Use

CO – Country office

CPAP - Country Programme Action Plan

CPD – Country Programme Document

DIM - Direct Implementation modality

ECRAN - Environment and Climate Regional Accession Network

EPA - Environmental Protection Agency

ETS and non-ETS sectors – Emission Trading System and Non Emission Trading System

ESCO – Energy Service Company

FBUR - First Biennial Update Report

GEF – Global Environmental Facility

GHG – Greenhouse Gases

GSP - Global Support Programme

INDC – Intended Nationally Determined Contribution

INC - Initial National Communication

IPPU - Industrial Processes and Product Use

MSDT - Ministry for Sustainable Development and Tourism

MONSTAT – State Statistical Office

M&E – Monitoring and Evaluation

NIS - National Inventory System

NCCS - National Climate Change Strategy

NCSD - National Council for Sustainable Development and Climate Change

NGO – Non Governmental Organization

PB – Project Board

PM – Project Manager

PMB – Project Management Board

PMU - Project Management Unit

PRODOC – Project Document

QA - Quality Assurance process

QC – Quality Control

PAC – Procurement Appraisal Committee

PPR - Project Progress Reports

RCU - Regional Coordination Unit

REDD – Reducing Emissions from Deforestation and forest degradation

SBAA – Standard Basic Assistance Agreement

SESP - Social and Environmental Screening Procedure

SNC - Second National Communication

TNC – Third National Communication

TOR – Terms of references

TBW – Total Budget and Workplan

UNFCCC – United Nations Framework Convention on Climate Change

UNDAF - United Nations Development Assistance Framework

UNDP - United Nations Development Programme

# Situation analysis

Montenegro became a party to the UN Framework Convention on Climate Change by succession, after becoming independent in 2006 year, becoming a non-Annex I Party to the UNFCCC.

The responsible authority and main body for coordinating and articulating national climate actions is the Ministry for Sustainable Development and Tourism, through its newly established Directorate for Climate Change. Taking into account the necessity of inter-sectoral cooperation on climate policy, the National Committee for Sustainable Development and Tourism has been transformed into the National Committee for Sustainable Development and Climate Change to ensure cooperation among all relevant stakeholders. This body has an advisory role and the mandate to actively participate in shaping of the national climate policy. Montenegro also developed National Climate Change Strategy by 2030 and submitted its INDC to the UNFCCC Secretariat, both in September 2015.

On its path towards EU, Montenegro will have to integrate numerous requirements of the EU climate policy into domestic legal framework and align it with the climate acquis. The latest EU Report on Montenegro’s progress in the accession process states that, in the area of climate change, a comprehensive national climate policy and a climate change strategy need to be developed in line with the expected EU 2030 policy framework on climate and energy. Substantial efforts are also needed to fully integrate climate considerations into all relevant sectorial policies and strategies. Furthermore, Montenegro regularly associated itself with EU positions at international level.

The intended nationally determined contribution (INDC) to the 2015 Climate Agreement was submitted to the UNFCCC Secretariat in September 2015, consistent with those of the EU and its Member States.

Regarding alignment with the climate acquis, significant efforts are required, especially, to strengthen the country’s monitoring, reporting and verification capacity. The establishment of the National Council for Sustainable Development and Climate Change marks a positive development in inter-institutional coordination and cooperation. The Council needs to be strengthened further.

Montenegro participated regularly in the Environment and Climate Regional Accession Network (ECRAN). Administrative capacity in the area of climate change needs to be significantly strengthened in order to address the need for enhanced climate action in a sustainable manner, beyond the project by project basis. Strengthening administrative capacity in the fields of environment and climate change needs to be a country priority.

On the international level, Montenegro is an active player, trying to assume voluntarily advanced reporting obligations, preparing for national contributions for the post 2020 period, and supporting EU in advocating its ambitious targets and objectives.

Montenegro is implementing several international obligations to move towards a low-carbon economy, including the establishment of goals for increasing the share of renewable energy by final energy demand, improving energy efficiency, and reducing GHG emissions in electricity generation by reducing operational hours of the existing lignite-fired power plant. In the public buildings sector, the government is focused on improving energy efficiency and comfort conditions in targeted buildings (hospitals, health centers, elementary schools, high schools, special schools, kindergartens and dormitories). In the residential buildings sector, the government is focused on penetration of solar water heating systems, as well as heating systems on modern biomass and improving living and working conditions for households residing on summer pasture lands. In the transport sector, the government is mostly focused on improving infrastructure (highway, motorways).

As a main driver of Montenegro’s economic growth and investment, the tourism sector is responsible (directly and indirectly) for the large share of GHG emissions from the transport, accommodation and other tourism-related activities. In April 2013, UNDP launched the Towards Carbon Neutral Tourism project that will adopt a comprehensive approach to minimizing the carbon footprint of Montenegro’s main and most dynamic economic sector, the tourism. Its ultimate objective is to reduce GHG emissions from tourism sector.

The Government adopted 30% reduction as an internal target by 2030 (INDC), compared to 1990 level, and is now evaluating and implementing mitigation options to meet this goal.

Under its commitments as a non-Annex 1 party of the UNFCCC, Montenegro prepared two National Communications (NCs), an Initial National Communication in 2011, the Second National Communication (SNC) in 2015. Montenegro follows non-Annex I guidance for the preparation of the NC and GHG inventories. Moreover, Montenegro submitted its First Biennial Update Report (FBUR) in January 2016.

In relation to gender, in Montenegro, there is only 17.2% of women in the National Parliament and 14% in local parliaments; only 3 out of 17 ministers are women, there is only 1 woman among 21 mayors, while female participation in entrepreneurship is below 10%.

Montenegro has a good legislative framework that ensures gender equality and equal access to opportunities. It also developed the appropriate institutional framework in order to promote gender equality. It is based on national legislation and the international instruments on human rights, as well as other legal documents of UN, CoE, EU and other international organizations, concerned with equality between women and men. However, the public in the country, and even representatives of the executive, legislative and judicial branches at all levels, are not sufficiently familiar with these documents. Due to the inadequate implementation of laws and court practice, the criticism from the EU often arrives. The Parliamentary Board for Gender Equality and the Department for Gender Equality within the Ministry of Human and Minority Rights are established, and there is also an institute of Ombudsman. However, there is no ultimate political will to empower women and achieve gender equality, and the resources allocated are symbolic. There is still a lack of personal sensibility and existence of stereotypical gender regimes of skilled workers, judges, prosecutors and other responsible actors, which is caused by the continuous problem in the implementation of law.

The Government of Montenegro has been demonstrating its commitment to the principles and norms of gender equality and to the fundamental documents on the advancement of women and takes concrete measures to ensure gender equality in both legislation and practice in the country. Recognizing this challenge, the Government of Montenegro is making serious efforts in meeting the needs of vulnerable population, including women and prepared the Action Plan for Achieving Gender Equality (2013-2017). Besides the Action Plan, various studies related to the status of women in Montenegro have been produced and published in recent years, such as Socio-economic status of women in Montenegro and Women in politics. Although the Government of Montenegro has made positive moves towards eliminating gender inequality, in practice the status of women in the country still needs further enhancement to ensure their equality.

UNDP mission in this area is defined as a support to Montenegro to set up gender agenda aligned with international frameworks (EU&UN) and development priorities of the country. In addition, the UNDP’s Country Office Montenegro, in collaboration with the Government of Montenegro, has identified the following priority areas for intervention, clearly listed in Country Office Gender Strategy that is aligned with the UNDAF for Montenegro:

• Improving the institutional framework to ensure that women and girls have full access to their rights, mainly political ones;

• Increased consideration of gender concerns in the allocation of public financial resources;

• Improving social perceptions and attitudes towards gender roles.

# Strategy

## Project Rationale

Under its commitments as a non-Annex 1 party of the UNFCCC, Montenegro has prepared two National Communications (NCs), an Initial National Communication in 2011, the Second National Communication (SNC) in 2015. Montenegro follows non-Annex I guidance for the preparation of the NC and GHG inventories. Moreover, Montenegro submitted its First Biennial Update Report (FBUR) in January 2016.

The National Climate Change Strategy (NCCS) until 2030 and appropriate Strategic Environmental Impact Assessment were adopted in September 2015. The NCCS provides methodology and detailed sectoral projections for key emission sectors, along with sensitivity and uncertainty analysis. The sectoral projections were done for two scenarios: with existing measures (WEM) and with additional measures (WAM). Besides, potential GHG saving measures with their belonging costs, adaptation measures to climate change with its belonging costs, compliance with EU climate change legislation, action plan and investment planning, and financing strategy implementation are also envisaged by this strategic document. National INDC technical paper is prepared and submitted to UNFCCC Secretariat and it is an integral part of the NCCS.

The Third NC will build on the gap/constraints findings and recommendations of previous National Communications and BUR work, as well as the outcomes of the ongoing complementary projects in the country and is planned to be submitted to the UNFCCC in the first half of 2020.

The main related gap/constraints, findings and recommendations are the following:

- GHG Inventory

The estimate of direct GHG emissions for all sectors for the period 1990-2011 was made in accordance with IPCC 1996 methodology, using a Tier 1 approach (SNC). The total measurement uncertainty of GHG emissions from the entire inventory is calculated according to Tier 1 methodology, amounting 4% for the whole period.

The main gaps and constraints are:

- Lack of data in certain categories of the inventory;

- Data uncertainty and inconsistency, especially in agriculture and forestry, as well as waste sector;

- Insufficient technical and human capacity for addressing the impact of climate change on different sectors, especially in Statistical Office MONSTAT;

- Insufficient financial resources.

In order to improve uncertainty for GHG emissions, it is necessary to:

- Revise the activity data;

- Calculate national emission factors;

- Change the calculation methodology to multiple Tier, i.e. do an estimate of measurement uncertainty by also using Tier 2 methodology, which is based on a simulation in Monte Carlo;

iv)   Continue applying and working in accordance with quality assurance and quality control practices (QA/QC).

2. Vulnerability and Adaptation:

The main gaps and constraints:

- Lack of an adequate strategic framework, lack of expert and scientific research, lack of data;

- Lack of technical and scientific research on the vulnerability of human health to climate change;

- No national strategy to mitigate the effects of climate change on water resources and agriculture;

- Lack of confidence in global end regional climate models;

- Insufficient technical and human capacity and financial resources.

In order to improve vulnerability assessment and the drafting of adaptation measures, it is necessary to:

- Strengthen early warning system for extreme weather and hydrology events;

- Strengthen support for scientific-research work and to improve inter-institutional cooperation;

- Establish databases per sector and to secure their regular updating,

- Encourage the drafting of studies, analyses, projections of the impact of climate change on priority sectors for implementation of adaptation measures.

3. Mitigation:

The main gaps and constraints:

- Align regulations with EU legislation in the area of climate change (transposition of EU directives) and strengthen legislative implementation;

- Develop appropriate strategic framework (action plan) that will define roles, responsibilities and activities to mitigate the impact of climate change;

- Integrate mitigation measures into strategic documents;

- Define goals for the reduction of GHG emissions - overall and per sector;

- Analyse possibilities for and develop NAMA projects;

- Introduce and promote the best available techniques (BAT) for mitigation measures regarding climate change, especially in the energy and industry sector.

In order to improve the analyses of GHG abatement measures and assess their impact, it is necessary to:

- Develop plans of emission reductions per sector;

- Build institutional capacities for the application of methods and models for assessing the impacts of measures, formulating and prioritizing programs and measures and evaluating the cost of measures aimed at reducing GHG emissions.

## Country Ownership

The responsible authority and main body for coordinating and articulating national climate actions is the Ministry for Sustainable Development and Tourism, through its newly established Directorate for Climate Change. Taking into account the necessity of inter-sectoral cooperation on climate policy, the National Council for Sustainable Development has been transformed into the National Council for Sustainable Development, Climate Change and Integrated Coastal Zone Management to ensure cooperation among all relevant stakeholders. This body has an advisory role and the mandate to actively participate in shaping of the national climate policy.

The project also intends to strengthen stakeholder’s participation including local community engagement, and women empowerment to collectively participate in addressing climate change issues and challenges in Montenegro. The stakeholders of the project are expected to come from various backgrounds, with particular emphasis on related sectors. Apart from the Ministry of Sustainable Development and Tourism, these will include the Ministry of Economy, Ministry of Agriculture and Rural Development, Ministry of Education and Science, Ministry of Transport and Maritime Affairs, Environmental Protection Agency, Institute of Hydrometeorology and Seismology, Public Health Institute, State Statistical Office, University of Montenegro, Academia of Sciences and Arts, National Council for Sustainable Development, Climate Change and Integrated Coastal Zone Management, NGOs, business-associations, including partnerships with women’s groups, youth groups and other NGOs and mass-media.

The Ministry of Sustainable Development and Tourism is the main institution for climate change related issues, and also responsible for land administration and waste sector. The Ministry of Economy is responsible for energy and industry sector, the Ministry of Agriculture and Rural Development is responsible for agriculture and forestry, while the Ministry of Transport and Maritime Affairs is responsible for transport sector. The role of the Public Health Institute within the process will be public health sector, while the Institute of Hydrometeorology and Seismology is responsible for climatology data and predictions. The role of the Environmental Protection Agency is to facilitate GHG Inventory, while Statistical Office is responsible for climate and gender data collection and processing. University of Montenegro along with the Academia is responsible for research in various areas related to climate change.

The National Council for Sustainable Development, Climate Change and Integrated Coastal Zone Management, headed by the President of the country, involves relevant experts from various ministries, NGO sector, business associations and independent experts. The Council is advisory body to the Government of Montenegro for sustainable development and climate change policy, responsible for providing professional support in strengthening inter-sectoral coordination and broader cooperation between social groups in the context of the harmonization of sectoral policies with the objectives and priorities of Montenegrin sustainable development. The media and NGOs responsibilities through the TNC will be public awareness campaigns, knowledge sharing and dissemination. The role of the Ministry of Education and Science is to integrate climate change topics in schools’ and universities curricula. At the end, business association will help with major involvement of private sector in climate change related issues.

## Project objective, outcomes and outputs/activities

The key objectives of the project are the following:

- Meeting the reporting requirements under Article 4 and 12 of the Convention; and

- Capacity building and enhancement of the national technical and institutional capacities in:

  - data collection, processing, archiving interpretation, and dissemination for GHG inventory,

  - development of mitigation and adaptation actions,

  - integrating climate change issues into sectoral and national development priorities.

Besides complying with reporting requirements, the project will link complementary and interrelated project milestones, in a much more efficient way, coordinating the schedules of expected outcomes. The capacities within various relevant institutions are already built through the INC, SNC and FBUR processes. Their involvement in the TNC process will further strengthen the institutional technical abilities to support the efficient implementation of the UNFCCC and enhance the reporting process overcoming weaknesses, constraints and gaps. Through the TNC, further capacity building on national and local level in order to implement climate change/environment legislative is envisaged. Involvement of the relevant institutions and experts in preparing TNC report provides developing communication systems between relevant institutions that enhance information sharing. Important outcome of the project is developing capacity of the national negotiators team to contribute to climate change international negotiations and formal dialogues under the UNFCCC in order to analyze opportunities and obligations rising from new regional and international initiatives.

The project outcomes will be achieved through a wide range of outputs compatible with the UNFCCC goals. Knowledge and awareness extension on climate change related issues at the planning and policy levels is crucial, so the institutions will be able to establish climate change issues into relevant social, economic, scientific and environmental policies, programs and strategies, in particular, those for low carbon development and adaptation to the adverse effects of climate change. Besides, such issues should be also reflected through national development priorities. That way, identified and prioritized mitigation and adaptation actions will be consistent with national sustainable development priorities and climate change mitigation and adaptation related projects may be eligible for mobilizing additional funding resources by GEF or other multilateral and bilateral organizations. The TNC implementation shall facilitate the following:

- Further upgrading and improving the national GHG inventory system, by filling out the gaps and minimizing the uncertainties from the previous inventories. This is particularly related to agriculture, waste and forestry input data. GHG emissions data collection process will be institutionalized, defining the process description, data flows, calculation, monitoring and verification, QA/QC and responsibilities, based on the IPCC adopted methodologies. Assessment of potential options to mitigate the increase in GHG emissions and to enhance removals by sinks will update existing and develop new mitigation measures taking into account long-term projections, up to 2030. Improving removals by sinks potential and considering estimation for REDD possibilities in the country is particularly important, since close to 70% of the country territory is covered with forests and forest land. These new mitigation measures will provide good platform for development of GHG projections upgraded scenarios and obtaining more precise calculation of GHG savings potential;

- Development of the analysis of options to adapt to the impacts of climate change with special attention to adequate adaptation for public health, water management and agriculture, because these sectors have not been properly assessed earlier;

- Addressing the capacity building needs and involvement of stakeholders, both on national and local level, within the context of a shared vision on climate change adaptation and mitigation;

- Continuation of awareness raising activities on climate change that interact with targeted audiences of various age groups including students, teachers, governmental officials, private sector, non-government organizations, civil society and general public;

- Mainstreaming gender perspectives through collecting and analyzing gender disaggregated data in relation to climate change. The data will be used in defining specific gender needs and proposing actions to promote women’s participation in defining mitigation and adaptation strategies;

- Updating an assessment of financial and technological requirements for climate change studies, research, monitoring, education, training and awareness raising institutional strengthening and climate change policy development will be elaborated, publicize findings and promote national communication.

## Activities for project implementation

### National Circumstances and Institutional arrangements

All components that define the national circumstances provided in the SNC/FBUR will be revised and updated, considering the new emerging issues in the country. For that purpose, the most recent databases and information systems and the recent socio-economic assessment will be used, as well as the data from new national documents and ongoing projects. Information on climate conditions, environment, population, natural and economic resources, socio-cultural, economic and social conditions will be updated, such as review of existing and ongoing international, regional, national projects, legislation and strategic documents. Policies and legal framework will be described in order to state the link between economic sectors development and the support of policies and legal framework.

For the first time, socio-economic parameters and their relation to climate change will be analyzed and special attention will be paid to collection of gender-disaggregated data in relation to climate change, as well as information that include gender-related issues and vulnerable groups under different conditions. Institutional arrangement can enhance effective coordination among all relevant stakeholders from the public and private sector, in meeting the reporting requirements under the Convention. It will assist in establishing procedures for continual collecting, processing, reporting and archiving required data and information.

### National Green House Gas Inventory

Under the previous NC’s, inventories of emissions by sources and removals by sinks were prepared for the years 1990-2011 according to IPCC 1996 methodology. During the recent FBUR work, GHG inventories were recalculated for the years 1990-2013 according to IPCC 2006 methodology, covering GHG emissions from the following sectors: energy, industrial processes and product use (IPPU), agriculture, forestry and other land–use (AFOLU) and waste. The national GHG inventory will be developed by the Environmental Protection Agency (EPA), which is also responsible for annual National GHG Emission Report preparation and its submission to the UNFCCC. The TNC project seeks to close the gaps for further development of the national GHG inventory, comprising several activities:

- An initial meeting will be held between the TNC team and the EPA team in order to harmonize criteria, delivery timetables, synergies, and other aspects, aiming to optimize the use of human, technical and financial resources. Special attention will be given to the coordination in the product delivery schedule of projects, and the national greenhouse gas inventory calculation and reporting requirements for the TNC.

- The IPCC 2006 methodology will be applied, that best corresponds to the national circumstances, according to recently updated GHG inventory, prepared within FBUR process. For this purpose, the GHG inventory collection data plan will be prepared with procedures for data archiving and role of institutions in the process.

- GHG inventory verification will take place consequently with the quality assurance process (QA/QC) in accordance with newly prepared QA/QC plan. The process will involve several participants: ministries, statistics, research institutions and technical experts. The outcomes will be in the consolidated technical skills and improvement of capacity of the involvement of stakeholders.

- Calculation of GHG inventory for period (2016-2018) will be carried out by trained staff of the EPA, supported by national/international experts. The strong institutional arrangements will facilitate efficient management of GHG inventory processes.

- Achieving technological synergies: the technological data base platform must match with the selected software, for the inventory calculation, through an interface. This will enable an automatic and more efficient calculation procedure to obtain national greenhouse gas inventory for all the years included in the TNC.

- Montenegro’s National Inventory System (NIS) management model defines the process description, data flows, calculation, monitoring and verification, and their representation. National GHG inventory for the TNC will be adopting the concept of integration in all its stages of processes. This process involves different stakeholders with arrangement for coordination and implementation of a set of human, technical and financial resources to assist and develop the regular and ongoing preparation of the national inventory.

- Procedure manuals, as part of the National Inventory System will be prepared, as well, in order to institutionalize the GHG inventory process.

The following methodological guidance will be used: Revised IPCC Guidelines (2006); IPCC Good Practice Guidance and Uncertainty Management in National Greenhouse Gas Inventories (2000); IPCC Good Practice Guidance on Land Use, Land-Use Change and Forestry (2003). The Handbook developed by UNDP on “Managing the National Greenhouse Gas Inventory” (2005) will be followed while conducting the national inventory in order to identify recommendations for the design of an inventory management system. Finally, the software and GHG reporting tables developed by the UNFCCC Secretariat (Decision 17/CP.8) for archiving data and data reporting of inventory results will be used. Appropriate approaches to ensure the quality of the estimates will be adopted. The taskforce will also be responsible for developing data archiving system to facilitate the inventory process, especially in their respective sectors.

National GHG inventory for the entire time series (1990-2018) will be updated to reduce previous gaps and uncertainties. This is particularly related to AFOLU and waste sectors, where the input data are not reliable and/or still missing. Agriculture and forestry input data will be recalculated, according to the new methodologies, developed by Statistical Office. Besides, waste statistical data will be updated as well in accordance with new methodology, developed in studies and strategic framework. New input data will require revision and recalculation of the existing GHG inventory (1990-2013). For the first time, the country-specific emission factors will be calculated and QA/QC plan for the GHG inventory will be applied.

To sustain the inventory team within the EPA, training opportunities will be promoted, especially for AFOLU sector.

### Vulnerability and Adaptation

Under the first and second NCs, V&A analysis based on the EBU-POM regional climate model, the variability of climate and climate changes observed up to 2010 with focus on analysis of extreme events (max. temperature, max. precipitation, droughts, heat waves and heavy rains) and country’s vulnerability to those events were prepared. The vulnerability analysis covered the following sectors: hydrology, with particular analysis of water regimes in two rivers, agriculture and forestry, coast and coastal zones, ground water, health and urban areas. Special attention was given to basic characteristics of small streams of the Montenegrin coast, assessing vulnerability of Montenegrin forest sector to climate change, analysis and projections of climate change impacts on the future distribution and growth of the main tree species in Montenegro and impact of climate change to human health. Some adaptation measures were prepared mostly within INC work and covered all the sectors (biodiversity, agriculture, forests, coastal area and human health). More detailed economic impacts of climate change in Montenegro, assessing Montenegrin water sector in light of climate change and assessing vulnerability of Montenegrin forest sector to climate change were also prepared within INC process.

Through vulnerability and adaptation assessments, the TNC will pay special attention to more direct links between the climate change scenarios and their socio-economic impacts. The project will be focused on closing some of the gaps between the obtained results and the ones reported during the INC/SNC and/or the achievements identified to date. It should be noted that the financing needs for adaptation studies are considerable, starting by running appropriate climate models, the development of vulnerability assessments, proposing the adaptation actions, developing models of possible hazards, and designing national adaptation policy.

Within the V&A study, many activities need to be elaborated, including the following:

  - Describe the progress made by Institute of Hydrometeorology and Seismology in monitoring climate, especially extreme weather events and risks, specifically those related to the quantity and quality of climate information generated and reported;

  - Compile information and update appropriate climate models, based on those used in INC/SNCs. Future climate change will be investigated using more parameters based on data availability and the testing/use of other IPCC models will complement the findings;

  - Development of models of possible hazards with related costs will be undertaken, so the impacts (e.g. rise of the sea level) can be assessed and appropriate adaptation measures defined, in order to increase adaptation capacities;

  - Interpretation of the results of climate models, making comparisons between results, establishing patterns and/or trends, strengthening the understanding of Montenegrin climate, formulating conclusions and consensus.

  - Revision of vulnerability & adaptation studies: the first step will consist of a compilation process of information related to vulnerability & adaptation assessment, already realized within the INC/SNC. Then, compilation of the information, selection of the methodology and development of the studies related to vulnerability of public health, water management and agriculture and formulation of conclusions on vulnerability, as well as preparation of appropriate adaptation plans for water ecosystems and agriculture. Since the agriculture sector is exceptionally vulnerable to extreme weather, special attention will be devoted to expected changes in extreme weather events frequency, intensity and distribution and their impact on agro-climatic conditions. Therefore, a vulnerability assessment in this sector will be extended in order to more precisely determine the climate change influence on agricultural production and the links with water resources which are also highly vulnerable to climate change and will be the subject of analysis. These synergetic potentials between the two sectors which are highly vulnerable to climate change will contribute to better adaptation of agricultural production, especially to drought and help propose irrigation plan and suitable farming systems for actual and expected agro-ecological conditions. Finally, analysis related to food security will be addressed. For public health sector, The National Heat Health Action Plan and The National Health Climate Change Adaptation Strategy will be developed. Studies preparation should gather employees from the Institute of Hydrometeorology and Seismology, Institute of Public Health, Biotechnology Faculty and Institute of Forestry and other technical experts;

  - Review of adaptation policies: the adaptation plan, including cost-benefit analysis for most vulnerable sectors will be prepared. Additionally, based on the vulnerability studies elaborated by the project, an adaptation policy proposal will be carried out consisting of specific actions to promote adaptation. Finally, the National Adaptation Plan will envisage adaptation actions based on the review of the existing adaptation processes and progress made in newly developed studies;

  - Circulation of studies, strategies and plan among the stakeholder and public in order to increase awareness.

### Mitigation actions

In the scope of previous reports to the UNFCCC Secretariat (INC, SNC and FBUR), the analysis of the reduction of greenhouse gasses emission has been prepared in order to assess the potential to which climate change impact could be alleviated at a national level, in line with economic development goals. The analysis envisaged the recognition of appropriate measures, practical examples, projects and/or interventions in all sectors where GHG emissions can be reduced and/or sinks increased during the period 2014-2020. GHG projections were based on two scenarios development (Business as Usual and mitigation) in all key sectors (energy, industry, agriculture, LULUCF and waste). For the purpose of calculation GHG savings in energy sector LEAP software was used, while IPCC software for non-energy sectors (industry, agriculture, LULUCF and waste) was applied.

The mitigation analysis will build on the results obtained in previous national communications. Analysis and results existing in the SNC/FBUR will be revised, GHG projections for the period 2020-2030 will be made and mitigation options will be summarized and analyzed. TNC will analyze the progress made in implementing mitigation measures in energy sector and appropriate subsectors, such as energy industries subsector, the largest contributor to the total GHG emissions in the country, energy consumption subsectors, as well as industrial processes and product use sector. Essential analysis of energy consumption will be further extended, including energy consumption in manufacturing industries subsector, transportation subsector and residential/commercial/public subsector, starting from the compilation and review of all the relevant initiatives, undertaken by different national actors, especially since SNC/FBUR.

The institutional capacity will be assessed upfront. Prior to the detailed GHG abatement analysis, all energy modelling work prepared recently in the scope of the National Climate Change Strategy and various international projects (LOCSEE, SLED, etc.) will be elaborated. Besides, the new data and strategic framework will be collected. Long-term analysis up to 2030, will be carried out based on at least 2 scenarios creation (with existing measures WEM and with additional measures WAM), using new IPCC 2006 methodology for key sectors, as in GHG inventory (energy, IPPU, AFOLU and waste) and appropriate software tools (Long-range Energy Alternatives Planning system and IPCC 2006). The analysis is going to include separately energy and non-energy sectors. Considering socio-economic trends, in-depth analysis of CO2 sinks potential and evaluation of REDD possibilities will be also part of the assessment. For the first time, the mitigation assessment will take into consideration the future participation of national installations within EU-ETS scheme. Besides, GHG abatement action plan will be conducted with major emphasis on energy and industrial processes sector. The plan will include cost-benefit analysis, timeframe, assessment of technology options for different mitigation options in various sectors, institutional capacity-building needs to sustain mitigation work and the related legal and institutional frameworks. Special attention will be given to increasing institutional technical capacities for undertaking mitigation estimation. In addition, the awareness raising activities will be strengthened through redesigned national climate web-platform, workshops, policy briefs and dissemination of leaflets.

The mitigation analysis will be carried out in the context of Montenegro’s development priorities in order to ensure that the mitigation options proposed are aligned with development needs. It will include relevant information on the barriers and opportunities for implementation of the proposed measures.

Thus, the mitigation related activities can be summarised as follows:

  - Capacity assessment for emission projections and their institutional set up conducted and short list of at least three options for institutional set up for projections presented to decision makers for their review and decision. The proposed three institutional solutions for projections should be ranked.

  - GHG emissions and sinks projections for the period 2020-2030. Projections should account for energy and non-energy sectors in line with division to ETS and non-ETS sectors in order to benefit national planning and alignment with EU acquis;

  - Analysis and possibilities related to mitigation presented in the SNC/FBUR reviewed and upgraded, including progress on implementation of the National Climate Change Strategy;

  - Necessary data and relevant information for scenario development collected, analyzed and used in the scenario development;

  - Mitigation scenarios with existing measures (WEM) and with additional measures (WAM) until 2030 for abatement of GHG emissions considering socio-economic trends developed;

  - A GHG emission abatement action plan until 2030 developed;

  - Long-term mitigation possibilities analyzed and proposed;

  - Potential for GHG emission reduction paths updated and mapped out and forward-looking set of policy framework and recommendations outlined;

  - Improved assessment of GHG mitigation options, measures related to NC;

  - Capacity for collecting and analyzing information on policy and mitigation measures strengthened;

  - REDD possibilities considered and evaluated;

  - Stakeholder consultation workshops, and awareness raising activities conducted, booklets and information materials disseminated, quarterly policy briefs in the form of 2 pager or infographics on various CC themes produced;

  - Redesign of the national climate change clearing mechanism i.e. www.unfccc.me in order to reinstate it as the most important repository of climate change related knowledge on national level.

### Other information

This section is considered as one of the most important information relevant towards achieving the objective of the Doha Work Programme on Article 6 of the Convention. In response to the Decision 15/CP.18 - Doha work program on Article 6 of the Convention, the preparation of the Third National Communication will be associated with increasing activities related to education, training and public awareness raising functions on climate change issues provided to identified stakeholder categories within different groups and communities having different relation to awareness and knowledge, including schools, universities, media and NGOs. The TNC will also have an important role in enhanced climate change information sharing during workshops as well as distribution of presentations and reports. The findings of the studies will be disseminated among universities, research institutions and others for further elaboration and creation of linkages with relevant thematic and specific areas.

A number of activities have been planned under this component, covering:

- list of projects in climate change area;

- analysis of national and regional institutional frameworks, projects, programmes and documents related to climate change;

- financial, technical and capacity constraints and needs;

- technology and technology transfer;

- climate research and systematic observation, education, training and public awareness;

- capacity building;

- collection, synthesis and analysis of relevant information;

- studies for implementation of climate change/environmental legislation by local governments;

- legal assistance in transposition and approximation of the EU and international climate change legislation and obligations.

The unavailability of financial and technical resources and absence of systematic approach are already considered as the main barriers to strengthen capacity and ensure sustainability of implementation of various programmes related to climate change. Description of key gaps and challenges faced by the relevant institutions will be evaluated and listed in addition to suggesting the measures to overcome these gaps. The update of financial, technical and capacity needs and constraints of institutions responsible for activities related to climate change will be conducted through the collection, synthesis and analysis of existing information. The results of this project will be used, as well as the results of other relevant projects that have been implemented by different stakeholders. The stakeholders are expected to come from a range of backgrounds, with particular emphasis on line ministries, agencies, in addition to local communities, local authorities and NGOs, media, research institutions and private sector.

The TNC will list all climate-change related recent and on-going projects. Identification of cost-effective technologies to implement priority mitigation and adaptation options, in addition to socio-economic consequences of different mitigation and adaptation options in Montenegro will be assessed. On research and systematic observation, the TNC activities will include identification of organizations and institutions involved in climate related research and systematic observations, their activities and programmes, capacities, gaps, needs and priorities, links and participation in regional and international activities. Finally, a description of the support received will be elaborated, along with contribution provided by the GEF for the TNC preparation.

The chapter will pay special attention on providing detailed studies for implementation of climate change/ environmental legislation. The first phase of aforementioned study for Support to the process of building the capacity of local self-governments for the implementation of environment and climate change legislation, related to recommended model central government – local self-government is already under preparation. Within the scope of the TNC, the second phase - procedures and the third phase - implementation of capacity building programs are to be developed. Besides, legal assistance in transposition and approximation of the EU and international climate change legislation and obligations in order to strengthen its implementation on national level is also envisaged.

### Gender dimension

The previous NCs had not dealt with gender mainstreaming issues, leaving room for improvement in the new NC. Mitigation actions largely focused on reduction of industrial greenhouse gas emissions, but also include the practice of energy efficiency and the application of renewable energy in commercial and residential sectors. The role of women in such climate change mitigation strategies has received no attention in previous NCs, as actions have been perceived to be either technical or scientific in nature.

The TNC project will incorporate a gender perspective in the identification, description and preparation of mitigation and adaptation actions, when relevant. Also, the women in the TNC will be meaningfully involved, not only as beneﬁciaries but also in the decision-making process of climate change related activities. As climate change is partly the result of human behavior and affects all people, mitigation and adaptation strategies in the TNC will consider the gendered patterns. Moreover, understanding how the different social roles and economic status of men and women are affected differently by climate change will be considered for appropriate adaptation and mitigation actions. In this sense, and for this specific project, the update of the national circumstances chapter of the TNC will consider this gender dimension in order to better understand how the different roles of men and women in Montenegro and social and economic circumstances may affect Montenegro’s ability to deal with mitigating and adapting to climate change.

Additionally, the project coordination will ensure that gender considerations become part of the TNC. Training Manuals on Gender and Climate Change will be followed. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men.

In this regards, the project will give special attention to gender as one of the key stakeholders and beneficiaries from climate change adaptation and mitigation.

In addition, workshops will be conducted in which gender balance will be ensured. Furthermore, gender will be mainstreamed into the TNC in a way that ensures that equitable participation of women in the decision-making process of climate change adaptation and mitigation. With regard to the technical team to be hired to implement the enabling activity, gender balance will be also considered.

## Sustainability and Replicability

The project will continue further on the work done under the INC and SNC and will involve key national institutions/partners/stakeholders/experts responsible for specific sections/topics, in order to maintain continuity of the process. In addition, one of the main project objectives is to raise capacity of national stakeholders in order to meet future reporting requirements under the UNFCCC. The newly established Directorate for Climate Change, as the main responsible institution for climate change policy, will also pay important role in maintaining the sustainability and replicability of the project results.

Following standard practice, the TNC will be adopted by the Government of Montenegro and subsequently sent to the UNFCCC Secretariat by the national UNFCCC focal point.

# Project Results Framework:

| This project will contribute to achieving the following Country Programme Outcome as defined in CPAP or CPD: Balanced and equitable regional economic growth based on sustainable planning and use of natural resources that will provide a high quality of life and long-term economic opportunities for its inhabitants |
| --- |
| Country Programme Outcome Indicators: 1. Quality of life: HDI disaggregated by region (2010: North: 6.21, 7.6; Centre: 6.5)/ NHDR; 2. Unemployment rates disaggregated by region (North: 29.6%, South 10.3%, Centre: 18%)/MONSTAT; greenhouse gas emissions (2003: 5320.17 CO2 eq tonnes) National Communications to UNFCCC |
| Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one): 1. Mainstreaming environment and energy OR 2. Catalyzing environmental finance OR 3. Promote climate change adaptation OR 4. Expanding access to environmental and energy services for the poor. |
| Applicable GEF Strategic Objective and Program: CCM-3: Foster Enabling Conditions to Mainstream Mitigation Concerns into Sustainable Development Strategies, Programme 5: Integrate findings of Convention obligations and enabling activities into national planning processes and mitigation targets. |
| Applicable GEF Expected Outcomes: Outcome B. Policy, planning and regulatory frameworks foster accelerated low GHG development and emissions mitigation |
| Applicable GEF Outcome Indicators: Indicator 7. Number of countries meeting convention reporting requirements and including specific GHG reduction targets |
|  | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| Project Objective (equivalent to output in ATLAS) To assist Montenegro in the preparation of its Third National Communication (NC) for the implementation of the obligations under the UNFCCC | Preparation and submission of Montenegro’s TNC | Under its commitments as a non-Annex 1 party of the UNFCCC, Montenegro prepared two NCs, an Initial NC in 2011, the Second NC (SNC) in 2015. Montenegro submitted its First Biennial Update Report (FBUR) in January 2016. | The Third National Communication for Montenegro adopted and submitted to the UNFCCC. | The TNC publication prepared and available at the UNFCCC web site: http://unfccc.int/national_reports/non-annex_i_natcom/submitted_natcom/items/653.php | The climate change issues not high on the political agenda of the country (due to other economic and social issues) and thus TNC not adopted by the Government on time. Parliamentary elections planned for September 2016, which can bring changes in structure of the Management Board (in case of changes within the main partner institutions), and/or slow down implementation of the activities planned for 2016. |
| Outcome 1 National Circumstances and Institutional Arrangements | Information on national circumstances and institutional arrangements relevant for the preparation of the TNC reviewed and updated and a chapter on National Circumstances prepared. | The SNC contains National Circumstances chapter, which will, for the purposes of TNC, be update with relevant information. | Chapter on National Circumstances developed 1.1 National circumstances in Montenegro updated, and appropriate CC measures to implement the UNFCCC are redefined and explained; 1.2 Information related to national circumstances; geography, climate, natural resources and socio-economic conditions related to the GHG emissions and absorption collected, analyzed and updated; 1.3 Specific needs and concerns arising from climate change, national development objectives, priorities; circumstances and programmes analyzed; 1.4 Gender disaggregated data in relation to climate change collected and analyzed, i.e. women roles and responsibilities in the context of climate change in addition to gender inequalities in terms of vulnerabilities, and access to modern energy, finance, and decision-making; 1.5 Specific gender empowerment needs analyzed and proper actions to promote women’s participation in defining mitigation and adaptation strategies which contribute to improved gender equality, MDGs achievements, and sustainable development in Montenegro proposed. | The final TNC publication |  |
| Outcome 2 National GHG Inventory | National inventory of anthropogenic emissions by sources and removal by sinks of all GHGs for the preparation of TNC including a national inventory report and the establishment of a national archiving system for GHG Inventory prepared and capacity to collect this information on an ongoing basis for future NCs enhanced | GHG Inventory currently covers period 1990-2013, and was updated in accordance with 2006 Guidelines. | Include data for two additional years, 2016-2017 (Second BUR will cover 2014-2015) 2.1 Activity data, required by IPCC 2006 guidelines, collected and analyzed, data gaps filled and inventory and database improved where needed; 2.2 Emission factors for key source categories prepared and recalculated; 2.3 Through development of the annual data collection plan, the GHG inventory data collection and analysis process maintained and national data collection capability enhanced and strengthened; 2.4 GHG inventories under the NC for all sectors (energy, IPPU, AFOLU, waste) and all gases considered in IPCC 2006 guideline for the years 2014-2017 prepared; 2.5 An analysis of key GHG emitting sectors (energy, IPPU, AFOLU, waste) carried out, procedures and arrangements for collection and archiving of data and role of institutions involved in preparation of GHG inventory described, and uncertainty analysis conducted; 2.6 Improved input data and GHG inventory especially for AFOLU (agriculture, forestry and other land-use) sector; 2.7 Constraints facing national inventories per sectors reviewed; 2.8 Quality assurance and Quality control plan developed and procedures for the QA/QC for the inventory data applied. | The final TNC publication | Main industries/GHG emitters might be unwilling or unable to provide relevant data for update of the GHG Inventory. |
| Outcome 3 Climate Change Mitigation | Updated report on policies and measures to mitigate CC prepared and capacity to collect and analyze this information on an ongoing basis for future NCs strengthened. Analysis of mitigation options prepared | SNC and FBUR cover certain mitigations measures which will be further reviewed and updated and various mitigations options developed. | Report on mitigation measures developed and analysis of mitigation options prepared. 3.1 Capacity assessment for emission projections and their institutional set up conducted and short list of at least three options for institutional set up for projections presented to decision makers for their review and decision. The proposed three institutional solutions for projections should be ranked. 3.2 GHG emissions and sinks projections for the period 2020-2030. Projections should account for energy and non-energy sectors in line with division to ETS and non-ETS sectors in order to benefit national planning and alignment with EU acquis; 3.3 Analysis and possibilities related to mitigation presented in the SNC/FBUR reviewed and upgraded, including progress on implementation of the National Climate Change Strategy; 3.4 Necessary data and relevant information for scenario development collected, analyzed and used in the scenario development; 3.5 Mitigation scenarios with existing measures (WEM) and with additional measures (WAM) until 2030 for abatement of GHG emissions considering socio-economic trends developed; 3.6 A GHG emission abatement action plan until 2030 developed; 3.7 Long-term mitigation possibilities analyzed and proposed; 3.8 Potential for GHG emission reduction paths updated and mapped out and forward-looking set of policy framework and recommendations outlined; 3.9 Improved assessment of GHG mitigation options, measures related to NC; 3.10 Capacity for collecting and analyzing information on policy and mitigation measures strengthened; 3.11 REDD possibilities considered and evaluated; 3.12 Stakeholder consultation workshops, and awareness raising activities conducted, booklets and information materials disseminated, quarterly policy briefs in the form of 2 pager or infographics on various CC themes produced; 3.13 Redesign of the national climate change clearing mechanism i.e. www.unfccc.me in order to reinstate it as the most important repository of climate change related knowledge on national level. | The final TNC publication | Insufficient technical and human capacities of national partners to deal with mitigation issues. |
| Outcome 4 Vulnerability Assessment & Adaptation to climate change (V&A) | Climate change vulnerability assessment of key priority sectors extended, and those for new sectors conducted, and plans for programmes containing measures to facilitate adequate adaptation to climate change prepared | SNC covers vulnerability assessment for certain sectors was developed. | VA for key priority sectors extended and for new identified sectors developed 4.1 Current climate change and the impact on socio-economic development of Montenegro described and analyzed; 4.2 Climate change scenarios revised using appropriate models, expert’s capacity on modeling climate change scenarios strengthened; 4.3 Vulnerability assessments for all sectors (water resources, coastal area, biodiversity, agriculture and forests, public health) conducted; 4.4 Progress in implementation of adaptation actions proposed in the SNC assessed. The adaptation plan for most vulnerable sectors (water resources, agriculture and public health), including cost-benefit analysis prepared; 4.5 Develop models of possible hazards with related costs, as well as impacts (e.g. rise of the sea level), in order to increase adaptation capacities, i.e. define proper adaptation measures. 4.6 Framework for effective integration of adaptation measures into national strategies identified; 4.7 A public campaign - to inform and raise awareness among the population about the impact of climate change on health with a special focus on vulnerable groups conducted; 4.8 Adaptation of health sector to climate change in order to protect population health, including Vulnerability Assessment Study, National Heat Health Action Plan and National Health Climate Change Adaptation Strategy prepared; 4.9 Adaptation to climate change in water resources management prepared; 4.10 Adaptation to climate change in agriculture with special emphasis on drought and irrigation plan prepared; 4.11 Stakeholder consultation workshops, and awareness raising activities conducted, booklets and information materials disseminated. | The final TNC publication | Insufficient/understaffed capacities of national partners to deal with vulnerability and adaptation issues. |
| Outcome 5 Other relevant information to the achievement of the UNFCCC (education, training and public awareness, financial aid and technology transfer, research and systematic observation, capacity building) | Other relevant information is described, covering research/systematic observation, technology transfer, education, public awareness, capacity building. Research and institution related to climate change and systematic observation assessed. Capacity building needs in local governments analyzed. | Low awareness raising in relation to climate change issues (health impact, projections, extreme weather conditions etc). Existing National Approximation Strategy summarising what bylaw, directives etc. will have to be transposed and aligned within the national legislation. | 5.1 A list of projects with focus on barriers and opportunities for future development of GHG inventory and implementation of adaptation and mitigation actions provided; 5.2 National plans and programmes on systematic observation, climate research and forecasting capacity reviewed; 5.3 Information on NGOs, individuals, community and sectoral initiatives in terms of climate change adaptation and mitigations explored, updated, and publicized as a contribution to the project’s knowledge sharing framework; 5.4 Information on integration of UNFCCC requirements into national legislation and strategies updated; 5.5 Study on support to the process of building the capacity of local self-governments for the implementation of environment and climate change legislation - procedures & implementation of capacity building programs prepared; 5.6 Legal assistance in transposition and approximation of the EU and international climate change legislation and obligations in order to strengthen its implementation on national level. | The final TNC publication |  |
| Outcome 6 Description of constraints and gaps, financial, technical and capacity needs | Identification, assessment and updates of constraints, gaps and needs related to financial aid and technology transfer provided, including summary of support needed and received. | Chapter on climate change related technological and capacity building constraints and gaps provided within the FBUR. This is to be properly updated within the TNC. | Chapter on technological, financial and capacity building needs and gaps developed. 6.1 Needs, gaps and priorities for education, training and public awareness identified and programmes prepared; 6.2 Information on financial, technical and capacity needs and constrains associated with the fulfilment of the national obligations under UNFCCC updated; 6.3 Progress on actions expected or implemented to address the restrictions, gaps and needs identified for the fulfilment of the national obligations under UNFCCC on the basis of the previous NCs assessed; 6.4 Financial resources, technology transfer and technical assistance received from the GEF, Annex I Parties and other developed country Parties, the GCF and multilateral institutions for GHG mitigation activities assessed. | The final TNC publication |  |
| Outcome 7 Compilation, editing and publication of final TNC report, Monitoring and Evaluation | Publication and submission of the third national communication, Monitoring and Evaluation | The INC and SNC developed and submitted to the UNFCCC in 2010 and 2015 respectively. | The final TNC publication submitted to the UNFCCC 7.1 TNC edited, finalized and reviewed by stakeholders; 7.2 Executive Summary prepared; 7.3 TNC document produced, translated into English language; 7.4 TNC submitted to project steering committee for technical review; 7.5 TNC published; 7.6 TNC submitted and approved by the Parliament; 7.7 TNC submitted to Executive Secretary of the UNFCCC; 7.8 TNC distributed to stakeholders; 7.9 Monitoring and evaluation in accordance with the requirements inclusive of monitoring, reporting and preparation of final audits for the entire project; 7.10 Lessons learned analysed, shared, and thematic studies and results disseminated. | Web site of the UNFCCC |  |

# Total budget and workplan

| Award ID: | 00090471 | Project ID(s): | 00096225 |
| --- | --- | --- | --- |
| Award Title: | Third National Communication |
| Business Unit: | MNE10 |
| Project Title: | Development of Montenegro’s Third National Communication to the UNFCCC |
| PIMS no. | #5817 |
| Implementing Partner (Executing Agency) | UNDP |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: National Circumstances and Institutional Arrangements | UNDP | 62000 | GEF | 71300 | Local Consultants | 0 | 0 | 5,000 | 0 | 5,000 | 1 |
|  |  |  |  | 72100 | Contractual services- companies | 0 | 2,000 | 1,000 | 500 | 3,500 | 2 |
|  |  |  |  | 71400 | Contractual services- individuals | 3,000 | 0 | 0 | 0 | 3,000 | 3 |
|  |  |  |  | 71600 | Travel | 0 | 500 | 500 | 500 | 1,500 | 4 |
|  |  |  |  | 72400 | Communication | 0 | 500 | 500 | 0 | 1,000 | 5 |
|  |  |  |  | 72500 | Supplies | 0 | 200 | 200 | 100 | 500 | 6 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 500 | 0 | 500 | 7 |
|  |  |  |  |  | Total Outcome 1 | 3,000 | 3,200 | 7,700 | 1,100 | 15,000 |  |
| OUTCOME 2: National Greenhouse Gas Inventory | UNDP | 62000 | GEF | 72100 | Contractual services- companies | 0 | 40,000 | 20,000 | 10,000 | 70,000 | 8 |
|  |  |  |  |  | Total Outcome 2 | 0 | 40,000 | 20,000 | 10,000 | 70,000 |  |
| OUTCOME 3: Climate Change Mitigation | UNDP | 62000 | GEF | 71200 | International Consultants | 0 | 10,000 | 10,000 | 0 | 20,000 | 9 |
|  |  |  |  | 71400 | Contractual Services - individuals | 5,000 | 5,000 | 10,000 | 17,000 | 37,000 | 3 |
|  |  |  |  | 71300 | Local Consultant | 0 | 17,000 | 12,750 | 2,750 | 32,500 | 10 |
|  |  |  |  | 72100 | Contractual services - companies | 500 | 0 | 0 | 1,500 | 2,000 | 11 |
|  |  |  |  | 71600 | Travel | 0 | 1,000 | 1,000 | 0 | 2,000 | 4 |
|  |  |  |  | 72400 | Communication | 500 | 0 | 0 | 500 | 1,000 | 5 |
|  |  |  |  | 74200 | Audio visual & printing prod. cost | 500 | 1,000 | 1,000 | 1,000 | 3,500 | 12 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 1,000 | 1,000 | 0 | 2,000 | 7 |
|  |  |  |  |  | Total Outcome 3 | 6,500 | 35,000 | 35,750 | 22,750 | 100,000 |  |
| OUTCOME 4: Vulnerability Assessment & Adaptation to climate change (V&A) | UNDP | 62000 | GEF | 71200 | International Consultants | 0 | 5,000 | 8,500 | 5,000 | 18,500 | 13 |
|  |  |  |  | 71300 | Local Consultants | 0 | 2,000 | 5,000 | 10,000 | 17,000 | 14 |
|  |  |  |  | 71400 | Contractual Services - individuals | 15,000 | 5,000 | 9,000 | 7,000 | 36,000 | 3 |
|  |  |  |  | 71600 | Travel | 0 | 2,000 | 2,000 | 1,000 | 5,000 | 4 |
|  |  |  |  | 72100 | Contractual services – companies | 0 | 18,000 | 10,000 | 10,000 | 38,000 | 15 |
|  |  |  |  | 72400 | Communication | 0 | 500 | 1,000 | 1,000 | 2,500 | 5 |
|  |  |  |  | 74200 | Audio visual & printing prod. cost | 0 | 1,000 | 500 | 500 | 2,000 | 12 |
|  |  |  |  | 72500 | Supplies | 0 | 500 | 0 | 0 | 500.00 | 6 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 500 | 500 | 500 | 1,500 | 7 |
|  |  |  |  | 75700 | Trainings, workshops and Conferences | 1,000 | 2,500 | 3,000 | 2,500 | 9,000 | 16 |
|  |  |  |  |  | Total Outcome 4 | 16,000 | 37,000 | 39,500 | 37,500 | 130,000 |  |
| OUTCOME 5: Other relevant (trainings and public awareness, capacity building, legal support) | UNDP | 62000 | GEF | 71300 | Local Consultants | 7,000 | 10,000 | 10,000 | 10,000 | 37,000 | 17 |
|  |  |  |  | 71400 | Contractual services - Individuals | 3,000 | 5,000 | 10,000 | 10,000 | 28,000 | 3 |
|  |  |  |  | 71600 | Travel | 0 | 5,000 | 5,000 | 1,000 | 11,000 | 4 |
|  |  |  |  | 72400 | Communication | 0 | 500 | 500 | 500 | 1,500 | 5 |
|  |  |  |  | 73100 | Supplies | 546 | 1,000 | 500 | 500 | 2,546 | 6 |
|  |  |  |  | 74200 | Audio visual & printing prod. cost | 0 | 1,000 | 1,000 | 1,000 | 3,000 | 12 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 500 | 500 | 500 | 1,500 | 7 |
|  |  |  |  | 72100 | Contractual services - companies | 0 | 10,000 | 10,000 | 5,000 | 25,000 | 18 |
|  |  |  |  |  | Total Outcome 5 | 10,546 | 33,000 | 37,500 | 28,500 | 109,546 |  |
| OUTCOME 6: Description of constraints and gaps, financial, technical and capacity needs | UNDP | 62000 | GEF | 71300 | Local Consultants | 0 | 0 | 5,000 | 0 | 5,000 | 19 |
|  |  |  |  | 71400 | Contractual services - individuals | 0 | 5,000 | 0 | 0 | 5,000 | 3 |
|  |  |  |  |  | Total Outcome 6 | 0 | 5,000 | 5,000 | 0 | 10,000 |  |
| OUTCOME 7: Compilation, editing and publication of final TNC report Monitoring, learning, adaptive, feedback & evaluation | UNDP | 62000 | GEF | 72100 | Contractual Services - companies | 0 | 0 | 0 | 6,000 | 6,000 | 20 |
|  |  |  |  | 74500 | Miscellaneous | 0 | 0 | 1,500 | 500.00 | 2,000 | 7 |
|  |  |  |  | 74100 | Professional Services | 3,000 | 3,000 | 3,000 | 3,000 | 12,000 | 21 |
|  |  |  |  |  | Total Outcome 5 | 3,000 | 3,000 | 4,500 | 9,500 | 20,000 |  |
| Project management unit | UNDP | 62000 | GEF | 71400 | Contractual services-individuals | 4,954 | 10,000 | 0 | 21,000 | 35,954 | 22 |
|  |  |  |  | 74598 | Direct project cost-GOE | 1,000 | 1,000 | 2,000 | 2,000 | 6,000 | 23 |
|  |  |  |  | 64398 | Direct project cost-staff | 500.00 | 1,000 | 1,000 | 1,000 | 3,500 | 24 |
|  |  |  |  |  | Total Management | 6,454 | 12,000 | 3,000 | 24,000 | 45,454 |  |
| PROJECT TOTAL | 45,500 | 168,200 | 152,950 | 133,350 | 500,000 |  |

| Summary of Funds: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Total |
|  |  |  |  | GEF | 45,500 | 168,200 | 152,950 | 133,350 | 500,000 |
|  |  |  |  | Government in-kind | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 |
|  |  |  |  | TOTAL | 65,500 | 188,200 | 172,950 | 153,350 | 580,000 |

Budget notes – justifications:

OUTCOME 1/ Activity 1:  National Circumstances and Institutional Arrangements

- Short term local consultant will be engaged for development of the National Circumstances Chapter.

- Local company is planned to be engaged to work on gender related data collection.

- Project team consisting of the project manager and local short-term consultants

- Travel expenses for related/UNFCCC trainings, workshops, exchange of experiences and similar

- Communications related expenses: acquisition of audio visual equipment, land telephone charges, mobile telephone charges, e-mail subscription, postage …

- Office supplies

- Various miscellaneous expenses which are permitted by the rules

OUTCOME 2 / Activity 2: National Greenhouse Gas Inventory

- National institutions in charge of GHG Inventory: EPA, MONSTAT and possibly other stakeholders, producers of state statistics.

OUTCOME 3/ Activity 3: Climate Change Mitigation

- Short Term international consultant to provide inputs in related to mitigation measures (as a support to national consultants).

- Project team consisting of the project manager and local short-term consultants

- Local consultants to work on mitigation chapter (with the support/training/coaching from international consultant).

- National company to provide support in organization of various meetings/trainings

4.   Travel expenses for related/UNFCCC trainings, workshops, exchange of experiences and similar

5.  	Communications related expenses: acquisition of audio visual equipment, land telephone charges, mobile telephone charges, e-mail subscription, postage …

- Translation costs during various meetings, and/or necessary promotion/education material related to climate change.

7. 	Various miscellaneous expenses which are permitted by the rules

OUTCOME 4/ Activity 4:  Vulnerability Assessment & Adaptation to climate change (V&A)

- Short term international consultant to work on V&A, together with the national consultants’ team and provide necessary trainings/coaching.

- Local consultants to work on vulnerability assessment and adaptation measures (in cooperation with international consultant).

3. 	Project team consisting of the project manager and local short-term consultants

4.  	Travel expenses for related/UNFCCC trainings, workshops, exchange of experiences and similar

- Engagement of local/national companies to develop chapter on V&A, together with the national/international consultants to be engaged for specific issues

5.  	Communications related expenses: acquisition of audio visual equipment, land telephone charges, mobile telephone charges, e-mail subscription, postage

12. Translation costs during various meetings, and/or necessary promotion/education material related to climate change.

6.  	Office supplies

7.  	Various miscellaneous expenses which are permitted by the rules

16. Costs of training workshops and various stakeholder consultations meetings

OUTCOME 5/ Activity 5: Other relevant (trainings and public awareness, capacity building, legal support)

- Long-term local consultant to provide legal support and advise to the MSDT

3.	Project team consisting of the project manager and local short-term consultants

4.	Travel expenses for related/UNFCCC trainings, workshops, exchange of experiences and similar

5.	Communications related expenses: acquisition of audio visual equipment, land telephone charges, mobile telephone charges, e-mail subscription, postage

6. 	Office supplies

12.	Translation costs during various meetings, and/or necessary promotion/education material related to climate change.

7. 	Various miscellaneous expenses which are permitted by the rules

18. 	National companies to be engaged to provide public awareness raising and capacity development related services

OUTCOME 6 / Activity 6: Description of constraints and gaps, financial, technical and capacity needs

19.  Local consultant to develop chapter on gaps and constraints.

3.  Project team consisting of the project manager and local short-term consultants

OUTCOME 7 / Activity 7: Compilation, editing and publication of final TNC report Monitoring, learning, adaptive, feedback & evaluation

20. Finalization and submission of the TNC (design, print and postal costs).

7.   Various miscellaneous expenses which are permitted by the rules

21. Anticipated audit fee

Project Management

22. These funds will be used to cover part of the salary of the project staff.

23.-24.  Direct project cost – GOE, Direct project cost – staff: Direct Project Costs (DPC) are the costs of administrative services (such as those related to human resources, procurement, finance, and other functions) provided by UNDP in relation to the project. Direct project costs will be charged based on the UNDP Universal Pricelist (UPL) or the actual corresponding service cost, in line with GEF rules on DPCs. The amounts indicated here are estimations, however as part of annual project operational planning the Direct Project Costs would be defined and the amount included in the yearly budgets.

# Management Arrangements

Project will be implemented according to Direct Implementation (DIM) modality.

The Implementing Partner for this project is UNDP Montenegro. The Implementing Partner is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources.

The Ministry for Sustainable Development and Tourism (MSDT), as Responsible Partner, implies the shared responsibility for timely and verifiable attainment of project objectives and outcomes. MSDT will provide support to, and inputs for the implementation of all project activities. The MSDT will nominate a high level official who will serve as the National Project Director (NPD) for the project implementation. The NPD will chair the Project Steering Committee (PSC) and other relevant stakeholder, sectoral and working groups under the project, and be responsible for providing government oversight and guidance to the project implementation. The NPD, in addition to the PSC members will not be paid from the project funds, but will represent a Government in-kind contribution to the Project.  The newly established Directorate for Climate Change within the Ministry of Sustainable Development and Tourism will be in charge of future climate activities in the country.

The project organisation structure is as follows:

The Project Board (also called Project Steering Committee) is responsible for making by consensus, management decisions when guidance is required by the Project Manager, including recommendation for UNDP/Implementing Partner approval of project plans and revisions. In order to ensure UNDP’s ultimate accountability, decisions should be made in accordance with standards that shall ensure management for development results, best value for money, fairness, integrity, transparency and effective international competition. In case a consensus cannot be reached within the Board, final decision shall rest with the UNDP Programme Manager. The Project Board meetings will be organized at least twice a year, and if necessary on more frequent basis. The Project Board will be comprised of the following individuals:

Mr. Srdjan Mugosa, Director of the Directorate for Climate Change, Ministry of Sustainable Development and Tourism (MSDT)

Mr. Djordjije Vulikic, UNFCCC national focal point, Director of the Directorate for Climate Change, MSDT

Ms. Lidija Scepanovic, Deputy Director, Environment Protection Agency

Ms. Marija Vukcevic/Mr. Andrej Lakic, Directorate for European Integrations and International Cooperation, MSDT (GEF operational focal point and Green Climate Fund focal point)

Mr. Luka Mitrovic, Institute for Hydro-Meteorology and Seismology

Ministry of Economy.

The final list of PMB members will be defined after their official nominations by relevant ministries/institutions.

The Project Manager will run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager function will end when the final project report and documentation required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project).  Add additional detail as appropriate.

The project assurance role will be provided by the UNDP Country Office, specifically Mr. Borko Vulikic, UNDP Programme Officer.  Additional quality assurance will be provided by the UNDP Regional Technical Advisor as needed.

The main project partners/beneficiaries will be included in the Project Management Board. In addition, the project will target general public through set of public awareness raising activities.

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  In order to accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware. Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy16 and the GEF policy on public involvement17.

The Project Team will consist of Project Manager and Project Assistant, UNDP CO Montenegro, Centre for Sustainable Development, Programme jointly implemented by the Government of Montenegro and UNDP as the model of close partnership. The administrative support (HR, procurement) will be provided by UNDP CO Operations Unit. The same team will also work on implementation of the project on development of the Second Biennial Update Report.

# Monitoring Framework and Evaluation

The project will be monitored through the following M&E activities. The M& E budget is provided in the table below.

Project start:

A Project Inception Workshop will be held within the first 2 months of project start with those with assigned roles in the project organization structure, UNDP country office and where appropriate/feasible regional technical policy and programme advisors as well as other stakeholders.  The Inception Workshop is crucial to building ownership for the project results and to plan the first year annual work plan.

The Inception Workshop should address a number of key issues including:

- Assist all partners to fully understand and take ownership of the project; Detail the roles, support services and complementary responsibilities of UNDP CO and RCU staff vis à vis the project team; Discuss the roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms. The Terms of Reference for project staff will be discussed again as needed.

- Based on the project results framework and the relevant GEF Tracking Tool if appropriate, finalize the first annual work plan.  Review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks.

- Provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements.  The Monitoring and Evaluation work plan and budget should be agreed and scheduled.

- Discuss financial reporting procedures and obligations, and arrangements for annual audit.

- Plan and schedule Project Board meetings.  Roles and responsibilities of all project organisation structures should be clarified and meetings planned.  The first Project Board meeting should be held within the first 12 months following the inception workshop.

An Inception Workshop report is a key reference document and must be prepared and shared with participants to formalize various agreements and plans decided during the meeting.

Quarterly:

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high. Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Bi-annual progress:

- Status Survey Questionnaires to indicate progress and identify bottlences as well as technical support needs will be carried out twice a year.

Annual progress:

- Annual report on project progress will be prepared as a regular UNDP CO reporting requirement.

Periodic Monitoring:

A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities.

Day to day monitoring of implementation progress will be the responsibility of the Project Coordinator, Director or CTA (depending on the established project structure) based on the project's Annual Work plan and its indicators. The Project Team will inform the UNDP CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

Periodic monitoring of implementation progress will be undertaken by the UNDP CO through quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

End of Project:

During the last three months, the project team will prepare the Project Terminal Report (Annex 4). This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Audit clause:

Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

Learning and knowledge sharing:

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Communications and visibility requirements:

Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.   The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at:

http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf. Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment. The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

M& E workplan and budget

| Type of M&E activity | Responsible Parties | Budget US0 Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | Project Manager UNDP CO, UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | Oversight by Project Manager Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | Project manager and team UNDP CO UNDP RTA UNDP EEG | None | Not applicable |
| Periodic status/ progress reports | Project manager and team | None | Quarterly |
| Mid-term Evaluation | Project manager and team UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | None | Not applicable for EA projects |
| Final Evaluation | Project manager and team, UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | None | Not applicable for EA projects |
| Project Terminal Report | Project manager and team UNDP CO local consultant | 0 | At least three months before the end of the project |
| Audit | UNDP CO Project manager and team | Indicative cost per year: 3,000 | Yearly |
| Visits to field sites | UNDP CO UNDP RCU (as appropriate) Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses | US0 22,000 (+/- 5% of total budget) |  |

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA [or other appropriate governing agreement] and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# annexes

Annex 1. Risk Analysis

Annex 2. Terms of Reference for key project personnel

Annex 3. Signed Social and Environmental Screening

Annex 4. End of Project Report

## Annex 1. Risk Analysis

RISK LOG

| Project Title: Development of Montenegro’s Third National Communication to UNFCCC | Award ID: 90471 | Date: April 2016. |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The climate change issues not high on the political agenda of the country (due to other economic and social issues) and thus TNC not adopted by the Government on time. | April 2016 | Political | In case this risk occurs Montenegro might not submit TNC to the UNFCCC Secretariat in time. P = 3 I = 4 | Work closely with the newly established Directorate for Climate Change within the Ministry of Sustainable Development and Tourism (MSDT), especially with the UNFCCC focal point | UNDP Programme Manager | UNDP Programme Manager | April 2016 | no change |
| 2 | Parliamentary elections planned for September 2016, which can bring changes in structure of the Management Board (in case of changes within the main partner institutions), and/or slow down implementation of the activities planned for 2016. | April 2016 | Political | In case this risk occurs project team might have to introduce the project to the new structure in main partner institutions and explain their related role and obligations. As for the activities planned for 2016, in case of delay, they would have to be postponed for next year. P = 3 I = 3 | Work closely with the project partners on more technical level, and plan activities in such a way that high-level management changed do not jeopardise the implementation. | UNDP Programme Manager | UNDP Programme Manager | April 2016 | no change |
| 3 | Main industries/GHG emitters might be unwilling or unable to provide relevant data for update of the GHG Inventory. | April 2016 | Operational | In case this risk occurs there will be higher uncertainty of the GHG inventory data and consequently projects will have higher uncertainty. P = 3 I = 3 | Work closely with the industries (especially two biggest emitters: KAP and TPP) in order to explain the necessity of having relevant data, and if needed work on raising their related capacities. | UNDP Programme Manager | UNDP Programme Manager | April 2016 | no change |
| 4 | Insufficient technical and human capacities of national partners to deal with mitigation issues. | April 2016 | Operational | In case this risk occurs, more international consultants will have to be engaged in order to provide relevant update of the mitigation chapter. P = 3 I = 2 | Scan necessary capacity building needs and work on raising capacities of national partners (preferably through learning-by-doing approach). | UNDP Programme Manager | UNDP Programme Manager | April 2016 | no change |
| 5 | Insufficient/understaffed capacities of national partners to deal with vulnerability and adaptation issues. | April 2016 | Operational | In case this risk occurs, international consultants will have to be engaged in order to work closely with national experts to provide high quality vulnerability and adaptation chapter. P = 2 I = 2 | Scan necessary capacity building needs and work on raising capacities of national partners (preferably through learning-by-doing approach). | UNDP Programme Manager | UNDP Programme Manager | April 2016 | no change |

## Annex 2. Terms of Reference for key project personnel

TERMS OF REFERENCE

- Job Title: Programme Manager

- Post Reference:

- Type of position: National

- Duty Station: Podgorica, Montenegro

- Contract Type: Service Contract (SB4)

- Duration of Appointment:

- Deadline for application:

- Background:

Montenegro became a party to the UN Framework Convention on Climate Change by succession, after becoming independent in 2006 year, becoming a non-Annex I Party to the UNFCCC.

The responsible authority and main body for coordinating and articulating national climate actions is the Ministry for Sustainable Development and Tourism (newly established Directorate for Climate Change). Taking into account the necessity of inter-sectoral cooperation on climate policy, the National Committee for Sustainable Development and Tourism has been transformed into the National Committee for Sustainable Development and Climate Change to ensure cooperation among all relevant stakeholders. This body has an advisory role and the mandate to actively participate in shaping of the national climate policy. Montenegro has recently developed National Climate Change Strategy by 2030 and submitted its INDC to the UNFCCC Secretariat.

On its path towards accession to the EU, Montenegro will have to integrate numerous requirements of the EU climate policy into domestic legal framework and align it with the climate acquis. The latest EU Report on Montenegro’s progress in the accession process states that, in the area of climate change, a comprehensive national climate policy and a climate change strategy need to be developed in line with the expected EU 2030 policy framework on climate and energy. Substantial efforts are also needed to fully integrate climate considerations into all relevant sectorial policies and strategies. Montenegro regularly associated itself with EU positions at international level.

The intended nationally determined contribution (INDC) to the 2015 Climate Agreement was submitted to the UNFCCC Secretariat in Sep 2015, consistent with those of the EU and its Member States.

Regarding alignment with the climate acquis, significant efforts are required, especially, to strengthen the country’s monitoring, reporting and verification capacity. The establishment of the National Council for Sustainable Development and Climate Change marks a positive development in inter-institutional coordination and cooperation. The Council needs to be strengthened further.

The Government adopted 30% reduction as an internal target by 2030 (INDC), compared to 1990 level, and is now evaluating and implementing mitigation options to meet this goal.

Under its commitments as a non-Annex 1 party of the UNFCCC, Montenegro has prepared two National Communications (NCs), an Initial National Communication in 2011, the Second National Communication (SNC) in 2015. Montenegro follows non-Annex I guidance for the preparation of the NC and GHG inventories. Moreover, Montenegro developed its First Biennial Report (FBUR) to be submitted during the first half of 2016.

Both, the Initial National Communication (INC 2010) and the Second National Communication (SNC 2015) identified the following vulnerable sectors: coastal zone, water resources, agriculture, forestry and public health.

Within currently prepared, Draft National Sustainable Development Strategy - NSDS (2016-2020), climate change issue is envisaged as a cross-sector topic for each of the country development directions.

The National Climate Change Strategy (NCCS) until 2030 and appropriate Strategic Environmental Impact Assessment were adopted in September 2015. The NCCS provides methodology and detailed sectoral projections for key emission sectors, along with sensitivity and uncertainty analysis. The sectoral projections were done for two scenarios: with existing measures (WEM) and with additional measures (WAM). Besides, potential GHG saving measures with their belonging costs, adaptation measures to climate change with its belonging costs, compliance with EU climate change legislation, action plan and investment planning, and financing strategy implementation are also envisaged by this strategic document. National INDC technical paper is prepared and submitted to UNFCCC Secretariat and it is an integral part of the NCCS.

The Third NC and the Second BUR will build on the gap/constraints findings and recommendations of previous National Communications and BUR work, as well as the outcomes of the ongoing complementary projects in the country and is planned to be submitted to the UNFCCC in the first half of 2020.

The main gap/constraints findings and recommendations related are the following:

In order to improve uncertainty for GHG emissions, it is necessary to:

i) Revise the activity data; ii) Calculate national emission factors; iii) Change the calculation methodology to multiple Tier, i.e. do an estimate of measurement uncertainty by also using Tier 2 methodology, which is based on a simulation in Monte Carlo; iv) Continue applying and working in accordance with quality assurance and quality control practices (QA/

QC).

In order to improve vulnerability assessment and the drafting of adaptation measures, it is necessary to:

i) Strengthen early warning system for extreme weather and hydrology events; ii) Strengthen support for scientific-research work and to improve inter-institutional cooperation; iii) Establish databases per sector and to secure their regular updating, iv) Encourage the drafting of studies, analyses, projections of the impact of climate change on priority sectors for implementation of adaptation measures.

In order to improve the analyses of GHG abatement measures and assess their impact, it is necessary to:

i) Develop plans of emission reductions per sector; ii) Build institutional capacities for the application of methods and models for assessing the impacts of measures, formulating and prioritizing programs and measures and evaluating the cost of measures aimed at reducing GHG emissions.

- Organizational Setting:

Under the supervision and guidance of the Manager for Sustainable Development Center, the Programme Manager will be responsible for overall programme implementation through managing day-to-day programme activities, and coordinating with the Senior Management to ensure efficient delivery of envisaged programme outputs.

J.	Job Content:

The Programme Manager will be responsible for ensuring that the programme is efficiently managed to fulfil its mission and objectives as set out in the Programme Document, and in accordance with the UNDP rules, standards and best practices.  The Programme Manager will be responsible to:

1.	Provide leadership to the programme team, manage its day-to-day activities and supervise programme team and consultants:

- Prepare implementation action plans; organize team meetings to assign tasks, monitor progress on a regular basis;

- Identify relevant sources of expertise required for the programme/activity implementation;

- Lead efforts on coordinating activities with other UN agencies, international organizations including resource mobilization efforts that will secure continuation/sustainability of ongoing efforts;

- Review official documents and communications;

- Advice the Senior Management on potential adjustments of actions and procedures in light of the changing requirements and needs;

- Regular monitoring of the relevant events and/or subjects in the local media.

2. 	Supervise delivery of inputs and outputs provided by the Programme, and ensure quality and timeliness of reporting and data production:

- Ensure that work plans are prepared and updated on time and reflect the Programme objectives and outputs; monitor data and programme progress;

- Ensure timely coordination and implementation of recruitment and deployment of experts to support the programme implementation;

- Manage procurement of goods and services under the programme, and ensure on-time delivery to recipient institutions;

- Monitor implementation progress and ensure quality and timely reporting to donors, as specified within the Programme Document;

- Ensure the establishment and maintenance of complete accounting records of all programme activities (budget, commitments, expenditures, income); Ensure that Issue, Quality, Risk, and Lessons-learnt logs are entered in Atlas and regularly (quarterly updated);

- Provide necessary back-up support to consultants in connection with the programme outputs;

- Be responsible for all assets purchased and used under the Programme;

- Hold the primary responsibility for managing the resources being spent i.e. approve requisitions and requests for non PO payments.

- With the help of the Country Office Communications Unit, the incumbent will make sure that the programme takes account of principal components of communications/advocacy campaigns in order to:

- Promote programme visibility and keep target publics informed about programme’s progress;

- Make sure that outputs produced find adequate recognition;

- Encourage positive participation and building and sustaining of political commitment.

The incumbent will also work to ensure that the project includes evaluations of the projects impact in terms of learning and behaviour change.

- Competencies:

Corporate Competencies:

- Demonstrates integrity by modelling the UN’s values and ethical standards;

- Promotes the vision, mission and strategic goals of UNDP;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability.

Functional Competencies:

Knowledge Management and Learning

- Promotes knowledge management in UNDP and a learning environment in the office through leadership and personal example;

- Actively works towards continuing personal learning and development in one or more Practice Areas related to governance, acts on learning plan and applied newly acquired skills.

- Seeks and applies knowledge, information and best practices from within and outside of UNDP.

Development and Operational Effectiveness

- Ability to lead strategic planning, results-based management and reporting;

- Ability to lead formulation, implementation, monitoring and evaluation of development programmes and projects, mobilize resources;

- Ability to formulate and manage budgets, to manage contributions and investments, manage transactions, conduct financial analysis and reporting.

Management and Leadership

- Builds strong relationships with clients, focuses on impact and result for the client and responds positively to feedback;

- Consistently approaches work with energy and a positive, constructive attitude;

- Demonstrates good oral and written communication skills

- Demonstrates ability to manage complexities and work under pressure, as well as the good conflict resolution skills.

- Qualifications and Experience

- University Degree, preferably in Economics and/or Social Sciences;

- Minimum 5 years of relevant management experience with progressively increasing responsibilities, preferably with an International Organization, government institution, a donor agency, or an NGO; the strong background in the sustainable development is preferred.

- Previous experience in communicating with ministries, private sector, NGOs, etc.

- Self-starting, independent and responsible personality;

- Demonstrated ability to manage and motivate people in a complex environment and achieve set goals under time pressure;

- Proven ability to think strategically, to express ideas clearly and concisely, to work both independently and in teams, to demonstrate self-confidence combined with sensitivity to gender and culture.

- Strong analytical, advocacy, communications and negotiation skills; strong resource mobilization skills; ability to apply a comprehensive development approach to policy issues.

- Knowledge of change management and institutions at the Republic and municipality levels would be an advantage;

- Fluency in English and local language; Excellent writing and advocacy skills.

- Computer proficiency (MS Office package, Internet).

TERMS OF REFERENCE

- Job Title: Administrative/Finance Assistant

- Post Reference:

- Type of position: National

- Duty Station: Podgorica, Montenegro

- Contract Type: Service Contract (SB3)

- Duration of Appointment:

- Background:

Montenegro became a party to the UN Framework Convention on Climate Change by succession, after becoming independent in 2006 year, becoming a non-Annex I Party to the UNFCCC.

The responsible authority and main body for coordinating and articulating national climate actions is the Ministry for Sustainable Development and Tourism (newly established Directorate for Climate Change). Taking into account the necessity of inter-sectoral cooperation on climate policy, the National Committee for Sustainable Development and Tourism has been transformed into the National Committee for Sustainable Development and Climate Change to ensure cooperation among all relevant stakeholders. This body has an advisory role and the mandate to actively participate in shaping of the national climate policy. Montenegro has recently developed National Climate Change Strategy by 2030 and submitted its INDC to the UNFCCC Secretariat.

On its path towards accession to the EU, Montenegro will have to integrate numerous requirements of the EU climate policy into domestic legal framework and align it with the climate acquis. The latest EU Report on Montenegro’s progress in the accession process states that, in the area of climate change, a comprehensive national climate policy and a climate change strategy need to be developed in line with the expected EU 2030 policy framework on climate and energy. Substantial efforts are also needed to fully integrate climate considerations into all relevant sectorial policies and strategies. Montenegro regularly associated itself with EU positions at international level.

The intended nationally determined contribution (INDC) to the 2015 Climate Agreement was submitted to the UNFCCC Secretariat in Sep 2015, consistent with those of the EU and its Member States.

Regarding alignment with the climate acquis, significant efforts are required, especially, to strengthen the country’s monitoring, reporting and verification capacity. The establishment of the National Council for Sustainable Development and Climate Change marks a positive development in inter-institutional coordination and cooperation. The Council needs to be strengthened further.

The Government adopted 30% reduction as an internal target by 2030 (INDC), compared to 1990 level, and is now evaluating and implementing mitigation options to meet this goal.

Under its commitments as a non-Annex 1 party of the UNFCCC, Montenegro has prepared two National Communications (NCs), an Initial National Communication in 2011, the Second National Communication (SNC) in 2015. Montenegro follows non-Annex I guidance for the preparation of the NC and GHG inventories. Moreover, Montenegro developed its First Biennial Report (FBUR) to be submitted during the first half of 2016.

Both, the Initial National Communication (INC 2010) and the Second National Communication (SNC 2015) identified the following vulnerable sectors: coastal zone, water resources, agriculture, forestry and public health.

Within currently prepared, Draft National Sustainable Development Strategy - NSDS (2016-2020), climate change issue is envisaged as a cross-sector topic for each of the country development directions.

The National Climate Change Strategy (NCCS) until 2030 and appropriate Strategic Environmental Impact Assessment were adopted in September 2015. The NCCS provides methodology and detailed sectoral projections for key emission sectors, along with sensitivity and uncertainty analysis. The sectoral projections were done for two scenarios: with existing measures (WEM) and with additional measures (WAM). Besides, potential GHG saving measures with their belonging costs, adaptation measures to climate change with its belonging costs, compliance with EU climate change legislation, action plan and investment planning, and financing strategy implementation are also envisaged by this strategic document. National INDC technical paper is prepared and submitted to UNFCCC Secretariat and it is an integral part of the NCCS.

The Third NC and the Second BUR will build on the gap/constraints findings and recommendations of previous National Communications and BUR work, as well as the outcomes of the ongoing complementary projects in the country and is planned to be submitted to the UNFCCC in the first half of 2020.

The main gap/constraints findings and recommendations related are the following:

In order to improve uncertainty for GHG emissions, it is necessary to:

i) Revise the activity data; ii) Calculate national emission factors; iii) Change the calculation methodology to multiple Tier, i.e. do an estimate of measurement uncertainty by also using Tier 2 methodology, which is based on a simulation in Monte Carlo; iv) Continue applying and working in accordance with quality assurance and quality control practices (QA/

QC).

In order to improve vulnerability assessment and the drafting of adaptation measures, it is necessary to:

i) Strengthen early warning system for extreme weather and hydrology events; ii) Strengthen support for scientific-research work and to improve inter-institutional cooperation; iii) Establish databases per sector and to secure their regular updating, iv) Encourage the drafting of studies, analyses, projections of the impact of climate change on priority sectors for implementation of adaptation measures.

In order to improve the analyses of GHG abatement measures and assess their impact, it is necessary to:

i) Develop plans of emission reductions per sector; ii) Build institutional capacities for the application of methods and models for assessing the impacts of measures, formulating and prioritizing programs and measures and evaluating the cost of measures aimed at reducing GHG emissions.

In addition to UNFCCC, Montenegro signed the Minamata Convention on Mercury on September 24th 2014.

On the basis of Article 34 of the Law on Chemicals ("Official Gazette", 18/12), Ministry of Sustainable Development and Tourism adopted the Rulebook on the prohibition and limitation of production, the marketing and production of chemicals that are unacceptable risk to human health and the environment ("Official Gazette", 49/13). In this Rulebook mercury (CAS no. 7439-97-6 EC no. 231-106-7) is prohibited for placing on the market for general use in the thermometer, other devices measuring (manometers, sphygmomanometers - devices for measuring pressure, barometers, thermometers and etc.). The prohibitions apply from 3 April 2014 for measuring devices for the first time placed on the market. Those measuring devices used as medical devices remain in circulation until the expiry of the deadline prescribed for medical devices. The prohibitions do not apply to measuring devices that were in use before 3 October 2014.

Montenegro has also ratified the Stockholm Convention in 2011 which states that Parties to the Convention must concentrate their efforts on managing the 22 POPs listed under the Convention including putting into place regulatory measures, undertaking comprehensive assessments of the presence of POPs and also develop the National Implementation Plan for the Stockholm Convention 2014-2021, in 2013.

The related project is in line with the Sustainable Development Goal 12 “Ensure sustainable consumption and production patterns”, or more specific, with the Target 12.4 “By 2020, achieve the environmentally sound management of chemicals and all wastes throughout their life cycle, in accordance with agreed international frameworks, and significantly reduce their release to air, water and soil in order to minimize their adverse impacts on human health and the environment”.

- Organizational Setting:

Under the supervision and guidance of the Manager for Sustainable Development Center and Regional Programme Manager, the Administrative/Finance Assistant will be responsible for the implementation of administrative and financial tasks, in order to support efficient delivery of the envisaged programme outputs.

- Job Content:

The Administrative/Finance Assistant is responsible for all the administrative and accounting matters under the respective Programme. More specifically, the incumbent will:

- Maintain administrative files relevant to the Programme; Undertake searches for information and select, prepare and compile pertinent abstracts and reports;

- Collect and compile information necessary for briefings, and prepare draft briefings for meetings and visits;

- Arrange meetings, both internal and external, some involving high ranking officials, and take minutes/notes at meetings; provide necessary back-up services including translating both orally and in writing, for international consultants and technical advisors involved in the programme;

- Draft routine correspondence, facsimile, memoranda and reports from oral instructions, previous correspondence or other available information sources, in accordance with the standard office procedures, and ensure appropriate follow-up.

- Maintain day-to-day communication with the Operations Unit regarding the Programme administration matters: procurement, human resources and finance matters; provide administrative support regarding recruitment of experts and procurement of goods and services under the Programme;

- Provide support to procurement processes related to the Programme implementation: provide inputs for preparation of procurement plans for the office; provide support to organization of procurement processes including preparation of tender documents, receipts of quotations, bids or proposals, and their preliminary evaluation;

- Perform regular financial and administrative duties necessary for the successful and timely Programme implementation:

- Enter daily transactions in Atlas system (vouchers, requisitions, etc.);

- Keep track of all transactions in a budget notebook;

- Perform regular budget revisions;

- Provide regular delivery estimation and monthly expense estimation to the Finance Unit; provide regular reporting regarding the programme expenditures;

- Prepare periodic programme asset/inventory reports;

- Ensure completeness of documentation, check accuracy of calculation for all financial transactions related to the Programme, and prepare/process financial transactions in the system in accordance with UNDP rules and procedures.

- Provide logistical support to the Programme and ensure provision of adequate secretarial and interpretation facilities (organization of programme events, meetings and study tours, arrangement of shipments, project vehicles maintenance, conference facilities arrangements, visits of experts, timely processed DSAs, etc.).

- Competencies:

Corporate Competencies:

- Demonstrates commitment to UNDP’s mission, vision and values;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability.

Functional Competencies:

Knowledge Management and Learning

- Shares knowledge and experience;

- Actively works towards continuing personal learning, acts on learning plan and applies newly acquired skills.

Development and Operational Effectiveness

- Ability to perform a variety of standard tasks related to Results Management, including screening and collecting of programme/projects documentation, projects data entering, preparation of revisions, filling, provision of information;

- Ability to provide input to business processes re-engineering, implementation of new systems.

Leadership and Self-Management

- Focuses on result for the client and responds positively to feedback;

- Consistently approaches work with energy and a positive, constructive attitude;

- Remains calm, in control and good humored even under pressure.

- Qualifications and Experience:

- Secondary Education; University Degree in Business or Public Administration is desirable, but it is not the requirement;

- Minimum 4 years of relevant administrative experience at the national or international level;

- Experience in office management, preferably with an international organization;

- Excellent working knowledge of written and spoken English language;

- Excellent computer skills; experience in operating in web management systems.

- Excellent inter-personal and communication skills;

- Excellent organizational skills with developed attention to detail;

- Ability to work independently and in a team.

## Annex 3.  Social and Environmental Screening

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document. Please refer to the Social and Environmental Screening Procedure for guidance on how to answer the 6 questions.]

Project Information

| Project Information |  |
| --- | --- |
| Project Title | Development of Montenegro’s Third National Communication to the UNFCCC |
| Project Number | 96225 |
| Location (Global/Region/Country) | RBEC/SEE/Montenegro |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

The project supports the meaningful participation and inclusion of all stakeholders, during the design, implementation and monitoring of the project. It is anticipated that they will participate to activities supported by the project and the project will support the development of an enabling environment conducive to the participation of stakeholders in the management of natural resources. This approach is consistent with the participation and inclusion of human rights principle. The stakeholder engagement process will accommodate a wide range of stakeholders and institutions both at the national and community-based levels. The issue of mainstreaming climate change considerations into policy formulation and national development strategies is becoming more prominent. Therefore, an inter-agency coordination to meet strategic objective of sustainable development and its goals is critical. Since the process of NC/BUR preparation supports this coordination, its role can be enhanced up to a regular exchange platform for mainstreaming, policy formulation, capacity building, awareness raising and knowledge exchange. The NC/BUR process will expand its network of stakeholders and include women associations.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The project intends to empower gender by identifying appropriate female local consultants, if available. In addition, workshops will be conducted in which gender balance will be ensured. Furthermore, gender will be mainstreamed into the TNC in a way that ensures that equitable participation of women in the decision-making process of climate change adaptation and mitigation. With regard to the technical team to be hired to implement the enabling activity, gender balance will be also considered. Equality between women and men is a precondition for the fulfilment of human rights and human development in general, and of the overall EU objectives in regard to growth, employment and social cohesion, in particular. In Montenegro, complex economic, social and political environment shadows and pushes women's issues aside. Gender stereotypes persist and overall social atmosphere is not supportive to gender equality. Institutional gender mechanisms (Department for Gender Equality within the Ministry of Human and Minority Rights and Parliamentary Board for Gender Equality) are severely under-mandated, under-staffed and under-budgeted. Due to persisting gender-based disadvantages, women are vulnerable and lack political and economic empowerment, including protection against family violence. Policy and legislative developments in the last few years (National Action Plan for Gender Equality and Law on Gender Equality) have created a solid ground to address these problems. It is now important to ensure that these laws and policies are implemented. This will require not only political will, human and financial capacities and continuous monitoring, but also an institutional and cultural transformation process. This should include elimination of gender bias in national development frameworks, as well as incorporation of gender awareness into broader policies, programs and institutional reforms. The previous NCs had not dealt with gender mainstreaming issues, leaving room for improvement in the new NC. Mitigation actions have largely focused on reduction of industrial greenhouse gas emissions, but also include the practice of energy efficiency and the application of renewable energy in commercial and residential sectors. The role of women in such climate change mitigation strategies has received no attention in previous NCs, as actions have been perceived to be either technical or scientific in nature. The TNC project will incorporate a gender perspective in the identification, description and preparation of mitigation and adaptation actions, when relevant. Also, the women in the TNC will be meaningfully involved, not only as beneﬁciaries but also in the decision-making process of climate change related activities. As climate change is partly the result of human behavior and affects all people, mitigation and adaptation strategies in the TNC will consider the gendered patterns. Moreover, understanding how the different social roles and economic status of men and women affect, and are affected differently by climate change will be considered for appropriate adaptation and mitigation actions. In this sense, and for this specific project, the update of the national circumstances chapter of the TNC will consider this gender dimension in order to better understand how the different roles of men and women in Montenegro and social and economic circumstances may affect Montenegro’s ability to deal with mitigating and adapting to climate change. Additionally, the project coordination will ensure that gender considerations become part of the TNC. Training Manuals on Gender and Climate Change will be followed. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men. In this regards, the project will give special attention to gender as one of the key stakeholders and beneficiaries from climate change adaptation and mitigation.

Briefly describe in the space below how the Project mainstreams environmental sustainability

The objective of the project is to assist the Government of Montenegro in preparation of its Third National Communication under the UNFCCC Convention in accordance with its commitments as a non-Annex 1 Party. Project is prepared in line with GEF-6 strategic focal area on climate change mitigation, objective CCM3 on fostering enabling conditions to mainstream mitigation concerns into sustainable development strategies; Program 5: Mainstream the integration of climate considerations into the national planning process. The project is designed to support the Government of Montenegro in deepening the mainstreaming and integration of climate change into national and sectorial development goals by giving continuity to the institutional and technical capacity strengthening process, partly initiated and sustained by the previous National Communications and the first BUR.

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |
| --- | --- | --- |
| Risk Description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |
| Risk 1: None | I = P = | N/A | N/A | N/A |
| [add additional rows as needed] |  |  |  |  |
|  | QUESTION 4: What is the overall Project risk categorization? |
|  | Select one (see SESP for guidance) | Comments |
|  | Low Risk | x | There are no environmental or social risks related to this project. |
|  | Moderate Risk | ☐ |  |
|  | High Risk | ☐ |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |
|  | Check all that apply | Comments |
|  | Principle 1: Human Rights | ☐ | None required |
|  | Principle 2: Gender Equality and Women’s Empowerment | ☐ | None required |
|  | 1. Biodiversity Conservation and Natural Resource Management | ☐ | None required |
|  | 2. Climate Change Mitigation and Adaptation | ☐ | None required |
|  | 3. Community Health, Safety and Working Conditions | ☐ | None required |
|  | 4. Cultural Heritage | ☐ | None required |
|  | 5. Displacement and Resettlement | ☐ | None required |
|  | 6. Indigenous Peoples | ☐ | None required |
|  | 7. Pollution Prevention and Resource Efficiency | ☐ | None required |

Final Sign Off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the Project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | No |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | No |
| 5. Are there measures or mechanisms in place to respond to local community grievances? | No |
| 6. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | No |
| 7. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 8. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 9. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 3. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | No |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | No |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas)? | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.4 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.5 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.6 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.7 Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | No |
| 6.8 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

## ANNEX 4. Final Report of Montenegro National Communication’s

(Please contact RTA and PA at the end of the project for the latest version of the End of project report)

Monitoring and Evaluation plans of climate change enabling activities for the preparation of National Communications on Climate Change and/or Biennial Update Reports do not require the production and publication of Terminal Evaluation Reports. Therefore, a number of intended purposes of such terminal exercises are not captured in full, including:

- The promotion of accountability and transparency, and the assessment and disclosure of the extent of the project accomplishments;

- A synthesis of lessons that can help to improve the selection, design and implementation of future GEF financed UNDP activities;

- The provision of feedback on issues that are recurrent across the portfolio, attention needed, and on improvements regarding previously identified issues; and

- The contribution to the GEF Evaluation Office databases for aggregation, analysis and reporting on effectiveness of GEF operations in achieving global environmental benefits and on the quality of monitoring and evaluation across the GEF system.

The intent of this Final Report is not to propose an abridged alternative to the Terminal Evaluation Report. Instead, its purpose is to gather some insightful details about the process of preparing the mandatory report under the UNFCCC that can be of use to both the UNDP support teams, and the current and future national project teams. Its focus is therefore on providing:

- A synthesis of lessons that can help to improve the selection, design and implementation of future GEF financed UNDP activities; and

- Feedback on issues that are recurrent across the portfolio, attention needed, and on improvements regarding previously identified issues.

National project teams in charge of the future enabling activity for the preparation of the National Communication or Biennial Update Report can therefore rely on a valuable source of information from inception to closure of the project, and UNDP support teams can further disseminate lessons across borders, fully up-taking its guiding role as implementing agency and partner within the Global Support Programme (GSP, previously known as National Communications Support Programme).

The template has been designed with the purpose of collecting relevant information, without representing a time-intensive and human resource-intensive burden to the current national project team. It is therefore divided into three core sections – project identification phase, project implementation phase and project follow-up –with for each section a limited number of open questions.

The intention is to have the team leader, project manager or equivalent figure completing the template, in close collaboration with other team members within the last two months of project implementation. It is furthermore the intention of the completion of this Final Report to trigger the discussions of the upcoming National Communication and/or Biennial Update Report, taking advantage of the momentum created by the ongoing project, the presence of the core of the current national project team, and the renewed interest of national counterparts with the perspectives of an eminent or recent submission to the UNFCCC.

The completion of this template has been made mandatory and has been budgeted for in all projects that received approval post 2013 (3 working days equivalent of project manager’s time). You are kindly invited to send the completed template to Damiano Borgogno, damiano.borgogno@undp.org and to Eva Huttova, eva.huttova@undp.org.

## Details of the project

| Project’s title |  |
| --- | --- |
| PIMS number |  |
| Overall budget including GEF grant including co-financing |  |
| Duration of implementation |  |
| Planned duration of project |  |
| Implementing partner |  |
| Team Leader’s name and contact details |  |
| Link to final report |  |

## Project identification phase

Duration of preparatory phase (expressed in months)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Was the project document developed by a national/international consultant? (Please, provide name if yes and expand on the satisfaction of this collaboration.)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Please, shortly describe the milestones of this initial preparatory phase (e.g. consultation workshops held, telephone interviews with key stakeholders, among others)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Where consultations made with one or more of the following stakeholder groups?

|  | Ministry of Finance (or equivalent) |  | Women’s associations |
| --- | --- | --- | --- |
|  | Other Ministries (not being the Ministry in charge of climate change) |  | Youth movements |
|  | Local Governments |  | Indigenous peoples’ representatives |
|  | National universities |  | Environment or climate related NGOs |
|  | Domestic Research Centers |  | Other NGOs/CSOs |
|  | Media |  | Others (specify) |

What were the main objectives for the project identified as a result of this preparatory phase?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What were the major challenges faced during this phase?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Looking back, what issues that were identified and/or overlooked during this preparatory phase had

an impact on the successive implementation phase?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

## Project implementation phase

Technical components

- GHG inventory

Base year of the GHG inventory:

Base years used in previous GHG inventories:

| Expected outcome |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |

| Final outcome |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the GHG inventory component, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the causes (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

- Mitigation actions

| Expected outcome(s) |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |
| … |  |

| Final outcome(s) |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the vulnerability and adaptation measures and mitigation measures components, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the causes (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

- Vulnerability & Adaptation for NC or MRV for BUR

| Expected outcome(s) |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |
| … |  |

| Final outcome(s) |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the vulnerability and adaptation measures and mitigation measures components, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the main reasons (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

- Constraints and Gaps/Support needed

| Expected outcome |  |
| --- | --- |
| Expected output 1 |  |
| Expected output 2 |  |
| Expected output 3 |  |
| … |  |

| Final outcome |  |
| --- | --- |
| Final output 1 |  |
| Final output 2 |  |
| Final output 3 |  |
| … |  |

Please, shortly discuss the expected outcomes and outputs of the Constraints and gaps, and related financial, technical and capacity needs component, and compare to what was actually realized within the context of this project. If there was any diverting from the originally expected outcomes and outputs, please explain the main reasons (e.g. lack of data, risk of duplication of work done in the context of parallel projects, among others).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Can you describe the process(es) implemented to generate and validate outcomes and outputs?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What pieces of advice do you have for future project teams?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Capacities and use of capacities

Do you believe the project has built - in a durable and cost-effective way - human and institutional capacities?

Please, elaborate.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Please, estimate the amount of work done by national consultants versus international consultants:

______________% national consultants. ________________% international consultants and

____________% national staff.

What work was entrusted to international consultants and for what reasons?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What would you have done differently, or do you advise the next project team to consider in this context?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Additional remarks

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Institutional arrangements

Please, summarize an overview of the institutional arrangements for the project implementation.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Please, describe the composition of the project team.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Will the team remain in place, even after the project has fully closed?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Were gender considerations taken into account during the project design and implementation? If so, how?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Which were the strengths and weaknesses of the institutional arrangements used?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What suggestions have you to make regarding the institutional arrangements for future NC/BUR work?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Additional remarks

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Technical support from GSP, CGE, or other bodies

Has the project team, or members of the project team, participated in national, regional or global training

events organized by a center of excellence or above mentioned body during the course of the project?

If yes, please, specify the training event(s).

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What has been the contribution of this participation to the project results?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

What identified knowledge gaps holding back the proper implementation of the NC project could not be

addressed by any of the above mentioned bodies?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

In addition to capacity building support, what other assistance did the project team receive

during project implementation? (E.g. review of draft report, technical backstopping of international expert)

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Has UNDP provided timely and valuable support during project design and implementation? Please explain.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

## Next steps

How will findings of the project be further disseminated, if at all?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Are balance funds available under the NC/BUR project going to be used to identify the strategy of the next report?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

At full project closure, is there a person or institute to whom one can turn in case there are follow-up questions to the NC/BUR?

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

Has the Government expressed interest to further work with UNDP on the next coming report? If no, please explain.

____________________________________________________________________________________

____________________________________________________________________________________

____________________________________________________________________________________

## Additional information

| Date |  |
| --- | --- |
| Name and e-mail address of person who completed this template |  |
| Others involved in completion of this template (names of individuals and their institutions) |  |
| In case a terminal evaluation report has been produced, please link it here. |  |
| Other attachments |  |

# Footnotes

For UNDP supported GEF funded projects as this includes GEF-specific requirements

Project is prepared in line with the GEF 6 Focal Area Objective “CCM-3: Foster Enabling Conditions to Mainstream Mitigation Concerns into Sustainable Development Strategies, Programme 5: Integrate findings of Convention obligations and enabling activities into national planning processes and mitigation targets.”

GHG Inventory for the period 2014-2015 is planned to be update through SBUR.

GHG Inventory for 2014-2015 will be updated through SBUR, while for 2016-2018 will be updated through TNC.

Objective (Atlas output) monitored quarterly ERBM  and annually in APR/PIR

All outcomes monitored annually in the APR/PIR.

Summary table should include all financing of all kinds: GEF financing, co-financing, cash, in-kind, etc...

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

2 In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

3 Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

# Text boxes

Total resources required           	580,000

Total allocated resources:		580,000

- Regular			________________

- Other:

  - GEF			500,000

  - Government In-kind	80,000

Programme Period:		        May 2016 – May 2020

Atlas Award ID:			00090471

Project ID:			00096225

PIMS #				5817

Start date:		     	May 2016

End Date			                May 2020

Management Arrangements		DIM

PAC Meeting Date			27 Apr 2016

Brief Description

The project will enable Montenegro to fulfil its commitments under UNFCCC and prepare and submit the TNC to the Conference of Parties of the UNFCCC. Further, it will assist in building national capacities to fulfil Montenegro’s commitments under the Convention on a continuous basis, while it will additionally increase the awareness on climate change issues particularly among policy-makers leading to full integration of climate considerations into national and sectoral polices, strategies and programmes.

Project Manager

National Project Manager

Project Board

Senior Beneficiary:

Ministry of Sustainable Development and Tourism

Executive:

UNDP

Senior Supplier:

UNDP

Project Assurance

(by Board members or delegated to other individuals)

UNDP

Project Support

Project Assistant

Project Organisation Structure

TEAM A

GHG Inventory

TEAM C

Vulnerability and Adaptation

TEAM B

Mitigation