# United Nations Development Programme

# 2011 HIV and AIDS Annual Working Plan

# Agency: UNDP Mozambique

UNDAF Pillar 3 Expected Outcome: Individuals, civil society and public and private sector institutions nationally empowered to halt the spread of HIV and AIDS among the population at risk and mitigate its impact

UNDAF CP Expected Outcome(s): 3.5 The provincial public sector plans, action plans of the civil society networks and private sector business plans mainstream HIV and AIDS, Gender and Natural Disasters including the corresponding budgets for its implementation

UNDAF CP Expected Outcome(s): 3.5.1 Setting up of National Mechanisms aiming at establishing a critical mass and institutional strengthening of Government, Employers' Association, Trade Union Organizations, Informal vendors and Civil Society Associations (including Youth associations and Youth Centres) in order to specialize in HIV and AIDS mainstreaming and feminization of HIV and AIDS

UNDAF 1 Outcome: By 2011, the Government and civil society capacity at local, provincial and national levels strengthened to plan, implement and monitor socio-economic development in a transparent, accountable, equitable and participatory way in order to achieve the Millennium Development Goals  (MDGs)

UNDAF CP 1.6 Expected Outcome(s): Organizations and civil society structures (including traditional authorities and gender equality activists) strengthened and involved in the development agenda at national and decentralized

UNDAF CP 1.6.4 Expected Outcome(s) Enhanced capacity to effectively mainstream HIV, AIDS, Gender and vulnerable groups issues in the of Governance processes at all levels

Implementing Partners: National Council to Combat AIDS (CNCS), National Network of Organizations against AIDS (MONASO), Associação dos Estudantes Finalistas Universitários de Mozambique (AEFUM), Eduardo Mondlane University (UEM)

# UNDP - Mozambique Annual Plan

Approved by:

Conselho Nacional do Combate ao Sida (CNCS)

________________________________________			_________________________

Joana Mangueira							Date

Executive Secretary

Rede Nacional de Organizações Contra o Sida (MONASO)

__________________________________________			_________________________

Gaspar Sitefane							Date

National Executive Director

Associação de Estudantes Finalistas de Moçambique (AEFUM)

______________________________					________________________

Ivo Mapanga

Coordinator								Date

United Nations Development Programme (UNDP)

__________________________________________			_________________________

Jocelyn Mason								Date

UNDP a.i. Resident Representative

| IMPLEMENTATION PARTNERS FACE AUTHORIZED SIGNATORIES |
| --- |
| Implementing Partner | Name (s) of the Authorized Signatories | Title (s) | Signature (s) |
| CNCS | Diogo Milagre | Deputy Executive-Secretary |  |
|  | Páscoa Themba | UPC Coordinator |  |
|  | Arminda Maculuve | UGF Coordinator |  |
| MONASO | Helder White | Programme Director |  |
|  | Helder Gune | Financial and Administrative Director |  |
| AEFUM | Ivo Mapanga | Coordinator |  |

Annual Plan for HIV and AIDS

| Component 5: HIV/AIDS and Gender |
| --- |
| CPAP Outcome for 2010 and 2011: 5.1.1 Resources and expertise on HIV and AIDS mainstreaming developed and capacities of targeted institutions staff at central and local levels created 5.1.2 HIV & AIDS profiles developed and integration of strategies and plans produced by selected institutions 5.1.3. Established an adequate network of facilitators’ capacity to support the HIV and AIDS mainstreaming processes under way in public and private sectors. 5.1.4. HIV / AIDS mainstreamed and institutionalized within the institutions of the national education system and knowledge of centres and resources and a shared network established 5.1.5. A functional monitoring and reporting mechanisms established to monitor progress in mainstreaming of HIV & AIDS. |
| EXPECTED OUTCOMES | KEY ACTIVITIES | DEADLINE | RESPONSABLE | BUDGET |
|  |  | Q1 2011 | Q2 2011 | Q3 2011 | Q4 2011 |  | Planned | Allocated |  |
| 5.1.1 HIV and AIDS public sector and civil society organizations focal points with knowledge of PEN III subject areas and HIV and AIDS mainstreaming in plans and programmes Listen Read phonetically | 5.1.1.1 To encourage ongoing testing of workers to know their Sero-status |  | X |  |  | CNCS/MFP | $3.000 | $3.000 | $3.000 OR |
|  | 5.1.1.2 Conduct studies CAP to inform the review of communication interventions to change behaviour |  | X |  |  | CNCS/MFP | $3.000 | $3.000 | $3.000 OR |
|  | 5.1.1.3 Capacity building of key ministries in several PEN III thematic areas | X |  |  |  | CNCS | $9.000 | $9.000 | $9.000 OR |
|  | 5.1.1.4 Mainstreaming of activities and operation of responses to HIV and AIDS in sectors planning cycle Listen Read phonetically |  | X | X | X | CNCS | $1.000 | $1.000 | $1.000 OR |
|  | 5.1.1.5 Production and printing of IEC materials including materials on good practices in addressing the integrating HIV in Plans | X |  |  |  | MONASO | $5,000 | $5,000 | $5,000 OR |
|  | 5.1.15 Preparation and publication of a compilation of national human rights instruments and international instruments rectified by Mozambique and an analysis of its implementation |  | X |  |  | CDHD | $20.000 | $20.000 | $20.000 OR (JP) |
|  | 5.1.1.7 Provide technical assistance MONASO (consultants, UNDP vehicle and other operating expenses) for the implementation of the project | X | X | X | X | MONASO | $10.000 | $10.000 | $10.000 RR |
| 5.1.2 HIV and AIDS district plans for Maputo City and Inhambane province finalized and its implementation started. | 5.1.2. Enhance the provinces for the implementation of district plans to fight HIV and AIDS, under the principle of decentralization of the response | X | X | X | X | CNCS/NPCS | $70.000 | $70.000 | $50.000 RR $20.000 OR |
| 5.1.3 Forums created and meetings organized to share knowledge, exchange experiences and good practices between parliamentarians and HIV and AIDS mainstreaming in plans facilitators | 5.1.3.1 Hiring of a consultant for the maintenance and management of SIF and MONASO Website | X |  |  |  | MONASO | $10.000 | $10.000 | 10.000 OR |
|  | 5.1.3.2 Organization of a national meeting for facilitators of HIV and AIDS mainstreaming |  |  | X |  | MONASO | $25,000 | $25,000 | $15,000 OR $10.000 RR |
|  | 5.1.2.3 Organization of a meeting for People Living with HIV / AIDS and vulnerable population with parliamentarians (travelling, perdiem, catering) |  |  | X |  | PARLAMENT – UNDP | $50,000 |  | $50.000 OR (JP) |
| 5.1.4 HIV/AIDS included in the UEM curriculum and knowledge and national resources on HIV/AIDS, Gender and Human Rights mainstreaming created Listen Read phonetically | 5.1.4.1. Provide technical assistance (consultancy services) to key sectors in the scope of PEN III operationalization | X | X | X | X | CNCS | $70,000 | $70,000 | $50.000 RR $20.000 OR |
|  | 5.1.4.2 Establish a partnership with the Ministry of Agriculture for the promotion of production systems for PLHIV |  |  | X |  | CNCS/MINAG/MMAS | $10.000 | $10.000 | $10.000 OR |
|  | 5.1.4.3 Promotion of education for Orphans and Vulnerable Children (COV’s), through the provision of a basic basket comprised by school materials and uniform |  | X | X | X | CNCS | $2.000 | $2.000 | $2.000 OR |
|  | 5.1.4.4 Capacity building of Parliamentarians in HIV and AIDS and Human Rights issues |  | X |  |  | UNDP and parliament | $10.000 | $10.000 | $10.000 RR |
|  | 5.1.4.5 Capacity building of University Graduates on HIV and AIDS mainstreaming in plans and programmes |  |  | X |  | AEFUM | $25,000 $10.000 | $25,000 $10.000 | $25,000 RR $10.000 OR |
|  | 5.1.4.6 Capacity building of students participating in the 6th edition of the project “holidays developing the district” on the inclusion of HIV and AIDS component in their sector plans | X |  |  |  | AEFUM | $15.000 | $15.000 | $15.000 RR |
|  | 5.1.4.7 Undertake a research on HIV and AIDS, prostitution and poverty in Maputo | X | X | X | X | UEM – Department of sociology | $25.000 | $25.000 | $25.000 OR |
| 5.1.5 Number of monitoring and evaluation reports prepared on the mainstreaming of HIV/AIDS in plans and programmes increased | 5.1.5.1 Establish a mechanism to include HIV and AIDS progress report in the Government monitoring and evaluation instruments (PES assessment) | X |  |  |  | CNCS | $2,000 | $2,000 | $2,000 OR |
|  | 5.1.5.2 Training of key officials in the planning sector at the level of key Ministries and provincial Governments in the use of mechanisms, instruments and guidelines. |  | X |  |  | CNCS/MPD | $30,000 | $30,000 | $30,000 OR |
|  | 5.1.5.3 Project implementation evaluation |  |  | X | X | UNDP and partners | $25.000 | $25.000 | $25.000 RR |
|  | 5.1.5.4 Participation of Project partners in conferences and national and international events about HIV-AIDS | X | X | X | X | All project partners | $10.000 | $10.000 | $10.000 RR |
|  | 5.1.5.5 Realization of joint monitoring visits and HIV and AIDS in the work place activities |  | X |  | X | UNDP and implementation partners | $15,000 | $15,000 | $15,000 RR |
| Procurement to be conducted by UNDP: Hiring of a consultant to undertake the evaluation of the HIV -AIDS project mainstreaming |
| MONASO - $30.000 OR $20.000 RR CNCS - $100.000 RR $100.000 OR AEFUM $40.000 RR $10.000 OR UEM – Department of Sociology $25.000 OR Parliament $50.000 OR $10.000 RR Centre for Human Studies and Development $20.000 OR Monitoring and Evaluation $50.000 RR |
| TOTAL |  |  |  |  |  |  | $220.000 RR $235.000 OR TOTAL - $455.000 |

# M&E Framework

| Expected Outcomes in the Annual Plan | Indicators, Base and Targets | Verification Means |
| --- | --- | --- |
| 5.1.1. Outcome of the year: IEC material on HIV and AIDS produced and disseminated and focal points for HIV and AIDS in the public sector and civil society organizations with knowledge in PEN III subject areas and in the mainstreaming of HIV and AIDS in plans and programmes | Indicator: Number of OSC members receiving training in HIV and AIDS mainstreaming issues Base: 265 Target: 300 | Monitoring Reports Project Progress Reports |
| 5.1.2 Outcome of the year: District Plans for HIV and AIDS finalized and their implementation started. | Indicator: Number of Ministries and Districts with HIV and AIDS incorporated in their plans (PES) Base: 2 Target: Provinces: 4 ; Districts: Gaza, Inhambane provinces and Maputo City | Monitoring Reports PES |
| 5.1.3. Outcome of the year: Forums created and meetings organized to share knowledge, exchange experiences and good practices between parliamentarians and HIV and AIDS mainstreaming in plans facilitators | Indicator: Number of meetings held to exchange experiences Base: 0 Target: 3 | National meeting reports |
| 5.1.4 Outcome of the year: Improved knowledge on public sector instruments to monitor and assess the integration of HIV / AIDS in plans and programmes | Indicator: Number of universities and graduate students trained in mainstreaming HIV and AIDS in the curricula Base: 300 Target: 500 | Courses/training seminars reports Monitoring Reports |
| 5.1.5. A functional monitoring and reporting mechanisms established to monitor progress in mainstreaming HIV & AIDS (including finance). | Indicator: Number of Ministries and Districts that have mainstreamed HIV and AIDS in their reports (PES assessment) Base: 3 Target: Ministries: 5; Nampula, Cabo Delgado, Sofala and Tete | Monitoring Reports PES and PES Assessment |
| Studies, research and evaluations |

Listen

Read phonetically

# Text boxes

Summary

This component of the programme, started in 2007, aims to ensure that HIV and AIDS issues are effectively incorporated into plans, budgets and sector monitoring processes through capacity building and the availability of local experts. The projects includes assisting in the formulation of guidelines and manuals for training and monitoring of planners and technical staff in the use of the aforementioned instruments and consolidate the network of facilitators. A process of capacity building was also initiated by the institutionalization of training in HIV and AIDS mainstreaming within national academic institutions, a key element for the development of technical capabilities to support ongoing long term mainstreaming efforts.

In 2010 the National Strategic Plan for HIV and AIDS from 2011 to 2014 was drafted and approved, more than 250 civil society organizations and graduate students were trained in mainstreaming HIV and AIDS programmes and plans.  The dissemination of law 12/2009 to fight stigma and discrimination against people living with HIV and AIDS was also undertaken.

Listen

Read phonetically

#### Dictionary - View detailed dictionary

- noun

  - mercadoria

  - comodidade

  - objeto útil

  - coneniência

#### Translate over 50 languages

- sư tử

- Es ist sehr interessant!

- Buongiorno Principessa!

- Comment allez-vous ?

- Langweilig

- Wie bitte?

- Je ne sais pas !

- बन्दर

- miracoloso

- χρησμός

- La voiture

- escargots

- お元気ですか?

- haydi gidelim

- děti

- ¿Cómo estás?

- Ich bin vierzig Jahre alt

- mijn vriend

- rouge

- กาแฟ

- आज मेरा जन्मदिन हैं.

- Hjelp!

- Pardon ??

- Wie gehts?

- παραλία

- Простите

- nazdar!

- Je parle un petit peu français.

- أحب كرة القدم

- 국수

- Wie heißen Sie?

- שמח

- hoje está ensolarado

- さようなら

- Wie spät ist es?

- ओह यार!

- Vær så snill

- มีสีสัน

- سلحفاة

The current phase aims at continuing the development of knowledge and implementation capacities of the public sector PEN III and the empowerment of civil society organizations for a better understanding of these concepts. In 2011 the project will continue to promote the mainstreaming of HIV and AIDS government sector and civil society plans and programmes. The project will also train more students in HIV and AIDS mainstreaming

Annual Estimated Budget:	US$ 455,000

- Regular Resource:		US$ 220.000

- Joint Programme:		US$ 235,000

Period of the Programme:		2010-2011

Component of the Programme:	HIV & AIDS

Budget Code:	00055052 (HIV and AIDS)

Year:				2011

Programa das Nações Unidas para o

Desenvolvimento

Governo de Moçambique