UN Mozambique

Annual Project Plan of Activities

Agency: UNDP

UNDAF Outcome: Democratic Governing guaranteed as a basic prerequisite for peace, security and sustainable political development.

Expected Outcomes CPAP: 3.1 Management of Performance and planning of national elections improved.

Expected effects CPAP : 3.1.1 Improved capacity of National Electoral Commission  (CNE)/Technical Secretariat for Electoral Administration (STAE) in planning elections, budgetary, organization and management in selected areas  3.1.2. Coordinating Mechanism CNE/STAE — government – donor strengthened.  3.1.3. New forms and channels for civic education and voting implemented during all electoral cycle.

Implementing Partner:	CNE / STAE

Other partners:	N/A.

By STAE: Felisberto Henrique Naife,  Director General

By UNDP: Ndolamb Ngokwey, UN System Coordinator and UNDP Resident Representative

UN Mozambique – Annual Project Plan of Activities

Implementing Partner

FACE: authorized signature:

Felisberto Henrique Naife / Director General

| 1 : Overall quality of elections increased |
| --- |
| Expected outcomes CPAP: 3.1.1. Improved capacity of National Electoral Commission (CNE)/Technical Secretariat for Electoral Administration (STAE) in planning elections, budgetary, organization and management in selected areas 3.1.2. Coordinating Mechanism CNE/STAE — government – donor strengthened. 3.1.3. New forms and channels for civic education and voting implemented during all electoral cycle. |
| EXPECTED RESULTS | ACTIVITIES KEY | CALENDAR | RESPONSIBLE ENTITY | PLANNED BUDGET |
|  |  | 1º T 2010 | 1º T 2010 | 1º T 2010 | 1º T 2010 |  | Planned budget | Allocated budget | Sources of resources |
| 1.1 Structure of management, implementation, assistance, monitoring and evaluation of the project, created. | 1.1.1 Structure of implementation and monitoring established | X | X | X | X | CNE/STAE | US$ 5,000 | - | OR (US$ 5,000) |
| 1.2 Capacity of the CNE/STAE in planning of elections, budgeting, organization and management in selected areas improved. | 1.2.1 Strengthening of capacity of organs of electoral administration to administer electoral processes. | X | X | X | X | CNE /STAE | US$ 206,000 | US$ 150,000 | UNDP RR (US$ 150,000) OR (US$ 56,000) |
|  | 1.2.2. The coordinating mechanisms within CNE/STAE – Government and partners strengthened. |  | X | X | X | CNE/STAE | US$ 4,000 | US$ 4,000 | UNDP RR (US$ 4,000) |
| 1.3 Institutionalised stable and sustainable electoral cycle with regular funding. | 1.3.1. Strategy for mobilization of resources outlined | X | X | X | X | CNE/STAE | US$ 5,000 | - | OR (US$ 5,000) |
|  | 1.3.2. Implementation of a Programme and new forms of electoral civic education. . | X | X | X | X | CNE/STAE | US$ 50,000 | US$ 50,000 | UNDP RR (US$ 50,000) |
| TOTAL 1 US$ |  |  |  |  |  |  | US$ 270,000 | US$ 204,000 | UNDP RR (US$ 204,000) OR (US$ 66,000) |
| 2. Strategy for effective communication adopted |
| 2.1 CNE/STAE maintain an effective communication with the public | 2.1.1 Mechanism for an easy exchange of information formulated. | X | X | X | X | CNA / STAE | US$ 30,000 | US$ 16,000 | UNDP RR (US$ 16,000) OR (US$ 14,000) |
| TOTAL 2 |  |  |  |  |  |  | US$ 30,000 | US$ 16,000 | UNDP RR (US$ 16,000) OR (US$ 14,000) |
| 3. Dialogue with all political parties promoted and maintained. |
| 3.2 Political parties supported in conducting electoral processes. | 3.2.1 Guidance Course conducted with at least 75% of political parties. |  | X | X | X | CNE/STAE | US$ 40,000 | - | OR (US$ 40,000) |
| TOTAL 3 US$ |  |  |  |  |  |  | US$ 40,000 |  | OR (US$ 40,000) |
| 4. Major capacity for speeding up the progress in order to reach a full/massive participation of electoral population |
| 4.1 Civic education for strengthen the capacity to reach informed results of the elections and to guarantee a massive/full participation of the electoral population in electoral processes. | 4.1.1 Participative Seminars / workshops for training in civic education issues for government, civic society organizations and religion organizations to increase the quality of participation in civic education. |  | X | X | X | CNE/STAE | US$ 80,000 | US$ 60,000 | UNDP RR (US$ 60,000) OR (US$ 20,000) |
|  | 4.1.2 Materials produced for the use by the electorate and other interested parties in electoral process. |  |  | X | X | CNE / STAE | US$ 30,000 | US$ 20,000 | UNDP RR (US$ 20,000) OR (US$ 10,000) |
|  | 4.1.3 Analysis of the impact of civic education on effectively of the electoral process carried out. |  |  |  |  |  | US$ 80,000 | - | OR (US$ 80,000) |
| 4.2 Capacity of civil society strengthened in order to attain an efficient electoral process. | 4.2.2 Capacity of Civic Society Organizations to monitor elections and political dialogue using instruments for participative monitoring. |  |  |  |  |  | US$ 40,000 | - | OR (US$ 40,000) |
|  | 4.2.3 Networks of civil society organizations strengthened for an effective political participation of women. |  |  |  |  |  | US$ 40,000 | - | OR (US$ 40,000) |
| TOTAL 4 US$ |  |  |  |  |  |  | US$ 270,000 | US$ 80,000 | UNDP RR (US$ 80,000) OR (US$ 190,000) |
| 5. ADMINISTRATIVE AND OPERATIONAL COSTS |
| EXPECTED RESULTS | KEY ACTIVITIES | CALENDAR | RESPONSIBLE ENTITY | PLANNED BUDGET |
|  |  | 1º T 2010 | 2º T 2010 | 3º T 2010 | 4º T 2010 |  | Planned budget | Allocated budget | Sources of resources |
| Administrative and operational back up provided effectively and on time. | Personnel (ALD-series-CTA) | X | X | X | X | UNDP | US$ 120,000 | US$ 120,000 | UNDP RR |
|  | General and operational costs | X | X | X | X | STAE/CTA | US$ 10,000 | US$ 10,000 | UNDP RR |
|  | Equipment and furniture |  |  |  |  |  | - | - | - |
|  | Travels | X | X | X | X | STAE/UNDP/CTA | US$ 15,000 | US$ 15,000 | UNDP RR |
|  | Stationery and Office materials | X | X | X | X | STAE/CTA | US$ 5,000 | US$ 5,000 | UNDP RR |
|  | Cost recovery (estimated) |  |  |  |  |  | - | - | - |
| TOTAL 5 |  |  |  |  |  |  | US$ 150,000 | US$ 150,000 | UNDP RR |
| GRAND TOTAL PARA 2010 |  |  |  |  |  |  | US$ 680,000 | US$ 450,000 | UNDP RR (US$ 450,000) OR (US$ 310,000) |

M&E – Monitoring and Assessment

| AWP Expected results | Indicators, databases and targets | Verifying Means |
| --- | --- | --- |
| 1.2.Capacity of the CNE/STAE in planning of elections, budgets, organization and management in selected areas improved | Indicator: 149 officers of the Technical Secretariat for Electoral Administration trained in electoral administration during the BRIDGE of 2002 and 2009. International Community interested in the Mozambican electoral process; UNDP assistance strengthened. Database: 34% of the trained staff in electoral administration. In the 2009, with the support of UNDP, many electoral agents were trained during 3 regional seminars held in Nampula, Chimoio and Namaacha. Weak communication between donors and electoral organs. In 2009, two meetings were held between National Electoral Commission/Technical Secretariat for Electoral Administration and the international community. Target: Increase up to 80% of the trained electoral staff at the Technical Secretariat for Electoral Administration/Headquarters and at the provincial branches of STAE organizing training seminars. Increase the level of training of personnel already trained to intermediate level. Coordinating Mechanism CNE/STAE – Government – Donor implemented. | Regular reports ; Inquiries ; Monitoring and assessment of the implementation Supervision visits of National Electoral Commission/Technical Secretariat for Electoral Administration and UNDP. Report of budget execution ; Verification Meeting of the level of implementation of UNDP Project Monitoring and Assessment Visits Reports of facilitators and specialists |
| 1.3. Institutionalized a stable and sustainable electoral cycle with regular funding. | Indicators: Interest of the Civil Society Organizations observed in 11 training sessions which were held in provinces of Maputo, Sofala, Manica, Inhambane, Zambezia, Nampula, Cabo Delgado and Niassa. Results of the Survey on the impact of civic education held in Maputo, Beira, Quelimane and Nampula by the Research Company GSC. Database : In 1999, the participation of voters in casting of ballots was of 69.54% while in 2004 was of 36.42%. 1/3 of the voters in Nampula, Quelimane and Beira are not informed on the existence of an electoral organ (gsc research) 60% of the people surveyed in Nampula, Quelimane and Beira indicate STAE as coordinating organ of the electoral process (gsc research). Targets: Increase of information on the electoral process in rural areas at the country largest constituencies. Level of participation in civic education of the Civil Society Organizations increased, monitored and assessed. High number of voting population educated on democratic rights and importance of electoral process. | Regular reports; Surveys; Monitoring and Assessment of the implementation Supervision visits of CNE/STAE and UNDP Report of budget execution; Verification Meeting of the level of implementation of UNDP Project Monitoring and assessment visits Study of impact of civic education. Reports of facilitators and specialists. |
| 2.1. CNE/STAE maintains effective communication with public. | Indicator: The structure exists but needs to be improved. The system of information between the electoral organs and public in general still needs to be reinforced. Database: The system of communication between CNE/STAE and public and other interested improved in 2008 with the setting up of a press centre and establishment of a website. Targets: System of internal communication improved, assessed and monitored by the end of 2010. Monthly Information sessions to the public established by the end of 2010 at the provincial and central levels. Website improved, updated and functional | Regular reports Monitoring and evaluation by CTA Communication at the information organs on the CNE/STAE activities. |
| 4.1. Civic education promoted to reinforce the capacity in order to reach the results communicated of elections and to guarantee a massive and full participation of the voting population in electoral processes. | Indicators: 4 CSO with relevance at the national level working with UNDP and conducted training sessions in civic education with elders, youth and women. Results of the Survey on the impact on civic education held in Maputo, Beira, Quelimane and Nampula by the Research Company GSC. h It is worth mentioning that there is interest of several CSO in participating in electoral civic education. Database: In 1999, the participation of voters in casting votes was of 69.54% while in 2004 was of 36.42%. 1/3 of voters in Nampula, Quelimane and Beira are not informed of the existence of an electoral organ (gsc research); 60% of the people surveyed in Nampula, Quelimane and Beira consider STAE as a coordinating organ of the electoral process (gsc research). Targets: Increase of information on electoral process within population in rural areas in the largest electoral circles of the country; Level of participation in civic education programmes by CSOs increased, monitored and assessed. High number of voting population educated on democratic rights and on importance of the electoral process. | Regular reports; Surveys; Monitoring and Assessment of the implementation Supervision visits of CNE/STAE and UNDP Report of budget execution; Verification Meeting of the level of implementation of UNDP Project Monitoring and assessment visits Study of impact of civic education. Reports of facilitators and specialists. |

# Text boxes

Duration of the programme: 01 January – 31 December 2010

Component: Strengthening of the democratic process

Budget Code: _____________

Year: 2010

Estimated annual budget: US$ 760,000

Allocation of resources : US$ 450,000 	       Government :

Regular: US$ 450,000

Others: US$ 310,000

Budget without resources: US$ 310,000

Narrative

Include a brief narrative of the programme, as per the Agency CPAP or Agreement with GoM and list the outcomes of the programme as per the CPAP or Agreement with GoM

Project description:

The overall objective of the project is to strengthen and improve the activities for electoral planning and administration, through the assistance to the development of the capacity of management, of planning and budget of organs for electoral administration. In parallel, searching to strengthen the coordinating mechanisms within donators, government and organs of electoral administration and to support the civic education and voter programmes. This plan of activities has impact in electoral cycle 2010-2011, mainly in the training of electoral organs and of the voter.