Project Title: SOCIAL INCLUSION AND EMPOWERMENT UNDAF Outcome(s): (Not applicable: Mauritius is a Category-C country) Expected CP Outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society. Expected Outputs: Targeting, delivery and monitoring arrangements for Ministry of Social Integration and Economic Empowerment social programmes (implemented through the National Empowerment Foundation) operational. Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors New models of service delivery and other pro-poor interventions and actions implemented and tested by the public sector, the private sector (through Corporate Social Responsibility activities), NGO’s and communities. Executing Entities: Ministry of Social Integration and Economic Empowerment (MSIEE) and Ministry of Social Security, National Solidarity and Reform Institutions (MSS) Implementing Agencies: The National Empowerment Foundation (NEF) and the Non-State Actors’ (NSA) Unit

Other Collaborating Agencies:

Ministry of Finance and Economic Development (MoFED); Ministry of Gender Equality, Child Development and Family Welfare; the National Computer Board; the Rodrigues Regional Assembly; Global Environment Facility / Small Grants Programme; the Decentralized Cooperation Programme (EU); the Mauritius Council of Social Services (MACOSS); the Rodrigues Council of Social Services (RCSS); Local Authorities in pilot areas (municipal and village councils, District Councils; Non-State Actors, including Civil Society Organisations (CSOs) and NGOs, Private Sector Associations, Foundations and Institutions; other Specialised UN Agencies (such as UNWOMEN), and other Development Partners.

Brief Description The ‘Social Inclusion and Empowerment’ project is designed to support the Government of Mauritius and Non-State Actors in exploring more effective ways of addressing poverty and the exclusion of vulnerable groups from the socio-economic benefits that the majority of the population has enjoyed over the past few decades. It will facilitate capacity development processes to enhance the effectiveness of public and private sector institutions, NGOs and CSOs in working together under interventions intended to directly combat poverty and exclusion. In so doing, efforts will contribute towards the empowerment of citizens, improved public participation and transparency in the delivery of services (in line with MDG1); an increased share of women working in the mainstream economy; the political empowerment of women (MDG3), and the promotion of IT literacy amongst vulnerable sections of society. The project takes a holistic, multi-sectoral, multi-agency, integrated approach. Emphasis is placed on learning from evidence-based best practices, the principles of which will then be replicated, scaled-up and used to inform policy level dialogue on issues relating to the delivery of projects and services intended to address poverty and exclusion. The overall intervention will be underpinned by the development of a culture and a capacity within all stakeholder agencies to engage in effective monitoring and evaluation. The project will be executed under National Implementation Modalities (NIM) by a Management Unit located within the premises of the MSIEE over a four year period, with a sub-unit in Rodrigues. The main executing agencies will be the MSIEE, with the support of the National Empowerment Foundation, and the MSS, supported by the NSA Unit. Multiple stakeholder agencies will collaborate in the project, which will be reviewed and monitored by relevant partners. The project also aims to contribute to the CP 2013-2016 outcomes of pillar 1 (Planning and Resource Management for inclusive growth) and pillar 3 (Energy and Environment) of the overall Country Programme in improving the quality of Mauritius’ growth and human development. The project also takes account of the need for UN Agencies to Deliver as One, and the implications of Net Contributing Country status post 2016. Programme Period: 2013 - 2016 Key Result Area: Poverty Reduction and Social Inclusion Atlas Award ID: _____ Document Completion Date: December 2012 Start date: January 2013 End Date: December 2016 PAC Meeting Date: 21st November 2012 Management Arrangements: NIM and UNDP Country Office Support to NIM Total resources required US$ 1,375,010 Total allocated resources: US$ (UNDP and UN Women) Regular (TRAC 1) US$ 543,000 Other: UNDP (TRAC 2) US$ 300,000 (TBC) UN Women US$ 110,000 (of which $60,000 TBC) Government MSS US$ 132,000 MSIEE US$ 140,000 MGE In kind NCB In kind RRA US$ 65,000 NEF In kind contributions to implementation of LIDPs CSR / Other Donors US$ (Dependent upon LIDP requirements & resource mobilisation efforts) *All figures are converted from Mauritian Rupees with the UN exchange rate of MUR 29 / 1 USD.

Agreed by Government

Ministry of Finance and Economic Development:		Date:

Mr. Ali Mansoor, Financial Secretary

Agreed by Executing Entities

Ministry of Social Integration and Economic Empowerment

Mr. B. Boyramboli, Permanent Secretary			Date:

Ministry of Social Security

Mr. R. Duva-Pentiah, Permanent Secretary			Date:

Agreed by United Nations Development Programme:

Mr.  Simon Springett, Resident Representative		Date:

I. Situation Analysis

1.1 In many respects, the rapid development of Mauritius since independence in 1968 has been remarkable. The country has successfully transformed itself from a low income, mono-crop agricultural economy based largely on sugarcane, to an upper middle-income country with a gross national income (GNI) per capita of US$8,240 in 2011. It also scores well in terms of Human Development, with a Human Development Index of 0.728, thereby ranking 77th out of 187 countries and second in Sub-Saharan Africa. These achievements may be attributed to successive Governments’ pursuit of liberal, open economic policies, focusing on growth and employment, and sound macro-economic management, and the simultaneous maintenance of an elaborate social welfare system. Despite the global economic crisis over recent years and the sovereign debt crisis in Europe, which is an important trading partner, Mauritius has been able to attain an average real GDP growth of 4.5% during the period 2007 to 2011. Efforts to diversify the economy from the traditional sectors of tourism, textiles and sugar to new ones such as information and communication technologies and financial services continue to yield successes. However, the unemployment rate has gone up from 7.2% in 2008 to 7.9 % in 2011.

1.2 Mauritius has also made significant progress in achieving the targets set in the Millennium Development Goals (MDGs), notably in areas such as education, gender equality in education, adult literacy, infant mortality and the provision of safe drinking water and improved sanitation. Nevertheless, the country has to deal with several important challenges. These include residual, but still significant levels of poverty, with some 26,000 households representing 7.9% of total households falling below the national Relative Poverty Line (Statistics Mauritius, Poverty Analysis 2006/07). This figure rises to 17.9% in Rodrigues. Inequality is also a feature of this poverty. Mauritius has a Gini coefficient of 0.38, and there are significant spatial disparities in the incidence of poverty. In particular, the island of Rodrigues has generally missed out on the rapid economic development experienced on the main island of the Republic. It is characterised by an economy largely dependent upon subsistence agriculture and fisheries, supported by a large public sector, with limited opportunities for private sector employment. According to the 2011 census, Rodrigues is the second most impoverished region of the country, surpassed only by Le Morne Village Council Area.

1.3 Gender disparities also persist across a range of social and economic issues. For example, only 18% of Members of Parliament are female, well below the SADC target of 30%, and female unemployment in 2011 stood at 13%, in comparison to the male rate of 4.7%. Gender-based violence also affects women more than men. In 2010, for example, out of 2,215 reported cases, 1,952 were women. There has also been a reversal in maternal mortality, with an increasing trend since 2007.

1.4 In addition, Mauritius faces major development challenges typical of middle–income Small Island Developing States (SIDS), such as environmental vulnerability and exposure to natural disasters, especially in the face of climate change; coastal zone erosion; endangered species; reduction in forest coverage; decrease in fish stocks; water shortages, and vulnerability to external economic trends, including decreasing Overseas Development Assistance. In order to sustain diversified growth, whilst promoting social inclusion and securing environmental sustainability, the Government has formulated an overarching plan,   Maurice Ile Durable (MID). This is built around five pillars - Education, Equity, Employment, Environment and Energy.

1.5 Furthermore, policy formulation and implementation of poverty reduction strategies are hampered by the lack of proper eligibility assessment mechanisms for social programmes, leading to substantial (constituting around 4.4% of GDP) but ineffective social spending, with large errors of both exclusion and inclusion. Tools to measure and manage programme performance are inadequate and there is a paucity of capacity and skills within public institutions and among Non-State Actors (NSAs) to conceptualise and design new initiatives to address poverty and social exclusion. Accountability for public service delivery and performance is also limited. The effects of these shortcomings manifest themselves in several widely recognised, tangible and inter-related problems, as follows:

- Current interventions do not reach those most in need of support

- Many programmes are poorly designed, with insufficient attention to the long term empowerment of the beneficiaries, leading instead to dependency

- Projects are designed with a short time horizon, with insufficient attention to sustainability and the nurturing of transformational processes

- Interventions tend to be activity-based, deliver products and pay insufficient attention to processes and accompaniment

- Policy makers and project planners lack the technical skills to analyse the needs of beneficiaries or underlying causes of poverty, and do not understand their aspirations

- There is insufficient participation of the beneficiaries in the formulation of projects and programmes, and a tendency towards a ‘top down’ approach

- Potential beneficiaries are not well informed and sensitized on services offered  and opportunities available under various progammes

- Few opportunities exist for citizens to provide feedback on the quality of services being provided

- There is lack of a proper M&E Framework to assess programmes within both the state and non-state sectors

- There is need to share best practices for greater effectiveness of social programmes

- Despite some positive developments over recent years under the National Empowerment Foundation and increasing levels of Corporate Social Responsibility, partnerships between the public sector, private sector and civil society have yet to realise concrete results

- Some programmes tend to be piecemeal and operate in ‘silos’. Without the required integrated, co-ordinated, holistic, multi-stakeholder approach, interventions  do not achieve the desired results in addressing the multi-dimensional nature of poverty and exclusion

- Co-operation between Ministries and Commissions of the RRA needs to be strengthened for greater sharing of knowledge and experiences

- Interventions designed for Mauritius should duly consider the specificities of Rodrigues for greater effectiveness of policies and programmes.

1.6 Over the next Programme Cycle (Country Programme 2013-2016), UNDP Mauritius has committed itself to assist the Government to strengthen institutional capabilities for accountable, equitable and effective use of public resources. These areas will be addressed by:

i. Improving the capacity of Government agencies in strategic planning, programme-based budgeting 	and 	effective service delivery;

ii Strengthening the capacity of the public sector, NSAs and vulnerable groups to 	promote a coordinated 	approach in policy formulation and implementation for a more equitable and inclusive society; and,

iii. Achieving environmental sustainability while addressing climate change and ensuring more effective 	protection and conservation of natural resources.

1.7 The Social Inclusion and Empowerment Project will focus on the second pillar mentioned above. However, linkages and synergies amongst the three components will be actively pursued. Public sector ministries and agencies and Non- State Actors will benefit from capacity-building initiatives in areas such as participatory planning and policy formulation; designing and delivering pro-poor projects, and M&E. The intended final beneficiaries will be the poor and marginalised living in areas of multiple deprivation, the so-called pockets of poverty. More generally, women will also benefit from empowerment interventions and an engendered policy environment.

II. Strategy

2.1 The National Strategy

The main areas of focus of the previous Country Programme were public sector reform, inclusive growth, environmental protection and climate change. The UNDP Country Strategy (2013 to 2016) has been designed to build on this former support, incorporating lessons learnt. As such, it will assist the Government in achieving more sustainable and equitable growth and human development, utilising a limited number of triggers that can have major multiplier effects across a broad spectrum of critical development issues – improving the outcomes of public expenditure, expanding opportunities and institutional channels for social inclusion, and enabling prudent management of natural resources and timely adaption to climate change. Thus, it will contribute to the realisation of the objectives of the Government’s Maurice Ile Durable.

The Country Programme will also continue support to, and inform the reform of, the National Empowerment Foundation (NEF). Despite this non-profit company’s objective of ensuring more coherence in the implementation of pro-poor programmes, and the large amount of resources at its disposal, generally speaking, results to date have not improved significantly. An evaluation in 2010 attributed these shortcomings to (amongst others) weaknesses in monitoring and evaluation and accountability systems; a weak focus on results; a lack of a common approach to targeting and performance measurement; a lack of ongoing analysis within programmes, and the absence of a working model of poverty and poverty reduction to guide analysis and planning. The new Country Programme will attempt to address these constraints. It will also assist the Government in reforming national social security services, in order to ensure more efficient and effective delivery of social welfare programmes. Building local capacity will underpin the overall approach.

2.2 Project Strategy

The intended outcome of the project is stated as follows:

Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society.

Thus, the project will support the Government’s strong commitment to assisting the country’s small population of poor households, in order to bring them into the mainstream of society. In pursuing this outcome, the project will involve a series of activities that will result in the delivery of specific products and services, grouped under three distinct, yet inter-dependent outputs. These are outlined in more detail in the following paragraphs.

Output 1:

Targeting, delivery and monitoring arrangements for Ministry of Social Integration and Economic Empowerment social programmes (implemented through the National Empowerment Foundation) operational.

In realising output 1, the project will attempt to bring about a more efficient identification of vulnerable groups and disadvantaged areas for inclusion in pro-poor programmes. Under previous programmes, UNDP provided assistance for the technical design of a Social Register of Mauritius (SRM) and a Proxy Means Test (PMT) to improve the targeting efficiency and harmonization of the multitude of social programmes operational in the country. The SRM, which is housed within MSS, has already been utilized to implement the new housing and crèches schemes announced in the 2012 budget. Under Pillar 1 of the Country Programme (2013 to 2016), technical assistance for the further development of the SRM will continue. The Social Inclusion and Empowerment pillar will utilise this system as a means of identifying final beneficiaries and geographic locations for the implementation of pilot projects (see output 3), along with complementary data collection tools. The SRM will also feed into improved monitoring and evaluation systems.

Output 1 will require capacity-building initiatives. Following a needs assessment, these will target the development of skills and tools for results-based project and programme planning for relevant staff working within MSS, NEF, Ministry of Gender, RRA and participating NSAs. In order to address the related issue of weak monitoring and evaluation systems, the project will continue the support that commenced in April 2012. This will require the ongoing deployment of an M&E expert funded by UNDP to operationalise the M&E Unit already established within NEF. MSIEE will appoint a suitably qualified counterpart to ensure skills transfer, national ownership and lasting benefits, and provide operational funds. The World Bank will provide technical assistance to the development of M&E systems designed to ensure value for money, transparency and accountability, as well as feedback on performance for improved, dynamic project management. The Unit will also address the capacity building needs of the public sector (Ministries, National Institutions, the RRA, the NEF (including case workers in its Rodrigues office) and the private sector working on CSR interventions to implement M&E systems at service delivery and project levels. The capacity building of NSAs to implement M&E systems at project level will be addressed in tandem through the Common Training Strategy Committee, established by the MSS in collaboration with the NGO Trust Fund, the EU funded Decentralised Cooperation Programme (DCP), MACOSS, and NCSR Committee.

In addition, the project will support the M&E Unit to review all existing NEF projects under each of its operational pillars (Placement and Training; Child and Family Welfare; Social Housing, and Community Empowerment). This will include the development of SMART OVI’s for each NEF programme, and the design of data collection tools and the establishment of appropriate baseline data. In carrying out its work, the Unit will work closely with the Economic Planning and Monitoring Unit (EPMU) of the Chief Commissioner’s Office in Rodrigues, and ensure appropriate solutions for M&E shortcomings on the island. It will also liaise with the NSA Unit on all issues related to M&E, and contribute to the Knowledge Management activities foreseen under output 3. (For detailed Terms of Reference for the M&E Officer, please refer to Annex II).

Output 2:

Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors

Output 2 activities will involve the empowerment of marginalised groups, focussing particularly on the needs of women. A major result area will address gender policy issues in both Mauritius and Rodrigues. Previously, UNDP supported the formulation of a National Gender Policy Framework (NGPF, 2008) and the implementation of gender-responsive budgeting (GRB) in eight Ministries. It also supported the capacity building of Gender Cells within sectoral Ministries to formulate effective strategies for integration of gender issues. Under the new project, the capacity of staff of the Ministry of Gender Equality will be strengthened to support other ministries on gender-mainstreaming issues, thereby reducing dependency on external assistance. Capacity building measures will link closely with the gender budgeting initiatives to be dealt with under Pillar 1 of the Country Programme.  The Gender Focal Point based at UNDP will ensure a coordinated approach with other multilateral agencies and institutions such as the Delegation of European Union and African Development Bank (AfDB) in the process of mainstreaming gender at national level.

Using the NGPF for Mauritius as a starting point, and adopting a multi-sectoral approach, support will be provided for the formulation and implementation of a Rodrigues-specific gender policy. This will commence with a participatory study and mapping of the status of women and men in Rodrigues, followed by clarification of the concept of gender and an awareness-raising programme relating to gender in Rodriguan society. These actions will be succeeded by the drafting of the policy and elaboration of a Plan of Action. A Training Needs Analysis of all stakeholders will then be undertaken to determine their capacity requirements to deliver the strategy. This will inform the detailed design of the training programme, which will then be rolled out. The overall process will be implemented through the RRA’s Commission for Women, and will involve actors from the state, private sector and civil society. UNDP and UN Women will provide either technical or financial support.

Previously, UNDP supported the development of a National Action Plan to Combat Domestic Violence. However, gender-based violence (GBV) remains a problem in both Mauritius and Rodrigues. The new project will focus on Rodrigues, by developing a Strategy to combat GBV on the island, under the funds allocated by UN Women. This will commence with a participatory study and assessment of GBV incidences on the island. Activities will involve greater cooperation between the RRA’s Commission for Women and the Ministry of Gender Equality, and an exchange visit to Mauritius to share experiences. The strategy will be drafted as part of a participatory workshop, and will be followed by the elaboration of a Plan of Action. A TNA of all stakeholders (including the Commission for Women, Police Family Unit & NSAs) will be undertaken to determine their capacity requirements to deliver the strategy. A training package will be developed and rolled out, eventually culminating in the establishment of improved services by the RRA.

Another result area under output 2 concerns the political empowerment of women. As previously noted, only 18% of MPs are female in the National Assembly. The situation is a little better at the level of the RRA, with 5 out of 18 Assembly Members being women. The project will provide further training to existing trainers and support the organisation of training workshops in Mauritius and Rodrigues concerning women in politics (with the assistance of the UNDP Gender Focal Point). Furthermore, under output 3, the project will encourage the decision-making empowerment of women at the grass-roots level of development by ensuring their active participation in the governance structures established to implement the pilot projects.

Despite the important role women play in Rodrigues, gender inequality remains a major concern. In order to address the island’s specificities in this regard, the project will support the development of best practice training materials to meet the current needs of women. This will include a review and updating of courses currently delivered at the two women’s centres, with more emphasis placed on life skills. Such initiatives will feed into the RRA’s concept of a “women’s leadership academy”. Technical assistance will be provided by UN WOMEN, working in conjunction with the Human Resources Council and MITD. A ToT approach will be adopted to ensure that local trainers can deliver the new materials. More generally, the project will also support activities aimed at raising awareness of gender issues amongst men and women in Rodrigues.

In addition, the project will facilitate improved co-operation between the Ministry of Gender Equality and the RRA, along with other stakeholders. The overall process will be supported by the UN Country Office Gender Focal Point.

Output 3:

New models of service delivery and other pro-poor interventions and actions implemented and tested by the public sector, the private sector (through Corporate Social Responsibility activities), NGO’s and communities.

Under the former Support to Inclusive Development Project, UNDP, in conjunction with UNV, assisted the Ministry of Social Security to establish the Non-State Actors (NSA) Unit in December 2009. Operating under the aegis of MSS, the unit’s primary responsibilities included the building of capacities amongst NGOs to engage proactively in development processes, in partnership with Government and the private sector, and the development and management of mechanisms intended to encourage and support national and international volunteers, and to channel their skills to meet the needs of civil society. Whilst the NSA Unit has provided tailored training to NGOs and a pool of volunteers has been established and trained in several subject areas, much more needs to be done on both aspects. The issue of providing stipends to volunteers must be resolved, as this is constraining the effective roll-out of the National Plan for Volunteerism. The new project will provide continued support to the unit, in particular through the provision of a UNDP funded Project Officer and UNDP supported Assistant Project Officer. MSS will provide operational funds and appoint a local executive counterpart to the project staff in order to maximise skills transfer and sustainability.

The NSA Unit will continue to promote the national volunteer scheme. In addition, it will consider the specific needs of such a scheme in Rodrigues, and identify a focal point on the island to oversee this initiative. A strong community development approach that increases the voluntary spirit amongst the population and restores the tradition of self-help could be very well suited to the Rodriguan context. The NSA Unit will explore a variety of potential volunteer schemes with the RRA and CSOs on the island, building on lessons learnt from current initiatives, and providing an alternative to the NEF’s Training and Placement Programme, as this failed in Rodrigues due to the limited size of the private sector. In this context the new scheme of HRDC at national level can be implemented in Rodrigues. Such a scheme and that of the NSA Unit would fit well with the RRA’s Programme (2012 to 2017), which emphasises a ‘participatory democracy approach’, with the active participation of the whole community in decision-making.

The NSA Unit will continue to provide capacity building support to NGO’s. This will be channelled through the Training Platform already established by the MSS in collaboration with the NGOTF, the NSA Unit, MACOSS, the National CSR Committee, and the EU funded DCP. Capacity building efforts will be intensified in Rodrigues. Activities will include support to the Commission of Social Security and Commission for Community Development on the management of NGOs; and the establishment of a Rodrigues NGO Forum to increase partnerships, participation, better coordination and more structured dialogue with the RRA. In both Mauritius and Rodrigues, the unit will promote a culture of M&E amongst NSA’s (in collaboration with DCP and the NEF M&E unit). Emphasis will also be placed upon training in community-centred development approaches, and the Unit will act as a facilitator in initiating and securing ongoing participation from NSAs in the pilot projects discussed below.

The Territorial Approach

Given the broad-based nature of social exclusion, the limited resources and timeframe available, and the inherent challenges of managing such an intervention on a national scale, the project will adopt an innovative, territorial approach to realising output three. This will involve the piloting of multi-sectoral, local integrated area development plans. One pilot area will be identified in Mauritius and one in Rodrigues, covering one or two contiguous Village Committees. These areas will be selected on the basis of the coincidence of needs and potentials. The Relative Development Index from Census 2011 and the SRM database will be used to identify localities and households that suffer most from deprivation and exclusion. These would then be supplemented using other information sources and field-based assessments. Selection criteria could include the following:

% of the local population in receipt of social aid and other social welfare programmes

% of the local population falling below the Poverty Line

Living conditions standards

Levels of unemployment

CPE graduation rates (or location within a ZEP)

Levels of crime.

It should be noted that a third pilot area may be identified, depending on availability of funding.

In order to establish areas of multiple deprivation with potential, criteria could include a good track record of active CBOs; the presence of NGO and CSR activity, and the likelihood of other major investments coming into the locality. For example, locations that are likely to benefit from infrastructure improvements through Government’s social housing programmes, or those planned through the UN Habitat’s Participatory Slum Upgrading Programme (PSUP) or the Mauritius Chamber of Commerce and Industry Foundation’s CSR interventions, could present potential opportunities for synergies and complementary social and local economic development activities.

The process will involve the initial identification of all agencies from the public (central and local) and private sectors, international development partner programmes and NGOs that provide services to the area, and the drawing up of MoU’s and partnership agreements amongst these entities, as the project will require new ways of working together beyond traditional approaches. Multi-disciplinary facilitation teams comprising the staff of each partner that will be working in the area will be established. Their capacities to plan and design interventions that address inequality and social exclusion would be assessed, followed by an ongoing process of on-the-job capacity-building. This would represent the practical application of the more generic, theoretical training provided under output one of the overall project.

The pilot projects will commence with a participatory needs appraisal and the establishment of governance structures that ensure community participation, especially from women and other vulnerable groups. Baseline surveys will be undertaken and Local Integrated Development Plans for each of the 2 pilot areas (with OVIs) will be developed through participatory planning techniques to ensure demand-driven development. These will provide a framework for the implementation of all services and pro-poor projects in the area. As such, they will guide the activities and investment decisions of each agency working in the area, as well as the community’s own self-help initiatives, and form the basis for additional resource mobilisation efforts. It will be important to harness CSR and NEF resources, along with those of other UN Agencies under the Delivering as One initiative and other international donors. These may be supplemented by encouraging and assisting NGOs to respond to local and international Calls for Proposals. There will also be resource synergies with the promotion of sustainable livelihoods and decent work for vulnerable groups under pillar three of the new Country Programme, especially in Rodrigues. Other partners, such as the Decentralised Cooperation Programme of the EU and the Small Grants Programme of Global Environment Facility, will be invited to participate, depending upon the needs identified.

The implementation of the Local Integrated Development Plans will be accompanied by the design of tools for capturing the lessons learnt and good practises that emerge from the pilot areas, based on a Theory of Change approach. This will be coordinated by the Monitoring and Evaluation Unit of NEF and will serve as a basis for the eventual setting up of a comprehensive Management Information System in partnership with other institutions. The NEF M&E unit will provide an intensive M&E service, supplemented by the RRA’s EPMU in the Rodrigues pilot, thus allowing in depth analysis of projects’ and programmes’ performance within the Local Integrated Development Plans and the generation of lessons learnt. Best practices will be disseminated through workshops, seminars and networks, and packaged into models of improved service delivery and project designs. Space will be created to facilitate advocacy and policy dialogue activities to take place around the new models of service delivery, allowing replication, scaling-up and strategic impact beyond the pilot areas. For example, new policy principles will inform the long term, strategic planning support that will be provided under pillar one of the Country Programme.

The first pilot area will be commenced in Mauritius, followed by Rodrigues. As the Local Integrated Development Plans will have time horizons of five years, even the initial pilot will extend beyond the project end date of December 2016. Hence, it will be essential to adopt a self-sustaining process approach, and ensure that local skills are developed from the beginning. Such an approach is especially appropriate, given the implications of Mauritius approaching Net Contributing Country status by the end of the current funding cycle or mid next cycle. Initial management of the component will be challenging and intensive. Hence, the overall Social Inclusion and Empowerment Project will be provided with a Project Manager  (based in Mauritius) and  Project Coordinator cum Community Organiser (based in Rodrigues), both of whom will have strong community development, participatory planning and facilitation skills, in addition to project management capabilities. These positions will be jointly funded by UNDP and the RRA.

Another important result area within output 3 will involve the empowerment of citizens to increase their public participation with a view to achieving greater transparency and feedback on public services. Within the pilot areas, activities will include raising awareness on rights issues amongst local communities, especially in relation to vulnerable groups; and the design of feedback systems and channels of communication to allow citizens to inform service delivery improvements, for example through scoring cards. Beyond the pilot areas, two to three key service areas will undergo similar treatment.

Finally, the project will encourage literacy in Information Technology for vulnerable sections of society, especially amongst women to enhance their employability. This result area will build upon previous UNDP support under the Community Empowerment Programme, and tackle the digital divide by facilitating marginalised groups’ participation in this new pillar of the economy. It will involve cooperation with the National Computer Board (NCB) in targeting its existing ICT literacy programmes within the pilot project areas, and strengthening the penetration of ICT throughout both Mauritius and Rodrigues via Women’s / Community / Youth /  Social Welfare / Day Care centres and HRC. In extending the NCB ICT intervention to the pilot areas, a two-phased programme is envisaged. The first step will be to propose an initiation programme on the use of computers, followed by a training programme of 45 hours in ICT. The support of the private sector under CSR will be sought in order to cover the minimal costs involved.

Training will be provided to volunteers in order to provide accompaniment and maximise the impact of the Government’s new e-governance portal. In addition to training, hardware may be provided with the support of CSR. Centres which are well used and managed, with a locally available pool of volunteer trainers will be prioritised. ICT activities in Rodrigues will be implemented by the newly set-up Centre of Excellence for ICT and will work closely with the recently created ICT Steering Committee. The latter comprises industry actors from both the public and private sectors. Its main objective is to prepare the island to maximise opportunities arising from the arrival of the optical cable.

2.3 Partnership Strategy

The project design is based around a complex and comprehensive partnership approach, involving multiple stakeholders from the public and private sectors, other UN agencies and development partners and civil society. This is essential in order to transcend traditional boundaries and explore new ways of working together to address multi-faceted, cross-sectoral development problems falling beyond the purview of individual agencies in a co-ordinated manner. It will also allow the comparative advantages of each actor to be exploited and the full extent of required technical and financial resources to be harnessed.

UNDP is well positioned to perform the role of a neutral broker, and to facilitate the active participation of all parties, including final beneficiaries, and the creation of an enabling environment for such partnerships. The integrated, area-based development plans in the pilot locations will, in particular, take the ‘Delivering as One’ approach well beyond the UN system. UNDP’s role in the project will be catalytic, allowing it to leverage its limited core resources to provide a credible, participatory framework into which other development partners, government agencies and CSR entities should be willing to channel parallel funding and technical inputs in pursuit of synergies and added value. As most stakeholders in Mauritius are of the view that resources per se are not a constraint in the fight against social exclusion and poverty, UNDP’s investments in developing the approach and frameworks should allow sufficient implementation funding to follow.

The following institutions will be actively involved in the project:

Ministry of Finance and Economic Development will maintain coordination and oversight of all components of the project, with the technical support of UNDP. It will also assist in liaising with donor agencies to solicit additional technical or financial resources, for example through the AfDB Country Programme and the Technical Cooperation Facility of the EU.

Ministry of Social Security will support the ongoing operations and further development of the Non-State Actors Unit, in collaboration with UNDP. It will also constitute one of the two co-executing agencies (the other being the MSIEE).

The NSA Unit will take the lead role in rolling out the national volunteer scheme, building the capacity of CSOs, and supporting their active involvement in the project. In doing so, it will work through the Common Training Strategy Committee, established by the MSS, and its participating agencies.

National Empowerment Foundation will support the development and operationalisation of the M&E Unit, in collaboration with UNDP. The Unit will take the lead in developing the capacities and skills required to implement new M&E systems to be developed with World Bank support at the level of NEF programmes. It will also oversee the development and implementation of M&E processes under the pilot projects. In addition, NEF will channel implementation resources to the pilot projects and adopt emerging principles of best practice throughout its programmes.

Ministry of Social Integration and Economic Empowerment will perform the role of a co-executing agency.  As such, it will host the Programme Manager of the overall programme. Ministry of Gender Equality and the Commission for Women will collaborate on all aspects related to gender, with the support of the UN’s Gender Focal Point and UN Women.

Ministry of Information and Communication Technology and the National Computer Board will collaborate on project interventions related to ICT.

Rodrigues Regional Assembly will be actively involved in the implementation of all project components on the island of Rodrigues, including its pilot area. The EPMU will have a local monitoring and coordinating role, while sectoral interventions will benefit from the inputs of the relevant Commissions. A Project Coordinator cum Community Organiser will also be recruited and based within the EPMU.

Local Authorities (Municipal and Village Council Areas, District Councils) will be active development partners in the pilot areas.

The M&E Unit of NEF will develop and coordinate the lessons learnt and good practices in the pilot areas.

Non-State Actors, including Civil Society Organisations (CSOs) and NGOs, will be active project implementers, especially in the pilot areas.

Private Sector Associations, Foundations and Institutions through their Corporate Social Responsibility (CSR) activities and international donor agencies will bring in additional resources, especially in the pilot areas.

As co-executing agencies, MSS and MSIEE will work together synergistically to realise the project’s intended outcome. They will both have significant inputs in the pursuit of outputs 1 (targeting, delivery and monitoring arrangements of MSIEE social programmes operational) and 3 (new models of service delivery by NSAs successfully tested…), with several MSS interventions centred around the NSA Unit and the SRM, and several MSIEE activities implemented through the NEF M&E Unit, in particular. However, the Annual Work Programmes section of this document specifies clearly which agency is responsible for each specific activity.

III RESULTS AND RESOURCES FRAMEWORK: SOCIAL INCLUSION AND EMPOWERMENT

Intended Outcome as stated in the Country Programme Results and Resources Framework: (2) Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society

Outcome indicators as stated in the Country Programme Results and Resources Framework, including baseline and targets: Progress on MDG indicators for Poverty Reduction, Gender Equality and Women Empowerment - Households falling below the Relative Poverty Line reduced from 7.9% (2006/7) to 7.1% (2016) - % of population deemed to be vulnerable by SRM in the pilot areas reduced by 10% - Qualitative assessment of targeted communities (based on feedback mechanisms utilised with panellists from the pilot areas) Improved competence of public sector, NSAs & vulnerable groups in delivering pro-poor interventions - Current capacity (established through a participatory baseline) relative to what is required to achieve the desired outcome, measured by simple indicators that proxy for progress towards objectives (as set out in Capacity-Results Frameworks for each capacity-building intervention) - NSAs effectively contributing to at least a 10% reduction in poverty rate by 2016 (in the pilot areas) - Improved performance of NGOs (in terms of achievement of planned results (eg. thru meta-evaluations, based on a pre-project sample baseline) - Qualitative assessment of targeted communities (based on feedback mechanisms utilised with panellists from the pilot areas)

Applicable Key Result Area (from 2008-11 Strategic Plan): Poverty Reduction and Social Inclusion

Partnership Strategy: UN ‘Delivering as One’

Project title and ID (ATLAS Award ID):

| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | RESPONSIBLE PARTIES | INPUTS |
| --- | --- | --- | --- | --- |
| Output 1 Targeting, delivery and monitoring arrangements of MSIEE social programmes operational Baseline: 1. Inadequate tools and capacity to measure and manage programme performance Indicators: 1.1 Increased inclusion of the poor in MSIEE social programmes 1.2 No. of stakeholders trained in Results-based planning & management Improvement in quality of project monitoring frameworks developed by NEF beneficiaries 1.3 NEF’s capacity to evaluate outcomes & impact of social programmes NSAs’ capacity to design & utilise M&E tools at project level & appreciate their value (for ongoing management & informing future actions & policy dialogue) | Targets (Years 1 to 3): 1.1 Two pilot areas identified using RDI, SRM & other pro-poor targeting mechanisms (Yr1) [with possible 3rd depending upon funds] No. of new public & private/CSR/CSO initiatives assisted to submit detailed requests to MSS for targeting support from SRM reaches x (Yr2); x (Yr3) 1.2 50 people trained in Results-based planning & design in Mauritius & 25 trained in Rodrigues (Yr1); 25 in Mauritius (Yr2) Proportion of projects submitted with adequate monitoring frameworks increased from x% (baseline prior to training) to y% by end Yr1; y% by end Yr2; y% by end Yr3 1.3 M&E Unit at NEF fully equipped & staffed, & range of M&E tools developed (Yr1) Proportion of final project reports prepared & submitted for all interventions supported under NEF considered to be ‘good’, increased from x% (baseline before training) to y% by end Yr1; y% by end Yr2; y% by end Yr3 NEF produces a quality meta-evaluation (based on a sample of interventions) for one of its intervention components (Yr1); two of its components (Yr2); three of its components (Yr3) All NEF programmes have baseline data & OVIs established by end Yr2 Targets (EoP): 1.1 Rate of inclusion of the poor in NEF programmes is increased from x% (pre project start-up) to y% All NEF programmes utilise SRM 1.2 At least x% of projects submitted have adequate monitoring frameworks 1.3 At least x% of final project reports prepared & submitted for all interventions supported under NEF are considered to be ‘good’ NEF produces quality meta-evaluations (based on a sample of interventions) for all of its intervention components M&E lessons learnt are internalised & reflected in the formulation of subsequent programmes | 1.1 Activity result: Efficient identification of vulnerable groups & disadvantaged areas for inclusion in pro-poor programmes achieved Use of SRM for initial identification Use of complementary data collection tools & other data sources (e.g. Statistics Mauritius) 1.2 Activity result: Results-based project & programme planning & management strengthened Assessment of needs Identification of resource persons / consultant for training Training of MSS, NEF, Ministry of Gender, RRA, NSAs 1.3 Activity result: M&E system operational Deployment of M&E Officer Appointment of suitable qualified local counterpart (MSIEE/NEF) (RRA-EPMU) Technical assistance for the development of M&E system Capacity building of NSAs to implement M&E systems at project level (Training platform -NSA unit -MSS; DCP, MACOSS, NGOTF) Capacity building of public sector (Ministries, National Institutions, & RRA, thru EPMU), NEF (including case workers in Rodrigues) & private sector (CSR) to implement M&E systems at service delivery & project levels Review of existing NEF projects Design of data collection tools & establishment of baseline data (including field surveys) Development of SMART OVI’s for each NEF programme | UNDP MSIEE (& NEF) RRA Chief Commissioner’s Office (EPMU) MSS (especially NSA Unit & SRM) Consultant: Trainer on Results-based planning & Management Collaborating Parties: DCP (training NSAs on M&E) | UNDP- Operational Support to M&E Unit (incl. trips to Rodrigues) = $15,000 Consultants for training in Results-based project and programme planning & management = $30,000 Contribution to workshop costs & information materials = $15,000 Human Resource Support to the NEF M&E Unit (for 4 yrs) = $145,000 MSIEE- Human Resource Support to NEF M&E Unit (Local M&E Officer over 4 yrs) = In-kind Operational Support to M&E Unit = $20,000 Contribution to workshop costs & information materials = $20,000 Field survey work =$40,000 |

| Output 2 Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors Baseline: 2.1 Inadequate capacity to mainstream gender issues in Mauritius 2.2 Lack of Rodrigues specific strategy to address gender issues 2.3 Lack of Rodrigues specific strategy to combat GBV 2.4 Low participation of women in politics 2.5 Lack of training materials in Rodrigues that are relevant to the current needs of women 2.6 Little formal cooperation between Ministry of Gender & Commission for Women Indicators: 2.1 All Gender Cells in Ministries operational & trained on gender mainstreaming (Yr1) 2.2 Gender strategy formulated for Rodigues & under full implementation 2.3 GBV strategies developed for Rodrigues & under full implementation 2.4 Increase in female MPS & Commissioners 2.5 No. of training packages developed 2.6 No. of exchange visits (in person days) | Targets (Years 1 to 3): 2.1 X people trained on gender mainstreaming (Yr1) All Gender Cells active (Yr2) No. of other Ministries supported by Ministry of Gender Equality on mainstreaming (Yr2; Yr3) 2.2 Gender Strategy & Action Plans for Rodrigues formulated (Yr1) 25 RRA & 25 NSA reps trained on roll out of strategy (Yr2) 2.3 Strategy to combat GBV in Rodrigues developed (Yr1) X trainers trained on strategy (Yr2) X males & X females trained on strategy issues in Yr3 Full implementation (Yr3) 2.4 10 Trainers trained & roll-out workshops (Mauritius & Rodrigues) (Yr1) 2.5 X training materials developed in Yr1 & X developed in Yr2 2.6 X person days of exchange visits per year by Yr2 Targets (EoP): 2.1 Capacity of Ministry of Gender Equality to train staff of other ministries & NSAs on gender mainstreaming established 2.2 Capacity of Commission for Women to train staff of other Commissions & NSAs established 2.3 X existing domestic violence services re-designed & X new GBV services launched in Rodrigues 2.4 % of female MPs & MRAs increased from 18% to x% & x% respectively at next election in 201X? 2.5 All training package needs initially identified met | 2.1 Activity result: Gender policy framework in Mauritius strengthened through a mainstreaming process Clarification of the role of Gender Cells in each ministry (eg. ToR) Training of staff in Gender Cells on gender mainstreaming & gender budgeting (under Pillar 1 activities) Strengthening the capacity of staff of Ministry of Gender (ToT) to support other ministries on gender issues to address priority issues ( & to reduce dependency on external assistance) Roll out of training across Ministries 2.2. Activity result: Gender policy for Rodrigues formulated & implemented Clarification of concept of gender in Rodrigues Development of awareness-raising programme Participatory study & mapping of status of women & men in Rodrigues (UN WOMEN TA / RRA) Drafting of policy & strategy with participation of all stakeholders (public/private/NSA) Elaboration of a Plan of Action Training Needs Analysis of all stakeholders to determine capacity requirements to deliver the strategy Roll out of training 2.3 Activity result: Strategy to combat GBV developed & implemented in Rodrigues Participatory study & assessment of GBV incidences in Rodrigues Exchange visit to Mauritius to share experiences Drafting of strategy with participation of all stakeholders (including participatory workshop) Elaboration of a Plan of Action TNA of all stakeholders (including Commission for Women, Police Family Unit & NSAs) to determine capacity requirements to deliver the strategy ToT Roll out of training Establishment of improved services. 2.4 Activity result: Political empowerment of women strengthened Further training of 10 current trainers Organisation of training workshops in Mauritius & Rodrigues concerning women in politics (with support of UNDP gender-mainstreaming focal point) 2.5 Activity result: Best practice training materials developed to meet the current needs of women in Rodrigues Technical support from UNWOMEN to HRC & MITD to develop specialised training programmes to empower women (possibly through the “women’s leadership academy”) Review & updating of courses currently delivered at women’s centres, including life skills (UNWOMEN / RRA) ToT Raise awareness of gender issues amongst men & women in Rodrigues 2.6 Activity result: Improved co-operation between Ministry of Gender, RRA & other stakeholders achieved Technical support to facilitate process from UNDP (gender focal point) | UNDP support to NIM Other UN Agencies, in particular UNWOMEN, Ministry of Gender Equality RRA (Commission of Women) Collaborating Parties: MITD & HRC | UNDP- Salary of Gender Focal Point (50% over 4 yrs) = $60,000 Workshops & training costs ( training staff of Min of Gender & women in politics) = $30,000 Roll-out of training for implementation of Gender Policy in Rodrigues =$10,000 Other UN- UNWOMEN Salary of Gender Focal Point (50% over 4 yrs) = $60,000 Costs of developing Gender Policy & Action Plan in Rodrigues = $20,000 Costs of developing GBV strategy in Rodrigues & ToT = $20,000 Costs of developing new training materials for women’s training in Rodrigues = $10,000 Ministry of Gender = In kind Travel & meeting costs for improved cooperation with RRA = In kind RRA Costs of rolling out training & GBV strategy awareness raising = In kind Travel & meeting costs for improved cooperation with Ministry of Gender = In kind |
| --- | --- | --- | --- | --- |

| Output 3 New models of service delivery by NSA’s successfully tested (e.g. women’s empowerment, placement and training and community development) Baseline: 3. Limited capacity in public institutions and NSAs to innovate programmatically Indicators: 3.1 Performance of PMU 3.2 Performance of Local Integrated Development Plans 3.3 Performance of NSA Unit 3.4 NSAs applying new models of service delivery 3.5 Active participation of final beneficiaries 3.6 ICT penetration | Targets (Years 1 to 3): 3.1 PMU operational (yr1) Annual Work Plan targets met 3.2 Local Integrated Development Plans formulated & resource mobilisation commenced -pilots 1 & 2 (Yr1); pilot 3 (Yr2) [if funding becomes available] Funding for LIDPs raised Annual targets in LIDPs met (Yr2 onwards) 3.3 NSA Unit fully staffed (including local exec. Counterpart) (Yr1) X volunteers trained in community-centred development - pilots 1 &2 (Yr1); pilot 3 (Yr2) [if funding becomes available] X NSAs trained in M&E (Yr1) Increasing quality of monitoring reports received from NEF beneficiaries Multi-disciplinary facilitation teams established & trained -- pilots 1 & 2 (Yr1); pilot 3 (Yr2) [if funding becomes available] 3.4 At least 2 new models of service delivery or project design developed by Yr2; 3 in Yr 3 - covering 5 key sector areas 100 NSAs equipped with new models of service delivery by 2014 (Yr3) At least 2 key policy issues addressed through advocacy & policy dialogue initiatives & documented each year (over Yrs2 &3) 3.5 Governance structures in pilot areas established (Yr1) All planned community-based planning & management meetings take place & are well-attended At least x% of participating beneficiaries submit service scoring cards according to schedule 3.6 X Volunteers for ICT accompaniment trained by NCB (Yr2) Targets (EoP): 3.1 NSA Unit fully functional & perceived to be valuable by majority of NSAs 3.2 3 pilot LIDPs realising objectives & handed over to local governance structures At least 1 additional LIDP is developed, beyond the 2 or 3 pilot areas 3.3 No. of active registered volunteers in Mauritius & Rodrigues increased by x% 3.4 200 NSAs (in total) equipped with new models of service delivery by EoP By EoP, at least 8 new models of service delivery or project design developed in 5 key sector areas At least 5 strategic issues addressed thru advocacy & policy dialogue initiatives & documented by EoP 3.5 At least x% of a representative panel of final beneficiaries in the pilot areas report a substantial improvement in voice & accountability related indicators 3.6 60,000 citizens trained through the Universal ICT Education Programme by 2016 ICT literacy in pilot areas increased from x% (baseline) to x% by EoP Employment rate (disaggregated by gender & other characteristics) in pilot areas increased from x% (baseline) to x% by EoP | 3.1 Activity result: Programme Management Unit established Recruitment of Project Manager, based within MSIEE in Mauritius Recruitment of Programme Coordinator cum Community Organiser, based within EPMU in Rodrigues 3.2 Activity result: Pilot Projects designed & implemented Identification of pilot areas (Mauritius - 1 area; Rodrigues – 1 area) [with 3rd in Mauritius if funding becomes available] Identification of stakeholders & partners Establishment of multi-disciplinary facilitation teams Assess capacity of public / private / NGO partners to plan & design interventions that address inequality & social exclusion Ongoing on-the-job capacity-building Participatory needs appraisal Establishment of programme governance structures (including community participation) Undertake baseline surveys Development & approval of Local Integrated Development Plans for pilot areas (with OVIs) Design of tools for the capturing of lessons learnt and good practices (Theory of Change approach) - NEF M&E unit Development & implementation of Resource Mobilisation Strategy (incl. Round Table donors’ workshops) Implementation of pilots (1st Mauritius, 2nd. Rodrigues, 3rd Mauritius) On-going M&E (coordinated by NEF M&E & EPMU in RRA) 3.3 Activity result: NSA unit within MSS strengthened to: Reinforcement of NSA Unit through Continued deployment of NSA Unit Project Officer Continued deployment of Asst. PO Appointment / recruitment of local executive counterpart Promote national volunteer scheme (In Mauritius & Rodrigues) – including development of focal point in Rodrigues and a Rodrigues specific scheme Provide capacity building support to NSA’s (under the current institutional training platform), including extension of services to Rodrigues (eg. intensifying support to Commission of Social Security on management of NGOs; establishing a Rodrigues NGO Forum to increase partnerships, participation, better coordination and more structured dialogue with RRA) Promote a culture of M&E amongst NSA’s (in collaboration with DCP & NEF M&E unit) Promote new approaches for community development 3.4 Activity result: New models of service delivery developed Analysis of projects’ / programmes’ performance within Integrated Development Plans Generation of lessons learnt Dissemination of best practices through workshops / seminars / networks Development of models of improved service delivery & project designs Advocacy & policy dialogue around issues highlighted 3.5 Activity result: Citizens empowered to increase their public participation with a view to achieving greater transparency & feedback on public services Pilots Raise awareness on rights issues with the community (especially vulnerable groups) Design feedback systems & channels of communication to allow citizens to inform service delivery improvements (e.g. scoring cards, NCB online feedback systems) Establish a small, stable, representative panel of final beneficiaries in each of the pilot areas to interview & provide feedback on progress, outcomes & impact Beyond pilot areas Identify 2 to 3 key service areas & design systems to facilitate citizen participation in decision making, leading to greater transparency & feedback 3.6 Activity result: Literacy in Information Technology among vulnerable sections of society promoted (especially women to enhance their employability & entrepreneurship) Cooperation with NCB in targeting their existing ICT literacy programmes within pilot projects to meet the needs of women, & other vulnerable groups Strengthen penetration of ICT throughout Rodrigues via Women’s Centres & Community Centres / Volunteers / HRC / CSR /NCB training/Centre of Excellence on ICT Liaison with CSR to meet any hardware gaps | UNDP / UNDP support to NIM Other UN Agencies, possibly UN Habitat MSS (especially NSA Unit & SRM) MSIEE (& NEF, especially M&E Unit) RRA Chief Commissioner’s Office RRA Commission of Social Security, Commission of Community Development Collaborating Parties: DCP (training NSAs on M&E) MACOSS RCSS Various sectoral ministries, government agencies & RRA commissions NCB M&E Unit of NEF Local Authorities NGOs & CBOs Private sector foundations & CSR Volunteers & Animateurs Communauteures | UNDP Inputs – Support to Project Manager (over 4 years) = $120,000 (Contribution to Programme Coordinator, based in Rodrigues (over 3 yrs) = $16,000 Human Resource Support to NSA Unit Salary for Project Officer for 28 mths over 4 yrs = $85,000 (Asst. Project Officer for 4 yrs) = $100,000 Contribution to NSA Unit operational field costs = $20,000 Contribution to field support costs for development & implementation of 2 pilots (including local community-based training) = $50,000 Resource mobilisation workshops for pilots = $ 15,000 Dissemination & advocacy workshops = $30,000 Development of Multi-media IEC = $30,000 Possible support for 3rd pilot = US$ 85,000 (TBC) MSS- Human Resource Support to NSA Unit (Local counterpart) Operational funds for NSA Unit (for 4 yrs) = $132,000 by MSS under regular operations MSIEE - Operational support to PMU = In kind Contribution to field support costs for development & implementation of 3 pilots = $60,000 RRA - Human Resource Support to Project Management (Contribution to Project Coordinator, based in Rodrigues, for 3 yrs) = $65,000 (Follow-up) Operational support to Project Coordinator /Community Organiser = In kind CSR / Donors – Pilot implementation funds |
| --- | --- | --- | --- | --- |

Summary of Budget

| SOURCE | OUTPUT 1 | OUTPUT 2 | OUTPUT 3 | TOTAL (US$) |
| --- | --- | --- | --- | --- |
| UNDP | 205,000 | 100,000 | 551,000 | 856,000 |
| MSIEE | 80,000 In kind (Local M&E Counterpart & Operational Support to M&E Unit) |  | 60,000 In kind (Operational Support to PMU) | 140,000 |
| UNWOMEN |  | 110,000 |  | 110,000 |
| RRA |  | In kind (Follow-up on Gender Strategy & GBV) | 65,000 In kind (Operational Support to PC) | 65,000 |
| Min of Gender Equality |  | In kind |  |  |
| MSS |  |  | 132,000 In kind (Operational costs of NSA Unit & Local Counterpart) | 132,000 |
| NCB |  |  | In kind - training (Minimal cost of Rs 750 per participant) |  |
| CSR / Donors (incl UNHabitat, UNAIDS, UNFPA) |  |  | Implementation (through resource mobilisation following LIDP formulation) | TBC |
| Implementation Support Services |  | 38,010 |
| Miscellaneous |  | 5,000 |
| Audit |  | 4,000 |
| Outcome Evaluation |  | 25,000 |
| GRAND TOTAL |  | 1,375,010 |

# IV Annual Work Plans

Year: 2013

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount (US$) |
| Output 1 Targeting, delivery and monitoring arrangements of MSIEE social programmes operational Baseline: 1. Inadequate tools and capacity to measure and manage programme performance Indicators: 1.1 Increased inclusion of the poor in MSIEE social programmes 1.2 No. of stakeholders trained in Results-based planning & management Improvement in quality of project monitoring frameworks developed by NEF beneficiaries 1.3 NEF’s capacity to evaluate outcomes & impact of social programmes NSAs’ capacity to design & utilise M&E tools at project level & appreciate their value (for ongoing management & informing future actions & policy dialogue) Targets (Year 1): 1.1 Three pilot areas identified using RDI, SRM & other pro-poor targeting mechanisms 1.2 50 people trained in Results-based planning & design in Mauritius & 25 trained in Rodrigues Proportion of projects submitted with adequate monitoring frameworks increased from x% (baseline prior to training) to y% by end Yr1 1.3 M&E Unit at NEF fully equipped & staffed, & range of M&E tools developed Proportion of final project reports prepared & submitted for all interventions supported under NEF considered to be ‘good’, increased from x% (baseline before training) to y% by end Yr1 NEF produces a quality meta-evaluation (based on a sample of interventions) for one of its intervention components Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 1.1 Activity result: Efficient identification of vulnerable groups & disadvantaged areas for inclusion in pro-poor programmes achieved - Use of SRM for initial identification - Use of complementary data collection tools & other data sources (e.g. Statistics Mauritius) | X x x | X x x | X | X | MSIEE (jointly with MSS for 1.1) | MSIEE | Field-based data collection | 10,000 |
|  | 1.2 Activity result: Results-based project & programme planning & management strengthened - Assessment of needs - Identification of resource persons / consultant for training - Training of MSS, NEF, Ministry of Gender, RRA, NSAs |  | X x | X x x | X x | MSIEE | UNDP | Trainers & costs for R-b Pl & M&E | 20,000 |
|  | 1.3 Activity result: - M&E system operational - Deployment of M&E Officer - Appointment of suitable qualified local counterpart (MSIEE/NEF) (RRA-EPMU) - Technical assistance for the development of M&E system - Capacity building of NSAs to implement M&E systems at project level (Training platform -NSA unit -MSS; DCP, MACOSS, NGOTF) - Capacity building of public sector (Ministries, National Institutions, & RRA, thru EPMU), NEF (including case workers in Rodrigues) & private sector (CSR) to implement M&E systems at service delivery & project levels - Review of existing NEF projects - Design of data collection tools & establishment of baseline data (including field surveys) - Development of SMART OVI’s for each NEF programme | X x x x x | X x x | X x x x x x x | X x x x x x x | MSIEE | UNDP | Operational Support to M&E Unit | 3,750 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 6,000 |
|  |  |  |  |  |  |  |  | M&E Officer | 36,250 |
|  |  |  |  |  |  |  | MSIEE | M&E Officer & other HR Support | In kind |
|  |  |  |  |  |  |  |  | Operational Support to M&E Unit | 5,000 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 10,000 |
|  |  |  |  |  |  |  |  | Field Survey Work | 15,000 |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount (US$) |
| Output 2 Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors Baseline: 2.1 Inadequate capacity to mainstream gender issues in Mauritius 2.2 Lack of Rodrigues specific strategy to address gender issues 2.3 Lack of Rodrigues specific strategy to combat GBV 2.4 Low participation of women in politics 2.5 Lack of training materials in Rodrigues that are relevant to the current needs of women 2.6 Little formal cooperation between Ministry of Gender & Commission for Women INDICATORS: 2.1 All gender cells in ministries operational & trained on gender mainstreaming 2.2 Gender strategy formulated for Rodigues & under full implementation 2.3 GBV strategies developed for Rodrigues & under full implementation 2.4 Increase in female MPS & Commissioners 2.5 No. of training packages developed 2.6 No. of exchange visits (in person days) Targets (Year 1): 2.1 All Gender Cells in Ministries operational and trained on gender mainstreaming 2.2 Gender Strategy & Action Plans for Rodrigues formulated (Yr1) 2.3 Strategy to combat GBV in Rodrigues developed 2.4 10 Trainers from trained & roll-out workshops (Mauritius & Rodrigues) 2.5 X training materials developed in Yr1 2.6 At least 2 exchange visits (MGE / Comm of Women) during Yr1 Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 2.1 Activity result: Gender policy framework in Mauritius strengthened through a mainstreaming process - Clarification of the role of Gender Cells in each ministry (eg. ToR) - Training of staff in Gender Cells on gender awareness, M&E, gender mainstreaming, policy formation, gender budgeting (under Pillar 1 activities) - Strengthening the capacity of staff of Ministry of Gender (ToT) for gender mainstreaming | X | X x | X x | X x | Ministry of Gender Equality | UNDP | Salary of Gender Focal Point (50%) | 15,000 |
|  |  |  |  |  |  |  | UN-WOMEN | Salary of Gender Focal Point (50%) | 15,000 |
|  | 2.2. Activity result: Gender policy for Rodrigues formulated & implemented - Participatory study & mapping of status of women & men in Rodrigues (UN WOMEN TA / RRA) - Drafting of policy & strategy with participation of all stakeholders (public/private/NSA) - Elaboration of a Plan of Action - Training Needs Analysis of all stakeholders to determine capacity requirements to deliver the strategy - ToT | X | X x | X x x x | X x x x | RRA – Commission for Women | UN-WOMEN | Costs of development of Gender Policy & Action Plan for Rodrigues | 20,000 |
|  | 2.3 Activity result: Strategy to combat GBV developed & implemented in Rodrigues - Participatory study & assessment of GBV incidences in Rodrigues - Exchange visit to Mauritius to share experiences - Drafting of strategy with participation of all stakeholders (including participatory workshop) - Elaboration of a Plan of Action - TNA of all stakeholders (including Commission for Women, Police Family Unit & NSAs) to determine capacity requirements to deliver the strategy - ToT | X | X x x | X x x x | X x x | RRA – Commission for Women | UN-WOMEN | Costs of developing GBV strategy in Rodrigues | 20,000 |
|  | 2.4 Activity result: Political empowerment of women strengthened - Further training of 10 current trainers |  |  | X x | X | Ministry of Gender Equality RRA – Commission for Women | UNDP | Workshops | 10,000 |
|  | 2.5 Activity result: Best practice training materials developed to meet the current needs of women in Rodrigues - Technical support from UNWOMEN to HRC & MITD to develop specialised training programmes to empower women - Review & updating of courses currently delivered at women’s centres, including life skills (UNWOMEN / RRA) - ToT |  |  | X x | X x x x | RRA – Commission for Women | UN-WOMEN | Development of new materials & ToT | 10,000 |
|  | 2.6 Activity result: Improved co-operation between Ministry of Gender, RRA & other stakeholders achieved - Technical support to facilitate process from UNDP (gender focal point) | X | X x | X | X | Ministry of Gender Equality RRA – Commission for Women | Ministry of GE / RRA | Travel / Meetings | In kind |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 3 New models of service delivery by NSA’s successfully tested (e.g. women’s empowerment, placement and training and community development) Baseline: 3. Limited capacity in public institutions and NSAs to innovate programmatically | 3.1 Activity result: Programme Management Unit established - Recruitment of Project Manager, based within MSIEE in Mauritius - Recruitment of Programme Coordinator, based within EPMU in Rodrigues | X x | X | X x | X | MSIEE UNDP RRA | UNDP | Support to Project Manager (over 4 years) | 30,000 |
|  |  |  |  |  |  |  |  | Contribution to Programme Coordinator, based in Rodrigues (over 3 yrs) | 2,650 |
|  |  |  |  |  |  |  | RRA | Contribution to Programme Coordinator (Rodrigues) over 3 yrs | 10,000 |
|  |  |  |  |  |  |  |  | Operational support to Project Coordinator | In kind |
|  |  |  |  |  |  |  | MSIEE | Operational support to PMU | In kind |
| Indicators: 3.1 Performance of PMU 3.2 Performance of Local Integrated Development Plans 3.3 Performance of NSA Unit 3.4 NSAs applying new models of service delivery 3.5 Active participation of final beneficiaries 3.6 ICT penetration Targets (Year 1): 3.1 PCU operational Annual Work Plan targets met 3.2 Local Integrated Development Plans formulated & resource mobilisation commenced -pilots 1 & 2 Funding for LIDPs raised | 3.2 Activity result: Pilot Projects designed & implemented - Identification of pilot areas (Mauritius + Rod.) - Identification of stakeholders & partners - Establishment of multi-disciplinary facilitation teams (2 pilots) - Assess capacity of public / private / NGO partners to plan & design interventions - Ongoing on-the-job capacity-building - Participatory needs appraisal (pilots 1 & 2) - Establishment of programme governance structures (including community participation) - Undertake baseline surveys (2 pilots) - Development & approval of 2 LIDPs - Design tools for the capturing of lessons learnt and good practices (NEF M&E unit) - Development & implementation of Resource Mobilisation Strategy (incl. Round Table donors’ workshops) – 2 pilot areas | X x x x | X x x x x x x | X x x x | X x x | MSIEE | UNDP | Contribution to field support costs for development & implementation of 2 pilots | 50,000 |
|  |  |  |  |  |  |  |  | Resource mobilisation workshops for pilots 1 & 2 | 10,000 |
|  |  |  |  |  |  |  | MSIEE | Contribution to field support costs for development & implementation of pilots | 20,000 |
| 3.3 NSA Unit fully staffed (including local exec. Counterpart) X volunteers trained in community-centred development - pilots 1 &2 (Yr1) X NSAs trained in M&E (Yr1) Increasing quality of monitoring reports received from NEF beneficiaries Multi-disciplinary facilitation teams established & trained -- pilots 1 & 2 3.5 Governance structures in pilot areas established All planned community-based planning & management meetings take place & are well-attended | 3.3 Activity result: NSA unit within MSS strengthened to: - Reinforcement of NSA Unit through continued deployment of Project Officer & Asst. PO (UNDP) - Appointment / recruitment of local executive counterpart - Promote national volunteer scheme (In Mauritius & Rodrigues) – including development of focal point in Rodrigues & a Rodrigues specific scheme - Provide capacity building support to NSA’s - Promote a culture of M&E amongst NSA’s (in collaboration with DCP & NEF M&E unit) - Promote new approaches for community development | X x x x x x x | X x x x x x x | X x x x x x x | X x x x x x x | MSS | UNDP | Salary for NSA Unit Project Officer for 28 mths over 4 yrs | 21,250 |
|  |  |  |  |  |  |  |  | Salary for NSA Unit Asst. Project Officer for 4 yrs | 25,000 |
|  |  |  |  |  |  |  |  | Contribution to NSA Unit operational field costs | 5,000 |
|  |  |  |  |  |  |  | MSS | Local Counterpart | Inkind |
|  |  |  |  |  |  |  |  | Operational funds for NSA Unit | 66,000 |

| Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 3.5 Activity result: Citizens empowered to increase their public participation with a view to achieving greater transparency & feedback on public services Pilots - Raise awareness on rights issues with the community (especially vulnerable groups) - Establish a small, stable, representative panel of final beneficiaries in each of the pilot areas to interview & provide feedback on progress, outcomes & impact |  | X x | X x | X x | MSIEE M&E Unit | UNDP | Costs largely covered through other support budget lines |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | MSIEE |  |  |
|  | 3.6 Activity result: Literacy in Information Technology among vulnerable sections of society promoted (especially women to enhance their employability & entrepreneurship) - Cooperation with NCB in targeting their existing ICT literacy programmes within pilot projects to meet the needs of women, & other vulnerable groups |  |  | X x | X | MSIEE (with NSA Unit & NCB) | UNDP | Costs of conducting ICT Hardware survey (thru volunteers) | 5,000 |
|  |  |  |  |  |  |  | NCB | Training of Volunteers (Rs 750 /participant ) (CSR) | In kind |
| TOTAL |  |  |  |  |  |  |  |  |  |

Year: 2014

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1 Targeting, delivery and monitoring arrangements of MSIEE social programmes operational Baseline: 1. Inadequate tools and capacity to measure and manage programme performance Indicators: 1.1 Increased inclusion of the poor in MSIEE social programmes 1.2 No. of stakeholders trained in Results-based planning & management Improvement in quality of project monitoring frameworks developed by NEF beneficiaries 1.3 NEF’s capacity to evaluate outcomes & impact of social programmes NSAs’ capacity to design & utilise M&E tools at project level & appreciate their value (for ongoing management & informing future actions & policy dialogue) Targets (Year 2): 1.1 No. of new public & private/CSR/CSO initiatives assisted to submit detailed requests to MSS for targeting support from SRM reaches x (Yr2) 1.2 25 people trained in Results-based planning & design in Mauritius (Yr2) Proportion of projects submitted with adequate monitoring frameworks increased from x% (baseline prior to training) to y% by end Yr2 1.3 Proportion of final project reports prepared & submitted for all interventions supported under NEF considered to be ‘good’, increased from x% (baseline before training) to y% by end Yr2 NEF produces a quality meta-evaluation (based on a sample of interventions) for two of its components (Yr2) All NEF programmes have baseline data & OVIs established by end Yr2 Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 1.1 Activity result: Efficient identification of vulnerable groups & disadvantaged areas for inclusion in pro-poor programmes achieved | X | X | X | X | MSIEE & MSS | MSIEE | Field-based data collection | 10,000 |
|  | 1.2 Activity result: Results-based project & programme planning & management strengthened - Training of MSS, NEF, Ministry of Gender, RRA, NSAs (3rd round, 25 people) | X |  |  |  | MSIEE | UNDP | Trainers & costs | 10,000 |
|  | 1.3 Activity result: - M&E system operational Continued deployment of M&E Officer & suitably qualified local counterpart (MSIEE/NEF) (RRA-EPMU) - Technical assistance for the development of M&E system - Capacity building of NSAs to implement M&E systems at project level (Training platform -NSA unit -MSS; DCP, MACOSS, NGOTF) - Capacity building of public sector (Ministries, National Institutions, & RRA, thru EPMU), NEF (including case workers in Rodrigues) & private sector (CSR) to implement M&E systems at service delivery & project levels - Review of existing NEF projects - Design of data collection tools & establishment of baseline data (including field surveys) | X | X | X | X | MSIEE | UNDP | Operational support to M&E Unit | 3,750 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 5,000 |
|  |  |  |  |  |  |  |  | M&E Officer | 36,250 |
|  |  |  |  |  |  |  | MSIEE | Counterpart M&E Officer & other HR support | In kind |
|  |  |  |  |  |  |  |  | Operational support to M&E Unit | 5,000 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 5,000 |
|  |  |  |  |  |  |  |  | Field Survey Work | 10,000 |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 2 Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors Baseline: 2.1 Inadequate capacity to mainstream and implement gender policy issues in Mauritius 2.2 Lack of Rodrigues specific strategy to address gender issues 2.3 Lack of Rodrigues specific strategy to combat GBV 2.4 Low participation of women in politics 2.5 Lack of training materials in Rodrigues that are relevant to the current needs of women 2.6 Little formal cooperation between Ministry of Gender & Commission for Women Indicators: 2.1 All gender cells in ministries operational & trained on gender mainstreaming 2.2 Gender strategy formulated for Rodigues & under full implementation 2.3 GBV strategies developed for Rodrigues & under full implementation 2.4 Increase in female MPS & Commissioners 2.5 No. of training packages developed 2.6 No. of exchange visits (in person days) | 2.1 Activity result: Gender policy framework in Mauritius strengthened through a mainstreaming process - Strengthening the capacity of staff of Ministry of Gender (ToT) to support other ministries on gender issues to address priority issues ( & to reduce dependency on external assistance) - Roll out of training across Ministries | X | X | X | X | Ministry of Gender Equality | UNDP | Salary of Gender Focal Point (50%) | 15,000 |
|  |  |  |  |  |  |  |  | Workshops & Training | 10,000 |
|  |  |  |  |  |  |  | UN-WOMEN | Salary of Gender Focal Point (50%) | 15,000 |
|  | 2.2. Activity result: Gender policy for Rodrigues formulated & implemented - Roll out of training - Implementation of the strategy | X | X | X | X | RRA- Commission for Women | RRA |  | In kind |
| Targets (Year 2): 2.1 All Gender Cells active No. of other Ministries supported by Ministry of Gender on strategy by Yr2 2008 Gender Strategy & Plan of Action (for Mauritius) evaluated, revised & relaunched 2.2 25 RRA & 25 NSA reps trained on roll out of strategy 2.5 X training materials developed in Yr1 & X developed in Yr2 2.6 X person days of exchange visits per year by Yr2 Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 2.3 Activity result: Strategy to combat GBV developed & implemented in Rodrigues - Roll out of training - Establishment of improved services. | X | X | X | X | RRA- Commission for Women | RRA- Commiss-ion for Women |  | In kind |
|  | 2.4 Activity result: Political empowerment of women strengthened - Organisation of training workshops in Mauritius & Rodrigues concerning women in politics (with support of UNDP gender-mainstreaming focal point) | X | X | X | X | Ministry of Gender Equality & RRA- Commission for Women | UNDP | Workshops | 20,000 |
|  | 2.5 Activity result: Best practice training materials developed to meet the current needs of women in Rodrigues - Raise awareness of gender issues amongst men & women in Rodrigues | X | X | X | X | RRA- Commission for Women | RRA- Commiss-ion for Women | Awareness raising workshops | In kind |
|  | 2.6 Activity result: Improved co-operation between Ministry of Gender, RRA & other stakeholders achieved - Technical support to facilitate process from UNDP (gender focal point) | X | X | X | X | Ministry of Gender Equality & RRA- Commission for Women | Covered from operation-al funds |  |  |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 3 New models of service delivery by NSA’s successfully tested (e.g. women’s empowerment, placement and training and community development) Baseline: 3. Limited capacity in public institutions and NSAs to innovate programmatically | 3.1 Activity result: Programme Coordination Unit established - Continued deployment of TA (Facilitator) / Project Coordinator, based within MSIEE in Mauritius - Continued deployment of TA (Facilitator) / Project Coordinator, based within EPMU in Rodrigues | X | X | X | X | MSIEE UNDP | UNDP | Support to Project Manager (over 4 years) | 30,000 |
|  |  |  |  |  |  |  |  | Contribution to Programme Coordinator, based in Rodrigues (over 3 yrs) | 5,300 |
|  |  |  |  |  |  |  | RRA | Contribution to Project Coordinator (Rod) over 3 yrs | 21,400 |
|  |  |  |  |  |  |  |  | Operational support to DPM |  |
|  |  |  |  |  |  |  | MSIEE | Operational support to PMU | In kind |
| Indicators: 3.1 Performance of PCU 3.2 Performance of Local Integrated Development Plans 3.3 Performance of NSA Unit 3.4 NSAs applying new models of service delivery 3.5 Active participation of final beneficiaries 3.6 ICT penetration Targets (Year 2): 3.1 Annual Work Plan targets met 3.2 Local Integrated Development Plan formulated & resource mobilisation commenced –pilot 3 Funding for LIDPs raised 3.3 X volunteers trained in community-centred development – pilot 3 Increasing quality of monitoring reports received from NEF beneficiaries Multi-disciplinary facilitation teams established & trained – pilot 3 | 3.2 Activity result: Pilot Projects designed & implemented - Ongoing on-the-job capacity-building - Establishment of multi-disciplinary facilitation team for pilot 3 - Undertake baseline surveys(pilot 3) -Undertake participatory needs appraisal (pilot 3) - Establish governance structures (pilot 3) - Development & approval of LIDP for 3rd pilot area (Mauritius rural) - Development & implementation of Resource Mobilisation Strategy ( pilot 3 & follow-up for 1 & 2) - Implementation of pilots (1st Mauritius, 2nd. Rodrigues) - On-going M&E (coordinated by NEF M&E & EPMU in RRA) - Ongoing implementation of knowledge management tools for lessons learnt | X | X | X | X | MSIEE | UNDP | Contribution to field support costs for development & implementation of pilots | 50,000 |
|  |  |  |  |  |  |  |  | Resource mobilisation workshops for pilots | 5,000 |
|  |  |  |  |  |  |  | MSIEE | Contribution to field support costs for development & implementation of 2 pilots | 15,000 |
|  |  |  |  |  |  |  | NEF / CSR / Other donors | Pilot project implementation funds | TBC |
| 3.4 At least 2 new models of service delivery or project design developed by Yr2 3.5 All planned community-based planning & management meetings take place & are well-attended 3.6 X Volunteers for ICT accompaniment trained by NCB (Yr2) Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 3.3 Activity result: NSA unit within MSS strengthened to: - Reinforcement of NSA Unit through continued deployment of Project Officer & Asst. PO (UNDP) - Continued deployment of local executive counterpart - Ongoing promotion of national volunteer scheme (In Mauritius & Rodrigues) – including development of focal point in Rodrigues & a Rodrigues specific scheme - Ongoing capacity building support to NSA’s - Ongoing promotion of a culture of M&E amongst NSA’s (in collaboration with DCP & NEF M&E unit) - Promotion of new approaches for community development | X | X | X | X | MSS | UNDP | Salary for NSA Unit Project Officer for 28 mths over 4 yrs | 21,250 |
|  |  |  |  |  |  |  |  | Salary for NSA Unit Asst. Project Officer for 4 yrs | 25,000 |
|  |  |  |  |  |  |  |  | Contribution to NSA Unit operational field costs | 5,000 |
|  |  |  |  |  |  |  | MSS | Local Counterpart | In kind |
|  |  |  |  |  |  |  |  | Operational funds for NSA Unit | 66,000 |
|  | 3.4 Activity result: New models of service delivery developed - Analysis of projects’ / programmes’ performance within Integrated Development Plans - Development of models of improved service delivery & project designs - Development of multi-media IEC | X | X | X | X | MSIEE M&E Unit | UNDP | Advocacy & dissemination workshops | 15,000 |
|  |  |  |  |  |  |  |  | Development of IEC materials | 10,000 |
|  | 3.5 Activity result: Citizens empowered to increase their public participation with a view to achieving greater transparency & feedback on public services Pilots - Raise awareness on rights issues with the community (especially vulnerable groups) - Ongoing engagement with a small, stable, representative panel of final beneficiaries in each of the pilot areas to interview & provide feedback on progress, outcomes & impact - Design feedback systems & channels of communication to allow citizens to inform service delivery improvements (e.g. scoring cards) Beyond pilot areas -Identify 2 to 3 key service areas & design systems to facilitate citizen participation in decision making, leading to greater transparency & feedback | X | X | X | X | MSIEE | UNDP | Costs largely covered thru other support budget lines Costs of designing & implementing scoring cards | 10,000 |
|  |  |  |  |  |  |  | MSIEE |  |  |
|  | 3.6 Activity result: Literacy in Information Technology among vulnerable sections of society promoted (especially women to enhance their employability & entrepreneurship) - Ongoing cooperation with NCB in targeting their existing ICT literacy programmes within pilot projects to meet the needs of women, & other vulnerable groups - Strengthen penetration of ICT throughout Rodrigues via Women’s Centres & Community Centres / Volunteers / HRC / CSR /NCB training/Centre of Excellence in ICT - Liaison with CSR to meet the necessary hardware gaps | X | X | X | X | MSIEE (with NSA Unit & NCB) | CSR | Provision of IT equipment (if required) | In kind |
|  |  |  |  |  |  |  | NCB | Training of Volunteers | In kind |
| TOTAL |  |  |  |  |  |  |  |  |  |

Year: 2015

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1 Targeting, delivery and monitoring arrangements of MSIEE social programmes operational Baseline: 1. Inadequate tools and capacity to measure and manage programme performance Indicators: 1.1 Increased inclusion of the poor in MSIEE social programmes 1.2 No. of stakeholders trained in Results-based planning & management Improvement in quality of project monitoring frameworks developed by NEF beneficiaries 1.3 NEF’s capacity to evaluate outcomes & impact of social programmes NSAs’ capacity to design & utilise M&E tools at project level & appreciate their value (for ongoing management & informing future actions & policy dialogue) Targets (Year 3): 1.1 No. of new public & private/CSR/CSO initiatives assisted to submit detailed requests to MSS for targeting support from SRM reaches x (Yr3) 1.3 Proportion of final project reports prepared & submitted for all interventions supported under NEF considered to be ‘good’, increased from x% (baseline before training) to y% by end Yr3 NEF produces quality meta-evaluations (based on a sample of interventions) for three of its components (Yr3) Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 1.1 Activity result: Efficient identification of vulnerable groups & disadvantaged areas for inclusion in pro-poor programmes achieved | X | X | X | X | MSIEE & MSS | MSIEE | Field-based data collection | 10,000 |
|  | 1.3 Activity result: - M&E system operational Deployment of M & E Officer & suitably qualified local counterpart (MSIEE/NEF) (RRA-EPMU) - Capacity building of NSAs to implement M&E systems at project level (Training platform -NSA unit -MSS; DCP, MACOSS, NGOTF) - Capacity building of public sector (Ministries, National Institutions, & RRA, thru EPMU), NEF (including case workers in Rodrigues) & private sector (CSR) to implement M&E systems at service delivery & project levels - Review of existing NEF projects - Design of data collection tools & establishment of baseline data (including field surveys) | X | X | X | X | MSIEE | UNDP | Operational support to M&E Unit | 3,750 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 2,000 |
|  |  |  |  |  |  |  |  | M&E Officer | 36,250 |
|  |  |  |  |  |  |  | MSIEE | M&E Officer & other HR support | In kind |
|  |  |  |  |  |  |  |  | Operational support to M&E Unit | 5,000 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 2,500 |
|  |  |  |  |  |  |  |  | Field Survey Work | 10,000 |
|  |  |  |  |  |  |  |  | M&E Officer | 36,250 |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 2 Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors Baseline: 2.1 Inadequate capacity to mainstreaming gender issues in Mauritius 2.2 Lack of Rodrigues specific strategy to address gender issues 2.3 Lack of Rodrigues specific strategy to combat GBV 2.4 Low participation of women in politics 2.5 Lack of training materials in Rodrigues that are relevant to the current needs of women 2.6 Little formal cooperation between Ministry of Gender & Commission for Women Indicators: 2.1 All gender cells in ministries operational and trained on gender mainstreaming 2.2 Gender strategy formulated for Rodigues & under full implementation 2.3 GBV strategies developed for Rodrigues & under full implementation 2.4 Increase in female MPS & Commissioners 2.5 No. of training packages developed 2.6 No. of exchange visits (in person days) | 2.1 Activity result: Gender policy framework in Mauritius strengthened through a mainstreaming process - Roll out of training on gender mainstreaming by Ministry of Gender Equality across other Ministries | X | X | X | X | Ministry of Gender Equality | UNDP | Salary of Gender Focal Point (50%) | 15,000 |
|  |  |  |  |  |  |  | UN-WOMEN | Salary of Gender Focal Point (50%) | 15,000 |
|  |  |  |  |  |  |  | Ministry of Gender Equality | Own funds for continued support to mainstreaming | In kind |
|  | 2.2. Activity result: Gender policy for Rodrigues formulated & implemented - Ongoing implementation of the strategy | X | X | X | X | RRA- Commission for Women | RRA | Own funds | In kind |
| Targets (Year 3): 2.1 No. of other Ministries supported by Ministry of Gender on gender mainstreaming (Yr3) 2.3 X males & X females trained on GBV strategy issues in Yr3 Full implementation (Yr3) Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 2.3 Activity result: Strategy to combat GBV developed & implemented in Rodrigues - Ongoing implementation of improved services to tackle GBV | X | X | X | X | RRA- Commission for Women | RRA- Commiss-ion for Women | Own funds | In kind |
|  | 2.6 Activity result: Improved co-operation between Ministry of Gender, RRA & other stakeholders achieved - Ongoing Technical support to facilitate process from UNDP (gender focal point) | X | X | X | X | Ministry of Gender Equality & RRA- Commission for Women |  | Covered from operation-al funds + MGE /RRA own funds | In kind |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 3 New models of service delivery by NSA’s successfully tested (e.g. women’s empowerment, placement and training and community development) Baseline: 3. Limited capacity in public institutions and NSAs to innovate programmatically Indicators: 3.1 Performance of PMU 3.2 Performance of Local Integrated Development Plans 3.3 Performance of NSA Unit 3.4 NSAs applying new models of service delivery 3.5 Active participation of final beneficiaries 3.6 ICT penetration | 3.1 Activity result: Programme Coordination Unit established - Continued deployment of TA (Facilitator) / Project Coordinator, based within MSIEE in Mauritius - Continued deployment of TA (Facilitator) / Deputy Project Coordinator, based within EPMU in Rodrigues | X | X | X | X | MSIEE UNDP | UNDP | Support to Project Manager (over 4 years) | 30,000 |
|  |  |  |  |  |  |  |  | Contribution to Programme Coordinator, based in Rodrigues (over 3 yrs) | 5,300 |
|  |  |  |  |  |  |  | RRA | Contribution to recruited Project Coordinator (Rod) over 3 yrs | 21,600 |
|  |  |  |  |  |  |  |  | Operational support to Project Coordinator | In kind |
|  |  |  |  |  |  |  | MSIEE | Operational support to PMU | In kind |
| Targets (Year 3): 3.1 Annual Work Plan targets met 3.2 Funding for LIDPs raised Annual targets in LIDPs met 3.3 Increasing quality of monitoring reports received from NEF beneficiaries 3.4 At least 3 new models of service delivery or project design developed Yr 3 100 NSAs equipped with new models of service delivery by 2014 (Yr3) At least 2 key policy issues addressed thru advocacy & policy dialogue initiatives & documented each year (over Yrs2 &3) 3.5 All planned community-based planning & management meetings take place & are well-attended At least x% of participating beneficiaries submit service scoring cards according to schedule | 3.2 Activity result: Pilot Projects designed & implemented - Ongoing on-the-job capacity-building - Ongoing field activities of multi-disciplinary facilitation teams in 2 pilots - Ongoing implementation of LIDPs in 2 pilots - On-going M&E (coordinated by NEF M&E & EPMU in RRA) - Ongoing implementation of knowledge management toolsfor lessons learnt | X | X | X | X | MSIEE | UNDP | Contribution to field support costs for development & implementation of pilots | 25,000 |
|  |  |  |  |  |  |  | MSIEE | Contribution to field support costs for development & implementation of 2 pilots | 12,500 |
|  |  |  |  |  |  |  | NEF / CSR / Other donors | Pilot project implementation funds | TBC |
| Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 3.3 Activity result: NSA unit within MSS strengthened to: - Reinforcement of NSA Unit through continued deployment of Project Officer & Asst. PO (UNDP) - Continued deployment of local executive counterpart - Ongoing promotion of national volunteer scheme (In Mauritius & Rodrigues) – including development of focal point in Rodrigues & a Rodrigues specific scheme - Ongoing capacity building support to NSA’s - Ongoing promotion of a culture of M&E amongst NSA’s (in collaboration with DCP & NEF M&E unit) - Promotion of new approaches for community development | X | X | X | X | MSS | UNDP | Salary for NSA Unit Project Officer for 28 mths over 4 yrs | 21,250 |
|  |  |  |  |  |  |  |  | Salary for NSA Unit Asst. Project Officer for 4 yrs | 25,000 |
|  |  |  |  |  |  |  |  | Contribution to NSA Unit operational field costs | 5,000 |
|  |  |  |  |  |  |  | MSS | Local Counterpart | In kind |
|  |  |  |  |  |  |  |  | Operational funds for NSA Unit | 66,000 |
|  | 3.4 Activity result: New models of service delivery developed - Analysis of projects’ / programmes’ performance within Integrated Development Plans - Development of models of improved service delivery & project designs - Generation of lessons learnt - Dissemination of best practices thru workshops / seminars / networks - Development of models of improved service delivery & project designs - Advocacy & policy dialogue around issues highlighted - Development of multi-media IEC (e.g. short films in pilots, etc) | X | X | X | X | MSIEE M&E Unit | UNDP | Advocacy & dissemination workshops | 15,000 |
|  |  |  |  |  |  |  |  | Development of IEC materials | 15,000 |

|  | 3.5 Activity result: Citizens empowered to increase their public participation with a view to achieving greater transparency & feedback on public services Pilots - Ongoing engagement with a small, stable, representative panel of final beneficiaries in each of the pilot areas to interview & provide feedback on progress, outcomes & impact - Design feedback systems & channels of communication to allow citizens to inform service delivery improvements (e.g. scoring cards) Beyond pilot areas - Ongoing implementation of systems designed to facilitate citizen participation in decision making, leading to greater transparency & feedback in 2 to 3 key service areas | X | X | X | X | MSIEE NEF M&E | UNDP | Costs largely covered thru other support budget lines Costs of designing & implementing scoring cards | 10,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 3.6 Activity result: Literacy in Information Technology among vulnerable sections of society promoted (especially women to enhance their employability & entrepreneurship) - Ongoing cooperation with NCB in targeting their existing ICT literacy programmes within pilot projects to meet the needs of women, & other vulnerable groups - Strengthen penetration of ICT throughout Rodrigues via Women’s Centres & Community Centres / Volunteers / HRC / CSR /NCB training - Liaison with CSR to meet the necessary hardware gaps | X | X | X | X | MSIEE (with NSA Unit & NCB) | CSR | IT equipment (if required) | In kind |
|  |  |  |  |  |  |  | NCB | Training of Volunteers | In kind |
| TOTAL |  |  |  |  |  |  |  |  |  |

Year: 2016

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1 Targeting, delivery and monitoring arrangements of MSIEE social programmes operational Baseline: 1. Inadequate tools and capacity to measure and manage programme performance Indicators: 1.1 Increased inclusion of the poor in MSIEE social programmes 1.2 No. of stakeholders trained in Results-based planning & management Improvement in quality of project monitoring frameworks developed by NEF beneficiaries 1.3 NEF’s capacity to evaluate outcomes & impact of social programmes NSAs’ capacity to design & utilise M&E tools at project level & appreciate their value (for ongoing management & informing future actions & policy dialogue) Targets (Year 4): 1.1 Rate of inclusion of the poor in NEF programmes is increased from x% (pre project start-up) to y% All NEF programmes utilise SRM 1.2 At least x% of projects submitted have adequate monitoring frameworks 1.3 At least x% of final project reports prepared & submitted for all interventions supported under NEF are considered to be ‘good’ NEF produces quality meta-evaluations (based on a sample of interventions) for all of its intervention components M&E lessons learnt are internalised & reflected in the formulation of subsequent programmes Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 1.1 Activity result: Efficient identification of vulnerable groups & disadvantaged areas for inclusion in pro-poor programmes achieved | X | X | X | X | MSIEE & MSS | MSIEE | Field-based data collection | 10,000 |
|  | 1.3 Activity result: - M&E system operational Continued deployment of M&E Officer & suitably qualified local counterpart (MSIEE/NEF) (RRA-EPMU) - Capacity building of NSAs to implement M&E systems at project level (Training platform -NSA unit -MSS; DCP, MACOSS, NGOTF) - Capacity building of public sector (Ministries, National Institutions, & RRA, thru EPMU), NEF (including case workers in Rodrigues) & private sector (CSR) to implement M&E systems at service delivery & project levels - Review of existing NEF projects - Design of data collection tools & establishment of baseline data (including field surveys) | X | X | X | X | MSIEE | UNDP | Operational support to M&E Unit | 3,750 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 2,000 |
|  |  |  |  |  |  |  |  | M&E Officer | 36,250 |
|  |  |  |  |  |  |  | MSIEE | M&E Officer & other HR support | In kind |
|  |  |  |  |  |  |  |  | Operational support to M&E Unit | 5,000 |
|  |  |  |  |  |  |  |  | Workshop costs & info materials | 2,500 |
|  |  |  |  |  |  |  |  | Field Survey Work | 5,000 |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 2 Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors Baseline: 2.1 Inadequate capacity to mainstream gender issues in Mauritius 2.2 Lack of Rodrigues specific strategy to address gender issues 2. Lack of Rodrigues specific strategy to combat GBV 2.4 Low participation of women in politics 2.5 Lack of training materials in Rodrigues that are relevant to the current needs of women 2.6 Little formal cooperation between Ministry of Gender & Commission for Women Indicators: 2.1 Gender strategies reviewed & revised in Mauritius & under full implementation 2.2 Gender strategy formulated for Rodigues & under full implementation 2.3 GBV strategies developed for Rodrigues & under full implementation 2.4 Increase in female MPS & Commissioners 2.5 No. of training packages developed 2.6 No. of exchange visits (in person days) | 2.1 Activity result: Gender policy framework in Mauritius strengthened through a mainstreaming process - Roll out of training on gender issues by Ministry of Gender Equality across other Ministries | X | X | X | X | Ministry of Gender Equality | UNDP | Salary of Gender Focal Point (50%) | 15,000 |
|  |  |  |  |  |  |  | UN-WOMEN | Salary of Gender Focal Point (50%) | 15,000 |
|  |  |  |  |  |  |  | Ministry of Gender Equality | Own funds for continued support to mainstreaming gender | In kind |
|  | 2.2. Activity result: Gender policy for Rodrigues formulated & implemented - Ongoing implementation of the strategy | X | X | X | X | RRA- Commission for Women | RRA | Own funds | In kind |
| Targets (Year 4): 2.1 Capacity of Ministry of Gender to train staff of other ministries on gender mainstreaming & NSAs established 2.2 Capacity of Commission for Women to train staff of other Commissions & NSAs established 2.3 X existing domestic violence services re-designed & X new GBV services launched in Rodrigues 2.4 % of female MPs & MRAs increased from 18% to x% & x% to x% respectively at next election in 201X? 2.5 All training package needs initially identified met Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society |  |  |  |  |  |  |  |  |  |
|  | 2.3 Activity result: Strategy to combat GBV developed & implemented in Rodrigues - Ongoing implementation of improved services to tackle GBV | X | X | X | X | RRA- Commission for Women | RRA- Commission for Women | Own resources | In kind |
|  | 2.6 Activity result: Improved co-operation between Ministry of Gender, RRA & other stakeholders achieved - Ongoing Technical support to facilitate process from UNDP (gender focal point) | X | X | X | X | Ministry of Gender Equality & RRA- Commission for Women |  | Covered from operational funds & own resources | In kind |

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIME-FRAME | RESPONS-IBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 3 New models of service delivery by NSA’s successfully tested (e.g. women’s empowerment, placement and training and community development) Baseline: 3. Limited capacity in public institutions and NSAs to innovate programmatically Indicators: 3.1 Performance of PCU 3.2 Performance of Local Integrated Development Plans 3.3 Performance of NSA Unit 3.4 NSAs applying new models of service delivery 3.5 Active participation of final beneficiaries 3.6 ICT penetration | 3.1 Activity result: Programme Coordination Unit established - Continued deployment of TA (Facilitator) / Project Coordinator, based within MSIEE in Mauritius - Continued deployment of TA (Facilitator) / Deputy Project Coordinator, based within EPMU in Rodrigues | X | X | X | X | MSIEE UNDP | UNDP | Support to Project Manager (over 4 years) | 30,000 |
|  |  |  |  |  |  |  |  | Contribution to Programme Coordinator, based in Rodrigues (over 3 yrs) | 2,650 |
|  |  |  |  |  |  |  | RRA | Contribution to Project Coordinator (Rod) over 3 yrs | 12,000 |
|  |  |  |  |  |  |  |  | Operational support to Project Coordinator | In kind |
|  |  |  |  |  |  |  | MSIEE | Operational support to PMU | In kind |
| Targets (Year 4): 3.1 NSA Unit fully functional & perceived to be valuable by majority of NSAs 3.2 3 pilot LIDPs realising objectives & handed over to local governance structures At least 1 additional LIDP is developed, beyond the 3 pilot areas 3.3 No. of active registered volunteers in Mauritius & Rodrigues increased by x% 3.4 200 NSAs (in total) equipped with new models of service delivery by EoP By EoP, at least 8 new models of service delivery or project design developed in 5 key sector areas At least 5 strategic issues addressed thru advocacy & policy dialogue initiatives & documented by EoP 3.5 At least x% of a representative panel of final beneficiaries in the pilot areas report a substantial improvement in voice & accountability related indicators | 3.2 Activity result: Pilot Projects designed & implemented - Ongoing on-the-job capacity-building - Ongoing field activities of multi-disciplinary facilitation teams in 2 pilots - Ongoing implementation of LIDPs in 2 pilots - On-going M&E (coordinated by NEF M&E & EPMU in RRA) - Ongoing implementation of tools for lessons learnt and good practices - Exit strategy & handover to local authorities & communities - Technical advice to any additional LIDPs emerging beyond the 2 pilots | X | X | X | X | MSIEE | UNDP | Contribution to field support costs for development & implementation of pilots | 25,000 |
|  |  |  |  |  |  |  | MSIEE | Contribution to field support costs for development & implementat-ion of 2 pilots | 12,500 |
|  |  |  |  |  |  |  | NEF / CSR / Other donors | Pilot project implementation funds | TBC |

| 3.6 60,000 citizens trained through the Universal ICT Education Programme by 2016 ICT literacy in pilot areas increased from x% (baseline) to x% by EoP Employment rate (disaggregated by gender & other characteristics) in pilot areas increased from x% (baseline) to x% by EoP Related CP outcome: Capacity of public sector, NSAs and vulnerable groups strengthened to promote a coordinated approach in policy formulation and implementation for a more equitable and inclusive society | 3.3 Activity result: NSA unit within MSS strengthened to: - Reinforcement of NSA Unit through continued deployment of Project Officer & Asst. PO (UNDP) - Continued deployment of local executive counterpart - Ongoing promotion of national volunteer scheme (In Mauritius & Rodrigues) – including development of focal point in Rodrigues & a Rodrigues specific scheme - Ongoing capacity building support to NSA’s - Ongoing promotion of a culture of M&E amongst NSA’s (in collaboration with DCP & NEF M&E unit) - Promotion of new approaches for community development | X | X | X | X | MSS | UNDP | Salary for NSA Unit Project Officer for 28 mths over 4 yrs | 21,250 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Salary for NSA Unit Asst. Project Officer for 4 yrs | 25,000 |
|  |  |  |  |  |  |  |  | Contribution to NSA Unit operational field costs | 5,000 |
|  |  |  |  |  |  |  | MSS | Local Counterpart | In kind |
|  |  |  |  |  |  |  |  | Operational funds for NSA Unit | 66,000 |

|  | 3.4 Activity result: New models of service delivery developed - Analysis of projects’ / programmes’ performance within Integrated Development Plans - Development of 3 more models of improved service delivery & project designs - Generation of lessons learnt - Dissemination of best practices thru workshops / seminars / networks - Development of models of improved service delivery & project designs - Advocacy & policy dialogue around issues highlighted - Development of multi-media IEC | X | X | X | X | MSIEE M&E Unit | UNDP | Advocacy & dissemination workshops | 20,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Development of IEC materials | 25,000 |

|  | 3.5 Activity result: Citizens empowered to increase their public participation with a view to achieving greater transparency & feedback on public Pilots - Ongoing engagement with a small, stable, representative panel of final beneficiaries in each of the pilot areas to interview & provide feedback on progress, outcomes & impact - Ongoing implementation of feedback systems & channels of communication to allow citizens to inform service delivery improvements (e.g. scoring cards) Beyond pilot areas - Ongoing implementation of systems designed to facilitate citizen participation in decision making, leading to greater transparency & feedback in 2 to 3 key service areas | X | X | X | X | MSIEE M&E Unit | UNDP | Costs largely covered thru other support budget lines Costs of designing & implementing scoring cards | 10,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 3.6 Activity result: Literacy in Information Technology among vulnerable sections of society promoted (especially women to enhance their employability & entrepreneurship) - Ongoing cooperation with NCB in targeting their existing ICT literacy programmes within pilot projects to meet the needs of women, & other vulnerable groups - Strengthen penetration of ICT throughout Rodrigues via Women’s Centres & Community Centres / Volunteers / HRC / CSR /NCB training - Liaison with CSR to meet the necessary hardware gaps | X | X | X | X | MSIEE (with NSA Unit & NCB) | CSR | Provision of IT equipment (if required) | In kind |
|  |  |  |  |  |  |  | NCB | Training of Volunteers | In kind |
| TOTAL |  |  |  |  |  |  |  |  |  |

V. Management Arrangements

Overall responsibility for the execution and coordination of this project will rest with the two co-executing agencies – the Ministry of Social Integration and Economic Empowerment (MSIEE) and the Ministry of Social Security. Activities will be implemented through the National Implementation Modality (NIM), including a cost-based management fee and the provision of implementation support from the UNDP’s Country Office. The project will also utilise the expertise of other specialised UN agencies and local and international consultants. The Gender Focal Point will be working part time with MOFED/ MGECDFW.

Project Board

A Project Board (PB) will be instituted, co-chaired by the MSIEE and by the MSS, to oversee the holistic execution of the project, whilst sub-committees will provide guidance on specific components. The Board will meet at least every six months.

UNDP will be represented on the PB. Other members will be drawn from the implementing agencies - NEF, NCB, NSA Unit, MACOSS, NGO Trust Fund, DCP, MGECDFW, RRA and MoFED. The PB will assume responsibility for overall guidance and monitoring of the execution of the programme. (Please refer to ToRs in Annex II).

Implementing Partners

Implementing partners are specified in relation to each output:

Output 1: Targeting, delivery and monitoring arrangements of MSIEE social programmes operational

This component will be co-financed by the UNDP Country Office and the Ministry of Social Integration and Economic Empowerment (MSIEE). UNDP will fully fund an M&E Officer and part finance the operational costs of the M&E Unit established within NEF, along with the hiring of consultants and related workshop costs for training in results-based project and programme planning and management, and M&E (for state actors).

The project will be managed through both the National Implementation Modality (NIM) and the Country Office support to NIM. An MoU / Agreement between UNDP and MSIEE will be established in order to set out working relations. Disbursement of funds will be effected through requests for direct payment (RDP) to the UNDP Country Office. The Country Office support to NIM will be partly adopted for the recruitment of human resources for consultancy assignments, as well as for other services. MSIEE / NEF will provide in-kind support such as office space, support staff, equipment and office recurrent expenditures. It will also ensure the deployment of a local counterpart M&E officer to the unit, and contribute funds to cover field operation costs, including survey work. The RRA will collaborate closely through its Economic Planning and Monitoring Unit (EPMU) on all M&E activities at the level of NEF programmes. (Refer also to output 3 management arrangements for Rodrigues).

Other collaborators will include the World Bank, which will provide Technical Assistance for the development of M&E systems within NEF. The NSA Unit will also liaise closely through its focus on M&E at project level with NGOs under output 3, in coordination with the EU funded DCP initiative on NSA capacity building.

Output 2: Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors

This component will be co-financed by the UNDP Country Office and UN WOMEN, with the main implementing partners being the Ministry of Gender Equality and the Commission for Women in Rodrigues. The UN agencies will share the costs of employing a Gender Focal Point. In addition, UNDP will fund workshops and training, especially on gender mainstreaming. For its part, UN WOMEN will focus on the development of a gender strategy and a strategy to combat GBV in Rodrigues, and to prepare materials and training specific to the island.  This component will be managed through both the National Implementation Modality (NIM) and the Country Office support to NIM. An MoU / Agreement between UNDP, UNWOMEN, Ministry of Gender and the RRA’s Commission for Women will be established in order to set out working relations. Disbursement of funds will be effected through requests for direct payment (RDP) to the UNDP Country Office. The Country Office support to NIM will be partly adopted for human resources for consultancy assignments, as well as for other services. The Ministry of Gender Equality and Commission for Women will provide in-kind support such as office space and transport. They will also ensure the full participation of technical staff in all activities.

Other collaborators will include the EU and AfDB, both of whom plan to undertake work on gender issues during the lifespan of this project.

Output 3: New models of service delivery by NSA’s successfully tested

This component will be co-financed by the UNDP Country Office, MSS, MSIEE / NEF and RRA. UNDP will provide full funding for a Project Officer and an Assistant Project Officer to the NSA Unit, and make a small contribution to its operational field costs. It will also provide part funding to facilitate field operations associated with the participatory formulation of Local Integrated Development Plans. In addition, UNDP will fund resource mobilisation efforts to implement the plans, the design of Knowledge Management tools through the M&E Unit, dissemination and advocacy workshops, the development of IEC materials, and the design and implementation of community feedback systems. UNDP will also fund the Project Manager (to be housed within MSIEE) and co-fund the Programme Co-ordinator cum Community Organiser based in Rodrigues, along with the RRA. UN Habitat may support activities related to social houses in the pilot areas.

MSS will provide operational funds for the NSA Unit, along with a local counterpart to the UNDP funded officers, support staff, office space and equipment. MSIEE will contribute towards the field support costs associated with the pilot projects, and will meet the operational costs of the overall Programme Management Unit (PMU). NEF will also channel funds through its programmes and guide CSR funding in order to contribute towards the implementation of interventions within the pilot areas. In addition, MSIEE will provide office space and equipment. Similarly, in Rodrigues, the EPMU of the Chief Commissioner’s Office will provide office space, equipment and general operational support to the Programme Coordinator.

The project will be managed through both the National Implementation Modality (NIM) and the Country Office support to NIM. An MoU / Agreement between UNDP, MSS, MSIEE / NEF and the Chief Commissioner’s Officer of the RRA will be drawn up in order to set out working relations. Disbursement of funds will be effected through requests for direct payment (RDP) to the UNDP Country Office. The Country Office support to NIM will be partly adopted for the recruitment of human resources for consultancy assignments, as well as other services.

As this component requires a multi-stakeholder, multi-sectoral approach, a large number of collaborators will be involved. These will include various line ministries and Commissions of the RRA and other Government agencies. Local Authorities covering the pilot areas will also be partners. Specifically, NCB will support the implementation of the ICT components; MACOSS and RCSS (with the support of the NSA Unit) will mobilise NSA participation in the project; DCP will provide training on M&E to NGOs; and private sector foundations and CSR companies will fund activities identified in the Local Integrated Development Plans. Furthermore, NGOs, CBOs, volunteers and animateurs communautaires will be supported through the NSA unit to contribute to community-centred development initiatives and survey work. Civil Society Organisations will also be encouraged and assisted to mobilise resources from other donors, for example by applying to relevant national and international Calls for Proposals.

Management and Technical Advisory Sub-Committees

Three Management and Technical Advisory Sub-Committees (MTASCs) with representatives of the teams for the respective components will be created to serve as a feedback mechanism for the project. These sub-committees will represent a suitable platform to monitor progress of the project’s outputs, and to identify any constraints and advise on appropriate solutions.

*Ministry of Finance and Economic Development, representative of RRA, Ministry of Gender Equality, Ministry of ICT, Government Agencies, Decentralized Cooperation Programme (DCP) (EU), Civil Society Organisations (CSOs) and Private Sector Associations and Institutions, Mauritius Council of Social Service (MACOSS), other Specialised UN Agencies and other Development Partners.

Prior obligations and prerequisites

Before starting project implementation, the Ministry of Social Integration and Economic Empowerment and the MSS should appoint the Co-Chairs of the Project Board (normally the PS of each Ministry). Furthermore, MSIEE / NEF and the Ministry of Social Security should each respectively appoint a National Project Director (NPD) (also normally the PSs of each ministry) and a Project Focal Point for their respective components of the Social Inclusion and Empowerment project. RRA and NEF will also designate a Focal Point within each of their management structures. (For the terms of reference of the focal points, please refer to annex II).

Financial Accountability

All financial disbursements to the implementing partners will be based on approved Annual Work Plans (AWP) agreed between the different implementing partners and UNDP. Cash transfers for activities detailed in the AWP will be made by UNDP using any one of the following modalities:

- Cash transferred directly to the Implementing Partner:

  - Prior to the start of activities (direct cash transfer), or

  - After activities have been completed (reimbursement);

- Direct payment to vendors or third parties for obligations incurred by implementing partners on the basis of requests signed by a designated official of an implementing agent;

- Direct payments to vendors or third parties for obligations incurred by UN agencies in support of activities agreed with Implementing Partners.

Disbursement

UNDP Country Office will authorise payments for project activities after formal approval of the UNDP Senior Project Manager or UNDP Resident Representative.

Accounting records

The UNDP Country Office will keep records of all expenditures involved in the implementation of the project. It will enter in a chronological order all the expenditures in accounting records and documents and it will keep all invoices and other evidence of expenditures in a file.

Audit Arrangements

The project will be audited as per National Implementation Modality requirements in accordance with the established procedures set out in the UNDP Programming and Finance manuals. The auditing will be carried out by a private auditor.

VI. Monitoring and Evaluation Framework

UNDP will undertake joint evaluations of the project with MSIEE and MSS, as per the Evaluation Plan, alongside national implementation modality audits. M&E systems will be built around the project’s Results and Resources Framework (which incorporates outputs and indicators for the project), in accordance with UNDP guidelines. The capacity of government staff to design interventions and to monitor their implementation will be integrated into programme management.

In order to facilitate the effective implementation and monitoring of this project, MSIEE / NEF, MSS and the various implementing partners will be required to formulate their detailed Annual Work Plans (AWP), following discussions with UNDP. Quarterly reports will be prepared for activities carried out over each three-month period for submission to UNDP, before their onward transmission to the Project Board.

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle-

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted (see annex I), a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project’s implementation.

- Based on the above information recorded in Atlas, a Project Progress Report (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- A project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project.

On an annual basis -

- Annual Review Report. An Annual Review Report shall be prepared by the Project Manager and shared with the Project Board. As a minimum requirement, the Annual Review Report shall consist of the Atlas standard format for the Quarterly Progress Report (QPR) covering the whole year with updated information for each element of the QPR, as well as a summary of results achieved against pre-defined annual targets at the output level.

- Annual Project Review. Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon thereafter, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to the outcome.

Quality Management for Project Activity Results

| OUTPUT 1: Targeting, delivery and monitoring arrangements of MSIEE social programmes operational |
| --- |
| Activity Result 1.1 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Efficient identification of vulnerable groups | Start Date: 2013 End Date:2016 |
| Purpose | What is the purpose of the activity? To improve the efficiency of identifying and targeting vulnerable groups and disadvantaged areas to ensure their inclusion in pro-poor social programmes, and to reduce leakage of resources to the non-poor |
| Description | Planned actions to produce the activity result. Use of SRM for initial identification Use of complementary data collection tools & other data sources (e.g. Statistics Mauritius) |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Increased inclusion of the poor in MSIEE social programmes | Data generated by SRM Baseline and EoP field-based surveys Qualitative assessments Panel of informants | 2013 2016 |

| Activity Result 1.2 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Training in Results-based planning and management | Start Date: 2013 End Date:2014 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To increase the capacity of state and non-state actors to plan, design and manage interventions, and to measure their outcomes and impacts, leading to better performing social programmes |
| Description | Planned actions to produce the activity result. Assessment of needs Identification of resource persons / consultant for training Training of MSS, NEF, Ministry of Gender, RRA, NSAs |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| No. of stakeholders trained in Results-based planning & management | Programme records of training events organised – attendance sheets & participant evaluation forms | Throughout 2013 to 2014 |
| Improvement in quality of project monitoring frameworks developed by NEF beneficiaries | Assessment of proposals submitted to NEF for funding – evaluation comments & scores | Throughout 2013 to 2014 |

| Activity Result 1.3 (Atlas Activity ID) | Short title to be used for Atlas Activity ID M&E System | Start Date: 2013 End Date: 2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To establish an M&E Unit within NEF to develop improved systems for the monitoring of social programmes, and to build the capacity of both state and non-state actors to implement M&E processes at service delivery & project implementation levels |
| Description | Planned actions to produce the activity result. Deployment of M&E Officer Appointment of suitable qualified local counterpart (MSIEE/NEF) (RRA-EPMU) Capacity building of NSAs to implement M&E systems at project level (Training platform -NSA unit -MSS; DCP, MACOSS, NGOTF) Capacity building of public sector (Ministries, National Institutions, & RRA, thru EPMU), NEF (including case workers in Rodrigues) & private sector (CSR) to implement M&E systems at service delivery & project levels Review of existing NEF projects Design of data collection tools & establishment of baseline data (including field surveys) Development of SMART OVI’s for each NEF programme |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| NEF’s capacity to evaluate outcomes & impact of social programmes | Growing quality of meta-evaluations conducted by NEF or its components Evidence of SMART OVIs & baselines being available for NEF interventions | 2013 (baseline) plus yearly internal reviews until 2016 (Final Project Review) |
| NSAs’ capacity to design & utilise M&E tools at project level & appreciate their value (for ongoing management & informing future actions & policy dialogue) | Rising quality of final reports submitted by NEF beneficiaries (based on scoring established at baseline) Evidence of internalisation of M&E lessons learnt & their incorporation in the formulation of subsequent projects – assessed & documented via learning events & discussions | 2013 (baseline) plus yearly internal reviews until 2016 (Final Project Review) |

| OUTPUT 2: Empowerment and specific needs of excluded groups (especially women) adequately addressed through services delivered by public agencies and Non-State Actors |
| --- |
| Activity Result 2.1 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Gender mainstreaming | Start Date: 2012 End Date: 2016 |
| Purpose | What is the purpose of the activity? To strengthen the gender policy framework in Mauritius by providing support to the gender cells established within each Ministry, and enhancing the capacity of staff within the Ministry of Gender Equality to provide ongoing assistance. Emphasis will be placed on gender mainstreaming. |
| Description | Planned actions to produce the activity result. Clarification of the role of Gender Cells in each ministry (eg. ToR) Training of staff in Gender Cells on gender awareness, M&E, gender mainstreaming, policy formation, gender budgeting (under Pillar 1 activities) Strengthening the capacity of staff of Ministry of Gender (ToT) to support other ministries on gender mainstreaming ( & to reduce dependency on external assistance) Roll out of training across Ministries |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Gender mainstreaming widely understood and practiced in Mauritius | Records showing that all Gender Cells in Ministries have been trained on their roles – training reports; attendance; participant evaluations | 2013 |
|  | All Gender Cells active & following action plans formulated during training – progress reports | 2014 |
|  | No. of other Ministries supported by Ministry of Gender Equality on gender mainstreaming – training records; attendance; participant evaluations | 2014 2015 |

| Activity Result 2.2 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Gender policy for Rodrigues | Start Date: 2013 End Date:2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To assess the current status of women & men in Rodrigues & support the formulation of a Gender policy that meets the specificities of the island. The RRA and other local stakeholders will also be trained to ensure that they have the capacity to implement the policy. |
| Description | Planned actions to produce the activity result. Participatory study & mapping of status of women & men in Rodrigues (UN WOMEN TA / RRA) Drafting of policy & strategy with participation of all stakeholders (public/private/NSA) Elaboration of a Plan of Action Training Needs Analysis of all stakeholders to determine capacity requirements to deliver the strategy Roll out of training |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Gender strategy formulated for Rodigues & under full implementation Awareness of gender policy | Gender Strategy & Action Plans for Rodrigues formulated & approved by RRA – RRA minutes; press coverage; attendance at fora & workshops to raise awareness; changing perceptions | 2013 |
|  | No. of RRA & NSA reps trained on roll out of strategy – training records; participant evaluations; no. of roll-out training sessions | 2014 |
|  | No. of RRA staff & NSAs trained by Commission for Women on the gender policy – training records; participant evaluations | 2016 |

| Activity Result 2.3 (Atlas Activity ID) | Short title to be used for Atlas Activity ID GBV in Rodrigues | Start Date: 2013 End Date:2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To strengthen & improve upon current measures to combat Gender-based Violence in Rodrigues, including the development of a strategy to meet the specificities of the island & building the capacity of stakeholders, leading to improved service delivers. |
| Description | Planned actions to produce the activity result. Participatory study & assessment of GBV incidences in Rodrigues Exchange visit to Mauritius to share experiences Drafting of strategy with participation of all stakeholders (including participatory workshop) Elaboration of a Plan of Action TNA of all stakeholders (including Commission for Women, Police Family Unit & NSAs) to determine capacity requirements to deliver the strategy ToT Roll out of training Establishment of improved services |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| GBV strategies developed for Rodrigues & under full implementation | Approval of Strategy to combat GBV in Rodrigues - RRA minutes No. of trainers trained on strategy – training reports; participant evaluations No. of males & females trained on strategy issues - training reports; participant evaluations No. of existing domestic violence services re-designed & new GBV services launched in Rodrigues | 2013 2014 2015 2016 |

| Activity Result 2.4 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Political empowerment of women | Start Date: 2013 End Date:2014 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To further strengthen the political empowerment of women. This activity will encourage women in Mauritius & Rodrigues to become more active the local & national political spheres |
| Description | Planned actions to produce the activity result. Further training of 10 current trainers Organisation of training workshops in Mauritius & Rodrigues concerning women in politics (with support of UNDP gender-mainstreaming focal point) |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| No. & quality of training workshops | 10 Trainers trained & roll-out workshops (Mauritius & Rodrigues) – training reports; participant evaluations; action plans emerging from training; follow-up | 2013 & 2014 |
| Increase in female MPS & Commissioners | Election results | TBC |

| Activity Result 2.5 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Training materials for Women in Rodrigues | Start Date: 2013 End Date:2014 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To develop contemporary training materials that meet the current needs of women in Rodrigues, and to train trainers on their use to assist the empowerment of women on the island |
| Description | Planned actions to produce the activity result. Technical support from Gender Focal Point to HRC & MITD to develop specialised training programmes to empower women Review & updating of courses currently delivered at women’s centres, including life skills (UNWOMEN / RRA) ToT Raise awareness of gender issues amongst men & women in Rodrigues |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| No. & quality of training packages developed | Feedback on training materials - participant evaluations; training records; no. of requests to participate Evidence of use made of training by women – follow-up | 2013 2014 |

| Activity Result 2.6 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Improve cooperation between RRA & Ministry of Gender Equality | Start Date: 2013 End Date:2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To develop closer working relationships between the Ministry of Gender and Equality & the RRA’s Commisson for Women, in order to improve co-operation & exchange experiences |
| Description | Planned actions to produce the activity result. Technical support to facilitate process from UNDP (gender focal point) |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| No. of exchange visits (in person days) No. of joint activities | Records & minutes of exchange visits Reports on follow-up actions agrees | 2013 - 2016 |

| OUTPUT 3: New models of service delivery by NSA’s successfully tested (e.g. women’s empowerment, placement and training and community development) |
| --- |
| Activity Result 3.1 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Establish Programme Management Unit | Start Date: 2013 End Date: 2016 |
| Purpose | What is the purpose of the activity? To establish a Programme Management Unit by recruiting a Project Manager (in Mauritius) & Programme Coordinator (in Rodriues) |
| Description | Planned actions to produce the activity result. Recruitment of Project Manager, based within MSIEE in Mauritius Recruitment of Programme Coordinator, based within EPMU in Rodrigues |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Performance of PCU Annual Work Plan targets met | Progress Reports Internal staff appraisals Internal reviews of Annual Work Plans | 2013 - 2016 |

| Activity Result 3.2 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Pilot projects | Start Date: 2013 End Date: 2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To identify 2 pilot areas and train multi-disciplinary / multi-agency facilitation teams to support the formulation of participatory Local Integrated Development Plans. The process & the plans that emerge will test new ways of delivering services to the poor, & will generate lessons that will inform wider policy issues. A third pilot may be added, should sufficient funds become available. |
| Description | Planned actions to produce the activity result. Identification of pilot areas (1 in Mauritius & 1 in Rodrigues) Identification of stakeholders & partners Establishment of multi-disciplinary facilitation teams Assess capacity of public / private / NGO partners to plan & design interventions that address inequality & social exclusion Ongoing on-the-job capacity-building Participatory needs appraisal Establishment of programme governance structures (including community participation) Undertake baseline surveys Development & approval of Local Integrated Development Plans for 3 pilot areas (with OVIs) Design of knowledge management tools (Theory of Change approach) - NEF M&E unit Development & implementation of Resource Mobilisation Strategy (incl. Round Table donors’ workshops) Implementation of pilots (1st Mauritius, 2nd. Rodrigues) On-going M&E (coordinated by NEF M&E & EPMU in RRA) |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Performance of Local Integrated Development Plans | Funding required for LIDPs raised & annual targets met – annual participatory reviews Pilot LIDPs realise their objectives – M&E system | 2014 to 2016 |

| Activity Result 3.3 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Support to NSA Unit | Start Date: 2013 End Date: 2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To reinforce the NSA Unit within MSS through the deployment of staff & operational support in order to promote the national volunteer scheme & enhance the capacity of NSAs to provide better services & projects to the poor. |
| Description | Planned actions to produce the activity result. Reinforcement of NSA Unit through Continued deployment of Project Officer Continued deployment of Asst. PO Appointment / recruitment of local executive counterpart Promote national volunteer scheme (in Mauritius & Rodrigues) – including development of focal point in Rodrigues and a Rodrigues specific scheme Provide capacity building support to NSA’s (under the current institutional training platform), including extension of services to Rodrigues (eg. intensifying support to Commission of Social Security on management of NGOs; establishing a Rodrigues NGO Forum to increase partnerships, participation, better coordination and more structured dialogue with RRA) Promote a culture of M&E amongst NSA’s (in collaboration with DCP & NEF M&E unit) Promote new approaches for community development |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Performance of NSA Unit No. of volunteers trained in community-centred development Increase in no. of active registered volunteers in Mauritius & Rodrigues No. of NSAs trained in M&E Increasing quality of monitoring reports received from NEF beneficiaries | Quarterly & Annual Progress Reports of NSA Unit Opinions of users on value of services provided – feedback surveys at EoP Training reports – attendance; participant evaluations National Register of Volunteers Training reports – attendance; participant evaluations Review of reports received M&E Unit meta-evaluations of NEF funded projects | 2013 to 2016 |

| Activity Result 3.4 (Atlas Activity ID) | Short title to be used for Atlas Activity ID New models of service delivery | Start Date: 2014 End Date:2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To develop new models of service delivery to better serve the poor and excluded, & to generate lessons learnt to feed into policy dialogue |
| Description | Planned actions to produce the activity result. Analysis of projects’ / programmes’ performance within Integrated Development Plans Generation of lessons learnt Dissemination of best practices through workshops / seminars / networks Development of models of improved service delivery & project designs Advocacy & policy dialogue around issues highlighted Development of multi-media IEC materials |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| No. of NSAs applying new models of service delivery No. of new models of service delivery or project design developed according to targets – No. of key policy issues addressed thru advocacy & policy dialogue initiatives & documented each year | Annual progress reports, surveys undertaken thru NSA patform, EoP review Workshop /seminar reports; review of IEC materials developed Workshop / seminar reports & network proceedings Papers prepared for Cabinet | 2014 - 2016 |

| Activity Result 3.5 (Atlas Activity ID) | Short title to be used for Atlas Activity ID Citizen participation in public services | Start Date: 2013 End Date:2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To raise awareness amongst vulnerable sections of the community of their rights to quality services & to facilitate their feedback on & active participation in the design of their delivery |
| Description | Planned actions to produce the activity result. Pilots Raise awareness on rights issues with the community (especially vulnerable groups) Design feedback systems & channels of communication to allow citizens to inform service delivery improvements (e.g. scoring cards) Establish a small, stable, representative panel of final beneficiaries in each of the pilot areas to interview & provide feedback on progress, outcomes & impact Beyond pilot areas Identify 2 to 3 key service areas & design systems to facilitate citizen participation in decision making, leading to greater transparency & feedback |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Active participation of final beneficiaries in service delivery All planned community-based planning & management meetings within the pilot areas take place & are well-attended Reported improvement in voice & accountability related indicators | No. of participating beneficiaries submitting service scoring cards according to schedule – analysis of cards Minutes of meetings; attendance registers Representative panel of beneficiaries – annual review | 2013 - 2016 |

| Activity Result 3.6 (Atlas Activity ID) | Short title to be used for Atlas Activity ID IT literacy amongst vulnerable sections of society | Start Date: 2013 End Date: 2016 |
| --- | --- | --- |
| Purpose | What is the purpose of the activity? To promote literacy in Information Technology among vulnerable sections of society, in particular women, in both Mauritius & Rodrigues through existing community infrastructure & services. Ultimately, interventions will enhance the employability & entrepreneurship skills of the targeted groups |
| Description | Planned actions to produce the activity result. Cooperation with NCB in targeting their existing ICT literacy programmes within pilot projects to meet the needs of women & other vulnerable groups Strengthen penetration of ICT throughout Rodrigues via Women’s Centres & Community Centres / Volunteers / HRC / CSR /NCB training Liaison with CSR to meet any funding gaps |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Increase in ICT penetration No. of volunteers for ICT accompaniment trained by NCB 60,000 citizens trained through the Universal ICT Education Programme by 2016 Increase in ICT literacy in pilot areas Increase employment rate (disaggregated by gender & other characteristics) in pilot areas | National surveys / statistics Baseline surveys conducted by volunteers / EoP surveys Training records & participant evaluations NCB figures Baseline survey & EoP survey National statistics Beneficiary panel interviews in pilot areas | 2013 - 2016 |

VII. Legal Context

This project document shall be the instrument referred to as such in Article 1 of the SBAA between the Government of Mauritius and UNDP, signed on 29th August 1974. Consistent with Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the executing agency and its personnel and property, and of UNDP’s property in the executing agency’s custody, rests with the executing agency.

The executing agency shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the executing agency’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The executing agency agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

VIII. Annexes

A) Risk Analysis

B) Terms of Reference

i.	Project  Manager

ii. 	Programme Coordinator (Rodrigues)

iii. 	M&E Officer

iv. 	NSA Unit Project Officer

v. 	NSA Unit Assistant Project Officer

vi.	Gender Focal Point

vii.	Project Board

viii.	National Project Directors (MSIEE and MSS)

ANNEX 1 – RISK ANALYSIS

OFFLINE RISK LOG

(see Deliverable Description for the Risk Log regarding its purpose and use)

| Project Title: Social Inclusion and Empowerment | Award ID: | Date: |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Co-financing difficulties. The project requires the support of several UN Agencies for management & facilitation purposes, & significant resources from NEF & private sector (CSR) for implementation of planned activities | August 2012 | Financial | If insufficient co-financing, the project cannot be properly / fully implemented I = 4 P = 3 | Strong resource mobilisation strategy from start of project. Strong communication strategy to ensure that potential donors fully understand the objectives of the project. Clear commitment from NEF. Consider reducing the amount of activities covered or reducing the number of pilot projects | UNDP / MISEE |  |  | No Change |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Funding. Difficulties in reallocating resources already earmarked within the PBB plan of MSIEE & MSS. Difficulties in fitting the project into the current objectives and activities within the PBB framework | Aug 2012 | Financial | If no allocation is made the project cannot be implemented I=5 P=3 | Early discussions with MoFED re additional resources or internal reallocations within planned ceilings | MOFED | UNDP | UNDP | No change |
| 3 | Budget allocation / management. Failure of MoFED to sanction payment of stipends (or lump sum payments as reimbursement of expenditures) to national volunteers | Aug 2012 | Financial | If reimbursement of expenditure are not paid to volunteers, the roll-out of the National Volunteer scheme & participation of volunteers in community development will be constrained I = 3 P = 4 | Further discussions with MoFED | MSS / NSA Unit | UNDP | UNDP | No change |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4 | Budget allocation / management. Failure to appoint local executive counterparts to NSA Unit & NEF M&E Unit | Aug 2012 | Financial / Organisat-ional | Absence of local executive counterparts will impede skills transfer & threaten the sustainability of processes commenced under the project I = 3 P = 3 | Further discussions with MoFED MSS & MSIEE consider redeploying existing staff | MSS / NSA Unit MSIEE / NEF |  |  | No change |
| 5 | Implementation arrangements are complex, with multiple stakeholders & funding sources, & multiple sectors. Innovative approach | Aug 2012 | Organisat-ional / Operation-al | Difficulties in co-ordinating inputs from multiple partners I = 3 P = 3 | Sound Project Management & co-ordination structures. Regular & effective Project Board Meetings. Dedicated Programme Manager & Programme Coordinator (Rodrigues) | UNDP / MSIEE / PMU |  |  | No change |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6 | Organisational Culture. The public, private & civil society sectors work to different rules & procedures & have different value systems. | Aug 2012 | Organisat-ional | Partnerships between the various sectors are constrained I = 3 P = 2 | Develop experimental, new ways of working across traditional boundaries. Highlight he flexibility in approach required in MoUs & Partnership Agreements | UNDP / MSIEE / PMU & all implem-enting partners |  |  | No change |
| 7 | Government & other stakeholders are not fully committed to exploring new ways of delivering pro-poor interventions | Aug 2012 | Political | Stakeholders are overly cautious about trying new ways of working together & redefining relationships. The status quo prevails & new approaches are resisted. I = 4 P = 3 | Involve all stakeholders from the conception stage. Ensure representation of all stakeholders in Project Board & Management Structures | UNDP / MSIEE / PMU |  |  | No change |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | Partnerships fail to deliver. Project relies mainly on UNDP resources. Stakeholders prefer to ‘go it alone’ | Aug 2012 | Strategic | Incomplete intervention with limited impact I = 4 P = 3 | Participatory approach & strong communications & networking strategy throughout | UNDP / MSIEE / PMU & all implem-enting partners |  |  | No change |
| 9 | Competition. Agencies continue to act in isolation & interventions are implemented as ‘silos’ | Aug 2012 | Strategic | Holistic approach is not developed. Piecemeal approach continues, with lack of synergy I = 4 P = 3 | Signing of MoUs & Partnership Agreements. Involving all stakeholders in the participatory planning exercises within the pilot areas. Demonstrating the benefits of a more holistic approach where they are used & have worked thru the M&E & Knowledge Management systems | UNDP / MSIEE / PMU & all implem-enting partners |  |  | No change |
| 10 | Social / cultural. Most needy are not interested in participating & contributing. Culture of passive subject of assistance | Aug 2012 | Environ-mental | Project interventions do not address the needs of the ultra poor. Limited reach. I = 4 P = 3 | Participatory approach throughout. Capacity & confidence building activities. Ensuring representation of the final beneficiaries in the governance structures of the project at field management level | UNDP / MSIEE / PMU, all partners & final benefic-iaries |  |  | No change |

Annex II. Terms of Reference

# Social Inclusion and Empowerment  Project

## Terms of Reference

- Project  Manager

Background

The ‘Social Inclusion and Empowerment’ project is designed to support the Government of Mauritius and Non-State Actors in exploring more effective ways of addressing poverty and the exclusion of vulnerable groups from the socio-economic benefits that the majority of the population has enjoyed over the past few decades. It will facilitate capacity development processes to enhance the effectiveness of public and private sector institutions, NGOs and CSOs in working together under interventions intended to directly combat poverty and exclusion. In so doing, efforts will contribute towards the empowerment of citizens, improved public participation and transparency in the delivery of services (MDG1); an increased share of women working in the mainstream economy and the political empowerment of women (MDG3); and the promotion of IT literacy amongst vulnerable sections of society.

The project takes a holistic, multi-sectoral, multi-agency, integrated approach. Emphasis is placed on learning from evidence-based best practices, the principles of which will then be replicated, scaled-up and used to inform policy level dialogue on issues relating to the delivery of projects and services intended to address poverty and exclusion.

The overall Social Inclusion and Empowerment project will be provided with a Project Manager (based in Mauritius within the offices of MSIEE), funded under UNDP resources.

Duration: 		48 months

Duty Station: 		Port Louis with frequent travel to Rodrigues

Remuneration: 	US $ 2,500/month

Reporting to: 	Permanent Secretary, MSIEE & to UNDP Senior Programme Officer

Overall Responsibilities

The Project Manager has overall responsibility for the management and implementation of the projects’ activities throughout Mauritius and Rodrigues. His/her prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

Specific Responsibilities

- Accountability for the overall programme to the Project Board in implementing its decisions;

- Liaise  with  the Project Directors / Focal Points to ensure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Ensure  overall project coordination and administration;

- Manage the realisation of project outputs through activities;

- Provide direct guidance on, and oversee the facilitation of, participatory Local Integrated Development Plans in the pilot areas;

- Facilitate and supervise activities in both Mauritius and Rodrigues, and provide guidance to the Programme Coordinator (Rodrigues);

- Liaise with the NSA Unit in ensuring that members of the Multi-disciplinary Facilitation Teams in the pilot areas are adequately trained to perform their roles

- Accompany the community facilitators in implementing  project activities;

- Liaise with Ministries / Government Departments, national institutions, NGOs, CSOs, district council/village councils, community leaders and private stakeholders, to ensure their  active participation in  project activities;

- Play a lead role in organising resource mobilisation efforts in order to secure funding for Local Integrated Development Plans in the pilot areas;

- Liaise with the M&E Unit in developing tools to generate lessons learnt and identify best practices;

- Liaise with the M&E Unit in the production of IEC materials;

- Organise learning platforms & policy dialogue activities;

- Take the lead on communication initiatives, and create opportunities for media coverage of project events;

- Fulfil any other duties as decided by the Project Board in the implementation of the project activities

Qualifications and experience

- A masters degree in social science, project management, international development, or a related discipline

- Previous experience as a senior programme officer

- Sound management capabilities, and capacity of synthesis to produce good quality documents for official purposes and for media dissemination;

- Former experience in civil society processes and community development programmes

- Experience in poverty alleviation with NGOs or State programmes

- Excellent facilitation skills and demonstrable experience in the use of participatory planning techniques

- Good ITC skills

- Good command of English is essential, French desirable. Good communication skills in Creole would be advantageous.

Personal Skills

- Very good communication and inter-personal skills

- Committed and result-oriented

- Respectful of, and interested in, different cultures

- Positive approach and attention to details

# Social Inclusion and Empowerment  Project

## Terms of Reference

(2) Programme Coordinator cum Community Organiser for Rodrigues

Background

The ‘Social Inclusion and Empowerment’ project is designed to support the Government of Mauritius and Non-State Actors in exploring more effective ways of addressing poverty and the exclusion of vulnerable groups from the socio-economic benefits that the majority of the population has enjoyed over the past few decades. It will facilitate capacity development processes to enhance the effectiveness of public and private sector institutions, NGOs and CSOs in working together under interventions intended to directly combat poverty and exclusion. In so doing, efforts will contribute towards the empowerment of citizens, improved public participation and transparency in the delivery of services (MDG1); an increased share of women working in the mainstream economy and the political empowerment of women (MDG3); and the promotion of IT literacy amongst vulnerable sections of society.

The project takes a holistic, multi-sectoral, multi-agency, integrated approach. Emphasis is placed on learning from evidence-based best practices, the principles of which will then be replicated, scaled-up and used to inform policy level dialogue on issues relating to the delivery of projects and services intended to address poverty and exclusion.

The overall Social Inclusion and Empowerment project will be provided with a Programme Coordinator cum Community Organiser (based in Rodrigues within the Economic Planning and Monitoring Unit of the Chief Commissioner’s Office), jointly funded by UNDP and RRA.

Duration: 		36 months over 3 years

Duty Station: 		Rodrigues, with travel to Mauritius as and when necessary

Remuneration: 	 $ 1,500 / month

Reporting: 		To the Head of EPMU, Rodrigues, and through the Project Manager in 						Mauritius to UNDP’s Senior Programme Officer

Overall responsibilities

The Programme Coordinator cum Community Organiser has the authority to assist the Project Manager in the overall project coordination in Rodrigues. He/She will be based in Rodrigues and will be responsible for day-to-day management and implementation of the projects’ activities. His/her prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

Specific responsibilities:

- Assist the Project Manager in the overall project coordination;

- Manage the realisation of project outputs through activities;

- Accompany the community facilitators in implementing project activities;

- Liaise with the RRA, national institutions, NGOs, CSOs, village committees, community leaders and private stakeholders, based in Rodrigues, to ensure their  active participation in project activities;

- Ensure coordination at field level with other UN system programmes;

- Accompany and support volunteers in their involvement in the pilot areas and receive feedback from them on field work in progress for relevant corrective measures;

- In liaison with the Project Manager in Mauritius, assure the overall direction and integrity of the project;

- Identify and obtain any support and advice required for the management, planning and control of the project;

- Take responsibility for project administration in Rodrigues;

- Liaise with local stakeholders;

- Facilitate and supervise activities in Rodrigues, especially concerning the participatory formulation and implementation of the Local Integrated Development Plan in the island’s pilot area;

- Fulfil any other duties as decided by the Project Manager in the implementation of the project.

Qualifications and Experiences

- At least a Bachelors degree in sociology, social science, public administration or similar field;

- At least five years of professional experience in coordination, project formulation and implementation with public administrations  and civil society organisations;

- Experience in volunteerism and NGO work, preferably also in poverty alleviation activities and in community mobilisation;

- Strong facilitation and participatory planning skills;

- Sound management capabilities, and capacity of synthesis to produce good quality documents for official purposes and for media dissemination;

- Good IT skills (word processing, presentation, spread sheets, internet, email)

- Fluency in English, French and good communication skills in the Creole language.

Personal Skills

- Very good communication and inter-personal skills

- Committed and result- oriented

- Respectful of other’s cultures

- Positive approach and attention to details.

# Social Inclusion and Empowerment Project

## Terms of Reference

(3) Monitoring and Evaluation Officer to the MSIEE/NEF

Background

The ‘Social Inclusion and Empowerment’ project is designed to support the Government of Mauritius and Non-State Actors in exploring more effective ways of addressing poverty and the exclusion of vulnerable groups from the socio-economic benefits that the majority of the population has enjoyed over the past few decades. It will facilitate capacity development processes to enhance the effectiveness of public and private sector institutions, NGOs and CSOs in working together under interventions intended to directly combat poverty and exclusion. The project takes a holistic, multi-sectoral, multi-agency, integrated approach. Emphasis is placed on learning from evidence-based best practices, the principles of which will then be replicated, scaled-up and used to inform policy level dialogue on issues relating to the delivery of projects and services intended to address poverty and exclusion.

In January 2010, the National Empowerment Foundation (NEF), which presently falls under the purview of the Ministry of Social Integration and Economic Empowerment,  was set up to implement projects with a view to contribute to the eradication of absolute poverty in Mauritius and empower vulnerable families to bring them into the mainstream of society. In order to achieve better coordination and ensure synergy in its actions, NEF requested technical assistance from the UNDP Country Office in Mauritius, and in response a joint scoping mission was undertaken by UNDP and the World Bank to identify a number of needs and challenges. Consequently, since April 2012, UNDP has supported the deployment of an M&E Expert to reinforce monitoring, review and evaluation processes within the Foundation. The new Social Inclusion and Empowerment project will continue this support, tailored to the current needs of NEF / MSIEE and other stakeholders, through the provision of an M&E Officer, funded by UNDP.

Duration:		48 months over a period of four years

Duty Station: 		MSIEE/NEF, Port Louis, with travel to Rodrigues

Remuneration: 	US $ 3,000/month

Reporting: 		To the National Project Director of MSIEE and the UNDP Senior 							Programme Officer

Overall responsibilities

The Monitoring and Evaluation Officer will provide Technical Assistance to the NEF in developing and institutionalising M&E systems for its programmes, and providing an intensive M&E function for activities undertaken in the pilot projects initiated under the project. Furthermore, the M&E Officer will coordinate monitoring and evaluation processes under the UNDP’s Country Programme, and support the EPMU in Rodrigues in monitoring project activities on the island.

Specific Responsibilities

- Operationalise the Monitoring and Evaluation Unit at NEF, and strengthen its capacity through the training of staff and the development of systems reflecting international best practices.

- Facilitate the formulation of an M&E Operational Manual in order to standardize M&E practices, based on results frameworks, including indicator development, establishing baselines and targets across all  NEF programmes and projects.

- Coordinate the quality and practice of M&E support supervision and its participatory approaches throughout NEF supported interventions.

- Provide technical advice to programme staff, government officials and other counterparts on the planning and management of integrated monitoring and evaluation systems, including EPMU in Rodrigues.

- Provide support to the implementation, monitoring and evaluation of the Pillars’ Outcomes towards the achievement of relevant goals and priorities.

- Follow-up on recommendations and key issues arising from monitoring processes.

- Increase learning among stakeholders, providing a vehicle through which NEF M&E and managerial staff can exchange views and thereby deepen their understanding of monitoring and evaluation practices.

- Develop a culture of information use amongst NEF staff to more fully understand monitoring and evaluation concepts, practices and their use in their respective fields.

- Provide an intensive M&E function for the pilot project areas implemented under the project, including technical assistance to, and capacity building of, members of the Multi-disciplinary Facilitation teams.

- Develop tools to solicit feedback from final beneficiaries within the pilot areas.

- Liaise closely with Common Training Strategy committee members in promoting M&E skills amongst NSAs.

- Develop tools to identify good practices and produce IEC materials to disseminate lessons learnt.

- Strengthen advocacy for the use of M&E data to fine-tune programming and inform the policy environment.

- Advise and provide support to the evaluation processes of the UNDP.

- Provide technical oversight to the consolidation of M&E reports for the UNDP as a conduit to achieve the outcomes of the Results and Resources Framework (RRF) of the overall Country Programme 2013 to 2016.

Qualifications & Experiences

- University degree (Masters or higher level) in one of the social sciences, such as Sociology, Project Management, Economics, or equivalent disciplines.

- Minimum 5 years of relevant national, regional and/or international experience in monitoring and evaluation related to regional development or international development fields.

- Previous experience with Enterprise Resources Programmes (ERP) systems desirable.

- Relevant and specific experiences related to project management, risks and general M&E functions.

- Excellent knowledge of M&E tools, procedures and international standards for monitoring of projects and programmes within the context of developmental support programmes.

- Significant previous background in the institutional environment of development cooperation (NGO’s, UN system, multilateral cooperation, etc.), with preference given to candidates with a wide experience in UN/ UNDP operations.

- Language requirements: The candidate should be perfectly bilingual, with the ability to write and speak in English and French.

Personal Skills

- Excellent communication and inter-personal skills;

- Committed and results oriented;

- Respectful of, and interested in, other’s cultures;

- Positive approach and attention to detail.

# Social Inclusion and Empowerment Project

## Terms of Reference

(4) Project Officer, NSA Unit

Background

The ‘Social Inclusion and Empowerment’ project is designed to support the Government of Mauritius and Non-State Actors in exploring more effective ways of addressing poverty and the exclusion of vulnerable groups from the socio-economic benefits that the majority of the population has enjoyed over the past few decades. It will facilitate capacity development processes to enhance the effectiveness of public and private sector institutions, NGOs and CSOs in working together under interventions intended to directly combat poverty and exclusion. The project takes a holistic, multi-sectoral, multi-agency, integrated approach. Emphasis is placed on learning from evidence-based best practices, the principles of which will then be replicated, scaled-up and used to inform policy level dialogue on issues relating to the delivery of projects and services intended to address poverty and exclusion.

Under a previous programme, entitled Support to Inclusive Development, a Non State Actors Unit was established within MSS. This entity was charged with the task of supporting sustainable human development at national level through the promotion of volunteerism, including the mobilization of volunteers. It serves the causes of peace and development through enhancing opportunities for participation by all peoples. It is universal, inclusive and embraces volunteer action in all its diversity. The Unit is also responsible for supporting the capacity development of NSAs in the country, especially through the Common Training Strategy committee. The new Social Inclusion and Empowerment project will continue this support, tailored to the current needs of NSAs, through the ongoing provision of an international Project Officer, and local Assistant Project Officer, both of whom will be funded by UNDP.

Project Officer

Duration: 		28 months over a period of 4 years

Duty Station: 		Port Louis with frequent travel to Rodrigues

Remuneration: 	US $ 3,000/month (on basis of 7 months per annum over 4 years)

Reporting: 		To Permanent Secretary, MSS, and to UNDP Senior Programme 				Officer

Overall Responsibilities

The NSA Project Officer will provide technical support to the MSS through the NSA Unit, particularly in relation to developing the national volunteer scheme and promoting the capacity of NSAs, in collaboration with other member organisations of the Common Training Strategy committee. The Project Officer will also facilitate the full participation of volunteers and NSAs within the pilot projects. In addition, s/he will assist in the process of integrating the unit with the NGO Trust Fund over the coming years.

Specific Responsibilities

- Find placement for volunteers in NGO projects or in state programmes

- Receive and screen requests of individuals to volunteer

- Receive and screen requests of organisations on the island of Mauritius to host volunteers and set up selection meetings

- Keep the volunteering database up to date

- Guarantee finalisation of TORs and contracts

- Organise the selection of volunteers

- Prepare, review and update as required training curricula

- Organize training, also taking care of logistical arrangements with the help of the support unit

- Organise psychological support for volunteers with professionals and / or volunteer psychologists

- Receive volunteers who have difficulties and provide them with bureaucratic, administrative and basic psychological support

- Receive, read, analyse and archive volunteers’ and hosting organisations’ reports

- Provide the Programme Coordinator with information for communication with media

- Elaborate monthly reports

- Highlight in staff meeting situations best practices and lessons learned

- Produce communication materials for citizens and for organisations

- Organise sessions in schools for presenting volunteerism, also through the help of volunteer lecturers

- Coordinate the annual volunteer award on the island

- Organise regular monitoring visits in situ, and coordinate volunteers for M&E activities

- Organise visits to field projects for the Project Manager and for members of the steering committee, as needed

- Capitalise on opportunities for resource mobilisation for the fund for volunteerism

- Liaise closely with stakeholders in Rodrigues, and assist in developing volunteer schemes sensitive to the specificities of the island.

Specific Responsibilities relating to Pilot Projects:

- Provide technical support and advice to the Project Manager

- Accompany and support volunteers in their involvement in the pilot areas and receive feedback from them on field work in progress for relevant corrective measures

- Assist the Project Manager and Programme Coordinator (Rodrigues) in organising and coordinating training for facilitators involved in the pilots

- Liaise with other members of the Common Training Strategy committee to ensure that NSAs are encouraged and supported to play a central role in the project.

Qualifications and Experience

- A degree in social science, project management, international development, or a related discipline

- Previous experience as a senior project officer

- Former experience as a volunteer, preferably as a tutor of volunteers

- Experience in poverty alleviation with NGOs or State programmes will be a bonus

- Good ICT skills

- Good command of English essential, French desirable.

Personal Skills

- Excellent  communication and inter-personal skills

- Committed and result-oriented

- Respectful and interested in others’ cultures

- Positive approach and attention to detail

# Social Inclusion and Empowerment Project

## Terms of Reference

(5)  Assistant Project Officer (Non-State Actor Unit)

Background

The ‘Social Inclusion and Empowerment’ project is designed to support the Government of Mauritius and Non-State Actors in exploring more effective ways of addressing poverty and the exclusion of vulnerable groups from the socio-economic benefits that the majority of the population has enjoyed over the past few decades. It will facilitate capacity development processes to enhance the effectiveness of public and private sector institutions, NGOs and CSOs in working together under interventions intended to directly combat poverty and exclusion. The project takes a holistic, multi-sectoral, multi-agency, integrated approach. Emphasis is placed on learning from evidence-based best practices, the principles of which will then be replicated, scaled-up and used to inform policy level dialogue on issues relating to the delivery of projects and services intended to address poverty and exclusion.

Under a previous programme, entitled Support to Inclusive Development, a Non State Actors Unit was established within MSS. This entity was charged with the task of supporting sustainable human development at national level through the promotion of volunteerism, including the mobilization of volunteers. It serves the causes of peace and development through enhancing opportunities for participation by all peoples. It is universal, inclusive and embraces volunteer action in all its diversity. The Unit is also responsible for supporting the capacity development of NSAs in the country, especially through the Common Training Strategy committee. The new Social Inclusion and Empowerment project will continue this support, tailored to the current needs of NSAs, through the ongoing provision of an international Project Officer, and local Assistant Project Officer, both of whom will be funded by UNDP.

Assistant Project Officer

Duration:		 48 months over a period of 4 years

Duty Station: 		Port Louis with regular missions to Rodrigues

Remuneration: 	$2,000 per month

Reporting: 		NSA Project officer, Permanent Secretary, MSS, and UNDP Senior 			Programme Officer

Overall Responsibilities

The Assistant Project Officer will assist the Project Officer in providing technical support to the MSS through the NSA Unit, particularly in relation to developing the national volunteer scheme and promoting the capacity of NSAs, in collaboration with other member organisations of the Common Training Strategy committee. The Assistant Project Officer will also facilitate the full participation of volunteers and NSAs within the pilot projects. In addition, s/he will assist in the process of integrating the unit with the NGO Trust Fund over the coming years.

Specific Resonsibilities

- Find placements for volunteers in NGO projects or in state programmes

- Receive and screen requests of individuals to volunteer

- Receive and screen requests of institutions and organisations on the island of Mauritius to host volunteers and set up selection meetings

- Keep the volunteering database up to date

- Guarantee finalisation of TORs and contracts

- Organise selection of volunteers

- Prepare training curricula and assist the Project Manager in reviewing and up-dating curricula

- Organize training, also taking care of logistical arrangements with the help of the support unit

- Organise psychological support for volunteers with professionals and / or volunteer psychologists

- Receive volunteers who have difficulties and provide them with bureaucratic, administrative and basic psychological support

- Receive, read, analyse and archive volunteers and hosting organisations’ reports

- Provide the Project Officer with information for communication with media

- Elaborate monthly reports

- Highlight in staff meeting situations  best practices and lessons learned

- In collaboration with the NSA Unit Project Officer and the overall Project Manager, produce  communication materials for citizens and for organisations

- Organise sessions in schools for presenting volunteerism, also through the help of volunteer lecturers

- Coordinate the annual volunteer award on the island

- Organise regular monitoring visits in situ, and coordinate volunteers involved in M&E activities

- Organise visits to field projects for the Project Officer and for members of the steering committee, as needed

- Pass on to the project officer possible opportunities for resource mobilisation for the fund for volunteerism

- Assist the project Officer in facilitating the full participation of NSAs and volunteers in the formulation, management and implementation of the pilot projects

- Assist stakeholders in Rodrigues to develop volunteer schemes sensitive to the specificities of the island.

Qualifications and Experience

- Degree in social science, project management, international development or a related discipline

- Previous experience as an assistant project officer

- Former experience as a volunteer is desirable

- Experience in poverty alleviation with NGOs or State programme is a plus

- Good ICT skills

- Good command of English and French essential, Creole desirable.

Personal Skills

- Excellent  communication and interpersonal skills

- Committed and result-oriented

- Respectful and interested in others’ cultures

- Positive approach and attention to detail.

# Social Inclusion and Empowerment Project

## Terms of Reference

(6) Gender Focal Point (Mauritius)

Background

The UN Common Framework of Assistance (CFA) is being developed for Mauritius. This will focus on a series of key areas, among which is UN technical support to the design, development and implementation of Gender activities for the CFAs of Mauritius. This will take onboard the Delivering as One approach, and result in the creation of a Gender Focal Point for the UNDP Country Programmes in Mauritius, in joint collaborative programming with UN Women.

The FP will operate under the general supervision and guidance of the United Nations Resident Coordinator (RC) in Mauritius and the UN Women Regional Director and operate under the direct supervision of the UNDP Senior Project Manager as the primary supervisor and the UN Women and/or UN Coordination Analyst.

The FP will perform specific duties assigned by the UNCT members cost-sharing the post, notably the United Nations Development Programme (UNDP) and the United Nations Entity for Gender Equality and the Empowerment of Women (UN Women). The services of the FP will also be provided to other agencies within the UNCT. UN Women is a non-resident agency, based in South Africa. The RC Office is hosted by the UNDP country office in Mauritius.

UNDP and UN Women have developed global programmes on Gender that meet the priority of the respective Governments of Mauritius and Seychelles, and they intend to implement these in Mauritius and Seychelles. The programmes will enhance the activities that both agencies have carried out in the countries and will contribute to the achievement of the partner agencies’ objectives.

Immediately upon the start of the contract, the FP will prepare a detailed work plan, indicating a specific list of activities and deliverables for the period of employment. This will be submitted at the end of the first fortnight to the UNDP, UN Women and RCO for validation.

Duration: 		4 Years

Duty Station: 		Office of the UN Resident Coordinator and UNDP Programme, Port-			Louis

Remuneration: 	US $ 1,334/month

Reporting: 		To the UNDP Senior Programme Officer (50% - 75%) and UN 				Coordination Analyst (less than 50%).

Duties and Responsibilities

- Identify opportunities and formulate proposals for new projects in the field of Gender Mainstreaming in Mauritius and Seychelles, as part of the UNDP Country Programmes, UN Women programmes and of the UN CFAs for both countries, with a focus on engendering programmes / projects, as well as policies, and strategies for various sectors for the Government of Mauritius and the Government of Seychelles;

- Design and develop new UN activities in the field of Gender, based on the proposals validated, wherein gender is mainstreamed throughout all outcomes of the UN CFAs for Mauritius and Seychelles;

- Oversee the subsequent good implementation of the joint UN Gender activities

- Ensure regular communication to the UNCT of information on Gender issues relevant to DaO work in Mauritius and Seychelles;

- Assist the non-resident agencies cost-sharing the post in the implementation and follow up of their regular activities in Mauritius and Seychelles, as well as in their DaO formulation activities with RCO and the UNCT;

- Undertake thorough analysis and research of the political, social and economic situation in Mauritius and Seychelles;

- Map out UNCT activities in Mauritius and Seychelles that are related to Gender, including  the relevant technical resources available within the UNCT;

- Design and develop joint UN activities in the field of Gender, based on the proposals validated;

- Finalise proposals following validation by the UNCT, in close consultation with the Governments of Mauritius and Seychelles, as well as with the private sectors and civil society organisations of both countries;

- Establish strategic partnerships with key non-UN stakeholders;

- Initiate resource mobilisation activities with donor organisations for the implementation of the joint activities;

- Oversee the subsequent effective implementation of the UNDP/UN Women programmes/projects and other joint UN Gender activities;

- Ensure the correct operational structure is set up by UN and non-UN stakeholders

- Monitor the effectiveness and efficiency of the UN Gender activities in Mauritius;

- Report back to the UNDP/UN Women and to the UNCT on the implementation of the   joint UN Gender activities.

- Ensure regular communication to the UNCT of information on Gender issues relevant to DaO work in Mauritius;

- Collect and communicate on a regular basis to UNDP/UN Women and to the UNCT, relevant information and documentation regarding Gender issues (emerging opportunities and challenges, lessons learnt and success stories, best practices, etc.)

- Assist the non-resident agencies cost-sharing the post in the implementation and follow up of their regular activities in Mauritius as well as in their DaO formulation activities with RCO and the UNCT, and act as the general focal point in Mauritius;

- Represent, on a non-formal and judicial basis, the partner NRAs in strategic and technical meetings with the governments and other UNCT members;

- Represent, on a non-formal and judicial basis, the partner NRAs in DaO activities  with the RCO, the governments and other UNCT members. ;

Qualifications & Experience

- Education: Master’s Degree in Social Sciences, with a special emphasis on gender  studies or any other relevant field;

- Experience: A minimum of five years of working experience, with at least three in project management in Gender Mainstreaming areas.

- Language Requirements: Fluency in spoken and written English and French.

Personal Skills

- Excellent analytical and communication skills, both oral and written, with the ability to write clearly and concisely on technical, socio-economic and financial issues related to the mandate of the UN Country Team for Mauritius and Seychelles in the field of Gender.

- Excellent knowledge of the public sector, private sector and civil society of Mauritius.  Good knowledge of the public sector, private sector and civil society of Seychelles preferable. Demonstrated ability to efficiently and effectively manage complex issues with partners of the public sector, private sector and civil society.

- Excellent organisational, problem-solving, team work and coordination skills and strong ability to manage demanding and complex programmes.

- Ability to establish effective working relations with people of different national and cultural backgrounds.

- Sound knowledge of the internet as well as good mastery of general office software.

- Ability to work under pressure and to meet deadlines.

- Good knowledge of the mandates of the UNDP and UN Women is preferable. Ability to adhere to the values of the United Nations.

# Social Inclusion and EMPOWERMENT PROJECT

## Terms of Reference

## (7) Project Board

Overall responsibilities:

The Project Board is the group responsible for making by consensus management decisions for a project when guidance is required by the Project Manager, including recommendation for UNDP/Implementing Partner approval of project plans and revisions. In order to ensure UNDP’s ultimate accountability, the Project Board’s decisions should be made in accordance to standards that ensure best value for money, fairness, integrity, transparency and effective international competition. All Project Board decisions shall be executive ones in order to empower immediate action from the Project Manager. In case a consensus cannot be reached, the final decision shall rest with the UNDP. Project reviews by this group are made at designated decision points during the running of the project, or as necessary when raised by the Project Manager.

Based on the approved annual work plan (AWP), the Project Board may review and approve project quarterly plans when required and authorise any major deviation from these agreed quarterly plans. The PB also signs off on the completion of each quarterly plan and authorises the start of the next quarterly plan. It ensures that the required resources are committed and arbitrates on any conflicts within the project, or negotiates solutions to any problems between the project and external bodies.

Composition and organisation:

The composition of the group will be as follows:

- The Permanent Secretaries of the Executing Agencies (MSIEE and MSS) who will be co-chairing/leading meetings of the Project Board.

- Two Project Directors - individuals representing the implementing agencies (MSIEE / NEF and MSS) and their respective Focal Points.

- The UNDP Senior Programme Manager and alternate individuals representing the interests of the parties concerned which provide funding and/or technical expertise to the project.

- Individuals representing the interests of those who will benefit from the project. Their primary function within the Board is to ensure the realisation of project results from the perspective of the project’s final beneficiaries.

- The national counterpart of the Programme Manager and the local counterpart of the Programme Coordinator cum Community organiser (Rodrigues).

Potential members of the Project Board will be reviewed and recommended for approval during the PAC meeting.

Specific responsibilities:

Initiating a project

- Agree on the responsibilities of the Project Manager and the Programme Coordinator cum Community organiser for Rodrigues;

- Delegate any Project Assurance function as appropriate;

- Review the Progress Report for the Initiation Stage;

- Review and appraise detailed Project Plans and AWPs, including Atlas reports covering activity definition, quality criteria, issue log, updated risk log and the monitoring and communication plan.

Running a project

- Provide strategic guidance and direction to the project, ensuring it remains within any specified parameters;

- Address project issues as raised by the Project Manager and Focal Points;

- Provide guidance and agree on possible countermeasures/management actions to address specific risks;

- Agree on Project Focal Points’ tolerances in the Annual Work Plan and quarterly plans when required;

- Conduct regular meetings to review the Project Quarterly Progress Report and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans.

- Review Combined Delivery Reports (CDR) prior to certification by the Implementing Partner;

- Appraise the Project Annual Review Report, make recommendations for the next AWP.

- Provide ad-hoc direction and advice for exceptional situations;

- Assess and decide upon project amendments through revisions.

Closing a project

- Assure that all planned project deliverables have been produced satisfactorily and provide rationale for deliverables not attained;

- Review and approve the Final Project Review Report, including lessons-learned;

- Make recommendations for follow-on actions.

# Social Inclusion and EMPOWERMENT PROJECT

## Terms of Reference

### (8) National Project Directors

Background

Two National Project Directors will be appointed, one from the Ministry of Social Integration and Economic Empowerment / NEF and the other from the Ministry of Social Security. They will ultimately be responsible for their respective project components at the level of the MSIEE / NEF and MSS. The National Project Directors’ role is to ensure that the project is focused throughout its life cycle on achieving its objectives and delivering outputs that will contribute to higher level outcomes. The National Project Directors have to ensure that the project gives value for money, ensuring a cost-conscious approach to the project, balancing the demands of beneficiary and supplier. (It should be noted that the post of Project Director is not remunerated.)

Specific Responsibilities

- Ensure that there is a coherent project organisational structure and logical set of plans

- Set tolerances in the AWP and other plans as required for the Programme Manager /  Programme Coordinator cum Community Organiser in Rodrigues and Focal Points

- Monitor and control the progress of the project at the strategic level

- Ensure that risks are being tracked and mitigated as effectively as possible

- Brief relevant stakeholders about project progress

- Sign the requests for direct payments.

The National Project Directors are responsible for overall assurance of their respective project components. If the project warrants, the National Project Directors may delegate some responsibility for the project assurance functions.

# Footnotes

The NEF is a non-profit, Government-owned company, initially set up in July 2008 as the Empowerment Programme. It is mandated to implement projects aimed at eradicating absolute poverty by 2020, alleviating poverty, and empowering vulnerable families to bring them into the mainstream of society. It also hosts the Corporate Social Responsibility Committee, which channels private sector funding to poverty focussed interventions implemented through NGOs. Since 2010, NEF has been under the aegis of the newly created Ministry of Social Integration and Economic Empowerment.

Rapid Assessment of the National Empowerment Foundation (NEF) Programmes (December 2010), Sifiso Chikandi and Esther Hanoomanjee

SRM implementation started in April 2012 for 3 social programmes to date. It will be extended to other schemes with a view to rationalize and restructure the social protection system.  In the near future it will be a pre-requisite for the targeting of beneficiaries under all NEF interventions, and the EU intends to employ it as part of the trigger mechanisms for releasing tranches of General Budget Support. The Social Inclusion and Empowerment Project will utilise the SRM within the three pilots, and will encourage NGOs to use its services, through MSS. The SRM also has significant policy level application potential.

The NSA Unit will work closely with DCP in particular in the development of a project M&E system for NGOs and training in its use. It will also liaise with the DCP in its focussed training of local consultants and NGOs, intended to take place during mid 2013.

Current schemes include the Home Students Work-based Learning Programme, which provides R500 per week to Rodriguan students studying in Mauritius during their home vacation whilst on work placement. This could be extended to placements in NGOs in an attempt to increase their capacities whilst providing valuable practical experience to students. The Rodrigues Island Education Initiative involves higher education students assisting slow learners in primary schools, for which they are paid R100 per session. The work-based compensation scheme introduced for octopus fishers during the two month closed season may also provide a model for a modest payment voluntary scheme for undertaking labour-intensive public works, especially in the area of environmental conservation. The system of Agents d’Education could also inform the development of a similar model for modestly paid community workers with higher qualifications to assist local associations. There is also potential for involving retired professionals to offer advice on technical and policy issues.

It should be noted that the NSA Unit will merge with the NGOTF in the near future, and operate with a common strategy.

The PSUP is a multi-stakeholder, bottom-up approach to shelter, implemented by UN Habitat with resources from the EU. The NSA Unit is already involved in contributing to the assessment exercises that have started in Barkly, Caro Calyptus and Cite EDC in Grand Rivière Noire. The MCCI Foundation’s project site will be at Gros Cailloux.

For example, DCP will launch a Small Grants Window from mid 2013 to support projects utilising partnership approaches. The GEF/SGP has an annual call for proposal relating to specific thematic areas at community level

Under the IC3 project, 156,000 secondary school pupils have been trained, and the Community Empowerment Programme led to the creation of 183 computer clubs in 23 Youth Centres, 17 Women’s Centres, 75 Community Centres, 53 Social Welfare Centres, 9 Day Care Centres and 6 NGOs / Municipal Councils / Village Halls. However, computer usage, especially amongst certain groups, remains low. Several other schemes for unemployed youth and inter-active learning under the E-Education Plan are also ongoing.

The Technical Cooperation Facility (TCF) may be used to source both local and international technical assistance, especially for studies. The African Development Bank can also provide grants for technical assistance and project funds to NGOs.

Includes US$ 85,000 for third pilot area, should funding become available

Evaluations are planned to take place in July 2015 and December 2016.

# Text boxes

United Nations Development Programme Mauritius

Project Document

Programme Manager &

Programme Coordinator (Rod)

Project Board

Other Collaborating Agencies*

Executing Entities

MSIEE and MSS

Implementing Agencies:

MSIEE / NEF & MSS / NSA

UNDP Country Office support to NIM

Project Assurance

(by Board members or delegated to other individuals)

Project Support

Staff

Project Organisation Structure

MTASC 1

Improved M&E and Targeting of NEF Programmes

MTASC 3

New models of service delivery & pro-poor project designs developed

MTASC 2

Empowerment of Excluded Groups (especially women)