## CAPACITY DEVELOPMENT IN SOCIAL WELFARE

2011 ANNUAL WORK PLAN

COUNTRY: MALAWI

2011 Annual Work Plan

Country: Malawi

Project Title		: 	Capacity Development in Social Welfare

UNDAF Outcomes (5.2):	Good governance, gender equality and rights based approach to development enhanced by 2011

Expected CPAP Outcome: 	Improved national capacity to formulate policy, manage, monitor and deliver services to protect the rights of vulnerable groups

Expected CP Outputs: 	Strengthened capacity for participatory planning and coordination at district level

Implementing Partner: 	Ministry of Gender, Children and Community Development

Narrative Summary of the AWP Activities: The Ministry of Gender, Children and Community Development through the District Social Welfare Department is committed to facilitate the support for care, protection and development of OVC in a coordinated manner in order to provide them with an environment to realize their full rights and potential. The coordination, monitoring and evaluation of OVC activities at the National, District and Community levels has proven to be the most effective way in sustaining the quality of care and support services to OVC. In spite of the fact that there is an overwhelming number of orphans and other vulnerable children in the country, the Department of Social Welfare at district level, together with the district councils, will continue to assist all supported initiatives in the districts.

| Programme Period: January 2008-December 2011 Programme Component: Orphans and other Vulnerable Children Programme / Family Based Care Intervention Title: Capacity Development in Social Welfare Project Code: Award ID: 00050880 Project ID: 00063081 Duration: 4 years | Estimated annualized budget: US$450,000 Allocated resources: Government (GFATM)/Cost Sharing: US$320,000 UNDP/One Fund: tbd Financial Gap: US$130,000 |
| --- | --- |

Agreed by Implementing Partner:

Ministry of Gender, Children and Community Development: ______________________________________________

Date:  _______________________________________________________________________

Lilongwe, Malawi

Agreed by Donor:

UNDP: ______________________________________________________________________

Date:  _______________________________________________________________________

Lilongwe,   Malawi

- SITUATION ANALYSIS

1.1		Background

The challenges of the HIV and AIDS pandemic in Malawi’s growth and development are clear. Globally, Malawi is the ninth most-affected country of HIV, with an estimated 12 percent of sexually active adults (15 to 49 years old) being infected and an estimated 1 million adults and children living with HIV infection. Reversing the continued spread of the HIV and AIDS pandemic is central to sustainable social development, social cohesion and food security in the country.

Increasing levels of poverty and the impact of the HIV and AIDS epidemic have contributed to high numbers of orphans, of which there are currently an estimated 1,008,000 in Malawi (NSO,2008), half of them due to HIV and AIDS. The epidemic continues to exert socio-economic pressures on children, their families and communities, leaving orphans under the care of the elderly mostly women or in some cases children, especially girls, fending for themselves.   Access by orphans and vulnerable children (OVC) to essential services including education, health, water and sanitation, nutrition and psychosocial support remain a challenge. Many live with additional effects of stigmatization, social exclusion, deprivation and discrimination, including gender discrimination and are subjected to increased risks of economic hardship, abuse and sexual exploitation. In addition, the absence of numerous quality social workers, and a robust child protection system with appropriate capacity to respond to the complex issues of OVC, is of grave concern.

To address the OVC crisis, the Government of Malawi, through the Ministry of Gender, Children and Community Development (MoGCCD), has been implementing the National Plan of Action (NPA) for OVC with the goal of building and strengthening family, community and government capacities to scale up response for the survival, growth, protection and development of OVC.NPA outlines a five-year strategy to scale up interventions to mitigate the OVC crisis in Malawi. However, the implementation of the NPA has been slow, partly due to the limitations at District Social Welfare Office level both in terms of actual skills and numbers of officers. Currently, the Ministry of Gender, Children and Community Development is operating at 60% of the staff requirements. Given the scale of the OVC crisis in Malawi, there is an urgent need to rapidly roll out the NPA and considerably increase the scale up of the OVC response.

There are a number of NGOs, CBOs and FBOs providing interventions targeting children. Funding levels for OVC interventions are also increasing due to the increased development partner attention, as well as Malawi’s successful Global Fund proposals.  Enhancing government’s capacity to better manage development projects is among UNDP’s core mandates and vital for the implementation of the NPA.The Capacity Development in Social Welfare project aims to strengthen the capacity of the MoGCCD in the scale up of OVC interventions through numerous activities. In order to establish an effective gender sensitive monitoring and evaluation system to assess the situation of OVC, United Nations Volunteer (UNV) Information Technology Specialists are recruited to assist in the operationalization of the national OVC electronic management system and database. The second area of capacity development is the recruitment of UNV Social Welfare Officers who are placed at district level to strengthen capacity of districts in the expansion of OVC interventions.

- 2011 ANNUAL WORK PLAN

The 2011 AWP continues the key activities as well as builds on achievements made in previous years. Support will continue to be given to enhance coordination and management at the district level and develop the capacity of social welfare officers. 2011 AWP focuses more on upstream activities, such as the development of inclusive guidelines for children’s parliament in collaboration with the National Assembly.  UNDP will also facilitate the development of a  gender responsive policy and strategic plan on Children’s Social Protection.

The following are the major planned activities in the 2011 AWP:

- Management of UNVs in District Social Welfare Offices

- Management of UNV IT specialist

- Coordination and Management

2.1   Estimated Budget

The 2011 estimated annualized budget is $450,000.  Of this amount, $ 320,000 is from cost sharing resources.  A total of $130,000 remains unfunded and will have to be mobilized.  The budget is distributed as follows:

- Management of UNVs in District Social Welfare Offices        $   149,264

- Management of UNV IT specialist	                                          $   72,757.5

- Coordination and Management                                                   $   203,718

- Program Coordination                                                                   $   4,500

- MANAGEMENT ARRANGEMENTS

3.1 Roles and Responsibilities

Project Board

Responsibility for the project achieving its designated outputs is ultimately held by the project board. The Project Board will be responsible for making management decisions relating to the initiation, direction, review and closure of the programme. The project board will make key decisions during the running of the programme, or as necessary when critical issues are raised by the National Programme Manager.

The Project Board will be made up of a member of UNDP, a programme analyst, a member of the UNV-unit and a member of MoGCCD. The Project Board shall meet quarterly and review reports produced by the project manager based on reports from the district commissioners supervising the UNVs.

Project Manager/Ministry of Women and Child Development

Ministry of Gender, Children and Community Development will manage the project and provide technical direction to UNVs.

District Commissioners

The District Commissioner is charged with the overall supervision of the UNVs in the districts. They also have the responsibility to assist the UNVs in finding suitable accommodation and organize office space including all necessary equipment.

UNDP

The role of UNDP, as the senior supplier is to support the programme, mobilizing and managing resources, prepare AWPs, budgets and communicate with MoGCCD to ensure that objectives and results are met. UNDP is also in charge of orientating newly recruited UNV’s on the Capacity Development in Social Welfare Project and introduction to the host organization.

UNV Unit

The UNV unit will be responsible for the recruitment and management of the UNV’s and their overall well-being upon arrival in Malawi.

3.2 Financial Arrangements

The Ministry of Gender, Children and Community Development has received grants from the National AIDS Commission of Malawi Grants Facility towards the cost of alleviating the HIV/AIDS pandemic. MoGCCD contributes funds to UNDP for the implementation of the Capacity Development in Social Welfare project. UNDP will receive and administer the funds for the implementation of the project in accordance with the regulations, rules and directives of the UNDP.

4    LEGAL CONTEXT

The Programme Document shall be the instrument referred to as such in Article 1 of the SBAA between the Government of the Republic of Malawi and UNDP, signed on 15 July 1977.  Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the executing agency and its personnel and property, and of UNDP’s property in the executing agency’s custody, rests with the executing agency. The executing agency shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the executing agency’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The executing agency agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Programme Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via this provision must be included in all sub-contracts or sub-agreements entered into under this Programme Document.

## Annual Work Plan                                                                                                           Year _January to December 2011

| EXPECTED CP OUTPUTS And indicators including annual targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| Strengthened capacity of districts in the scale up of OVC interventions. Indicator: Selected District social welfare offices with one international UNV Baseline: 6 Target: 6 | 1.0 Management of UNVs in District Social Welfare offices |
|  | Support UNVs | X | X | X | X | UNDP, MoGCCD, UNV | GFATM/ MoGCCD | 71500 UN Volunteers | 140,119.9 |
|  |  |  |  |  |  |  |  | 71600 Travel | 7,080.0 |
|  |  |  |  |  |  |  |  | 74500 Miscellaneous | 2,064.0 |
|  |  | Subtotal | 149,264 |
| Indicator: UNV IT specialists working at MoGCCD Baseline: 2, Target 2 Indicator: National OVC electronic management information system at the Ministry linked to all districts in place | 2.0 Management of UNV IT specialists |
|  | Support UNV IT specialists | X | X | X | X | UNDP, MoGCCD, UNV | GFATM/ MoGCCD | 71500 UN Volunteers | 70,060 |
|  |  |  |  |  |  |  |  | 71600 Travel | 1,665.5 |
|  |  |  |  |  |  |  |  | 74500 Miscellaneous | 1,032 |
|  |  | Subtotal | 72,757.5 |
|  | General Management Support (3%) |  |  |  |  |  |  |  | 6,660.6 |
|  |  | Sub-total | 228,682.1 |
| EXPECTED CP OUTPUTS And indicators including annual targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 5.3 Strengthened capacity in the delivery of OVC services at the District level. Baseline 1 (2010) Target: 12 Districts Activities of the DSWO monitored and supervised Indicator: # of monitoring and supervisory visits conducted Target: 2 | 3.0 Coordination and Management 3.1. Engage 24 data entry clerks to update the OVC Database | X | X | X | X | UNV, DSWO | UNDP | 72100 Contractual Services | 7,525 |
|  | 3.2. Train 90 Child Protection Committees | X | X | X | X | DSWO, UNV & Key Partners | UNDP | 72100 Contractual Services | 12,500 |
|  | 3.3. Conduct bi-annual monitoring visits to the 12 District Councils. |  | X |  | X | MGCCD & UNDP. | UNDP | 71600 Travel | 7,204 |
|  | 3.4. Hold stakeholder meetings at district level with women and men participants to disseminate and mobilize resources for district action plans for OVC. | X | X | X | X | MOGCCD ,DSWO & Key partners | UNDP | 72100 Contractual Services | 14,200 |
|  | 3.5. Annual review meeting with UNV Social Welfare Officers |  |  | X |  | MOGCCD DSWO, UNV & UNDP | UNDP | 71600 Travel 72100 Contractual Services | 12,600 |
|  | 3.6.Hold Annual TPR meeting |  |  |  | X | MOGCCD, MoF & UNDP | UNDP | No cost | 0 |
|  | 3.6. Facilitate development of children’s policy and strategic plan for children. Conduct and engender the needs assessment leading to children’s policy and strategic plan Hold workshop to discuss needs assessment findings |  | X | X X | X |  | UNDP | 71400-Contractual Services-Individual 71200-Contractual Services 71600- Travel | 20,000 12,000 |
| The capacity of social welfare officers developed Indicator: Gender sensitive Curriculum developed Target: 1 | 3.7. Support the development of a tailor made curriculum for upgrading of graduate social workers who have non social work qualifications: engage Catholic University/UNIMA to develop tailor made gender sensitive social work curriculum for social workers | X | X | X | X | MOGCCD, UNDP | UNDP | 71200-Contractual Services | 12,000 |
| Capacity of District Councils enhanced to conduct effective and meaningful children’s parliaments Indicator: # of districts oriented Number and gender of DC staff orientated Target: 12 districts |  |  |  |  |  |  |  |  |  |
|  | 3.8. Review, print and distribute gender responsive Guidelines and Training manuals for children’s Parliament in collaboration with the National Assembly | X | X |  |  |  | UNDP | 71200-Contractual Services | 10,500 |
|  | 3.9. Orient District Councils on conducting Child Parliaments |  |  | X |  |  | UNDP | 71200-Contractual Services | 16,689 |
|  | 3.10. Hold District Children’s Parliaments |  |  | X | X |  | UNDP | 71200-Contractual Services 71600-Travel | 20,500 |

| EXPECTED CP OUTPUTS And indicators including annual targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| District Coordination enhanced Indicator: # of Coordination meetings held Number and gender of participants in coordination meetings Target: 48 meetings | 3.11. Conduct quarterly district coordination meetings in each of the 12 districts | X | X | X | X | DSWO & UNDP and partners | UNDP | 71600-Travel | 18,000 |
|  | 3.12. Procure Vehicle to facilitate movement of Social Welfare Officers |  | X |  |  | MOGCCD & UNDP | UNDP | 72300- Equipment & Goods 71200-Contractual Services | 40,000 |
|  | 3.13. Conduct a mapping exercise of key OVC partners working in the 12 districts and analyze capacities and programmes that could be leveraged to ensure harmonization and sustainability. Include assessment of capacity of partners in gender analysis and mainstreaming in OVCs | X | X | X | X | DSWO &UNV | UNDP | No cost | 0 |
|  | Subtotal | 203,718 |
|  | 3.15. UNDP Trainings, Communications, Participation | X | X | X | X | MOGCCD | UNDP | 71600-Travel 71200-Contractual Services | 4,500 |
|  | General Management Services (3%)One Fund | 13,107.0 |
|  | GRAND TOTAL | 450,007.0 |

Risk Analysis Table

| # | Description | Type | Impact & Probability (scale from 1-low to 5-high) | Countermeasures/Management response | Owner | Last Update | Status of Risk |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The level of funding is dependent on the successful approval of proposals from Global Fund Secretariat through Ministry of Health | Financial | Risk occurring would have a serious negative impact making it difficult to achieve the programme outcomes Probability 2 Impact 5 | Global fund does guarantee continued funding for projects that are achieving results | Project Committees | 11.01.11 | Low: 2011 funds guaranteed |
| 2 | Limited experienced UNV’s undertake the assignment | Strategic | The achievement of results is based on the performance and capacity of the UNV’s. Poor performance seriously affects the projects outcome in districts Probability :2 Impact:4 | Selection Committee applies a strict criterion while selecting candidates. UNV’s performance is assessed annually. | UNV | 11.01.11 | Medium: Targeted IUNVs in place for 2011. |
| 3 | Limited Ministry staff to manage project | Strategic | Ministry programme staff are required to improve the delivery of the programme and meet some of its challenges Probability:3 Imapct:4 | The Ministry has appointed another officer to support in the programme management | MoGCCD | 11.01.11 | High: There is less commitment from government to fill vacant posts in MoGCCD |
| 4 | UNV unit experiencing delays in their service delivery for UNVs | Operational | Slow or bad service to the UNVs could affect the morale and work of the UNVs Probability:3 Impact:2 | In order to improve the services, UNV unit has recruited a new Program Analyst and Intern in addition to the Program Assistant, COA and PO. | PA,UNDP | 11.01.11 | Medium |

Annual Work Plan (AWP) Monitoring Tool                                                                                                          Year 2011

CP Component

| EXPECTED DP OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS CP4.2 Strengthened capacity of districts in the scale up of OVC interventions | PLANED ACTIVITIES List all the activities including monitoring and evaluation activities to be undertaken during the year towards stated CP outcomes | EXPENDITURES List actual expenditures against activities completed | RESULTS OF ACTIVITIES For each activity, state the results | PROGRESS TOWARDS ACHIEVING CP OUTPUTS Using data on annual indicator targets, state progress towards achieving the CP outputs. Where relevant, comment on factors that facilitated and/or constrained achievement of results |
| --- | --- | --- | --- | --- |
| CP Output 5.1: Strengthened capacity of central and local government to formulate policies and strategic plans, deliver services and be more visibly accountable to the populace |
| Indicator: Selected Districts social welfare offices with one IUNV Target:6 Indicator: UNV IT Specialists working at MoGCCD Target: 3 Indicator: National OVC electronic management information systems at the Ministry linked to all districts in place | Management of UNVs in District Social Welfare Offices |
|  | Facilitate upkeep payments of IUNVs in the districts |  |  |  |
|  | Management of UNV IT specialists at the national level |
|  | Facilitate upkeep payment of 3 IUNV IT specialists |  |  |  |
| Indicator: OVC services improved in 12 districts | Conduct stakeholder meetings at district level to disseminate and mobilize funds for implementation of district action plans for OVC |  |  |  |
|  | Conduct needs assessment leading to children’s policy and strategic plan |  |  |  |
|  | Review, print and distribute guidelines and training manual for children’s parliament |  |  |  |
|  | Conduct quarterly district coordination meetings in each of the 12 districts |  |  |  |
|  | Procure one vehicle to facilitate movement of DSWO in one district |  |  |  |
|  | Conduct mapping exercise of key OVC partners in 12 districts, analyze capacities & programmes to be leveraged for harmonization & sustainability |  |  |  |