# WASTE FOR WEALTH: PROMOTING A ZERO WASTE ENVIRONMENT

# 2011 Annual Work Plan

Country: MALAWI

UNDAF Outcome(s):	1.By 2011 Government policies and local national institutions effectively support equitable economic growth and the achievement of food and nutritional security while minimizing or reversing environmental degradation

1.3 linked to 3. increased equitable access to and utilization of quality basic social services by 2011.

Expected CP Outcome(s):   	1.3 Enhanced conservation of the natural resource base.

Expected CP Output(s):      A public private partnership management framework for sustainable waste     management in Lilongwe City established.

      - Sanitation and solid waste management at community and city level improved.

      - Waste management based employment in communities created.

      - The capacity of key stakeholders in solid waste management enhanced.

      - Gender sensitive regulatory environment and institutional arrangement to facilitate citywide sustainable solid waste management created.

      - Women groups and women entrepreneurs empowered for local service delivery.

Implementing partner:         Lilongwe City Assembly

Responsible parties:	Bunda College, Four Seasons Nurseries ,CCODE, SWAM, Community Waste Enterpreneurs, Ministry of Local Government & Rural Development

Agreed byLilongwe City Assembly: _____________________________

Agreed by Implementing Partner:

Lilongwe City Council:_____________________________________________________

Date: ____________________________________________________________________

Ministry of Local Government and Rural Development:__________________________

Date: _____________________________________________________________________

Approved  by UNDP:________________________________________________________

Date: ______________________________________________________________________

## Annual Work Plan

##### Year : 2011

| EXPECTED CP OUTPUTS and indicators including annual targets | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount US$ |
| OUTPUT 1 A public – private partnership management framework for sustainable waste management established Baseline : PPP in waste management in place Indicator: Progress reports based on signed MoU Annual Target: bring in at least one more partner to the partnership | Conduct Review Retreats for activities in the partnership |  |  | x | x | LCC | PPP SD | 72100 Contractual Services 71600 Travel | 10,000 |
|  | Conduct official launch of products from waste (eg compost manure) |  |  | x |  | LCC | PPP SD | 74200 Audio Vis 71600 Travel | 8,000 |
|  | Leadership learning workshop on PPPs and ISWM |  | x |  |  | LCC, PPPSD | PPPSD | 71600 Travel | 11,000 |
|  | Promote the PPP model within and outside the assembly in basic services delivery |  |  | x | x | LCC | PPP SD | 72400 Communication 71600 Travel | 6,000 |
|  | Review of LCC Solid waste services tariff structure to ensure sustainability of the model |  | x |  |  | LCC | PPP SD | 71300 local consultants | 7,000 |
| Subtotal |  |  |  |  |  |  |  |  | 42,000 |
| OUTPUT 2 Waste Management based employment created in communities Baseline: No. of community waste entrepreneurs by gender Indicators: No and gender of community waste entrepreneurs registered and functional. Annual target: Register 30 community waste entrepreneurs (men and women) | Support establishment of community waste entrepreneurs as local private associates as well as individuals. | x |  |  |  | LCA, SWAM, CCODE, Bunda, Four Season | UNDP CO | 72500 Supplies | 2,000 |
|  | Training community entrepreneurs in solid waste management (including composting and recycling, gender mainstreaming and service delivery) | x | x | x | x | Bunda, Four Season | UNDP CO | 72100 Contractual Services 72500 Supplies | 8,000 |
|  | Link community entrepreneurs with financial lending institution | x | x | x | x | LCA, SWAM, CCODE, | UNDP CO | 72500 Supplies | 2,000 |
|  | Identify and link community entrepreneurs especially women to other market outlets for products | x | x | x | x | LCA, SWAM, CCODE, Four Seasons | UNDP CO | 72500 Supplies | 5,000 |
|  | Develop a marketing strategy for compost manure and recyclables | x | X |  |  | LCC, SWAM, CCODE, Bunda, Four Seasons | UNDP CO | 72100 contractual services 71600 Travel | 5,000 |
|  | Implementation of a marketing strategy for compost manure and recyclables |  |  | x | x | LCA, SWAM, CCODE, Bunda, Four Season | UNDP CO | 71300 Local consultant 74200 Audio Vis | 6,000 |
| Sub-total |  |  |  |  |  |  |  |  | 28,000 |
| OUTPUT 3 Solid waste management at community level improved. Baseline: Existing PPP-SWM service in Mtandire and Area 25 Indicators: Number of illegal dumps removed. Annual Target: 100% of all illegal waste dumps removed. | Procurement of equipment to support waste management activities | x |  |  |  | LCA,UNDP | UNDP CO | 72300 Materials and goods | 5,000 |
|  | Develop waste management guidelines manual |  |  | x |  | LCC, | ONE UN FUND | 72300 Contractual 71600 Travel | 2,000 |
|  | Implementation of sanitation and door step recycling manuals |  |  | x | x | SWAM, CCODE | ONE UN FUND | 72500 Supplies | 3,000 |
|  | Intensify and roll out door to door separation and recycling of waste at source |  |  | x | x | LCA, SWAM, CCODE | ONE UN FUND | 72500 Supplies | 3,000 |
|  | Supporting establishment of sorting/composting centre | x |  |  |  | SWAM, CCODE | UNDP CO | 72300 Materials and goods | 10,000 |
|  | Support establishment of best kept house, zone, market and school competition |  |  | x | x | SWAM, CCODE | ONE UN FUND | 74500 Miscellenous | 5,000 |
| Sub-total |  |  |  |  |  |  |  |  | 28,000 |
| OUTPUT 4 The capacity of key stakeholders in solid waste management developed Baseline: Capacitated participatory community in PPP-SWM Indicators: Number and gender of people trained in SWM Annual Target: 100 people trained at least 50% women | Carry out participatory awareness campaigns on good SWM in the two communities ensuring participation of women |  |  | x | x | SWAM, CCODE, | ONE UN FUND | 74200 Audio Vis 72400 Communication | 12,000 |
|  | Gender sensitization campaign in the two communities | x |  | x |  | CCODE SWAM | PPP SD | 71600 Travel | 3,000 |
|  | Conduct training in leaderships and assertiveness skills for Women entrepreneurs |  |  | x | x | CCODE SWAM | ONE UN FUND | 72100 Contractual Services | 7,000 |
|  | Set up and operationalise school sanitation clubs with participation of boys and girls | x | x | x | x | CCODE SWAM | PPP SD | 72500 Supplies | 2000 |
|  | Set up, train and operationalise market and community sanitation committees with at least 50%membership being women | x | x | x | x | SWAM CCODE | PPP SD | 72500 Supplies | 3,000 |
|  | Carry out a training of municipal staff and implementing partners in effective monitoring of activities and performance of local solid waste providers |  |  | x |  | LCC Bunda | ONE UN FUND | 72100 Contractual Services | 8,000 |
|  | Train community waste entrepreneurs especially women in business management and group dynamics |  |  | x | x | Bunda CCODE SWAM | ONE UN FUND | 72100 Contractual Services | 7,000 |
|  | Develop manual for sanitation and door step recycling at source and composting |  |  | x |  | Bunda LCC SWAM CCODE Fourseasons | ONE UN FUND | 72500 Supplies | 3,000 |
|  | Conduct workshop to report and to present developed manuals |  |  |  | x | Bunda | ONE UN FUND | 72100 Contractual Services | 5,000 |
|  | Document, develop and disseminate knowledge products and lessons learnt from the project to national and international audience |  |  | x | x | Bunda LCC | ONE UN FUND | 72100 Contractual Services | 4,000 |
|  | Learning visit to Maseru City Council with participation for both men and women |  |  | x |  | LCC | ONE UN FUND | 71600 Travel | 12,000 |
|  | UNV | x | x | x | x | UNDP | UNDP CO | 71500 UNV | 7,000 |
| Sub-total |  |  |  |  |  |  |  |  | 73,000 |
| OUTPUT 5 Creation of gender sensitive regulatory environment and institutional arrangement to facilitate citywide sustainable solid waste management. Indicator 1: Revised draft LCA Solid waste by-law document Annual target: draft by-laws Indicator 2: Number of women and men participating in solid waste management and other urban service delivery Annual target: At least fifty percent of new entrants into solid waste business are women | Conduct review of institution framework and current municipal policies and by-laws on waste to promote the participation of women, youth and private sector ien waste management |  | x | x | x | LCC | UNDP CO | 71300 local consultants | 30,000 |
|  | Gender sensitive Information Education and Communication on waste management by laws and policies |  |  | x | x | LCC | ONE UN FUND | 71300 local consultants | 22,458 |
| Sub-total |  |  |  |  |  |  |  |  | 52,458 |
| Project Management | Monitoring and supervision which ensure collection, maintenance and use of gender disaggregated data | x | x | x | x | LCC | UNDP CO | 72500 Supplies 71600 Travel 72400 Communication | 13,000 |
|  | IP review meetings and monitoring | x | x | x | x | UNDP | UNDP |  | 5,000 2,000 |
| Sub-total |  |  |  |  |  |  |  |  | 20,000 |
| GMS on ONE UN FUND (7%) |  |  |  |  |  |  |  |  | 6,542 |
| TOTAL |  |  |  |  |  |  |  |  | 250, 000 |

# FUNDING SOURCES:

# UNDP CO: USD 100,000

# ONE UN FUND: USD 100,000

# PPP-SD: USD 50, 000The Annual Work Plan (AWP) Monitoring Tool							Year:2011

# CP Component______________________

Implementing Partner : Lilongwe City Assembly

| EXPECTED CP OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS | PLANNED ACTIVITIES List all the activities including monitoring and evaluation activities to be undertaken during the year towards stated CP outputs | EXPENDITURES List actual expenditures against activities completed | RESULTS OF ACTIVITIES For each activity, state the results of the activity | PROGRESS TOWARDS ACHIEVING CP OUTPUTS Using data on annual indicator targets, state progress towards achieving the CP outputs. Where relevant, comment on factors that facilitated and/or constrained achievement of results including: Whether risks and assumptions as identified in the CP M&E Framework materialized or whether new risks emerged Internal factors such as timing of inputs and activities, quality of products and services, coordination and/or other management issues |
| --- | --- | --- | --- | --- |
| OUTPUT 1 A public – private partnership management framework for sustainable waste management established Baseline : PPP in waste management in place Indicator: Progress reports based on signed MoU Annual Target: bring in atleast one more partner to the ppp model | Conduct Review Retreats for activities in the partnership |  |  |  |
|  | Conduct official launch of products from waste (eg compost manure) |  |  |  |
|  | Leadership learning workshop on PPPs and ISWM |  |  |  |
|  | Promote the PPP model within and outside the assembly in basic services delivery |  |  |  |
| OUTPUT 2 Waste Management based employment created in communities Baseline: No. of community waste entrepreneurs Indicators: No of community waste entrepreneurs registered and functional. Annual target: Register 30 community waste entrepreneurs | Support establishment of community waste entrepreneurs as local private associates as well as individuals. |  |  |  |
|  | Training community entrepreneurs in solid waste management (including composting and recycling, gender mainstreaming and service delivery) |  |  |  |
|  | Link community entrepreneurs with financial lending institution |  |  |  |
|  | Identify and link community enterpreneurs to other market outlets for products |  |  |  |
|  | Develop a marketing strategy for compost manure and recyclables |  |  |  |
|  | Implementation of a marketing strategy for compost manure and recyclables |  |  |  |
| OUTPUT 3 Solid waste management at community level improved Baseline: Existing PPP-SWM service in Mtandire and Area 25 Indicators: Number of illegal dumps removed. Annual Target: 100% of all illegal waste dumps removed | Procure of equipment to support waste management activities |  |  |  |
|  | Develop waste management guidelines manual |  |  |  |
|  | Implementation of sanitation and door step recycling manuals |  |  |  |
|  | Identify, stop and clear all illegal dump sites in Mtandile and Area 25 |  |  |  |
|  | Intensify and roll out door to door separation and recycling of waste at source |  |  |  |
|  | Monitoring and surveillance of emerging illegal dump sites, |  |  |  |
|  | Supporting establishment of sorting/composting centre |  |  |  |
|  | Support establishment of best kept house, zone, market and school competition |  |  |  |
| OUTPUT 4 The capacity of key stakeholders in solid waste management developed Baseline: Capacitated participatory community in PPP-SWM Indicators: Number of people trained in SWM Annual Target: 100 people trained | Gender sensitization campaign in the two communities |  |  |  |
|  | Conduct training in leaderships and assertiveness skills for Women enterpreneurs |  |  |  |
|  | Set up and operationalise school sanitation clubs with participation of boys and girls |  |  |  |
|  | Set up,train and operationalise market and community sanitation committees with at least 50% membership being women |  |  |  |
|  | Carry out a training of municipal staff and implementing partners in effective monitoring of activities and performance of local solid waste providers |  |  |  |
|  | Train community waste entrepreneurs in business management and group dynamics |  |  |  |
|  | Develop manual for sanitation and door step recycling at source and composting |  |  |  |
|  | Conduct workshop to report and to present developed manuals |  |  |  |
|  | Document, develop and disseminate knowledge products and lessons learnt from the project to national and international audience |  |  |  |
|  | Establish tree nurseries and plant trees in Area 25 and Mtandire locations |  |  |  |
|  | Learning visit to Maseru City Council |  |  |  |
|  | UNV |  |  |  |
| OUTPUT 5 Creation of gender sensitive regulatory environment and institutional arrangement to facilitate citywide sustainable solid waste management. Indicator 1: Revised draft LCA Solid waste by-law document Annual target: draft by-laws Indicator 2: Number of women participating in solid waste management and other urban service delivery Annual target: At least fifty percent of new entrants into solid waste business are women | Conduct review of institution framework and current municipal policies and by-laws on waste to promote the participation of women, youth and private sector in waste management |  |  |  |
|  | Information Education and Communication on waste management by laws and policies |  |  |  |

# Text boxes

Narrative

A two- level Public Private Partnership (PPP) will be established in Lilongwe City, Malawi to deliver a waste management service in two low-income communities of Mtandile and Area 25. Firstly Lilongwe City Assembly (LCA) will engage community waste entrepreneurs, especially women’s groups at local level to collect, sort and transfer solid waste. Secondly, will partner with Four Seasons Nurseries, a large private horticultural company to buy and compost solid waste for organic manure. Two local NGOs – CCODE and SWAM will be responsible for community mobilization, capacity development and Bunda College will be responsible for capacity development and research of solid waste management alternatives. It is expected that the project will form an effective frame work for a pro-poor PPP in waste management, create employment, improve the urban environment, generate data and information for planning and decision making process, build capacity of waste stakeholders, reduce costs associated with municipal solid waste management at community level and support a conducive regulatory environment for sustainable solid waste management.

Estimated annualized budget:	       250,000

Allocated resources:

- Government		_________

- Regular                       100,000

- Other:

PPP SD	                50,000

One UN Fund      100,000

Unfunded budget:		       _______

Programme Period:		2008 - 2011

Programme Component:	Environment and   Energy

Intervention Title:	Waste for Wealth:

Promoting a zero waste

Environment

Budget Code:		Award ID: 00057696

Project ID: 00071385

Duration:		2009-2011