# 2011 Annual Work Plan PIMS 2085 Private Public Partnership in Sustainable Land Management in the

# Shire River Basin

Country: Malawi

UNDAF Outcome(s):  By 2011, Government policies and local and national institutions effectively support equitable economic growth and the achievement of food and nutrition security while minimizing or reversing environmental degradation

Expected CP Outcome(s): 1. Enhanced conservation of natural resource base by 2011

Expected CP Output(s):

1.1 National strategies, policies and action plans which integrate the environmental provisions of the MGDS   are implemented in meaningful partnerships with civil society and with effective coordination of development partners.

1.2 At least two programmes that meaningfully inter-relate poverty reduction and environmental management are prepared with national partners, approved and under implementation.

1.3 Development of business-led solutions for sustainable resource management and poverty reduction.

1.4 One MDG-based integrated rural development Programme implemented in at least 2 districts contributing to improved livelihoods and increased incomes of the poor

Lead Coordinating Partner:   Ministry Natural Resources, Energy and Environment.

Key Implementing partner(s): Ministry of Lands and Housing, Department of Energy, Department of Forestry, Environment Affairs Department, Ministry of Irrigation and Water Development, Ministry of Agriculture and Food Security, Department of Climate Change and Meteorological Services and CURE.

Other Implementing Partners: Ministry of Tourism, National Parks and Wild Life, Ministry of Industry and Trade, Ministry of Women, Child Development and Community Services, Millennium Villages Project, District Assemblies, Ministry of Agriculture and Food Security, Ministry of Development Planning and Co-operation, Malawi Micro-finance Network (MAMN), ESCOM and Southern Region Water Board.

PROJECT BRIEF

The Shire River basin covers over 3.1 million ha and directly or indirectly influences the livelihoods of over 5.5 million people in the southern region of Malawi.  The basin is of critical economic importance: it is the source of over 98% of the country’s power generating capacity, supplies water to major urban centres such as Blantyre and Limbe, supports a locally significant artisanal fishery, and supplies irrigation water for valuable crops. Malawi’s economy is based primarily on agriculture, dominated by subsistence and rain-fed food production systems that are greatly challenged by land degradation and declining soil fertility.  Extensive land use including extensive tree felling in the Middle and Upper Shire have  resulted in severe deforestation, land degradation and soil erosion, losing 13 percent of the total forest cover between 1990 and 2005 and 35 of the primary forest cover in the period 2000 – 2005. The dramatic land degradation in the Shire basin driven by poor agricultural practices and deforestation has in turn been driven by the negative interrelationship of high dependence on natural resources coupled with poor resource management, poverty, rapid population growth, ineffective policy implementation, and poor economic development, and more recently, climate change. There are three key barriers to the adoption of sustainable land management systems in the Shire River Basin: weaknesses in the policy, planning and institutional environment that influence SLM; weak financial incentives for adoption of SLM; weak capacities and inadequate skills at all levels required for promoting and/or adopting SLM. The overall goal of the project is: “Sustainable Land Management” and will be achieved through: (1) policy and institutional arrangement for basin-wide SLM. (2) private public partnerships providing financial incentives for SLM (through green water credits and sustainable charcoal. (3) improving knowledge and skills at all levels to support SLM (4) through crop insurance to provide a basis for increased access to credits as well as increased use of up to date weather information and (5) project management, monitoring/evaluation. This four year project will be coordinated by the Environmental Affairs Department (EAD) of the Ministry of   Natural Resources Energy and Environment and actual implementation will be through the relevant ministries and departments such as agriculture, forestry, energy and rural development, and will involve local leadership and communities. The project’s immediate focus is the middle and lower Shire river basin. Lessons learnt will be up scaled to the entire Basin through the River Shire Development Authority established through the project. Following the project inception workshop held on 14th December 2011, the major activities of the project in 2011 will include; orientation of the participating district councils (Blantyre, Mwanza, Neno and Balaka), preparation of area action plans, recruitment of project personnel, reviewing and aligning relevant policies, preparation of establishment of Shire River Basin Authority, developing concepts for Payments for Ecosystems Services (PES),  and for Crop Weather Insurance Scheme, etc.

Agreed by Lead Coordinating Partner:

Ministry of Natural Resources, Energy and Environment: ____________________________________________

Date: __________________________________

Place: Lilongwe, Malawi

Agreed by Implementing Partners:

Environmental Affairs Department: ________________________________________________________________

Date: __________________________

Place: Lilongwe, Malawi

Approved by UNDP:_________________________________________________________________________________

Date:_________________________________

Place: Lilongwe, Malawi

## PIMS 2085   ANNUAL WORK PLAN 						_____2011_______

| EXPECTED CP OUTPUTS and indicators including annual targets | Expected output | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY-(IES) | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Account Code | ATLAS Budget Description | Amount |
| 1.1National strategies, policies and action plans which integrate the environmental provisions of the MGDS are implemented, in meaningful partnerships with civil society and with effective coordination of development partners. Network of key technical officers on SLM established 1.1 National strategies, policies and action plans which integrate the environmental provisions of the MGDS are implemented, in meaningful partnerships with civil society and with effective coordination of development partners. | Output 1: The Policy, regulatory and institutional arrangement support sustainable land management in the Shire River Basin. ( Creation of the Shire River Basin Authority) Activity 2 in ATLAS Output 1: The Policy, regulatory and institutional arrangement support sustainable land management in the Shire River Basin. ( Creation of the Shire River Basin Authority) Activity 2 in ATLAS | Alignment of sector policies improved |
|  |  | 1.1.1Conduct meetings for network of focal points to develop consultancy TORs for a study to identify gaps and areas of conflict of policies e.g. Transport, Settlement, Industry etc at the same time taking into account gender considerations | X | X |  |  | MNREE, MIWD, DOF, LRCB, | UNDP | 72500 | Stationery | 500.00 |
|  |  |  | X | X | X | X |  | UNDP | 72400 | Communication | 2,000.00 |
|  |  |  | X | X | X | X |  | UNDP | 72100 | Conference hire | 2,500.00 |
|  |  | 1.1.2 Hire a consultant to review policies and identify gaps and conflict (this activity will be done in close consultation with a similar activity under Climate Change) |  | X | X | X | EAD, DOF, DCCMS, MIWD | GEF | 71400 | Contractual services | 36,000.00 |
|  |  |  |  |  |  |  |  | GEF | 71600 | Travel | 2,500.00 |
|  |  |  |  |  |  |  |  | GEF | 74200 | Publicity advert | 1,500.00 |
|  |  | 1.1.3 Conduct meetings for the network of focal points to develop consultancy TORs for review of relevant policies (e.g. Forestry Policy, water, agriculture, etc) |  | X | X |  | DOF, EAD, DOE, MNREE | UNDP | 71600 | Travel and meetings | 2,500.00 |
|  |  |  |  |  |  |  |  | UNDP | 72400 | Communication cost | 500.00 |
|  |  | 1.1.4 Hire consultant to review Forestry, water and agriculture policies for SLM |  |  | X | X | DOF, EAD, MAFS, UNDP | GEF | 71400 | Contractual services | 20,000.00 |
|  |  |  |  |  |  |  |  | UNDP | 71600 | Travel | 1,000.00 |
|  |  | 1.1.5 Conduct sensitization meetings on agriculture policy in line with SLM for the basin |  | X | X | X | MAFS, EAD, MNREE, DOF, | UNDP | 74200 | Publicity | 500.00 |
|  |  |  |  |  |  |  |  | UNDP | 72800 | Supplies | 500.00 |
|  |  | Sub-total 1.1 | GEF UNDP TOTAL | 60,000.00 10,000.00 70,000.00 |
|  |  | 1.2. Shire River Basin Development Authority formed and supported to improve coordination of SLM, environmental management and development |
|  |  | 1.2.1 Conduct consultative and awareness meetings with NGOs on Sustainable Land Management(SLM) and implementation of Water Resources Bill | X | X | X | X | MNREE, MIWD, MAFS, MLHUD, MLGRD, Pvt. Sector | GEF | 71200 | Contractual services- indiv. | 10,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel and meetings | 4,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72100 | Conference Hall hire | 5,000.00 |
|  |  |  |  |  | X | X |  | GEF | 74200 | Publicity | 5,000.00 |
|  |  | 1.2.2.Hire a consultant to document lessons on River Basin Authorities including any gender considerations and difference with respect to resource use, and conduct consultative and awareness meetings with Parliamentary Committee to lobby for enactment of the Water Resources Bill. | X | X | X |  | MNREE, EAD, MIWD, National Assembly | GEF | 71400 | Contractual services - indiv. | 10,000.00 |
|  |  |  | X | X | X |  |  | UNDP | 71600 | Travel | 5,000.00 |
|  |  |  | X | X | X |  |  | GEF | 74200 | Promotional materials | 3,000.00 |
|  |  | 1.2.3 Conduct capacity needs assessment for community(women, men, children, senior citizens) awareness raising on SLM and related. |  | X | X | X | MNREE, EAD | GEF | 71200 | Contractual Services Int. | 12,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72100 | Contractual services - Company | 6,000.00 |
|  |  |  |  | X | X | X |  | GEF | 71600 | Travel | 4,500.00 |
|  |  |  |  | X | X | X |  | GEF | 72800 | Supplies | 500.00 |
|  |  | 1.2.4 Conduct study tours to countries with established SRBA. |  | X | X | X |  | UNDP | 71600 | Travel | 5,000.00 |
|  |  | 1.2.5 Institutional building activities toward establishment of the SRBA |  | X | X | X |  | GEF | 72200 | Procurement | 10,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72500 | Supplies | 2,000.00 |
|  |  |  |  | X | X | X |  | GEF | 71600 | Travel | 3,000.00 |
|  |  | Sub-total 1.2 | GEF UNDP TOTAL | 80,000.00 10,000.00 90,000.00 |
|  | Output 1 Total | GEF UNDP TOTAL | 140,000.00 20,000.00 160,000.00 |
| 1.1 National strategies, policies and action plans which integrate the environmental provisions of the MGDS are implemented, in meaningful partnerships with civil society and with effective coordination of development partners 2011 Target Final Inception workshop report | Output 5: Program management support (Activity 6 in ATLAS) | 5.1 Promote Adaptive Learning Monitoring and evaluation (activity 4 in ATLAS ) |
|  |  | Taking into account gender issues:- -document indigenous knowledge on SLM -Determine factors hindering the adoption of SLM practices and incentives required for promoting adoption through consultancy services -Document successful practices and propose mechanisms for scaling up successful interventions |  |  | X | X |  | GEF | 71400 | Contract services | 11,088.00 |
|  |  |  |  |  | X | X |  | GEF | 72500 | Stationery | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel and meetings | 4,000.00 |
|  |  |  |  |  | X | X |  | UNDP | 74200 | Publicity | 2,000.00 |
|  |  | Conduct study tours in country |  |  | X | X |  | UNDP | 71600 | Travel and meetings | 2,000.00 |
|  |  | Sub-total 5.1 | GEF UNDP TOTAL | 17,088.00 4,000.00 21,088.00 |
|  |  | 5.2 Project Management Unit |
|  |  | -Hire SLM Project Manager, -Hire SLM Project Advisor -Hold at least three steering committee meetings |  | X | X | X | MNREE | GEF | 61100 | Contract | 120,912.00 |
|  |  |  |  | X | X | X |  | GEF | 61200 | Contract | 35,000.00 |
|  |  |  |  | X | X | X |  | GEF | 71600 | Travel | 4,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72200 | Equipment | 10,000.00 |
|  |  |  |  | X | X | X |  | UNDP | 72200 | Equipment | 10,000.00 |
|  |  | -Procure audio/ visual equipment -Facilitate Study tours both local and international - |  | X | X | X | EAD, MNREE | GEF | 72500 | Stationery | 2,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72800 | Supplies | 10,000.00 |
|  |  |  |  | X | X | X |  | UNDP | 74100 | Professional services | 5,000.00 |
|  |  | Sub-total 5.2 | GEF UNDP TOTAL | 186,912.00 10,000.00 196,912.00 |
|  | Output Total 5 | GEF UNDP TOTAL | 204,000.00 14,000.00 218,000.00 |
| CP OUTCOME 1 TOTAL | GEF UNDP TOTAL | 344,000.00 34,000.00 378,000.00 |
| 1.3 Development of business-led solutions for sustainable resource management and poverty reduction. Target Training needs assessment report Number of charcoal producers identified and sensitized 1.3 Development of business-led solutions for sustainable resource management and poverty reduction 2011 Target Needs Assessment report | Output 2: Private Public Partnerships (PPP) providing financial incentives for SLM (through green water credits and sustainable charcoal); Activity3 in ATLAS Output 2: Private Public Partnerships (PPP) providing financial incentives for SLM (through green water credits and sustainable charcoal); Activity3 in ATLAS | 2.1 Green Water Credits Scheme operationalized to provide financial incentive for SLM |
|  |  | Identify network of focal points for green water credit scheme. |  | X |  |  | MNREE, Private sector, NGOs, EAD, CSO, DOF, Chancellor College | GEF | 72400 | Communications | 500.00 |
|  |  |  |  | X |  |  |  | GEF | 72800 | Supplies | 0.00 |
|  |  | Synthesize lessons from existing Green water Credit Schemes/Study tours (GWCS)- sensitization meetings. The network is encouraged to be gender sensitive during the conduct of the meetings and studies |  |  | X | X | MNREE, Private sector, NGOs, CSO, Chancellor College | UNDP | 71400 | Contractual services -local | 20,000.00 |
|  |  |  |  |  | X | X |  | UNDP | 71600 | Travel | 6,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72500 | Stationery | 2,000.00 |
|  |  | Based on results of the meetings above develop consultancy TORs for development of GWCS. Consultant to be gender sensitive and to takeinto account lessons from the village level natural resources management committees and village & area development committees. |  |  | X | X | MNREE, Private sector, NGOs, CSO, Chancellor College, EAD, DOF | GEF | 71200 | Contractual services-int. | 4,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71400 | Contractual services -local | 4,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel | 2,500.00 |
|  |  |  |  |  | X | X |  | GEF | 72800 | Supplies | 2,000.00 |
|  |  | Hire consultancy services for development of Green Water Credit Scheme. |  |  |  | X | MNREE, Private sector, NGOs, CSO, Chancellor College | GEF | 71200 | Contractual services-int | 20,000.00 |
|  |  |  |  |  |  | X |  | GEF | 71400 | Contractual services | 4,000.00 |
|  |  |  |  |  |  | X |  | GEF | 71600 | Travel | 2,000.00 |
|  |  | Meetings of Network Focal Points in the development of concepts for carrying out relevant studies to facilitate in the development of the green water scheme |  | X |  |  | MNREE, EAD, DOF, NPWL | GEF | 71200 | Contractual services-int | 2,000.00 |
|  |  |  |  | X |  |  |  | GEF | 71400 | Contractual services -local | 6,000.00 |
|  |  |  |  | X |  |  |  | GEF | 71600 | Travel and meetings | 7,000.00 |
|  |  | Conduct necessary studies to facilitate the establishment of GWC- Including hydrological modeling of the SRB |  |  | X | X | MNREE, UNDP | GEF | 71400 | Contractual services -local | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel & meetings | 1,000.00 |
|  |  | Explore the feasibility and requirements for the establishment of a Water User Associations |  |  | X | X | BWB, ESCOM, Private sector | GEF | 71200 | Contractual services-int | 3,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71400 | Contractual services -local | 4,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel | 15,000.00 |
|  |  | Sub-total 2.1 | GEF UNDP TOTAL | 82,000.00 26,000.00 108,000.00 |
|  |  | 2.2 Sustainable charcoal providing additional income as an incentive for sustainable woodlands management |
|  |  | Develop consultancy TORs for conducting needs assessment for sustainable charcoal |  | X |  |  | MNREE, DOF, MPDC, MOF | GEF | 71400 | Contracts – ind | 12,000.00 |
|  |  |  |  | X |  |  |  | GEF | 71600 | Travel | 15,000.00 |
|  |  |  |  | X |  |  |  | GEF | 72100 | Contracts | 13,500.00 |
|  |  |  |  | X |  |  |  | GEF | 72400 | Communication | 1,500.00 |
|  |  | Hire a consultant to undertake the needs assessment. |  |  | X | X | EAD, DOF, UNDP | GEF | 71400 | Contractual services | 40,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel | 5,000.00 |
|  |  |  |  |  | X | X |  | GEF | 74299 | Publicity | 2,000.00 |
|  |  | Conduct capacity building trainings for Forestry Department staff and Local Forest Organizations in Forest Management Planning ( and identify training needs for sustainable charcoal production at village level for men and women) | X | X | X | X | DOF, EAD | GEF | 71600 | Travel | 15,500.00 |
|  |  |  | X | X | X | X |  | UNDP | 71400 | Contractual services | 30,000.00 |
|  |  |  | X | X | X | X |  | GEF | 72200 | Procure equip. | 10,000.00 |
|  |  |  | X | X | X | X |  | GEF | 72100 | Contracts | 13,000.00 |
|  |  |  | X | X | X | X |  | UNDP | 72200 | Equipment | 19,000.00 |
|  |  |  | X | X | X | X |  | GEF | 72400 | Communication | 1,300.00 |
|  |  |  | X | X | X | X |  | UNDP | 71600 | Travel & meetings | 6,000.00 |
|  |  |  | X | X | X | X |  | UNDP | 72500 | Supplies | 5,000.00 |
|  |  | Sub-total 2.2 | GEF UNDP TOTAL | 128,800.00 60,000.00 188,800.00 |
|  | Output 2 | GEF UNDP TOTAL | 210,800 86,000.00 296,800.00 |
| 1.3 Development of business-led solutions for sustainable resource management and poverty reduction. 2011 Target Report 1.3 Development of business-led solutions for sustainable resource management and poverty reduction. 2011 Target Report on microcredit firms Number of officers trained | Output 3: Crop insurance providing the basis for improved increased access to credit as well as increased use of up to date weather information in decision makingActivity 4 in ATLAS Output 3: Crop insurance providing the basis for improved increased access to credit as well as increased use of up to date weather information in decision making | 3. 1 Index based crop piloted using lessons learnt during the initial pilot to refine the scheme |
|  |  | Conduct assessment of number and density of weather stations. Within the mid shire river basin and link up with similar initiatives e.g. AAP |  | X | X | X | EAD, MIWD, DCCMS, MOAFS DOF | GEF | 71200 | Consultantsint | 0.00 |
|  |  |  |  | X | X | X |  | GEF | 71400 | Contractual | 10,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72500 | Supplies | 5,000.00 |
|  |  |  |  | X | X | X |  | UNDP | 72500 | Supplies | 2,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72100 | Contract | 5,000.00 |
|  |  |  |  | X | X | X |  | GEF | 72400 | Communication | 700.00 |
|  |  | Conduct awareness on index based crop insurance products |  |  | X | X | EAD, DCCMS, MAFS | GEF | 71400 | Contractual | 12,000.00 |
|  |  |  |  |  | X | X |  | GEF | 74200 | Publicity | 2,000.00 |
|  |  | Motivate micro finance institutions to participate in index based insurance scheme. |  |  | X | X | EAD, MAFS, DCCMS, | UNDP | 71600 | Meetings and Travel | 5,500.00 |
|  |  |  |  |  | X | X | Trade & Industry | GEF | 74200 | Publicity | 6,000.00 |
|  |  | Identify farmers to participate in the crop insurance crops scheme. |  |  | X | X | EAD, MAFS DCCMS, | UNDP | 71600 | Travel | 5,000.00 |
|  |  |  |  |  | X | X |  | UNDP | 72100 | Contractual services | 5,000.00 |
|  |  | Hire a local consultant to identify suitable micro-finance institutions and credit schemes in the impact area. |  |  | X | X | EAD, UNDP DCCMS, MAFS, | UNDP | 72500 | Supplies | 7,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Travel | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72400 | Communication | 2,000.00 |
|  |  | Develop TORs for a consultant to identify suitable micro-finance institutions and credit schemes |  |  | X | X | EAD, MAFS, DCCMS | UNDP | 72100 | Workshops | 4,000.00 |
|  |  |  |  |  | X | X |  | UNDP | 72400 | Communication | 1,500.00 |
|  |  | Hire consultant to develop an index based crop insurance scheme |  |  | X | X | EAD, MAFS, DCCMS | GEF | 71200 | Contractual services int. | 20,000.00 |
|  |  | Sub-total 3.1 | GEF UNDP TOTAL | 64,700.00 30,000.00 94, 700.00 |
|  |  | 3.2 Improving weather data generation and use in decision making |
|  |  | Identify factors required for the success of a scheme to improve on data generation. |  |  | X | X | MNREE, MET, EAD, MIWD, MAFS | GEF | 71400 | Contractual services | 500.00 |
|  |  |  |  |  | X | X |  | GEF | 72400 | Communication | 500.00 |
|  |  |  |  |  | X | X |  | GEF | 72500 | Stationery | 500.00 |
|  |  |  |  |  | X | X |  | GEF | 72800 | Supplies | 500.00 |
|  |  | Build technical capacity of government technical officers (aim 50% female participation) to capture data. This activity will be linked with the Climate Change project) |  |  | X | X |  | GEF | 71400 | Contractual services | 500.00 |
|  |  |  |  |  | X | X |  | GEF | 72200 | Procurement | 11,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72800 | Supplies | 500.00 |
|  |  | Sub-total 3.2 | GEF UNDP TOTAL | 14,000.00 0.00 14,000.00 |
|  | Output 3 total | GEF UNDP TOTAL | 78,700.00 30,000.00 108,700.00 |
| 1.3 Development of business-led solutions for sustainable resource management and poverty reduction. 2011 Target Reports of training workshops on knowledge skills 1.3 Development of business-led solutions for sustainable resource management and poverty reduction. 2011 Target Baseline for forest resource report Map of hotspots in SRB | Output 4: Knowledge skills provided for SLM management Activity 5 in ATLAS and Activity 3 in ATLAS Output 4: Knowledge skills provided for SLM management Activity 5 in ATLAS and Activity 3 in ATLAS Output 4: Knowledge skills provided for SLM management | 4.1.Deepen assessment of best SLM practices in the country and in the region |
|  |  | 4.1.1 -Taking into consideration PPG studies findings - Conduct meetings to improve knowledge and skills of men and women at all levels to support SLM |  |  | X | X | MIWD, UNIMA, MAFS, MNREE, Pvt Sector , CSOs | GEF | 71400 | Contractual services | 7,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Meetings and Travel | 2,000.00 |
|  |  | Conduct SLM orientation and trainings for female and male staff and female and male farmers in the pilot hot spots---( such training will document successful practices, challenges etc in line with proposals in paragraph 135 to 140 of the PRODOC) |  |  | X | X |  | GEF | 72400 | Communication | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72500 | Stationery | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72100 | Contracts | 5,000.00 |
|  |  | Develop gender sensitive training manuals to improve knowledge and skills at all levels to support SLM. |  |  | X | X |  | GEF | 74200 | Publicity | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72800 | Supplies | 3,000.00 |
|  |  | Sub-total 4.1 | GEF UNDP TOTAL | 23,000.00 0.00 23,000.00 |
|  |  | 4.2.Forest productivity increased to match demand for wood products without causing further land degradation |
|  |  | Conduct consultative meeting to develop consultancy TORs for developing an action plan to increase forestry productivity. Consultancy to include gender considerations, co-management for income generation, promotion of urban forestry and improvement of plantation. |  | X | X |  | MNREE, DOF | GEF | 72400 | Communication | 3,500.00 |
|  |  |  |  | X | X |  |  | GEF | 71600 | Meetings and Travel | 5,000.00 |
|  |  |  |  | X | X |  |  | GEF | 72200 | Procurement | 4,000.00 |
|  |  | Hire services to develop an action plan to increase forestry productivity |  |  | X | X |  | GEF | 71400 | Contractual services | 15,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72500 | Stationery | 6,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72800 | Supplies | 3,000.00 |
|  |  | Sub-total 4.2 | GEF UNDP TOTAL | 36,500.00 0.00 36,500.00 |
|  |  | 4.3 A participatory M&E system available and being used to monitor socio-economic and ecological changes in the SRB |
|  |  | Conduct consultative meeting to develop consultancy TORs for developing an M&E system |  | X | X |  |  | GEF | 72400 | Communication | 1,000.00 |
|  |  |  |  | X | X |  |  | GEF | 71600 | Meetings and Travel | 2,000.00 |
|  |  | Hire a consultant to develop an M&E systems and link to the Environmental Sustainability Criteria framework |  |  | X | X |  | GEF | 71400 | Contractual services | 5,000.00 |
|  |  |  |  |  | X | X |  | GEF | 71600 | Meetings and Travel | 1,500.00 |
|  |  | Monitor and evaluate the Sustainable Land Management (SLM). |  |  | X | X |  | GEF | 71600 | Meetings and Travel | 2,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72500 | Stationery | 500.00 |
|  |  | Conduct baseline forest resource, vegetation cover, water quality, charcoal production etc. assessment- Link with the Climate change activities |  |  | X | X |  | GEF | 71600 | Meetings and Travel | 2,500.00 |
|  |  |  |  |  | X | X |  | GEF | 72200 | Equipment | 5,000.00 |
|  |  |  |  |  | X | X |  | GEF | 72800 | Supplies | 500.00 |
|  |  | Hold a workshop with both public and private sector to determine other parameters for consideration in monitoring SLM |  |  |  | X |  | GEF | 71600 | Meetings and Travel | 5,000.00 |
|  |  |  |  |  |  | X |  | GEF | 72100 | Contractual services | 2,000.00 |
|  |  | Conduct mapping of the whole impact area and individual hotspots; using GIS based techniques- Link up with DRR and APP project activities |  |  | X | X |  | GEF | 74100 | Professional Services | 0.00 |
|  |  |  |  |  | X | X |  | GEF | 72100 |  | 3,000.00 |
|  |  | Sub-total 4.3 | GEF UNDP TOTAL | 27,000.00 0.00 27,000.00 |
|  | Output 4 Total | GEF UNDP TOTAL | 86,500.00 0.00 86,500.00 |
| CP OUTCOME 1.3 TOTAL | GEF UNDP TOTAL | 376,000.00 116,000.00 492,000.00 |
| GRAND TOTAL | GEF UNDP TOTAL | 720,000.00 150,000.00 870,000.00 |

Nb: Outputs are stated as per the PRODOC and have been linked to the Outcomes in the UNDP Country Program

It is difficult to anticipate the scope of the various consultancies, and therefore the network of focal points will be developing the TORs as part of project implementation.

# The Annual Work Plan (AWP) Monitoring Tool							Year____2011___

# CP Component___1___________________

Implementing Partner:-  ________________

| EXPECTED CP OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS | PLANNED ACTIVITIES List all the activities including monitoring and evaluation activities to be undertaken during the year towards stated CP outputs | EXPENDITURES List actual expenditures against activities completed | RESULTS OF ACTIVITIES For each activity, state the results of the activity | PROGRESS TOWARDS ACHIEVING CP OUTPUTS Using data on annual indicator targets, state progress towards achieving the CP outputs. Where relevant, comment on factors that facilitated and/or constrained achievement of results including: Whether risks and assumptions as identified in the CP M&E Framework materialized or whether new risks emerged Internal factors such as timing of inputs and activities, quality of products and services, coordination and/or other management issues |
| --- | --- | --- | --- | --- |
| CP OUTCOME 1.1: INDICATOR 1.1 TARGET FOR THE YEAR: 2011 An operational project coordination unit Draft report on proposed policies revisions INDICATOR 1.2 TARGET FOR THE YEAR: 2011 | 1.0 Policy regulations and institutional support |  |
|  | 1.1 Alignment of forestry and agriculture policies |  | A consultancy report containing proposed amendments to the forestry policy, agriculture policy |  |
|  | 1.2 Facilitate establishment of Shire River Basin Authority |  | A report of community awareness meetings A report from study tours A draft report on the proposed SBA A report of parliamentarians |  |
|  | Project management |  |
|  | 5.1Adaptive learning |  | A report on status of SLM in the country |  |
|  | 5.2 Strengthen support for SLM in the country |  | Project Advisor and project manager and supporting staff in SLM coordination unit Quarterly progress report Risk management report |  |
| CP OUTCOME 1.3 INDICATOR 2.1WITH TARGET FOR THE YEAR 2011: | 2.0 Private Public Partnerships (PPP) providing financial incentives for SLM (through green water credits and sustainable charcoal) |  |
|  | 2.1 Conduct awareness raising for green water credits (GWC) and propose a GWC scheme |  | Consultancy Report on green water credits A hydrological modeling report of the impact area |  |
|  | 2.2 Assess capacity needs for a successful implementation of sustainable charcoal interventions in the impact area |  | Capacity needs assessment report Number of men and women trained in sustainable charcoal production including in construction of energy efficient kilns. |  |
|  | 3.0 Crop insurance providing the basis for improved increased access to credit as well as increased use of up to date weather information in decision making |  |
|  | 3.1 Knowledge skills management |  | Report containing number of weather stations, and on awareness raising activities on crop insurance schemes |  |
|  | 3.2 Crop insurance and access to credit |  | A draft index based crop insurance scheme. |  |
|  | 4.0 Knowledge skills provided for SLM management |  |
|  | 4.1 Build capacity of female and male farmers in the impact areas. |  | Number of men and women equipped with skills in SLM A draft gender training sensitive manual on SLM |  |
|  | 4.2 Enhanced forestry productivity in the impact areas |  | Action plan on increasing forestry productivity |  |
|  | 4.3 Develop a Participatory M&E system |  | Baseline data on SLM A map of the impact area Field monitoring reports |  |

# Text boxes

USD

Estimated annualized budget:	       870,000.00

Allocated resources

UNDP    (Regular)                :                  150,000.00

Government in kind              :                  100,000.00

Other	(GEF)                      :                  720,000.00

Unfunded budget                    :	                    0.00

Program Period        :      2010-2014

Program Component:      Energy, Environment &Climate Change

Intervention Title     :      PIMS 2085 PPP in Sustainable Land Management in the SRB

Budget Code            :      (Award No.) 00058857

(Project ID) MWI 00073331

Duration                   :      One year (2011)