# Annual Work Plan 2014

Rev3, 30 Dec 2013

# PRIVATE SECTOR DEVELOPMENT PROJECT

Country: MALAWI

Theme 1: Sustainable and Equitable Economic Growth and Food Security

UNDAF Outcome 1.3:	Productive poor benefit from decent work, income generation and pro-poor private sector growth by 2016

UNDAF Output 1.3.3:	National Export Strategy clusters are supported through enterprise and skills development, financial services, cooperative development, promotion of structured markets and national quality infrastructure

Expected CPD Output(s):	Inclusive finance products expanded, new business-to-business opportunities for Malawi products

Expected Project Outputs: 	1. The Industrial development policy and prioritized sectoral policies and strategies developed and implemented

2. The MICF is established and operational to increase inclusiveness and competitiveness of value chains in agriculture and manufacturing

3. Loan facility provided to smallholder farmers, low income women and youth

Implementing partner:	Ministry of Industry and Trade

Other Partners:	UNDP, Ministry of Industry and Trade, Private Sector, Financial Service Provider

Agreed by Ministry of Industry and Trade:

_______________________________________				____________________

Randson Mwadiwa, Principal Secretary					Date

Agreed by UNDP:

_______________________________________				____________________

Mia Seppo, Resident Representative 					Date

## Annual Work Plan

##### 02 January 2014 – 31 December 2014

| EXPECTED CP OUTPUTS and indicators including annual targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount US$ |
| OUTPUT 1: The Industrial development policy and prioritized sectoral policies and strategies developed and implemented |
| Number or Industrial Policies developed and approved by Cabinet Baseline: 0; Target: 1 | 1.1.1 Develop an Industrial Policy aligned to the SADC Industrialization Framework Industrial Policy development, validation, printing and dissemination |  |  |  |  | Ministry of Industry and Trade | UNDP TRAC | 72100 Contractual Services Companies 75700 Training, Workshops and Confer | 47,920 10,000 |
| Number of Sectoral Policies and strategies in oil seeds, legumes, sugar and manufacturing, aligned to the NES and MICF, fast-tracked and implemented Baseline: tbd; Target: 1 | 1.2.1 Review of the Trade Policy Trade Policy reviewed, validation, printing and dissemination |  |  |  |  | Ministry of Industry and Trade | UNDP TRAC | 72100 Contractual Services Companies 75700 Training, Workshops and Confer | 20,000 10,000 |
|  | 1.2.2 Development of Guidelines for Industrial Rebates in Malawi Guidelines developed, validation, printing and dissemination |  |  |  |  | Ministry of Industry and Trade | UNDP TRAC | 71200 International Consultants 75700 Training, Workshops and Confer | 19,100 10,000 |
| Number of SWGs operationalized through the conduit of the NES Baseline: 0; Target: 1 | 1.3.1 Support to the NES Manufacturing prioritized cluster Manufacturing TA based in the MoIT |  |  |  |  |  | UNDP TRAC | 61300 Salary and related costs TA/IP cost | 194,363 |
|  | 1.3.2 Policy Advocacy for the Manufacturing Strategy Research and consultative meetings for the Manufacturing Cluster |  |  |  |  | Ministry of Industry and Trade | UNDP TRAC | 72100 Contractual Services Companies 75700 Training, Workshops and Confer | 10,000 7,508 |
| Sub-Total |  |  |  |  |  |  |  |  | 328,891 |

| OUTPUT 2: The MICF is established and operational to increase inclusiveness and competitiveness of value chains in agriculture and manufacturing |
| --- |
| Number of new business models that increase average net incomes of the poor are developed in each IMD intervention (Agriculture and Manufacturing) Baseline: 0; Target: 5 Additional investment leveraged from the Private Sector through the MICF Baseline: 0, Target: $900,000 Additional annual revenue received by companies successful in the MICF Baseline: n.a. Target: tbd at first round of competition Annual income for the poor Baseline: 0. Target: tbd at first round of competition Percentage increase in the incomes of existing 80,000 farmers (including at least 30% women farmers) Baseline: tbd at first round of competition. Target: 30% 2.6 Percentage increase in incomes of 10,000 new farmers (including at least 30% women farmers/youth) Baseline: tbd at first round of competition. Target:100% 2.7 Number of new jobs created (at least 30% for women and youth) Baseline: 0. Target: 400 | 2.1.1 MICF Fund Management |  |  |  |  | UNDP | UNDP TRAC | 72100 –Contractual Services Companies | 509,602 |
|  | 2.1.2 Engage members of the Investment Panel |  |  |  |  | UNDP | UNDP TRAC UNDP TRAC UNDP TRAC UNDP TRAC UNDP TRAC | 71600 – Travel 75700 – Training, Workshops and Confer 71200 – International Consultants 71300 – Local Consultants 72500 – Supplies | 9,000 5,000 2,400 1,600 1,000 |
|  | 2.1.3 Sensitization Campaigns for the MICF |  |  |  |  | UNDP | UNDP RR | 75700 – Training, Workshops and Confer | 8,000 |
|  | 2.1.4 Disburse Grants to successful MICF applicants |  |  |  |  | UNDP | DFID | 72600 –Grants | 1,500,000 |
| Sub-Total |  |  |  |  |  |  |  |  | 2,036,602 |
| OUTPUT 3: Loan facility provided to smallholder farmers, low income women and youth |
| Number of productive poor have access to loans for IMD Interventions (at least 30% women and youth) Baseline: 0; Target: 0 | 3.1.1 Select a FSP to manage the Pro-Poor Loan Facility |  |  |  |  | UNDP | UNDP TRAC | 72500 Supplies | 200 |
| Sub-Total |  |  |  |  |  |  |  |  | 200 |
| OUTPUT 4: Programme Management |
| Communication and M&E |
| Monitoring and Evaluation | Monitoring and Evaluation Communication Costs On site visits |  |  |  |  | UNDP | UNDP TRAC | 71600 Travel 72300 Materials & Goods 72400 Communic & Audio Visual | 2,000 1,000 3,000 |
| Programme Assurance, Coordination and Management |
| Programme Assurance, Coordination and Management | Salaries for Programme Analyst, Associate |  |  |  |  | UNDP | UNDP TRAC | 77100/61200 Salary and related costs–TA/NP | 36,000 |
|  | PSD Advisor (International) |  |  |  |  | UNDP | UNDP TRAC | 61300 Salary and related costs–TA/IP | 160,000 |
|  | PSD Specialist (National) |  |  |  |  | UNDP | UNDP TRAC | 77100 -TA/NP cost | 28,808 |
|  | Office Supplies |  |  |  |  | UNDP | UNDP TRAC | 72500 Supplies | 5,000 |
|  | Quarterly Steering Committee Meetings & Monitoring Visits |  |  |  |  | UNDP | UNDP TRAC | 72300 Materials and Goods 71600 Travel | 3,000 3,000 |
| UNDP Administrative Cost (GMS 7%) |  |  |  |  |  |  |  |  | 105,000 |
| Sub-Total |  |  |  |  |  |  |  |  | 330,808 |
| GRAND TOTAL |  |  |  |  |  |  |  |  | 2,702,500 |

# The Annual Work Plan (AWP) Monitoring Tool							Year 2014

# CP Component: Poverty Reduction

Implementing Partner: Ministry of Finance

| EXPECTED CP OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS | PLANNED ACTIVITIES List all the activities including monitoring and evaluation activities to be undertaken during the year towards stated CP outputs | EXPENDITURES List actual expenditures against activities completed | RESULTS OF ACTIVITIES For each activity, state the results of the activity | PROGRESS TOWARDS ACHIEVING CP OUTPUTS Using data on annual indicator targets, state progress towards achieving the CP outputs. Where relevant, comment on factors that facilitated and/or constrained achievement of results including: Whether risks and assumptions as identified in the CP M&E Framework materialized or whether new risks emerged Internal factors such as timing of inputs and activities, quality of products and services, coordination and/or other management issues |
| --- | --- | --- | --- | --- |
| OUTPUT 1: The Industrial development policy and prioritized sectoral policies and strategies developed and implemented OUTPUT INDICATORS: Number of Industrial Policies developed and approved by Cabinet Baseline: 0 ; Target: 1 Number of Sectoral Policies and strategies in oil seeds, legumes, sugar and manufacturing, aligned to the NES and MICF, fast-tracked and implemented Baseline: tbd; Target: 1 Number of SWGs operationalized through the conduit of the NES Baseline: 0; Target: 1 | 1.1.1 Develop an Industrial Policy aligned to the SADC Industrialization Framework |  |  |  |
|  | 1.2.1 Review of the Trade Policy |  |  |  |
|  | 1.2.2 Development of Guidelines for Industrial Rebates in Malawi |  |  |  |
|  | 1.3.1 Support to the NES Manufacturing prioritized cluster 1.3.2 Policy Advocacy for the Manufacturing Strategy |  |  |  |
| OUTPUT 2: The MICF is established and operational to increase inclusiveness and competitiveness of value chains in agriculture and manufacturing OUTPUT INDICATORS: Number of new business models that increase average net incomes of the poor are developed in each IMD intervention (Agriculture and Manufacturing) Baseline: 0; Target: 5 Additional investment leveraged from the Private Sector through the MICF Baseline: 0, Target: $900,000 Additional annual revenue received by companies successful in the MICF Baseline: n.a. Target: tbd at first round of competition Annual income for the poor Baseline: 0. Target: tbd at first round of competition Percentage increase in the incomes of existing 80,000 farmers (including at least 30% women farmers) Baseline: tbd at first round of competition. Target: 30% 2.6 Percentage increase in incomes of 10,000 new farmers (including at least 30% women farmers/youth) Baseline: tbd at first round of competition. Target:100% 2.7 Number of new jobs created (at least 30% for women and youth) Baseline: 0. Target: 400 | 2.1.1 MICF Fund Management |  |  |  |
|  | 2.1.2 Engage members of the Investment Panel |  |  |  |
|  | 2.1.3 Sensitization Campaigns for the MICF |  |  |  |
|  | 2.1.4 Disburse Grants to successful MICF applicants |  |  |  |

| OUTPUT 3: Loan facility provided to smallholder farmers, low income women and youth OUTPUT INDICATORS: Number of productive poor have access to loans for IMD Interventions (at least 30% women and youth) Baseline: 0; Target: 0 | 3.1.1 Select a FSP to manage the Pro-Poor Loan Facility |  |  |  |
| --- | --- | --- | --- | --- |
| Monitoring and Evaluation Baseline: 0; Target: 2 | Monitoring and Evaluation – On Site Visits |  |  |  |

# Text boxes

Narrative

Malawi lacks a private sector that can increase the low levels of investment and production and transform the economic structure of the country through the diversification of its economy and exports. The Private Sector Development Project (PSDP) is a private sector led and private sector driven project. It aims at incentivizing the private sector to deliver sustained, rapid and inclusive growth; ensuring that value chains with strong potential, identified by the National Export Strategy (NES), contribute to growth and poverty reduction and are inclusive of the poor; and better aligning business incentives with development objectives to promote innovations and inclusive business models to draw poor communities into markets more efficiently.

More specifically, the overall goal of the PSD project is to support productive partnerships within the private sector, particularly between lead firms and poor producers and entrepreneurs, especially smallholders. The project has the ambition of contributing to the transformation of the private sector into the engine of real growth and anchor for economic diversification, job creation and greater economic opportunity for the poor that Malawi requires.

The project will also facilitate access to finance to smallholder farmers and low-income people through the establishment of a Loan Facility and will ensure a more receptive policy and institutional environment for Agriculture and Manufacturing value chains.

The PSDP operational approach is characterized by the use of two instruments: UNDP’s Inclusive Markets Development (IMD) and the Challenge Fund.

In 2014, a Malawi Innovation Challenge Fund (MICF) will be launched and pioneered for the first time in Malawi under the PSDP. This will provide direct support to lead businesses with grant finance and technical assistance, with a view to supporting agriculture and manufacturing value chains to work better for the poor following the IMD approach and within the framework of the National Export Strategy (NES). At Policy level, support is provided for the development of an Industrial Policy to hasten the industrial development of Malawi`s economy and aligned to SADC`s Industrialization framework. Also, guidelines for Industrial rebates will be developed and the Trade Policy reviewed. Likewise, to sustain vertical and horizontal integration and of smallholder farmers, low income women and youth in corporate supply chains, a Loan facility will be set-up in the course of the year.

Estimated annualized budget:	$2,702,500

(inclusive of GMS)

Allocated resources:

Government		in kind

UNDP Regular 		$1,097,500

DFID			$1,500,000

Unfunded budget:	$0

AWP Period:			02 January 2014

31 December 2014

Programme Component:	Poverty Reduction and MDGs

Intervention Title:	Private Sector Development Project

Atlas Award ID: 	00072218

Project ID: 			00085368

Duration:			1 year